Document Accession #: 20221216-3065	Filed Date: 12/16/2022

181 FERC ¶ 61,236

UNITED STATES OF AMERICA

FEDERAL ENERGY REGULATORY COMMISSION

Before Commissioners:  Richard Glick, Chairman;

James P. Danly, Allison Clements,

Mark C. Christie, and Willie L. Phillips.

Clean Path New York LLC	Docket No. ER23-253-000

ORDER GRANTING WAIVER 
(Issued December 16, 2022)

On October 28, 2022, pursuant to Rules 207(a)(5) and 212 of the Commission’s 
Rules of Practice and Procedure,1 Clean Path New York LLC (Clean Path) submitted a 
request for waiver of section 25.6.2.3.1 of Attachment S of the New York Independent 
System Operator, Inc. (NYISO) Open Access Transmission Tariff (OATT), which 
requires an interconnection project to have an Interconnection System Reliability Impact 
Study (SRIS) approved by the NYISO Operating Committee2 before entering a Class 
Year Study.  As discussed below, we grant Clean Path’s waiver request.

I.	Background

NYISO’s generator interconnection process features three interconnection studies:

(1) an interconnection feasibility study; (2) an SRIS; and (3) a combined Class Year

Study, in which all projects that have fulfilled the requirements and elected to be included 
in a given Class Year are studied together.3  Section 30.7.4 of Attachment X of NYISO’s 
OATT provides that NYISO shall use reasonable efforts to complete the SRIS within 
120 calendar days following receipt of certain required materials, including a study

1 18 C.F.R. §§ 385.207(a)(5), 385.212 (2021).

2 Capitalized terms used but not otherwise defined in this order have the meanings ascribed to them in NYISO’s OATT.

3 NYISO, NYISO Tariffs, NYISO OATT, § 30 (Attachment X), § 30.6

(Interconnection Feasibility Study) (4.0.0); id. § 30.7 (Interconnection System Reliability Impact Study) (9.0.0); id. § 30.8 (Interconnection Facilities Study) (7.0.0).

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 2 -

deposit, required technical data, and a demonstration of site control.4  Section 30.7.5

requires that NYISO provide a draft SRIS report to the developer and transmission

owners and allow them 15 business days to review.5  Once NYISO issues the final SRIS report, the SRIS is reviewed by the Transmission Planning Advisory Subcommittee of the NYISO Operating Committee within three months, and subsequently by the NYISO Operating Committee.

Section 25.6.2.3.1 of NYISO’s OATT establishes the main requirements for a

Large Facility project to be eligible to be included in a given Class Year Study.  No later 
than the Class Year Start Date, the project must have:  (1) a completed SRIS approved 
by the NYISO Operating Committee; and (2) the applicable regulatory milestone for its 
project in accordance with Attachment S, or in lieu of satisfying such milestone, a two-
part deposit or a qualifying contract.6  The date that the Class Year Study commences is 
the Class Year Start Date, and occurs on the first business day after 30 calendar days

following the completion of the prior Class Year.  Following the Class Year Start Date, NYISO develops the Annual Transmission Baseline Assessment base cases.7

4 NYISO, NYISO Tariffs, NYISO OATT, § 30 (Attachment X), 30.7

(Interconnection System Reliability Impact Study) (9.0.0), § 30.7.4 (Interconnection System Reliability Impact Study Procedures).

5 NYISO, NYISO Tariffs, NYISO OATT, § 30 (Attachment X), (Interconnection System Reliability Impact Study) (9.0.0), § 30.7.5 (Study Report Meeting).

6 NYISO, NYISO Tariffs, NYISO OATT, § 25 (Attachment S), § 25.6 (Cost Allocation Methodology For ERIS) (10.0.0), § 25.6.2.3.1.

7 NYISO, NYISO Tariffs, NYISO OATT, § 25 (Attachment S), § 25.6 (Cost

Allocation Methodology For ERIS) (10.0.0), § 25.6.1.1.1.1 (Procedure for Annual

Transmission Baseline Assessment); NYISO, Transmission Expansion and

Interconnection Manual, § 3.3.3.6.3 (“The major steps of the Class Year Study include: 1. Preparation of Base Cases for the [Annual Transmission Baseline Assessment] and 
[Annual Transmission Reliability Assessment] - NYISO requests updates of information from the TOs, neighboring ISOs/RTOs, and Developers and prepares steady state, 
dynamic, and short circuit base cases for the [Annual Transmission Baseline Assessment] and [Annual Transmission Reliability Assessment]. In doing so, NYISO prepares data for modeling each of the Class Year Projects to be used in the studies.”).

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 3 -

II.	Waiver Request

Clean Path explains that it is the developer of the Clean Path Transmission Line, 
a proposed 178-mile, 1,300 MW underground submarine high voltage direct current 
transmission line to be located within the NYISO footprint.8  Clean Path states that, in 
September 2021, its Clean Path Transmission Line proposal was selected by the New 
York State Energy and Research Development Authority (NYSERDA) after an extensive 
solicitation process for projects that meet New York State’s policy goal of eliminating the 
use of fossil fuels for electricity generation.9  Clean Path asserts that it entered into a 
renewable energy certificate purchase and sale agreement with NYSERDA in November 
2021, which was approved by the New York State Public Service Commission (New 
York Commission) in April 2022.10  Clean Path explains that its contract with 
NYSERDA sets an expected commercial operation date of June 30, 2027.11  Clean Path 
asserts that, in order to meet the June 2027 commercial operation date, Clean Path must 
complete the interconnection process by no later than December 2024.

Clean Path states that it submitted its interconnection request to join NYISO’s 
interconnection queue on October 21, 2021 with the expectation that its SRIS would be approved with sufficient time to join NYISO’s upcoming 2023 Class Year.12  Clean Path states that it timely provided the required deposits, modeling data, and site control 
demonstrations for the SRIS by December 28, 2021.13  However, Clean Path claims that delays in the completion of its SRIS and approval of the SRIS by NYISO’s Operating 
Committee jeopardize Clean Path’s ability to obtain SRIS approval in time to join 
NYISO’s 2023 Class Year Study.14

8 Waiver Request at 1, 4.

9 Id. at 4-5.

10 Id. at 2, 5 (citing New York Commission, Case 15-E-0302, Order Approving 
Contracts for the Purchase of Tier 4 Renewable Energy Certifications (issued Apr. 14, 
2022)).

11 Id. at 5.

12 Id. at 2.  Clean Path states that its contract with NYSERDA contemplates that Clean Path will seek to enter the first Class Year for which it is eligible after the 
contract’s effective date.  Id. at 5.

13 Id. at 10.

14 Id. at 9-10.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 4 -

Specifically, Clean Path explains, in December 2021, NYISO estimated that the

SRIS would be completed 150 days (rather than 120 days) from the date NYISO finalized 
the base cases for the study.15  Clean Path next states that, on March 4, 2022, NYISO 
reached out to Clean Path with questions about the modeling data submitted in December 
2021, and that Clean Path provided responses and updated models by March 15, 2022. 
Clean Path asserts that, on June 28, 2022, NYISO provided the SRIS base cases to Clean 
Path and the connecting transmission owners for comment by July 7, 2022.16  Clean Path 
states that it provided comments on July 11, 2022, and further discussed the modeling 
and SRIS in a meeting on July 18, 2022.17  Clean Path contends that it received multiple 
rounds of questions from NYISO from July to September 2022 and responded promptly 
to all inquiries.  Clean Path states that, on September 26, 2022, NYISO finalized the base 
cases and commenced the SRIS process.18  Clean Path states that NYISO subsequently 
revised the expected completion date to December 31, 2022.  Clean Path argues that, 
given this series of events, it is uncertain whether NYISO’s Operating Committee will 
approve the SRIS prior to the 2023 Class Year Start Date.  Clean Path estimates that it 
may not receive SRIS approval until early 2023 and potentially miss the opportunity to 
enter the 2023 Class Year by a matter of days or weeks.

Clean Path requests waiver of the requirement in section 25.6.2.3.1 of Attachment S of NYISO’s OATT to have an approved SRIS prior to the Class Year Start Date as a condition to joining the 2023 Class Year Study.19  Clean Path argues that its waiver 
request satisfies the Commission’s criteria for granting waiver.  First, Clean Path asserts that it is acting in good faith because it has responded promptly to technical and modeling questions from NYISO and the connecting transmission owner and has proactively 
communicated with NYISO as to the status of its SRIS.20  Clean Path also asserts that it acted in good faith in timely submitting its interconnection request, diligently pursuing it, and taking every step it could to advance the process.21

15 Id.

16 Id. at 10-11.

17 Id. at 11.

18 Id. at 12.

19 Id. at 13.

20 Id. at 14.

21 Id. at 15.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 5 -

Second, Clean Path argues that the waiver request is limited in scope.22

Specifically, Clean Path argues that its waiver request is limited to Clean Path’s

interconnection request and would apply only to the extent that Clean Path’s SRIS is

approved before NYISO completes the Annual Transmission Baseline Assessment base 
cases for the 2023 Class Year.  Clean Path explains that the interconnection process for 
its planned transmission line has been uniquely complex, because the transmission line:

(1) is the first internal controllable line to proceed through a Class Year process (and the only known internal controllable line seeking entrance into the 2023 Class Year);

(2) would interconnect at two different points within NYISO’s footprint; and (3) involves multiple transmission owners.  Clean Path adds that the waiver request is limited to 
waiver of a single timing requirement.23

Third, Clean Path contends that the waiver request addresses a concrete problem.24 Clean Path argues that, if the SRIS approval is delayed beyond the 2023 Class Year Start Date, and Clean Path is unable to participate in the 2023 Class Year Study, the 
development of the Clean Path Transmission Line will be delayed by at least 18-24 
months.  According to Clean Path, this would delay the realization of significant benefits that the project is expected to provide to New York.25

Finally, Clean Path argues that granting the waiver request would not have

undesirable consequences or harm third parties because the window for the upcoming

2023 Class Year Study has not been set, nor has the study commenced.26  Clean Path

adds that granting waiver will not delay the study process because Clean Path commits to 
meeting all other applicable requirements to enter the 2023 Class Year; thus, it will be 
ready to proceed quickly after approval of the SRIS.  Clean Path commits to withdrawing 
its waiver request or notifying the Commission that it did not need to rely upon the 
Commission’s grant of waiver if its SRIS is approved before the 2023 Class Year Start 
Date.27

22 Id. at 16.

23 Id. at 17.

24 Id.

25 Id. at 3, 17-18.

26 Id. at 18.

27 Id. at 3 n.8.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 6 -

Clean Path asks the Commission to issue an order granting the requested relief by 
no later than December 16, 2022, to provide certainty should NYISO begin preparatory 
activities for the next Class Year while Clean Path awaits completion and approval of its 
SRIS.28

III. 	Notice and Responsive Pleadings

Notice of Clean Path’s filing was published in the Federal Register, 87 Fed. Reg. 
66,291 (Nov. 3, 2022) with interventions and protests due on or before November 18, 
2022.  The New York Commission filed a notice of intervention, and NYSERDA and 
Helix Ravenswood, LLC filed timely motions to intervene.  Timely motions to intervene 
and comments were filed by: NYISO; Thousand Island Solar, LLC (Thousand Island); 
Clean Energy Advocates;29 New York Power Authority; and ConnectGen Montgomery 
County LLC (ConnectGen).  New York State Agencies30 filed comments.  On

November 23, 2022, New Leaf Energy, Inc. (New Leaf) filed a motion to intervene 
out of time.  Thousand Island submitted corrected comments on December 2, 2022.

NYISO supports Clean Path’s requested waiver.31  NYISO explains that Clean

Path’s SRIS is still ongoing, because the Clean Path Transmission Line is a unique cross-
state, controllable transmission line that raises novel reliability issues requiring a level of 
input and analysis far in excess of what a typical SRIS would require.32  NYISO requests 
that, if the Commission grants Clean Path’s waiver, the Commission extend the waiver to 
all similarly situated projects.  NYISO explains that the similarly situated projects in this 
instance would include those projects that have an SRIS currently in progress.33  NYISO 
contends that this approach would provide the same amount of additional time for

similarly situated projects to have their SRIS completed and approved by the NYISO

Operating Committee to enter the 2023 Class Year, which would minimize the potential 
for delays that could result from developers requesting similar waivers later in the Class

28 Id. at 19.

29 Clean Energy Advocates include the Alliance for Clean Energy New York and Natural Resources Defense Council.

30 New York State Entities include the New York Commission and NYSERDA.

31 NYISO Comments at 6.

32 Id. at 2-3.

33 Id. at 7 (stating that the SRISs in progress are those SRISs that have had their initial scope approved by the Operating Committee as of the date of the waiver request, i.e., October 28, 2022).

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 7 -

Year Study process.  NYISO asserts that the Commission has previously granted waivers that apply to entities similarly situated to the requesting entity.34

NYISO states that, to minimize the potential adverse impacts on the Class Year 
Study process, the waiver should not be open-ended.35  NYISO argues that the 
Commission should clarify that Clean Path or any similarly situated project has until the 
completion date of the Annual Transmission Baseline Assessment base cases to have its 
SRIS report approved by NYISO’s Operating Committee in order to satisfy the 
requirements for entering NYISO’s 2023 Class Year.  NYISO states that the Annual 
Transmission Baseline Assessment establishes the pre-existing baseline system before 
Class Year Projects are included.  NYISO explains that the development of the Annual 
Transmission Baseline Assessment base cases is its initial step in the Class Year Study 
process and takes approximately 60 days to complete from the Class Year Start Date. 
NYISO contends that, if it were required to add new members to the Class Year after 
completion of the Annual Transmission Baseline Assessment base cases, such action 
would potentially disrupt finished study work and delay the ultimate completion of the 
Class Year Study for all members.36  NYISO adds that the Commission should clarify 
that Clean Path and similarly situated projects are required to satisfy the other entry 
requirements for the Class Year Study in accordance with the existing rules and timing 
requirements established in Attachments X and S of NYISO’s OATT.

New York State Agencies, NYPA, and Clean Energy Advocates also support 
Clean Path’s waiver request.37  New York State Agencies, NYPA, and Clean Energy 
Advocates explain that Clean Path’s project is expected to deliver significant amounts 
of renewable energy (i.e., from 23 generation resources, including 1,932 MW of wind 
capacity and 1,430 MW of solar capacity) to New York City.  New York State Agencies, 
NYPA and Clean Energy Advocates assert that the Clean Path Transmission Line and its 
timely development are key components of meeting New York’s clean energy goals.38 
Clean Energy Advocates add that, if the Clean Path Transmission Line is not able to join

34 Id. (citing N.Y. Power Auth., 139 FERC ¶ 61,157, at P 27 (2012) (NYPA) (providing that the waiver granted to the requesting party applies equally to all other similarly situated parties identified by NYISO in the proceeding)).

35 Id. at 8.

36 Id. at 9.

37 New York State Agencies Comments at 2-3; NYPA Comments at 4-5; Clean Energy Advocates Comments at 5-6.

38 New York State Agencies Comments at 3; NYPA Comments at 5; Clean Energy Advocates Comments at 6.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 8 -

NYISO Class Year 2023, there could be a delay in additional benefits, such as reducing 
congestion and other reliability benefits in New York.39  New York State Agencies add 
that Clean Path’s waiver request is narrowly limited to avoid potential delays to NYISO’s 
2023 Class Year process by making the waiver contingent upon the SRIS being approved 
before NYISO completes the Annual Transmission Baseline Assessment.40  NYPA also 
adds that Clean Path’s waiver is limited to one interconnection request and seeks a

definitive time-bound extension for its SRIS to be approved.41  New York State Agencies 
and Clean Energy Advocates further state that they support NYISO’s request that the 
waiver apply to all similarly situated projects that have an SRIS currently in progress.42

Thousand Island and ConnectGen state that they are developers of large facilities 
in NYISO’s interconnection queue and explain that they have projects that would benefit 
from the Commission’s extension of Clean Path’s waiver request.43  Accordingly, 
Thousand Island and ConnectGen state that they support Clean Path’s waiver request and 
NYISO’s request for extension of the waiver.44  Thousand Island states that it anticipates 
receiving an initial draft of its SRIS in December 2022 and explains that is well-
positioned to enter the 2023 Class Year Study if NYISO’s request for the extension of 
Clean Path’s waiver to similarly situated entities is granted.45  ConnectGen explains that 
its SRIS process commenced on January 8, 2021, and the SRIS base case was finalized 
on May 10, 2021.46  ConnectGen explains that the ability of its Mill Point Project to be 
included in the 2023 Class Year Study is in jeopardy.  ConnectGen further contends that 
its SRIS study has been significantly delayed, and while recent communications with 
NYISO have suggested the SRIS may be forthcoming shortly, there is no certainty 
as to the timing of the Mill Point SRIS release or how such release would align with 
opportunities for and timing of presentation by the Transmission Planning Advisory 
Subcommittee and the NYISO Operating Committee. Thousand Island and ConnectGen

39 Clean Energy Advocates Comments at 6.

40 NYPA Comments at 4.

41 Id.

42 New York State Agencies Comments at 3; Clean Energy Advocates Comments

at 6-7.

43 Thousand Island Comments at 3; ConnectGen Comments at 4.

44 Thousand Island Comments at 3-4; ConnectGen Comments at 4-5.

45 Thousand Island Comments at 3.

46 ConnectGen Comments at 4.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 9 -

argue that each of the Commission’s waiver criteria is fully satisfied by Clean Path and NYISO.47  ConnectGen adds that NYISO’s request seeks to ensure a level playing field, in which all other similarly situated projects have the same opportunity.48

Several parties support Clean Path’s request for an order by December 16, 2022, 
because it would provide certainty concerning the requirements applicable to SRISs prior 
to NYISO’s Class Year Start Date, which could begin as early as January 3, 2023.49

IV.   Discussion

A.	Procedural Matters

Pursuant to Rule 214 of the Commission’s Rules of Practice and Procedure,

18 C.F.R. § 385.214 (2021), the notice of intervention and timely, unopposed motions to intervene serve to make the entities that filed them parties to this proceeding.

Pursuant to Rule 214(d) of the Commission’s Rules of Practice and Procedure,

18 C.F.R. § 385.214(d) (2021), we grant New Leaf’s late-filed motion to intervene given its interest in the proceeding, the early stage of the proceeding, and the absence of undue prejudice or delay.

B.	Substantive Matters

We grant Clean Path’s request for a waiver of the requirement in section

25.6.2.3.1 of Attachment S of NYISO’s OATT to have an SRIS approved by the NYISO 
Operating Committee before entering a Class Year Study. Thus, Clean Path may enter 
the upcoming 2023 Class Year Study if Clean Path has its SRIS by the completion date 
of the Annual Transmission Baseline Assessment base cases and satisfies the other 
requirements for entering a Class Year Study in accordance with NYISO’s OATT.

The Commission has granted waiver of tariff provisions where: (1) the applicant 
acted in good faith; (2) the waiver is of limited scope; (3) the waiver addresses a concrete 
problem; and (4) the waiver does not have undesirable consequences such as harming

47 Thousand Island Comments at 3; ConnectGen Comments at 5.

48 ConnectGen Comments at 5-6.

49 NYISO Comments at 11; Clean Energy Advocates Comments at 7; Thousand Island Comments at 4.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 10 -

third parties.50  As discussed below, we find that Clean Path’s waiver request satisfies these criteria.

First, we find that Clean Path acted in good faith.  The record demonstrates that Clean Path has timely and diligently worked with NYISO and the connecting transmission owners to support the completion of its SRIS.51

Second, we find that the waiver is limited in scope because Clean Path seeks a 
one-time waiver of a single timing requirement in section 25.6.2.3.1 of Attachment S 
of NYISO’s OATT to have an SRIS approved by NYISO’s Operating Committee for 
the 2023 Class Year Study.  The waiver would apply only to the extent that Clean 
Path’s SRIS is approved before NYISO completes the Annual Transmission Baseline 
Assessment base cases for the 2023 Class Year and only to Clean Path’s project.

Third, we find that the waiver addresses a concrete problem.  Absent waiver, Clean Path’s project would likely not be eligible to participate in the 2023 Class Year Study, which could cause significant delays in the development of the Clean Path 
Transmission Line.52

Finally, we find that the waiver request will not have undesirable consequences, 
such as harming third parties, because the 2023 Class Year Study has not yet begun and 
granting this waiver will not delay other participants in the 2023 Class Year Study 
process.53

We decline to extend the grant of waiver to any other developers with an SRIS 
in progress, as NYISO requests.  We find that, unlike in NYPA, NYISO did not identify 
the entities it asserts are similarly situated and further did not sufficiently justify how 
all projects with an SRIS in progress are similarly situated and satisfy the four waiver 
criteria.54

50 See, e.g., Citizens Sunrise Transmission LLC, 171 FERC ¶ 61,106, at P 10 
(2020); Midcontinent Indep. Sys. Operator, Inc., 154 FERC ¶ 61,059, at P 13 (2016).

51 Waiver Request at 14.

52 Id.

53 Id. at 19.

54 Nothing in this order precludes NYISO from submitting for Commission

consideration a request for waiver applicable to similarly situated projects that seeks to make these and any other necessary showings.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Docket No. ER23-253-000	- 11 -

The Commission orders:

Clean Path’s waiver request is hereby granted, as discussed in the body of this

order.

By the Commission. ( S E A L )

Kimberly D. Bose, 
	Secretary.

Document Accession #: 20221216-3065	Filed Date: 12/16/2022

Document Content(s)

ER23-253-000.docx	1