Service Agreement No. 2641

STANDARD SMALL GENERATOR INTERCONNECTION AGREEMENTBETWEEN   
 NIAGARA MOHAWK POWER CORPORATION D/B/A

NATIONAL GRID AND CAPITAL HILL SOLAR LLC

TABLE OF CONTENTS

Article 1 Scope and Limitations of Agreement

1.1 Applicability

1.2 Purpose

1.3 Scope of Interconnection Service

1.4 Limitations

1.5 Responsibilities of the Parties

1.6 Parallel Operation Obligations

1.7 Metering

1.8 Reactive Power and Primary Frequency Response

1.9 Capitalized Terms

Article 2. Inspection, Testing, Authorization, and Right of Access

2.1 Equipment Testing and Inspection

2.2 Authorization Required Prior to Parallel Operation

2.3 Right of Access

Article 3 Effective Date, Term, Termination, and Disconnection

3.1 Effective Date

3.2 Term of Agreement

3.3 Termination

3.4 Temporary Disconnection

3.4.1 Emergency Conditions

3.4.2 Routine Maintenance, Construction, and Repair

3.4.4 Adverse Operating Effects

3.4.5 Modification of the Small Generating Facility

3.4.6 Reconnection

Article 4. Cost Responsibility for Interconnection Facilities and Distribution Upgrades

4.1 Interconnection Facilities

4.2 Distribution Upgrades

Article 5. Cost Responsibility for System Upgrade Facilities and System Deliverability

Upgrades

5.1 Applicability

5.2 System Upgrades

5.3 Special Provisions for Affected Systems

Article 6. Billing, Payment, Milestones, and Financial Security

6.1 Billing and Payment Procedures and Final Accounting

6.2 Milestones

6.3 Financial Security Arrangements

Article 7. Assignment, Liability, Indemnity, Force Majeure, Consequential Damages,

and Default

7.1 Assignment

7.2 Limitation of Liability

7.3 Indemnity

7.4 Consequential Damages

7.5 Force Majeure

7.6 Breach and Default

Article 8. Insurance

Article 9. Confidentiality

Article 10. Disputes

Article 11. Taxes

Article 12. Miscellaneous

12.1 Governing Law, Regulatory Authority, and Rules

12.2 Amendment

12.3 No Third-Party Beneficiaries

12.4 Waiver

12.5 Entire Agreement

12.6 Multiple Counterparts

12.7 No Partnership

12.8 Severability

12.9 Security Arrangements

12.10 Environmental Releases

12.11 Subcontractors

12.12 Reservation of Rights

Article 13. Notices

13.1 General

13.2 Billing and Payment

13.3 Alternative Forms of Notice

13.4 Designated Operating Representative

13.5 Changes to the Notice Information

Article 14. Signatures

Attachment 1 - Glossary of Terms

Attachment 2 - Detailed Scope of Work, Including Description and Costs of the Small   
 Generating Facility, Interconnection Facilities, and Metering Equipment Attachment 3 - One-line Diagram Depicting the Small Generating Facility,   
 InterconnectionFacilities, Metering Equipment, and Upgrades   
Attachment 4 - Milestones

Attachment 5 - Additional Operating Requirements for the New York State Transmission   
 System, the Distribution System and Affected Systems Needed to Support   
 theInterconnection Customer’s Needs

Attachment 6 - Connecting Transmission Owner’s Description of its Upgrades and Best   
 Estimateof Upgrade Costs

Attachment 7 - Insurance Coverage

Attachment 8 Initial Synchronization Date   
Attachment 9 Commercial Operation Date

i

This Small Generator Interconnection Agreement (“Agreement” or “SGIA”) is made and entered into this 15th day of June, 2021, by and between Niagara Mohawk Power Corporation d/b/aNational Grid, a corporation organized and existing under the laws of the State of New York (“Connecting Transmission Owner”), and Capital Hill Solar LLC, a limited liability company organized and existing under the laws of the State of Delaware (“Interconnection Customer”) eachhereinafter sometimes referred to individually as “Party” or referred to together as the “Parties.”

In consideration of the mutual covenants set forth herein, the Parties agree as follows:

2

Article 1 Scope and Limitations of Agreement

1.1 Applicability

This Agreement hereby incorporates by reference the terms of the ISO OATT as they

apply to interconnection services provided by the Connecting Transmission Owner and taken by the Interconnection Customer. To the extent a conflict exists between the terms and conditions of this Agreement and the ISO OATT, the provisions of this Agreement shall prevail.

1.2 Purpose

This Agreement governs the terms and conditions under which the Interconnection

Customer’s Small Generating Facility will interconnect with, and operate in parallel with, the New York State Transmission System or the Distribution System.

1.3 Scope of Interconnection Service

1.3.1 The New York Independent System Operator, Inc., a not-for-profit corporation   
 organized and existing under the laws of the laws of the State of New York   
 (“NYISO”) will provide Energy Resource Interconnection Service to   
 Interconnection Customer at the Point of Interconnection.

1.3.2 This Agreement does not constitute an agreement to purchase or deliver the   
 Interconnection Customer’s power. The purchase or delivery of power and other   
 services that the Interconnection Customer may require will be covered under   
 separate agreements, if any, or applicable provisions of NYISO’s or Connecting   
 Transmission Owner’s tariffs. The Interconnection Customer will be responsible   
 for separately making all necessary arrangements (including scheduling) for

delivery of electricity in accordance with the applicable provisions of the ISO   
OATT and Connecting Transmission Owner’s tariff. The execution of this   
Agreement does not constitute a request for, nor agreement to, provide Energy, any   
Ancillary Services or Installed Capacity under the NYISO Services Tariff or any   
Connecting Transmission Owner’s tariff. If Interconnection Customer wishes to   
supply or purchase Energy, Installed Capacity or Ancillary Services, then   
Interconnection Customer will make application to do so in accordance with the   
NYISO Services Tariff or Connecting Transmission Owner’s tariff.

1.4 Limitations

Nothing in this Agreement is intended to affect any other agreement between the

3

Connecting Transmission Owner and the Interconnection Customer, except as otherwise expressly provided herein.

1.5 Responsibilities of the Parties

1.5.1 The Parties shall perform all obligations of this Agreement in accordance with all   
 Applicable Laws and Regulations, Operating Requirements, and Good Utility   
 Practice.

1.5.2 The Interconnection Customer shall construct, interconnect, operate and maintain   
 its Small Generating Facility and construct, operate, and maintain its   
 Interconnection Facilities in accordance with the applicable manufacturer’s   
 recommended maintenance schedule, and in accordance with this Agreement, and   
 with Good Utility Practice.

1.5.3 The Connecting Transmission Owner shall construct, operate, and maintain its   
 Interconnection Facilities and Upgrades covered by this Agreement in accordance   
 with this Agreement, and with Good Utility Practice.

1.5.4 The Interconnection Customer agrees to construct its facilities or systems in   
 accordance with applicable specifications that meet or exceed those provided by   
 the National Electrical Safety Code, the American National Standards Institute,   
 IEEE, Underwriter’s Laboratory, and Operating Requirements in effect at the time   
 of construction and other applicable national and state codes and standards. The   
 Interconnection Customer agrees to design, install, maintain, and operate its Small   
 Generating Facility so as to reasonably minimize the likelihood of a disturbance   
 adversely affecting or impairing the system or equipment of the Connecting   
 Transmission Owner or Affected Systems.

1.5.5 The Connecting Transmission Owner and Interconnection Customer shall operate,   
 maintain, repair, and inspect, and shall be fully responsible for the facilities that it   
 now or subsequently may own unless otherwise specified in the Attachments to this   
 Agreement. Each Party shall be responsible for the safe installation, maintenance,   
 repair and condition of its respective lines and appurtenances on its respective sides   
 of the point of change of ownership. The Connecting Transmission Owner and the   
 Interconnection Customer, as appropriate, shall provide Interconnection Facilities   
 that adequately protect the Connecting Transmission Owner’s electric system,   
 personnel, and other persons from damage and injury. The allocation of   
 responsibility for the design, installation, operation, maintenance and ownership of   
 Interconnection Facilities shall be delineated in the Attachments to this Agreement.

4

1.5.6 The Connecting Transmission Owner shall cooperate with the NYISO to coordinate   
 with all Affected Systems to support the interconnection.

1.5.7 The Interconnection Customer shall ensure “frequency ride through” capability and

“voltage ride through” capability of its Small Generating Facility. The   
Interconnection Customer shall enable these capabilities such that its Small   
Generating Facility shall not disconnect automatically or instantaneously from the   
system or equipment of the Connecting Transmission Owner and any Affected   
Systems for a defined under-frequency or over-frequency condition, or an under-  
voltage or over-voltage condition, as tested pursuant to section 2.1 of this

Agreement. The defined conditions shall be in accordance with Good Utility   
Practice and consistent with any standards and guidelines that are applied to other   
generating facilities in the Balancing Authority Area on a comparable basis. The   
Small Generating Facility’s protective equipment settings shall comply with the   
Transmission Owner’s automatic load-shed program. The Transmission Owner   
shall review the protective equipment settings to confirm compliance with the   
automatic load-shed program. The term “ride through” as used herein shall mean   
the ability of a Small Generating Facility to stay connected to and synchronized   
with the system or equipment of the Transmission Owner and any Affected Systems   
during system disturbances within a range of conditions, in accordance with Good   
Utility Practice and consistent with any standards and guidelines that are applied to   
other generating facilities in the Balancing Authority on a comparable basis. The   
term “frequency ride through” as used herein shall mean the ability of a Small   
Generating Facility to stay connected to and synchronized with the system or   
equipment of the Transmission Owner and any Affected Systems during system   
disturbances within a range of under-frequency and over-frequency conditions, in   
accordance with Good Utility Practice and consistent with any standards and   
guidelines that are applied to other generating facilities in the Balancing Authority   
Area on a comparable basis. The term “voltage ride through” as used herein shall   
mean the ability of a Small Generating Facility to stay connected to and   
synchronized with the system or equipment of the Transmission Owner and any   
Affected Systems during system disturbances within a range of under-voltage and   
over-voltage conditions, in accordance with Good Utility Practice and consistent   
with any standards and guidelines that are applied to other generating facilities in   
the Balancing Authority Area on a comparable basis.

1.6 Parallel Operation Obligations

Once the Small Generating Facility has been authorized to commence parallel operation,   
the Interconnection Customer shall abide by all rules and procedures pertaining to the parallel   
operation of the Small Generating Facility in the applicable control area, including, but not limited   
to: (1) the rules and procedures concerning the operation of generation set forth in the NYISO   
tariffs or ISO Procedures or the Connecting Transmission Owner’s tariff; (2) any requirements   
consistent with Good Utility Practice or that are necessary to ensure the safe and reliable operation

5

of the Transmission System or Distribution System; and (3) the Operating Requirements set forth in Attachment 5 of this Agreement.

1.7 Metering

The Interconnection Customer shall be responsible for the Connecting Transmission   
Owner’s reasonable and necessary cost for the purchase, installation, operation, maintenance,   
testing, repair, and replacement of metering and data acquisition equipment specified in   
Attachments 2 and 3 of this Agreement. The Interconnection Customer’s metering (and data   
acquisition, as required) equipment shall conform to applicable industry rules and Operating   
Requirements.

1.8 Reactive Power and Primary Frequency Response

1.8.1 Power Factor Design Criteria

1.8.1.1 Synchronous Generation. The Interconnection Customer shall design its Small Generating Facility to maintain a composite power delivery at continuous rated power output at the Point of Interconnection at a power factor within the range of 0.95 leading to 0.95 lagging, unless the NYISO or the Connecting Transmission Owner in whose Transmission District the Small Generating Facility interconnects has established different requirements that apply to all similarly situated generators in the New York Control Area or Transmission District (as applicable) on a comparable basis, in accordance with Good Utility Practice.

1.8.1.2 Non-Synchronous Generation. The Interconnection Customer shall   
design its Small Generating Facility to maintain a composite power delivery at   
continuous rated power output at the high-side of the generator substation at a   
power factor within the range of 0.95 leading to 0.95 lagging, unless the NYISO or   
the Connecting Transmission Owner in whose Transmission District the Small   
Generating Facility interconnects has established a different power factor range that   
applies toall similarly situated non-synchronous generators in the control area or   
Transmission District (as applicable) on a comparable basis, in accordance with   
Good Utility Practice. This power factor range standard shall be dynamic and canbe   
met using, for example, power electronics designed to supply this level of reactive   
capability (taking into account any limitations due to voltage level, real power   
output, etc.) or fixed and switched capacitors, or a combination of the two. This   
requirement shall only apply to newly interconnecting non-synchronousgenerators   
that have not yet executed a Facilities Study Agreement as of September21, 2016.

6

1.8.2 The Parties understand that the Interconnection Customer shall be paid by the   
 NYISO for reactive power, or voltage support service, that the Interconnection   
 Customer provides from the Small Generating Facility in accordance with Rate   
 Schedule 2 of the NYISO Services Tariff.

1.8.3 Primary Frequency Response. Interconnection Customer shall ensure the primary

frequency response capability of its Small Generating Facility by installing,   
maintaining, and operating a functioning governor or equivalent controls. The term   
“functioning governor or equivalent controls” as used herein shall mean the   
required hardware and/or software that provides frequency responsive real power   
control with the ability to sense changes in system frequency and autonomously   
adjust the Small Generating Facility’s real power output in accordance with the   
droop and deadband parameters and in the direction needed to correct frequency   
deviations. Interconnection Customer is required to install a governor or equivalent   
controls with the capability of operating: (1) with a maximum 5 percentdroop and   
±0.036 Hz deadband; or (2) in accordance with the relevant droop, deadband, and   
timely and sustained response settings from an approved Applicable Reliability   
Standard providing for equivalent or more stringent parameters. The droop   
characteristic shall be: (1) based on the nameplate capacity of the Small Generating   
Facility, and shall be linear in the range of frequencies between 59 to 61 Hz that are   
outside of the deadband parameter; or (2) based on an approved Applicable   
Reliability Standard providing for an equivalent or more stringent parameter. The   
deadband parameter shall be: the range of frequencies above and below nominal   
(60 Hz) in which the governor or equivalent controls is not expectedto adjust the   
Small Generating Facility’s real power output in response to frequencydeviations.   
The deadband shall be implemented: (1) without a step to the droop curve, that is,   
once the frequency deviation exceeds the deadband parameter, the expected change   
in the Small Generating Facility’s real power output in response to frequency   
deviations shall start from zero and then increase (for under-frequencydeviations) or   
decrease (for over-frequency deviations) linearly in proportion to themagnitude of   
the frequency deviation; or (2) in accordance with an approved Applicable

Reliability Standard providing for an equivalent or more stringent parameter. Interconnection Customer shall notify NYISO that the primary frequency response capability of the Small Generating Facility has been tested andconfirmed during commissioning. Once Interconnection Customer has synchronized the Small Generating Facility with the New York State TransmissionSystem, Interconnection Customer shall operate the Small Generating Facility consistent with the provisions specified in Articles 1.8.3.1 and 1.8.3.2 of this Agreement. The primary frequency response requirements contained herein shallapply to both synchronous and nonsynchronous Small Generating Facilities.

1.8.3.1 Governor or Equivalent Controls. Whenever the Small Generating Facility   
is operated in parallel with the New York State Transmission System,   
Interconnection Customer shall operate the Small Generating Facility with its   
governor or equivalent controls in service and responsive to frequency.

7

Interconnection Customer shall: (1) in coordination with NYISO, set the deadband   
parameter to: (1) a maximum of ±0.036 Hz and set the droop parameter to a   
maximum of 5 percent; or (2) implement the relevant droop and deadband settings   
from an approved Applicable Reliability Standard that provides for equivalent or   
more stringent parameters. Interconnection Customer shall be required to provide   
the status and settings of the governor and equivalent controls to NYISO and/or the   
Connecting Transmission Owner upon request. If Interconnection Customer needs   
to operate the Small Generating Facility with its governor or equivalent controls   
not in service, Interconnection Customer shall immediately notify NYISO andthe   
Connecting Transmission Owner, and provide both with the following information:

(1) the operating status of the governor or equivalent controls (i.e., whether it is   
currently out of service or when it will be taken out of service); (2) thereasons for   
removing the governor or equivalent controls from service; and (3) a reasonable   
estimate of when the governor or equivalent controls will be returned to service.   
Interconnection Customer shall make Reasonable Efforts to return its governor or   
equivalent controls into service as soon as practicable. Interconnection Customer   
shall make Reasonable Efforts to keep outages of the Small Generating Facility’s   
governor or equivalent controls to a minimum whenever the Small Generating   
Facility is operated in parallel with the New YorkState Transmission System.

1.8.3.2 Timely and Sustained Response. Interconnection Customer shall ensure   
that the Small Generating Facility’s real power response to sustained frequency   
deviations outside of the deadband setting is automatically provided and shall begin   
immediately after frequency deviates outside of the deadband, and to the extent the   
Small Generating Facility has operating capability in the direction needed to correct   
the frequency deviation. Interconnection Customer shall not block or otherwise   
inhibit the ability of the governor or equivalent controls to respond and shall ensure   
that the response is not inhibited, except under certain operational constraints   
including, but not limited to, ambient temperature limitations, physical energy   
limitations, outages of mechanical equipment, or regulatory requirements. The   
Small Generating Facility shall sustain the real power response at least until system   
frequency returns to a value within the deadband setting of the governor or   
equivalent controls. An Applicable Reliability Standard with equivalent or more   
stringent requirements shall supersede the above requirements.

1.8.3.3 Exemptions. Small Generating Facilities that are regulated by the United   
States Nuclear Regulatory Commission shall be exempt from Articles 1.8.3,

1.8.3.1, and 1.8.3.2 of this Agreement. Small Generating Facilities that are behind   
the meter generation that is sized-to-load (i.e., the thermal load and the generation   
are near-balanced in real-time operation and the generation is primarilycontrolled   
to maintain the unique thermal, chemical, or mechanical output necessary for the   
operating requirements of its host facility) shall be required to install primary   
frequency response capability requirements in accordance with the droop and   
deadband capability requirements specified in Article 1.8.3, but shall be

8

otherwise exempt from the operating requirements in Articles 1.8.3, 1.8.3.1,

1.8.3.2, and 1.8.3.4 of this Agreement.

1.8.3.4 Electric Storage Resources. Interconnection Customer interconnecting an   
electric storage resource shall establish an operating range in Attachment 5 of its   
SGIA that specifies a minimum state of charge and a maximum state of charge   
between which the electric storage resource will be required to provide primary   
frequency response consistent with the conditions set forth in Articles 1.8.3, 1.8.3.1,

1.8.3.2, and 1.8.3.3 of this Agreement. Attachment 5 shall specify whether the   
operating range is static or dynamic, and shall consider (1) the expected magnitude   
of frequency deviations in the interconnection; (2) the expected duration that   
system frequency will remain outside of the deadband parameter in the   
interconnection; (3) the expected incidence of frequency deviations outside of the   
deadband parameter in the interconnection; (4) the physical capabilities of the   
electric storage resource; (5) operational limitations of the electric storage resources   
due to manufacturer specification; and (6) any other relevant factors agreed to by   
theNYISO, Connecting Transmission Owner, and Interconnection Customer. If the   
operating range is dynamic, then Attachment 5 must establish how frequently the   
operating range will be reevaluated and the factors that may be considered during   
its reevaluation.

Interconnection Customer’s electric storage resource is required to provide timely   
and sustained primary frequency response consistent with Article 1.8.3.2 of this   
Agreement when it is online and dispatched to inject electricity to the New York   
State Transmission System and/or receive electricity from the New York State   
Transmission System. This excludes circumstances when the electric storage   
resource is not dispatched to inject electricity to the New York State Transmission   
System and/or dispatched to receive electricity from the New York State   
Transmission System. If Interconnection Customer’s electric storage resource is   
charging at the time of a frequency deviation outside of its deadband parameter, it   
is to increase (for over-frequency deviations) or decrease (for under-frequency   
deviations) the rate at which it is charging in accordance with its droop parameter.   
Interconnection Customer’s electric storage resource is not required to change from   
charging to discharging, or vice versa, unless the response necessitated by the droop   
and deadband settings requires it to do so and it is technically capable of making   
such a transition.

1.9 Capitalized Terms

Capitalized terms used herein shall have the meanings specified in the Glossary of Terms in Attachment 1 or the body of this Agreement. Capitalized terms used herein that are not so defined shall have the meanings specified in Appendix 1 of Attachment Z, Section 25.1.2 of Attachment S, or Section 30.1 of Attachment X of the ISO OATT.

9

Article 2. Inspection, Testing, Authorization, and Right of Access

2.1 Equipment Testing and Inspection

2.1.1 The Interconnection Customer shall test and inspect its Small Generating Facility   
 and Interconnection Facilities prior to interconnection. The Interconnection   
 Customer shall notify the NYISO and theConnecting Transmission Owner of such   
 activities no fewer than five Business Days (or as may be agreed to by the Parties)   
 prior to such testing and inspection. Testing and inspection shall occur on a   
 Business Day. The Connecting Transmission Owner may, at its own expense, send   
 qualified personnel to the Small Generating Facility site to inspect the   
 interconnection and observe the testing. The Interconnection Customer shall   
 provide the NYISO and Connecting Transmission Owner a written test report when   
 such testing and inspection is completed. The Small Generating Facility may not   
 commence parallel operations if the NYISO, in consultation with the Connecting   
 Transmission Owner, finds that the Small Generating Facility has not been installed   
 as agreed upon or may not be operated in a safe and reliable manner.

2.1.2 The Connecting Transmission Owner shall, and the NYISO may, provide the   
 Interconnection Customer written acknowledgment that it has received the   
 Interconnection Customer’s written test report. Such written acknowledgment shall   
 not be deemed to be or construed as any representation, assurance, guarantee,or   
 warranty by the NYISO or Connecting Transmission Owner of the safety,   
 durability, suitability, or reliability of the Small Generating Facility or any   
 associated control, protective, and safety devices owned or controlled by the   
 Interconnection Customer or the quality of power produced by the Small   
 Generating Facility.

2.2 Authorization Required Prior to Parallel Operation

2.2.1 The Connecting Transmission Owner, in consultation with the NYISO, shall use   
 Reasonable Efforts to list applicable parallel Operating Requirements in   
 Attachment 5 of this Agreement. Additionally, the Connecting Transmission   
 Owner, in consultation with the NYISO, shall notify the Interconnection Customer   
 of any changes to these requirements as soon as they are known. The NYISO and   
 Connecting Transmission Owner shall make Reasonable Efforts to cooperate with   
 the Interconnection Customer in meeting requirements necessary for the   
 Interconnection Customer to commence parallel operations by the in-service date.

2.2.2 The Interconnection Customer shall not operate its Small Generating Facility in   
 parallel with the New York State Transmission System or the Distribution System   
 without prior written authorization of the NYISO. The Parties understand that the

10

NYISO, in consultation with the Connecting Transmission Owner, will provide   
such authorization once the NYISO receives notification that the Interconnection   
Customer has complied with all applicable parallel Operating Requirements. Such   
authorization shall not be unreasonably withheld, conditioned, or delayed.

2.3 Right of Access

2.3.1 Upon reasonable notice, the NYISO and/or Connecting Transmission Owner may   
 send a qualified person to the premises of the Interconnection Customer at or   
 immediately before the time the Small Generating Facility first produces energy to   
 inspect the interconnection, and observe the commissioning of the Small   
 Generating Facility (including any required testing), startup, and operation for a   
 period of up to three Business Days after initial start-up of the unit. In addition, the   
 Interconnection Customer shall notify the NYISO and Connecting Transmission   
 Owner at least five Business Days prior to conducting any on-site verification   
 testing of the Small Generating Facility.

2.3.2 Following the initial inspection process described above, at reasonable hours, and   
 upon reasonable notice, or at any time without notice in the event of an emergency   
 or hazardous condition, the NYISO and Connecting Transmission Owner each shall   
 have access to the Interconnection Customer’s premises for any reasonable purpose   
 in connection with the performance of the obligations imposed on them by this   
 Agreement or if necessary to meet their legal obligation to provide service to their   
 customers.

2.3.3 Each Party shall be responsible for its own costs associated with following this   
 article.

11

Article 3 Effective Date, Term, Termination, and Disconnection

3.1 Effective Date

This Agreement shall become effective upon execution by the Parties subject to acceptance   
by FERC (if applicable), or if filed unexecuted, upon the date specified by the FERC. The   
Connecting Transmission Owner shall promptly file, or cause to be filed, this Agreement with   
FERC upon execution, if required. If the Agreement is disputed and the Interconnection Customer   
requests that it be filed with FERC in an unexecuted form, the Connecting TransmissionOwner shall   
file, or cause to be filed, this Agreement and the Connecting Transmission Owner shall identify   
the disputed language.

3.2 Term of Agreement

This Agreement shall become effective on the Effective Date and shall remain in effect for a period of 20 years from the Effective Date or such other longer period as the Interconnection Customer may request and shall be automatically renewed for each successive one-year period thereafter, unless terminated earlier in accordance with article 3.3 of this Agreement.

3.3 Termination

No termination shall become effective until the Parties have complied with all Applicable   
Laws and Regulations applicable to such termination, including the filing with FERC of a notice   
of termination of this Agreement (if required), which notice has been accepted for filing by FERC.

3.3.1 The Interconnection Customer may terminate this Agreement at any time by   
 giving the Connecting Transmission Owner 20 Business Days written notice. The   
 Connecting Transmission Owner may terminate this Agreement after the Small   
 Generating Facility is Retired.

3.3.2 Either Party may terminate this Agreement after Default pursuant to article 7.6.

3.3.3 Upon termination of this Agreement, the Small Generating Facility will be   
 disconnected from the New York State Transmission System or the Distribution   
 System, as applicable. All costs required to effectuate such disconnection shall be   
 borne by the terminating Party, unless such termination resulted from the non-  
 terminating Party’s Default of this Agreement or such non-terminating Party   
 otherwise is responsible for these costs under this Agreement.

3.3.4 The termination of this Agreement shall not relieve either Party of its liabilities and   
 obligations, owed or continuing at the time of the termination. The

12

Interconnection Customer shall pay all amounts in excess of any deposit or other   
security without interest within 30 calendar days after receipt of the invoice for such   
amounts. If the deposit or other security exceeds the invoice, the Connecting   
Transmission Owner shall refund such excess within 30 calendar days of the   
invoice without interest. If the Interconnection Customer disputes an amount to be   
paid the Interconnection Customer shall pay the disputed amount to the Connecting   
Transmission Owner or into an interest bearing escrow account, pending resolution   
of the dispute in accordance with Article 10 of this Agreement.To the extent the   
dispute is resolved in the Interconnection Customer’s favor, that portion of the   
disputed amount will be returned to the Interconnection Customer with interest at   
rates applicable to refunds under the Commission’s regulations. Tothe extent the   
dispute is resolved in the Connecting Transmission Owner’s favor, that portion of   
any escrowed funds and interest will be released to the Connecting Transmission   
Owner.

3.3.5 The limitations of liability, indemnification and confidentiality provisions of this   
 Agreement shall survive termination or expiration of this Agreement.

3.4 Temporary Disconnection

Temporary disconnection shall continue only for so long as reasonably necessary under Good Utility Practice.

3.4.1 Emergency Conditions

“Emergency Condition” shall mean a condition or situation: (1) that in the judgment of the   
Party making the claim is imminently likely to endanger life or property; or (2) that, in the case of   
the NYISO or Connecting Transmission Owner, is imminently likely (as determined in a non-  
discriminatory manner) to cause a material adverse effect on the security of, or damage to the New   
York State Transmission System or Distribution System, the Connecting Transmission Owner’s   
Interconnection Facilities or the electric systems of others to which the New York State   
Transmission System or Distribution System is directly connected; or (3) that, in the case of the   
Interconnection Customer, is imminently likely (as determined in a non-discriminatory manner) to   
cause a material adverse effect on the security of, or damage to, the Small Generating Facility or   
the Interconnection Customer’s Interconnection Facilities. Under Emergency Conditions, the   
NYISO or Connecting Transmission Owner may immediately suspend interconnection service and   
temporarily disconnect the Small Generating Facility. The Connecting Transmission Owner shall   
notify the Interconnection Customer promptly when it becomes aware of an Emergency Condition   
that may reasonably be expected to affect the Interconnection Customer’s operation of the Small   
Generating Facility. The Interconnection Customer shall notify the NYISO and Connecting   
Transmission Owner promptly when it becomes aware of an Emergency Condition that may   
reasonably be expected to affect the New York State Transmission System or Distribution System   
or any Affected Systems. To the extent information is known, the notification shall describe the

13

Emergency Condition, the extent of the damage or deficiency, the expected effect on the operation   
of each Party’s facilities and operations, its anticipated duration, and the necessary corrective   
action.

3.4.2 Routine Maintenance, Construction, and Repair

The NYISO or Connecting Transmission Owner may interrupt interconnection service or   
curtail the output of the Small Generating Facility and temporarily disconnect the Small   
Generating Facility from the New York State Transmission System or Distribution System when   
necessary for routine maintenance, construction, and repairs on the New York State Transmission   
System or Distribution System. The NYISO or theConnecting Transmission Owner shall providethe   
Interconnection Customer with five Business Days’ notice prior to such interruption. The   
Connecting Transmission Owner shall use Reasonable Efforts to coordinate such reduction or   
temporary disconnection with the Interconnection Customer. The Parties understand that any   
actions the NYISO is authorized to take under this article 3.4.2 are conditioned upon the NYISO’s   
use of Reasonable Efforts to coordinate such reduction or temporary disconnection with the   
Interconnection Customer.

3.4.3 Forced Outages

During any forced outage, the NYISO orConnecting Transmission Owner may suspend   
interconnection service to the Interconnection Customer to effect immediate repairs on the New   
York State Transmission System or the Distribution System. The Connecting Transmission Owner   
shall use Reasonable Efforts to provide the Interconnection Customer with prior notice. Ifprior   
notice is not given, the Connecting Transmission Owner shall, upon request, provide the   
Interconnection Customer written documentation after the fact explaining the circumstances of the   
disconnection. The Parties understand that any suspension or disconnection the NYISO is   
authorized to make under this article 3.4.3 is conditioned upon: (i) the NYISO’s use of Reasonable   
Efforts to provide the Interconnection Customer with prior notice; and (ii) if prior notice is not   
given, the NYISO’s provision to the Interconnection Customer, upon request, of written   
documentation after the fact explaining the circumstances of the disconnection.

3.4.4 Adverse Operating Effects

The NYISO orConnecting Transmission Owner shall notify the Interconnection Customeras   
soon as practicable if, based on Good Utility Practice, operation of the Small Generating Facility   
may cause disruption or deterioration of service to other customers served from the same electric   
system, or if operating the Small Generating Facility could cause damage to the New York State   
Transmission System, the Distribution System or Affected Systems, or if disconnection is   
otherwise required under Applicable Reliability Standards or the ISO OATT. Supporting   
documentation used to reach the decision to disconnect shall be provided to the Interconnection   
Customer upon request. If, after notice, the Interconnection Customer fails to remedy the adverse   
operating effect within a reasonable time, the NYISO or Connecting Transmission Owner may   
disconnect the Small Generating Facility. The NYISO or Connecting Transmission Owner shall

14

provide the Interconnection Customer with five Business Day notice of such disconnection, unless the provisions of article 3.4.1 apply.

3.4.5 Modification of the Small Generating Facility

The Interconnection Customer must receive written authorization from the NYISO and   
Connecting Transmission Owner before making any change to the Small Generating Facility that   
may have a material impact on the safety or reliability of the New York State Transmission System   
or the Distribution System. Such authorization shall not be unreasonably withheld.Modifications   
shall be done in accordance with Good Utility Practice. If the Interconnection Customer makes   
such modification without the prior written authorization of the NYISO and Connecting   
Transmission Owner, the Connecting Transmission Owner shall have the right to temporarily   
disconnect the Small Generating Facility. If disconnected, the Small Generating Facility will not   
be reconnected until the unauthorized modifications are authorized or removed.

3.4.6 Reconnection

The Parties shall cooperate with each other to restore the Small Generating Facility,   
Interconnection Facilities, and the New York State Transmission System and Distribution System   
to their normal operating state as soon as reasonably practicable following a temporary   
disconnection.

15

Article 4. Cost Responsibility for Interconnection Facilities and Distribution   
 Upgrades

4.1 Interconnection Facilities

4.1.1 The Interconnection Customer shall pay for the cost of the Interconnection   
 Facilities itemized in Attachment 2 of this Agreement. The Connecting

Transmission Owner, shall provide a best estimate cost, including overheads, for   
the purchase and construction of its Interconnection Facilities and provide adetailed   
itemization of such costs. Costs associated with Interconnection Facilitiesmay be   
shared with other entities that may benefit from such facilities by agreementof the   
Interconnection Customer, such other entities, and the Connecting Transmission   
Owner.

4.1.2 The Interconnection Customer shall be responsible for its share of all reasonable   
 expenses, including overheads, associated with (1) owning, operating, maintaining,   
 repairing, and replacing its own Interconnection Facilities, and (2) operating,   
 maintaining, repairing, and replacing the Connecting Transmission Owner’s   
 Interconnection Facilities, as set forth in Attachment 2 to this Agreement.

4.2 Distribution Upgrades

The Connecting Transmission Owner shall design, procure, construct, install, and own the   
Distribution Upgrades described in Attachment 6 of this Agreement. If the Connecting

Transmission Owner and the Interconnection Customer agree, the Interconnection Customer may construct Distribution Upgrades that are located on land owned by or otherwise under the control of the Interconnection Customer.The actual cost of the Distribution Upgrades, including overheads, shall be directly assigned to theInterconnection Customer. The Interconnection Customer shall be responsible for its share of allreasonable expenses, including overheads, associated with owning, operating, maintaining, repairing, and replacing the Distribution Upgrades, as set forth in Attachment 6 to this Agreement.

16

Article 5. Cost Responsibility for System Upgrade Facilities and System   
 Deliverability Upgrades

5.1 Applicability

No portion of this article 5 shall apply unless the interconnection of the Small Generating Facility requires System Upgrade Facilities or System   
Deliverability Upgrades.

5.2 System Upgrades

The Connecting Transmission Owner shall procure, construct, install, and own the System Upgrade Facilities and System Deliverability Upgrades described in Attachment 6 of this Agreement. To the extent that design work is

necessary in addition to that already accomplished in the Class Year

Interconnection Facilities Study for the Interconnection Customer, the

Connecting Transmission Owner shall perform or cause to be performed such work. If all the Parties agree, the Interconnection Customer may construct System Upgrade Facilities and System Deliverability Upgrades.

5.2.1 As described in Section 32.3.5.3 of the SGIP in Attachment Z of the ISO

OATT, the responsibility of the Interconnection Customer for the cost of the   
System Upgrade Facilities and System Deliverability Upgrades described in   
Attachment 6 of this Agreement shall be determined in accordance with

Attachment S of the ISO OATT, as required by Section 32.3.5.3.2 of

Attachment Z. The Interconnection Customer shall be responsible for all

System Upgrade Facility costs as required by Section 32.3.5.3.2 of Attachment Z or its share of any System Upgrade Facilities and System Deliverability   
Upgrades costs resulting from the final Attachment S process, as applicable, and Attachment 6 to this Agreement shall be revised accordingly.

5.2.2 Pending the outcome of the Attachment S cost allocation process, if applicable,

the Interconnection Customer may elect to proceed with the interconnection of   
its Small Generating Facility in accordance with Section 32.3.5.3 of the SGIP.

5.3 Special Provisions for Affected Systems

For the repayment of amounts advanced to the Affected System Operator for   
System Upgrade Facilities or System Deliverability Upgrades, the   
Interconnection Customer and Affected System Operator shall enter into an   
agreement that provides for such repayment, but only if responsibility for the   
cost of such System Upgrade Facilities is not to be allocated in accordance   
with Attachment S of the ISO OATT. The agreement shall specify the terms   
governing payments to be made by the Interconnection Customer to the   
Affected System Operator as well as the repayment by the Affected System   
Operator.

Article 6. Billing, Payment, Milestones, and Financial Security

6.1 Billing and Payment Procedures and Final Accounting

17

6.1.1 The Connecting Transmission Owner shall bill the Interconnection Customer for   
 the design, engineering, construction, and procurement costs of Interconnection   
 Facilities and Upgrades contemplated by this Agreement on a monthly basis, or as   
 otherwise agreed by the Parties. The Interconnection Customer shall pay all invoice   
 amounts within 30 calendar days after receipt of the invoice.

6.1.2 Within three months of completing the construction and installation of the   
 Connecting Transmission Owner’s Interconnection Facilities and/or Upgrades   
 described in the Attachments to this Agreement, the Connecting Transmission   
 Owner shall provide the Interconnection Customer with a final accounting report   
 of any difference between (1) the Interconnection Customer’s cost responsibility   
 for the actual cost of such facilities or Upgrades, and (2) the Interconnection   
 Customer’s previous aggregate payments to the Connecting Transmission Owner   
 for such facilities or Upgrades. If the Interconnection Customer’s cost   
 responsibility exceeds its previous aggregate payments, the Connecting   
 Transmission Owner shall invoice the Interconnection Customer for the amount   
 due and the Interconnection Customer shall make payment to the Connecting   
 Transmission Owner within 30 calendar days. If the Interconnection Customer’s   
 previous aggregate payments exceed its cost responsibility under this Agreement,   
 the Connecting Transmission Owner shall refund to the Interconnection Customer   
 an amount equal to the difference within 30 calendar days of the final accounting   
 report.

6.1.3 If the Interconnection Customer disputes an amount to be paid, the Interconnection   
 Customer shall pay the disputed amount to the Connecting Transmission Owner or   
 into an interest bearing escrow account, pending resolution of the dispute in   
 accordance with Article 10 of this Agreement. To the extent the dispute is resolved   
 in the Interconnection Customer’s favor, that portion of the disputed amount will   
 be credited or returned to the Interconnection Customer with interest at rates   
 applicable to refunds under the Commission’s regulations. To the extent the dispute   
 is resolved in the Connecting Transmission Owner’s favor, that portion of any   
 escrowed funds and interest will be released to the Connecting TransmissionOwner.

18

6.2 Milestones

Subject to the provisions of the SGIP, the Parties shall agree on milestones for which each   
Party is responsible and list them in Attachment 4 of this Agreement. A Party’s obligations under   
this provision may be extended by agreement. If a Party anticipates that it will be unable to meeta   
milestone for any reason other than a Force Majeure event, it shall immediately notify the other   
Party of the reason(s) for not meeting the milestone and: (1) propose the earliest reasonable   
alternate date by which it can attain this and future milestones, and (2) requesting appropriate   
amendments to Attachment 4. The Party affected by the failure to meet a milestone shall not   
unreasonably withhold agreement to such an amendment unless: (1) it will suffer significant   
uncompensated economic or operational harm from the delay, (2) attainment of the same milestone   
has previously been delayed, or (3) it has reason to believe that the delay in meeting the milestone   
is intentional or unwarranted notwithstanding the circumstances explained by the Party proposing   
the amendment.

6.3 Financial Security Arrangements

At least 20 Business Days prior to the commencement of the design, procurement,   
installation, or construction of a discrete portion of the Connecting Transmission Owner’s   
Interconnection Facilities and Upgrades, the Interconnection Customer shall provide the   
Connecting Transmission Owner, at the Interconnection Customer’s option, a guarantee, a surety   
bond, letter of credit or other form of security that is reasonably acceptable to the Connecting   
Transmission Owner and is consistent with the Uniform Commercial Code of the jurisdiction   
where the Point of Interconnection is located. Such security for payment shall be in an amount   
sufficient to cover the costs for constructing, designing, procuring, and installing the applicable   
portion of the Connecting Transmission Owner’s Interconnection Facilities and Upgrades and shall   
be reduced on a dollar-for-dollar basis for payments made to the Connecting Transmission Owner   
under this Agreement during its term. The Connecting Transmission Owner may draw on any such   
security to the extent that the Interconnection Customer fails to make any payments due underthis   
Agreement. In addition:

6.3.1 The guarantee must be made by an entity that meets the creditworthiness   
 requirements of the Connecting Transmission Owner, and contain terms and   
 conditions that guarantee payment of any amount that may be due from the   
 Interconnection Customer, up to an agreed-to maximum amount.

6.3.2 The letter of credit or surety bond must be issued by a financial institution or insurer   
 reasonably acceptable to the Connecting Transmission Owner and must specify a   
 reasonable expiration date.

6.3.3 Notwithstanding the above, Security posted for System Upgrade Facilities for a   
 Small Generating Facility required to enter the Class Year process, or cash or

19

Security provided for System Deliverability Upgrades, shall meet the requirements for Security contained in Attachment S to the ISO OATT.

Article 7. Assignment, Liability, Indemnity, Force Majeure, Consequential Damages,

and Default

7.1 Assignment

This Agreement, and each and every term and condition hereof, shall be binding upon and inure to the benefit of the Parties hereto and their respective successors and assigns. This Agreement may be assigned by either Party upon 15 Business Days prior written notice and opportunity to object by the other Party; provided that:

7.1.1 A Party may assign this Agreement without the consent of the other Parties to any   
 affiliate of the assigning Party with an equal or greater credit rating and with the   
 legal authority and operational ability to satisfy the obligations of the assigning   
 Party under this Agreement, provided that the Interconnection Customer promptly   
 notifies the NYISO andthe Connecting Transmission Owner of any such   
 assignment. A Party may assign this Agreement without the consent of the other   
 Party in connection with the sale, merger, restructuring, or transfer of a substantial   
 portion of all of its assets, including the Interconnection Facilities it owns, so long   
 as the assignee in such a transaction directly assumes all rights, duties and   
 obligation arising under this Agreement.

7.1.2 The Interconnection Customer shall have the right to assign this Agreement,   
 without the consent of the NYISO orConnecting Transmission Owner, for   
 collateral security purposes to aid in providing financing for the Small Generating   
 Facility.

7.1.3 Any attempted assignment that violates this article is void and ineffective.   
 Assignment shall not relieve a Party of its obligations, nor shall a Party’s   
 obligations be enlarged, in whole or in part, by reason thereof. An assignee is   
 responsible for meeting the same financial, credit, and insurance obligations as the   
 Interconnection Customer. Where required, consent to assignment will not be   
 unreasonably withheld, conditioned or delayed.

7.2 Limitation of Liability

Each Party’s liability to the other Party for any loss, cost, claim, injury, liability, or expense,   
including reasonable attorney’s fees, relating to or arising from any act or omission in its   
performance of this Agreement, shall be limited to the amount of direct damage actually incurred.

20

In no event shall either Party be liable to the other Party for any indirect, special, consequential, or punitive damages.

7.3 Indemnity

7.3.1 This provision protects each Party from liability incurred to third parties as a result   
 of carrying out the provisions of this Agreement. Liability under this provision is   
 exempt from the general limitations on liability found in article 7.2.

7.3.2 Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and   
 hold harmless the other Party (the “ Indemnified Party”) from, any and all damages,   
 losses, claims, including claims and actions relating to injury to or death of any   
 person or damage to property, the alleged violation of any Environmental Law, or   
 the release or threatened release of any Hazardous Substance, demand, suits,   
 recoveries, costs and expenses, court costs, attorney fees, and all other obligations   
 by or to third parties (any and all of these a “Loss”), arising out of or resulting from:

(i) the Indemnified Party’s performance under this Agreement on behalf of the Indemnifying Party, except in cases where the Indemnifying Party can demonstrate that the Loss of the Indemnified Party was caused by the gross negligence or intentional wrongdoing by the Indemnified Party, or (ii) the violation by the Indemnifying Party of any Environmental Law or the release by the Indemnifying Party of a Hazardous Substance.

7.3.3 If a Party is entitled to indemnification under this article as a result of a claim by a   
 third party, and the Indemnifying Party fails, after notice and reasonable   
 opportunity to proceed under this article, to assume the defense of such claim, such   
 Indemnified Party may at the expense of the Indemnifying Party contest, settle or   
 consent to the entry of any judgment with respect to, or pay in full, such claim.

7.3.4 If the Indemnifying Party is obligated to indemnify and hold the Indemnified Party   
 harmless under this article, the amount owing to the Indemnified Party shall be the   
 amount of such Indemnified Party’s actual loss, net of any insurance or other   
 recovery.

7.3.5 Promptly after receipt by the Indemnified Party of any claim or notice of the   
 commencement of any action or administrative or legal proceeding or investigation   
 as to which the indemnity provided for in this article may apply, the Indemnified   
 Party shall notify the Indemnifying Party of such fact. Any failure of or delay in   
 such notification shall not affect a Party’s indemnification obligation unless such   
 failure or delay is materially prejudicial to the Indemnifying Party.

21

7.4 Consequential Damages

Other than as expressly provided for in this Agreement, neither Party shall be liable under any provision of this Agreement for any losses, damages, costs or expenses for any special, indirect, incidental, consequential, or punitive damages, including but not limited to loss of profit or revenue, loss of the use of equipment, cost of capital, cost of temporary equipment or services, whether based in whole or in part in contract, in tort, including negligence, strict liability, or any other theory of liability; provided, however, that damages for which a Party may be liable to the other Party under another agreement will not be considered to be special, indirect, incidental, or consequential damages hereunder.

7.5 Force Majeure

7.5.1 As used in this article, a “Force Majeure Event” shall mean “any act of God, labor   
 disturbance, act of the public enemy, war, insurrection, riot, fire, storm or flood,   
 explosion, breakage or accident to machinery or equipment, any order, regulation   
 or restriction imposed by governmental, military or lawfully established civilian   
 authorities, or any other cause beyond a Party’s control. A Force Majeure Event   
 does not include an act of negligence or intentional wrongdoing.” For the purposesof   
 this article, this definition of Force Majeure shall supersede the definitions of Force   
 Majeure set out in Section 32.10.1 of the ISO OATT.

7.5.2 If a Force Majeure Event prevents a Party from fulfilling any obligations under this   
 Agreement, the Party affected by the Force Majeure Event (“Affected Party”) shall   
 promptly notify the other Party, either in writing or via the telephone, of the   
 existence of the Force Majeure event. The notification must specify in reasonable   
 detail the circumstances of the Force Majeure Event, its expected duration, and the   
 steps that the Affected Party is taking to mitigate the effects of the event on its   
 performance. The Affected Party shall keep the other Party informed on a   
 continuing basis of developments relating to the Force Majeure Event until the   
 event ends. The Affected Party will be entitled to suspend or modify its   
 performance of obligations under this Agreement (other than the obligation to make   
 payments) only to the extent that the effect of the Force Majeure Event cannot be   
 mitigated by the use of Reasonable Efforts. The Affected Party will use Reasonable   
 Efforts to resume its performance as soon as possible.

7.6 Breach and Default

7.6.1 No Breach of this Agreement shall exist where such failure to discharge an   
 obligation (other than the payment of money) is the result of a Force Majeure Event   
 or the result of an act or omission of the other Party. Upon a Breach, the non-  
 breaching Party shall give written notice of such Breach to the Breaching Party.

22

Except as provided in article 7.6.2, the Breaching Party shall have 60 calendar days   
from receipt of the Breach notice within which to cure such Breach; provided   
however, if such Breach is not capable of cure within 60 calendar days, the   
Breaching Party shall commence such cure within 20 calendar days after notice and   
continuously and diligently complete such cure within six months from receipt of   
the Breach notice; and, if cured within such time, the Breach specified in such   
notice shall cease to exist.

7.6.2 If a Breach is not cured as provided in this article, or if a Breach is not capable of   
 being cured within the period provided for herein, a Default shall exist and the non-  
 defaulting Party shall thereafter have the right to terminate this Agreement, in   
 accordance with article 3.3 hereof, by written notice to the defaulting Party at any   
 time until cure occurs, and be relieved of any further obligation hereunder and,   
 whether or not that Party terminate this Agreement, to recover from the defaulting   
 Party all amounts due hereunder, plus all other damages and remedies to which they   
 are entitled at law or in equity. The provisions of this article shall survive   
 termination of this Agreement.

7.6.3 In cases where the Interconnection Customer has elected to proceed under Section

32.3.5.3 of the SGIP, if the Interconnection Request is withdrawn or deemed withdrawn pursuant to the SGIP during the term of this Agreement, this Agreement shall terminate.

23

Article 8. Insurance

8.1 The Interconnection Customer shall, at its own expense, maintain in force general liability

insurance without any exclusion for liabilities related to the interconnection undertaken   
pursuant to this Agreement. The amount of such insurance shall be sufficient to insure   
against all reasonably foreseeable direct liabilities given the size and nature of the   
generating equipment being interconnected, the interconnection itself, and the   
characteristics of the system to which the interconnection is made. Such insurance coverage   
is specified in Attachment 7 to this Agreement. The Interconnection Customer shall obtain   
additional insurance only if necessary as a function of owning and operating agenerating   
facility. Such insurance shall be obtained from an insurance provider authorized to do   
business in New York State where the interconnection is located.Certification that such   
insurance is in effect shall be provided upon request of the Connecting Transmission   
Owner, except that the Interconnection Customer shall show proof of insurance to the   
Connecting Transmission Owner no later than ten Business Daysprior to the anticipated   
commercial operation date. An Interconnection Customer of sufficient creditworthiness   
may propose to self-insure for such liabilities, and such a proposal shall not be   
unreasonably rejected.

8.2 The Connecting Transmission Owner agree to maintain general liability insurance or self-

insurance consistent with the existing commercial practice. Such insurance or selfinsurance shall not exclude the liabilities undertaken pursuant to this Agreement.

8.3 The Parties further agree to notify one another whenever an accident or incident occurs

resulting in any injuries or damages that are included within the scope of coverage of such insurance, whether or not such coverage is sought.

24

Article 9. Confidentiality

9.1 Confidential Information shall mean any confidential and/or proprietary information

provided by one Party to the other Party that is clearly marked or otherwise designated   
“Confidential.” For purposes of this Agreement all design, operating specifications, and   
metering data provided by the Interconnection Customer shall be deemed Confidential   
Information regardless of whether it is clearly marked or otherwise designated as such.   
Confidential Information shall include, without limitation, information designated as such   
by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

9.2 Confidential Information does not include information previously in the public domain,

required to be publicly submitted or divulged by Governmental Authorities (after notice to the other Party and after exhausting any opportunity to oppose such publication or release), or necessary to be divulged in an action to enforce this Agreement. Each Party receiving Confidential Information shall hold such information in confidence and shall not disclose it to any third party nor to the public without the prior written authorization from the Party providing that information, except to fulfill obligations under this Agreement, or to fulfill legal or regulatory requirements.

9.2.1 Each Party shall employ at least the same standard of care to protect Confidential   
 Information obtained from the other Party as it employs to protect its own   
 Confidential Information.

9.2.2 Each Party is entitled to equitable relief, by injunction or otherwise, to enforce its   
 rights under this provision to prevent the release of Confidential Information   
 without bond or proof of damages, and may seek other remedies available at law or   
 in equity for breach of this provision.

9.3 Notwithstanding anything in this article to the contrary, and pursuant to 18 CFR §

lb.20, if FERC, during the course of an investigation or otherwise, requests   
information from the other Party that is otherwise required to be maintained in   
confidence pursuant to this Agreement, the Party shall provide the requested   
information to FERC, within the time provided for in the request for information.   
In providing the information to FERC, the Party may, consistent with 18 CFR §   
388.112, request that the information be treated as confidential and non-public by   
FERC and that the information be withheld from public disclosure. Each Party is   
prohibited from notifying the other Party to this Agreement prior to the release of   
the Confidential Information to FERC. The Party shall notify the other Party to this   
Agreement when it is notified by FERC that a request to release Confidential   
Information has been received by FERC, at which time either of the Parties may   
respond before such information would be made public, pursuant to 18 CFR §   
388.112. Requests from a state regulatory body conducting a confidential   
investigation shall be treated in a similar manner if consistent with the applicable

25

state rules and regulations.

9.4 Consistent with the provisions of this article 9, the Parties to this Agreement will

cooperate in good faith to provide each other, Affected Systems, Affected System

Operators, and state and federal regulators the information necessary to carry out

the terms of the SGIP and this Agreement.

Article 10. Disputes

10.1 The NYISO, Connecting Transmission Owner and Interconnection Customer agree to attempt to

resolve all disputes arising out of the interconnection process according to the provisions of this   
article.

10.2 In the event of a dispute, the Parties will first attempt to promptly resolve it on an informal basis.

The NYISO will be available to the Interconnection Customer and Connecting Transmission

Owner to help resolve any dispute that arises with respect to performance under this Agreement. If the Parties cannot promptly resolve the dispute on an informal basis, then any Party shall   
provide the other Parties with a written Notice of Dispute. Such notice shall describe in detail the nature of the dispute.

10.3 If the dispute has not been resolved within two Business Days after receipt of the notice, any Party

may contact FERC’s Dispute Resolution Service (“DRS”) for assistance in resolving the dispute.

10.4 The DRS will assist the Parties in either resolving their dispute or in selecting an appropriate

dispute resolution venue (e.g., mediation, settlement judge, early neutral evaluation, or technical   
expert) to assist the Parties in resolving their dispute. The result of this dispute resolution process   
will be binding only if the Parties agree in advance. DRS can be reached at 1-877-337-2237 or   
via the internet at [http://www.ferc.gov/legal/adr.asp.](http://www.ferc.gov/legal/adr.asp./)

10.5 Each Party agrees to conduct all negotiations in good faith and will be responsible for one-third of

any costs paid to neutral third-parties.

10.6 If any Party elects to seek assistance from the DRS, or if the attempted dispute resolution fails,

then any Party may exercise whatever rights and remedies it may have in equity or law consistent with the terms of this Agreement.

26

Article 11. Taxes

11.1 The Parties agree to follow all applicable tax laws and regulations, consistent with

FERC policy and Internal Revenue Service requirements.

11.2 Each Party shall cooperate with the other Parties to maintain the other Party’s tax

status. Nothing in this Agreement is intended to adversely affect the tax status of   
either Party including the status of any Connecting Transmission Owner with   
respect to the issuance ofbonds including, but not limited to, Local Furnishing   
Bonds. Notwithstanding any other provisions of this Agreement, LIPA, NYPA   
and Consolidated Edison Company of New York, Inc. shall not be required to   
comply with any provisions of this Agreement that would result in the loss of tax-  
exempt status of any of their Tax-Exempt Bonds or impair their ability to issue   
future tax-exempt obligations. For purposes of this provision, Tax-Exempt Bonds   
shall include the obligations of the Long Island Power Authority, NYPA and   
Consolidated Edison Company of New York, Inc., the interest on which is not   
included in gross income under the Internal Revenue Code.

11.3 LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the

FPA, from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general ratemaking authority.

11.4 Any payments due to the Connecting Transmission Owner under this Agreement shall be

adjusted to include any tax liability incurred by the Connecting Transmission Owner with respect to the interconnection request which is the subject of this Agreement. Such adjustments shall be made in accordance with the provisions of Article 5.17 of the LGIA in Attachment X of the ISO OATT. Except where otherwise noted, all costs, deposits, financial obligations and the like specified in this Agreement shall be assumed not to reflect the impact of applicable taxes.

27

Article 12. Miscellaneous

12.1 Governing Law, Regulatory Authority, and Rules

The validity, interpretation and enforcement of this Agreement and each of its provisions shall be governed by the laws of the state of New York, without regard to its conflicts of law principles. This Agreement is subject to all Applicable Laws and Regulations. Each Party expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, or regulations of a Governmental Authority.

12.2 Amendment

The Parties may amend this Agreement by a written instrument duly executed by the Parties, or under article 12.12 of this Agreement.

12.3 No Third-Party Beneficiaries

This Agreement is not intended to and does not create rights, remedies, or benefits of any   
character whatsoever in favor of any persons, corporations, associations, or entities other than the   
Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their   
successors in interest and where permitted, their assigns. Notwithstanding the foregoing, any   
subcontractor of the Connecting Transmission Owner assisting that Party with the Interconnection   
Request covered by this Agreement shall be entitled to the benefits of indemnification provided   
for under Article 7.3 of this Agreement and the limitation of liability provided for in Article 7.2 of   
this Agreement.

12.4 Waiver

12.4.1 The failure of a Party to this Agreement to insist, on any occasion, upon strict   
 performance of any provision of this Agreement will not be considered a waiver of   
 any obligation, right, or duty of, or imposed upon, such Party.

12.4.2 Any waiver at any time by a Party of its rights with respect to this Agreement shall   
 not be deemed a continuing waiver or a waiver with respect to any other failure to   
 comply with any other obligation, right, duty of this Agreement. Termination or   
 default of this Agreement for any reason by Interconnection Customer shall not   
 constitute a waiver of the Interconnection Customer’s legal rights to obtain an   
 interconnection from the NYISO. Any waiver of this Agreement shall, if requested,   
 be provided in writing.

28

12.5 Entire Agreement

This Agreement, including all Attachments, constitutes the entire agreement between the Parties with reference to the subject matter hereof, and supersedes all prior and contemporaneous understandings or agreements, oral or written, between the Parties with respect to the subject matter of this Agreement. There are no other agreements, representations, warranties, or covenants which constitute any part of the consideration for, or any condition to, either Party’s compliance with its obligations under this Agreement.

12.6 Multiple Counterparts

This Agreement may be executed in two or more counterparts, each of which is deemed an original but all constitute one and the same instrument.

12.7 No Partnership

This Agreement shall not be interpreted or construed to create an association, joint venture, agency relationship, or partnership between the Parties or to impose any partnership obligation or partnership liability upon either Party. Neither Party shall have any right, power or authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, the other Party.

12.8 Severability

If any provision or portion of this Agreement shall for any reason be held or adjudged to   
be invalid or illegal or unenforceable by any court of competent jurisdiction or other Governmental   
Authority, (1) such portion or provision shall be deemed separate and independent, (2) the Parties   
shall negotiate in good faith to restore insofar as practicable the benefits to each Party that were   
affected by such ruling, and (3) the remainder of this Agreement shall remain in full force and   
effect.

12.9 Security Arrangements

Infrastructure security of electric system equipment and operations and control hardware   
and software is essential to ensure day-to-day reliability and operational security. FERC expects   
the NYISO, the Connecting Transmission Owner, Market Participants, and Interconnection   
Customers interconnected to electric systems to comply with the recommendations offered by the   
President’s Critical Infrastructure Protection Board and, eventually, best practice   
recommendations from the electric reliability authority. All public utilities are expected to meet   
basic standards for system infrastructure and operational security, including physical, operational,

29

and cyber-security practices.

12.10 Environmental Releases

Each Party shall notify the other Party, first orally and then in writing, of the release of any   
hazardous substances, any asbestos or lead abatement activities, or any type of remediation   
activities related to the Small Generating Facility or the Interconnection Facilities, each of which   
may reasonably be expected to affect the other Party. The notifying Party shall: (1) provide the   
notice as soon as practicable, provided such Party makes a good faith effort to provide the notice   
no later than 24 hours after such Party becomes aware of the occurrence, and (2) promptly furnish   
to the other Party copies of any publicly available reports filed with any governmental authorities   
addressing such events.

12.11 Subcontractors

Nothing in this Agreement shall prevent a Party from utilizing the services of any subcontractor as it deems appropriate to perform its obligations under this Agreement; provided, however, that each Party shall require its subcontractors to comply with all applicable terms and conditions of this Agreement in providing such services and each Party shall remain primarily liable to the other Party for the performance of such subcontractor.

12.11.1 The creation of any subcontract relationship shall not relieve the hiring

Party of any of its obligations under this Agreement. The hiring Party shall   
be fully responsible to the other Party to the extent provided for in Sections

32.7.2 and 32.7.3 above for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been made; provided, however, that in no event shall the Connecting Transmission Owner be liable for the actions or inactions of the Interconnection Customer or its subcontractors with respect to obligations of the Interconnection Customer under this Agreement. Any applicable obligation imposed by this Agreement upon the hiring Party shall be equally binding upon, and shall be construed as having application to, any subcontractor of such Party.

12.11.2 The obligations under this article will not be limited in any way by any

limitation of subcontractor’s insurance.

12.12 Reservation of Rights

Nothing in this Agreement shall alter the right of the Connecting Transmission Owner to   
make unilateral filings with FERC to modify this Agreement with respect to any rates, terms and   
conditions, charges, classifications of service, rule or regulation under Section 205 or any other

30

applicable provision of the Federal Power Act and FERC’s rules and regulations thereunder which rights are expressly reserved herein, and the existing rights of the Interconnection Customer to make a unilateral filing with FERC to modify this Agreement under any applicable provision of the Federal Power Act and FERC’s rules and regulations are also expressly reserved herein; provided that each Party shall have the right to protest any such filing by the other Party and to participate fully in any proceeding before FERC in which such modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties or of FERC under Sections 205 or 206 of the Federal Power Act and FERC’s rules and regulations, except to the extent that the Parties otherwise agree as provided herein.

Article 13. Notices

13.1 General

Unless otherwise provided in this Agreement, any written notice, demand, or request required or authorized in connection with this Agreement shall be deemed properly given if delivered in person, delivered by recognized national currier service, or sent by first class mail, postage prepaid, to the person specified below:

If to the Interconnection Customer:

Interconnection Customer: Capital Hill Solar LLC Attention: William Miller

Address: 106 Isabella Street, Suite 400

City: Pittsburgh State: PA Zip: 15212

Phone: (412) 618-7721

If to the Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a/ National Grid Attention: Kevin Reardon, Director, Commercial Services Address: 40 Sylvan Road

City: Waltham State: MA Zip: 02451

Phone: (781) 907-2411   
Fax: (781) 907-5707

E-mail: Kevin.reardon@nationalgrid.com

31

13.2 Billing and Payment

Billings and payments shall be sent to the addresses set out below:

Interconnection Customer: Capital Hill Solar LLC   
 Attention: William Miller

Address: 106 Isabella Street, Suite 400

City: Pittsburgh State: PA Zip: 15212

Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a/ National Grid Attention: Kevin Reardon, Director, Commercial Services Address: 40 Sylvan Road

City: Waltham State: MA Zip: 02451

Phone: (781) 907-2411   
Fax: (781) 907-5707

E-mail: Kevin.reardon@nationalgrid.com

13.3 Alternative Forms of Notice

Any notice or request required or permitted to be given by either Party to the other and not required by this Agreement to be given in writing may be so given by telephone or e-mail to the telephone numbers and e-mail addresses set out below:

If to the Interconnection Customer:

Interconnection Customer: Capital Hill Solar LLC Attention: William Miller

Address: 106 Isabella Street, Suite 400

City: Pittsburgh State: PA Zip: 15212

Phone: (412) 618-7721

E-mail: William.miller@oridenpower.com

If to the Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a/ National Grid   
Attention: Kevin Reardon, Director, Commercial Services

32

Address: 40 Sylvan Road

City: Waltham State: MA Zip: 02451

Phone: (781) 907-2411   
Fax: (781) 907-5707

E-mail: Kevin.reardon@nationalgrid.com

33

13.4 Designated Operating Representative

The Parties may also designate operating representatives to conduct the communications   
which may be necessary or convenient for the administration of this Agreement. This person will   
also serve as the point of contact with respect to operations and maintenance of the Party’s   
facilities.

Interconnection Customer’s Operating Representative:

Interconnection Customer: Capital Hill Solar LLC Attention: Gary Verkleeren

Address: 106 Isabella Street, Suite 400

City: Pittsburgh State: PA Zip: 15212

Phone: (412) 915-9017

E-mail: gary.verkleeren@oridenpower.com

Connecting Transmission Owner’s Operating Representative: Niagara Mohawk Corporation d/b/a National Grid

Attention: ERCC Shift Supervisor

Address: 5215 Western Turnpike

City: Altamont State: NY Zip: 12009 Phone: (518) 356-6471

34

13.5 Changes to the Notice Information

Either Party may change this information by giving five Business Days written notice prior to the effective date of the change.

35

Article 14.Signatures

IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their respective duly authorized representatives.

For the Connecting Transmission Owner

Sign:

Name:   
Title:   
Date:

For the Interconnection Customer   
Sign:

Name: Masahiro Ogiso Title: President

Date: June , 2021

36

Attachment 1 - Glossary of Terms

Affected System - An electric system other than the transmission system owned, controlled or operated by the Connecting Transmission Owner that may be affected by the proposed interconnection.

Affected System Operator - Affected System Operator shall mean the operator of any Affected   
System.

Affected Transmission Owner - The New York public utility or authority (or its designated agent) other than the Connecting Transmission Owner that: (i) owns facilities used for the transmission of Energy in interstate commerce and provides Transmission Service under the Tariff,and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State Transmission System where System Deliverability Upgrades or System Upgrade Facilities are installed pursuant to Attachment Z and Attachment S to the ISO OATT.

Applicable Laws and Regulations - All duly promulgated applicable federal, state and local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or administrative orders, permits and other duly authorized actions of any Governmental Authority, including but not limited to Environmental Law.

Applicable Reliability Standards - The criteria, requirements and guidelines of the North   
American Electric Reliability Council, the Northeast Power Coordinating Council, the New York   
State Reliability Council and related and successor organizations, or the Transmission District to   
which the Interconnection Customer’s Small Generating Facility is directly interconnected, as   
those criteria, requirements and guidelines are amended and modified and in effect from time to   
time; provided that neither Party shall waive its right to challenge the applicability of or validity   
of any criterion, requirement or guideline as applied to it in the context of Attachment Z to the ISO   
OATT and this Agreement. For the purposes of this Agreement, this definition of Applicable   
Reliability Standards shall supersede the definition of Applicable Reliability Standards set out in   
Attachment X to the ISO OATT.

Base Case - The base case power flow, short circuit, and stability data bases used for the Interconnection Studies by NYISO, Connecting Transmission Owner or Interconnection Customer; described in Section 32.2.3 of the Large Facility Interconnection Procedures.

Breach - The failure of a Party to perform or observe any material term or condition of this Agreement.

Business Day - Monday through Friday, excluding federal holidays.

37

Capacity Resource Interconnection Service - The service provided by NYISO to

Interconnection Customers that satisfy the NYISO Deliverability Interconnection Standard or that   
are otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT; such   
service being one of the eligibility requirements for participation as a NYISO Installed Capacity   
Supplier.

Commercial Operation shall mean the status of the Small Generating Facility that has

commenced generating electricity for sale, excluding electricity generated during Trial Operation,   
notice of which must be provided to the NYISO in the form of Attachment 9 to this Agreement.

Connecting Transmission Owner - The New York public utility or authority (or its designated agent) that: (i) owns facilities used for the transmission of Energy in interstate commerce and provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an interest in the portion of the New York State Transmission System or Distribution System at the Point of Interconnection, and (iii) is a Party to this Agreement.

Default - The failure of a Party in Breach of this Agreement to cure such Breach under this Agreement.

Distribution System - The Transmission Owner’s facilities and equipment used to distribute   
electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s Large Facility   
Interconnection Procedures in Attachment X to the ISO OATT or Small Generator Interconnection   
Procedures in Attachment Z to the ISO OATT under FERC Order Nos. 2003 and/or 2006. For the   
purpose of this Agreement, the term Distribution System shall not include LIPA’s distribution   
facilities.

Distribution Upgrades - The additions, modifications, and upgrades to the Connecting

Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate interconnection of the Small Generating Facility and render the transmission service necessary to effect the Interconnection Customer’s wholesale sale of electricity in interstate commerce. Distribution Upgrades do not include Interconnection Facilities or System Upgrade Facilities or System Deliverability Upgrades.

Energy Resource Interconnection Service - The service provided by NYISO to interconnect the   
Interconnection Customer’s Small Generating Facility to the New York State Transmission   
System or Distribution System in accordance with the NYISO Minimum Interconnection   
Standard, to enable the New York State Transmission System to receive Energy and Ancillary   
Services from the Small Generating Facility, pursuant to the terms of the ISO OATT.

Force Majeure - Any act of God, labor disturbance, act of the public enemy, war, insurrection,   
riot, fire, storm or flood, explosion, breakage or accident to machinery or equipment, any order,   
regulation or restriction imposed by governmental, military or lawfully established civilian   
authorities, or any other cause beyond a Party’s control. A Force Majeure event does not include   
an act of negligence or intentional wrongdoing. For the purposes of this Agreement, this definition   
of Force Majeure shall supersede the definitions of Force Majeure set out in Section

38

32.2.11 of the NYISO Open Access Transmission Tariff.

39

Good Utility Practice - Any of the practices, methods and acts engaged in or approved by a   
significant portion of the electric industry during the relevant time period, or any of the practices,   
methods and acts which, in the exercise of reasonable judgment in light of the facts known at the   
time the decision was made, could have been expected to accomplish the desired result at a   
reasonable cost consistent with good business practices, reliability, safety and expedition. Good   
Utility Practice is not intended to be limited to the optimum practice, method, or act to the   
exclusion of all others, but rather to be acceptable practices, methods, or acts generally accepted   
in the region.

Governmental Authority - Any federal, state, local or other governmental regulatory or   
administrative agency, court, commission, department, board, or other governmental subdivision,   
legislature, rulemaking board, tribunal, or other governmental authority having jurisdiction over   
the Parties, their respective facilities, or the respective services they provide, and exercising or   
entitled to exercise any administrative, executive, police, or taxing authority or power; provided,   
however, that such term does not include the Interconnection Customer, NYISO, Affected   
Transmission Owner, Connecting Transmission Owner or any Affiliate thereof.

Initial Synchronization Date shall mean the date upon which the Small Generating Facility is

initially synchronized and upon which Trial Operation begins, notice of which must be provided to the NYISO in the form of Attachment 8.

In-Service Date shall mean the date upon which the Developer reasonably expects it will be ready   
to begin use of the Connecting Transmission Owner’s Interconnection Facilities to obtain back feed   
power.

Interconnection Customer - The entity, including the Transmission Owner or any of the affiliates or subsidiaries, that proposes to interconnect its Small Generating Facility with the New York State Transmission System or the Distribution System.

Interconnection Facilities - The Connecting Transmission Owner’s Interconnection Facilities and the Interconnection Customer’s Interconnection Facilities. Collectively, Interconnection Facilities include all facilities and equipment between the Small Generating Facility and the Point of Interconnection, including any modification, additions or upgrades that are necessary to physically and electrically interconnect the Small Generating Facility to the New York State Transmission System or the Distribution System. Interconnection Facilities are sole use facilitiesand shall not include Distribution Upgrades or System Upgrade Facilities.

Interconnection Request - The Interconnection Customer’s request, in accordance with the   
Tariff, to interconnect a new Small Generating Facility, or to materially increase the capacity of,   
or make a material modification to the operating characteristics of, an existing Small Generating   
Facility that is interconnected with the New York State Transmission System or the Distribution   
System. For the purposes of this Agreement, this definition of Interconnection Request shall   
supersede the definition of Interconnection Request set out in Attachment X to the ISO OATT.

40

Interconnection Study - Any study required to be performed under Sections 32.2 or 32.3 of the   
SGIP.

ISO - The NYISO.

41

Material Modification - A modification that has a material impact on the cost or timing of any Interconnection Request with a later queue priority date.

New York State Transmission System - The entire New York State electric transmission system,   
which includes: (i) the Transmission Facilities under ISO Operational Control; (ii) the

Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities within the New York Control Area.

NYISO - The New York Independent System Operator, Inc. or its successor.

NYISO Deliverability Interconnection Standard - The standard that must be met, unless   
otherwise provided for by Attachment S to the ISO OATT, by (i) any generation facility larger   
than 2 MW in order for that facility to obtain CRIS; (ii) any Class Year Transmission Project   
proposing to interconnect to the New York State Transmission System and receive Unforced   
Capacity Delivery Rights; (iii) any entity requesting External CRIS Rights, and (iv) any entity   
requesting a CRIS transfer pursuant to Section 25.9.5 of Attachment S to the ISO OATT. To meet   
the NYISO Deliverability Interconnection Standard, the Interconnection Customer must, in   
accordance with the rules in Attachment S to the ISO OATT, fund or commit to fund any System   
Deliverability Upgrades identified for its project in the Class Year Deliverability Study.

NYISO Minimum Interconnection Standard - The reliability standard that must be met by any   
generation facility or Class Year Transmission Project that is subject to NYISO’s Large Facility   
Interconnection Procedures in Attachment X to the ISO OATT or the NYISO’s Small Generator   
Interconnection Procedures in this Attachment Z, that is proposing to connect to the New York   
State Transmission System or Distribution System, to obtain ERIS. The Minimum Interconnection   
Standard is designed to ensure reliable access by the proposed project to the NewYork State   
Transmission System or to the Distribution System. The Minimum Interconnection Standard does   
not impose any deliverability test or deliverability requirement on the proposed interconnection.

OATT - The Tariff.

Operating Requirements - Any operating and technical requirements that may be applicable due to Regional Transmission Organization, Independent System Operator, control area, or the Connecting Transmission Owner’s requirements, including those set forth in this Agreement. Operating Requirements shall include Applicable Reliability Standards.

Party or Parties - The Connecting Transmission Owner, Interconnection Customer or both.

Point of Interconnection - The point where the Interconnection Facilities connect with the New York State Transmission System or the Distribution System.

42

Reasonable Efforts - With respect to an action required to be attempted or taken by a Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and are otherwise substantially equivalent to those a Party would use to protect its own interests.

Small Generating Facility - The Interconnection Customer’s device no larger than 20 MW for the production and/or storage for later injection of electricity identified in the Interconnection Request, but shall not include the Interconnection Customer’s Interconnection Facilities.

System Deliverability Upgrades - The least costly configuration of commercially available components of electrical equipment that can be used, consistent with Good Utility Practice and Applicable Reliability Requirements, to make the modifications or additions to the existing New York State Transmission System that are required for the proposed project to connect reliably to the system in a manner that meets the NYISO Deliverability Interconnection Standard for Capacity Resource Interconnection Service.

System Upgrade Facilities - The least costly configuration of commercially available components   
of electrical equipment that can be used, consistent with good utility practice and Applicable   
Reliability Requirements to make the modifications to the existing transmission system that are   
required to maintain system reliability due to: (i) changes in the system, including such changesas   
load growth and changes in load pattern, to be addressed in the form of generic generation or   
transmission projects; and (ii) proposed interconnections. In the case of proposed interconnection   
projects, System Upgrade Facilities are the modification or additions to the existing New York   
State Transmission System that are required for the proposed project to connect reliably to the   
system in a manner that meets the NYISO Minimum Interconnection Standard.

Tariff - The NYISO’s Open Access Transmission Tariff, as filed with the FERC, and as amended or supplemented from time to time, or any successor tariff.

Trial Operation shall mean the period during which Interconnection Customer is engaged in on-  
site test operations and commissioning of the Small Generating Facility prior to Commercial   
Operation.

Upgrades - The required additions and modifications to the Connecting Transmission Owner’s portion of the New York State Transmission System or the Distribution System at or beyond the Point of Interconnection. Upgrades may be System Upgrade Facilities or System Deliverability Upgrades Distribution Upgrades. Upgrades do not include Interconnection Facilities.

43

Attachment 2 - Detailed Scope of Work, Including Description and Costs of the Small Generating Facility, Interconnection Facilities, and Metering Equipment

Equipment, including the Small Generating Facility, Interconnection Facilities, and metering equipment shall be itemized and identified as being owned by the Interconnection Customer, or the Connecting Transmission Owner. The Connecting Transmission Owner will provide a best estimate itemized cost, including overheads, of its Interconnection Facilities and metering equipment, and a best estimate itemized cost of the annual operation and maintenance expenses associated with its Interconnection Facilities and metering equipment.

A. PROJECT DESCRIPTION

The generating facility, located at: 1400 Washington Avenue, Albany, NY 12222,

consists of a 1,500kW PV system including 4,783 solar modules and 25 inverters. The Point of Interconnection (POI) and the Point of Change of Ownership (POCO) shall be the point where the existing Interconnecting Transmission Owner 115kV “State Campus - Menands #15” line crosses the fence line of the existing State University of New York at Albany “State Campus Station” located in Albany, NY.

B. INTERCONNECTION CUSTOMER’S INTERCONNECTION

FACILITIES

The Interconnection Customer’s Interconnection Facilities consist of new electrical wire   
and conduit to be installed at electric manhole #32, a new load break switch, and all existing   
equipment and conductors currently providing power to the existing loads located at the State   
University of New York at Albany from the “State Campus Station” from the POCO and POI,   
and which will additionally serve to transmit power from the generating facility to the POI, to the   
extent that the power is not consumed by load located at the State University of New York at   
Albany.

C. CONNECTING TRANSMISSION OWNER’S INTERCONNECTION

FACILITIES

The Connecting Transmission Owner’s Interconnection Facilities (“CTOIFs”) consist of

all existing structures, conductor and facilities owned by the Connecting Transmission Owner

and located at the POI and POCO.

D. SCOPE OF WORK AND RESPONSIBILITIES

1. Interconnection Customer’s Scope of Work and Responsibilities

44

The Interconnection Customer’s Interconnection Facilities shall be designed, constructed, operated, and maintained by the Interconnection Customer in accordance with the following   
requirements, to the extent not inconsistent with the terms of this Agreement, the NYISO OATT, or applicable NYISO Procedures: NYISO requirements,, industry standards and specifications, regulatory requirements, the Connecting Transmission Owner’s applicable Electric System   
Bulletins (“ESBs”), provided at the following website:

[https://www.nationalgridus.com/ProNet/Technical-Resources/Electric-Specifications](https://www.nationalgridus.com/pronet/technical-resources/electric-specifications/), the Project   
Specific Specifications, and Good Utility Practice. All protection scheme design drawings and   
relay settings shall be prepared by the Interconnection Customer’s NYS licensed professional   
engineer, and the design and equipment specifications shall be provided to the Connecting   
Transmission Owner for review, comment and acceptance, prior to application and testing in   
accordance with the ESBs. Interconnection Customer’s Small Generating Facility is afforded   
the exemptions contained in Article 1.8.3.3 of this Agreement and Interconnection Customer   
shall make Reasonable Efforts to keep outages of the Small Generating Facility’s governor or   
equivalent controls and their impact on droop and deadband capability requirements contained in   
Article 1.8.3 to a minimum whenever the Small Generating Facility is operated in parallel with   
the New York State Transmission System.

2. Connecting Transmission Owner’s Scope of Work and Responsibilities

No new CTOIFs are planned to support this generator. All CTOIF facilities currently exist. Operation and maintenance costs associated with the Small Generating Facility,   
Interconnection Customer Interconnection Facilities, and CTOIFs will be borne by the Party owning such facilities.


E. ESTIMATED COSTS OF INTERCONNECTION FACILITIES

No new facilities are expected to be constructed by the Connecting Transmission Owner. Customer construction document review, site review and witness testing of customer equipment are the only activities required of the Connecting Transmission Owner. This is estimated to be a cost of $0 to the Interconnection Customer and will be reconciled to the actual costs at project completion. A refund or further invoice will be generated based on the actual costs.

45

Attachment 3 - One-line Diagram Depicting the Small Generating Facility,Interconnection Facilities, Metering Equipment, and Upgrades

46



4

Attachment 4 - Milestones

In-Service Date: July 12, 2021

Critical milestones and responsibility as agreed to by the Parties:

Milestone/Date

(1) Building Permit - February 19, 2021

(2) Construction NTP - March 15, 2021

(3) Main Equipment Delivery - May 26, 2021

(4) Connection in Manhole - June 16, 2021

(5) Meter installation - June 18, 2021

(6) Mechanical Completion - June 25, 2021

(7) Energization/utility testing - July 9, 2021

(8) Issue permission to operate - July 12, 2021

(9) Project closeout/reconciliation: October 12, 2021

48

Responsible Party

Interconnection Customer   
 Interconnection Customer   
 Interconnection Customer   
 Interconnection Customer   
 Interconnection Customer   
 Interconnection Customer   
Connecting Transmission Owner

Connecting Transmission Owner   
Connecting Transmission Owner

Attachment 5 - Additional Operating Requirements for the New York State

Transmission System, the Distribution System and Affected Systems Needed to Support the Interconnection Customer’s Needs

The Connecting Transmission Owner shall also provide requirements that must be met by the Interconnection Customer prior to initiating parallel operation with the New York State   
Transmission System or the Distribution System.

(a) The Interconnection Customer must comply with all applicable NYISO tariffs and procedures, as amended from time to time.

(b) To the extent not inconsistent with the terms of this Agreement, the NYISO OATT, or applicable NYISO procedures, Interconnection Customer must comply with Connecting   
Transmission Owner’s operating instructions and requirements, which requirements shall include the dedicated data circuits, including system protection circuits, to be maintained by   
Interconnection Customer in accordance with Article 1.5 of this Agreement. Interconnection   
Customer must also comply with the applicable requirements as set out in the Connecting   
Transmission Owner’s ESBs, which have been identified and provided to the Interconnection   
Customer as amended from time to time to the extent not inconsistent with the terms of this   
Agreement or applicable NYISO tariffs and procedures. Upon the Connecting Transmission   
Owner’s notice to the Interconnection Customer of amendments to the ESBs, the Interconnection Customer has 30 days to comply with such amendments.

49

Attachment 6 - Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of Upgrade Costs

The Connecting Transmission Owner shall describe Upgrades and provide an itemized   
best estimate of the cost, including overheads, of the Upgrades and annual operation and   
maintenance expenses associated with such Upgrades. The Connecting Transmission Owner   
shall functionalize Upgrade costs and annual expenses as either transmission or distribution   
related.

The cost estimate for System Upgrade Facilities and System Deliverability Upgrades   
shall be taken from the ISO OATT Attachment S cost allocation process or applicable   
Interconnection Study, as required by Section 32.3.5.3.2 of Attachment Z. The cost estimate for Distribution Upgrades shall include the costs of Distribution Upgrades that are reasonably   
allocable to the Interconnection Customer at the time the estimate is made, and the costs of any Distribution Upgrades not yet constructed that were assumed in the Interconnection Studies for the Interconnection Customer but are, at the time of the estimate, an obligation of an entity other than the Interconnection Customer.

The cost estimates for Distribution Upgrades, System Upgrade Facilities, and System Deliverability Upgrades are estimates. The Interconnection Customer is ultimately responsible for the actual cost of the Distribution Upgrades, System Upgrade Facilities, and System   
Deliverability Upgrades needed for its Small Generating Facility, as that is determined under Attachments S, X, and Z of the ISO OATT.

A. DISTRIBUTION UPGRADES

None.

B. SYSTEM UPGRADE FACILITIES (“SUF”) - STAND ALONE SUFs

None.

C. SYSTEM UPGRADE FACILITIES - OTHER SUFs

None.

D. COST ESTIMATES RELATED TO DISTRIBUTION UPGRADES AND

SYSTEM UPGRADE FACILITIES

None.

50

Attachment 7 - Insurance Coverage

Interconnection Customer shall, at its own expense, maintain in force throughout the period of this Agreement, the following minimum insurance coverage, with insurers authorized to do business in the State of New York.

Commercial General Liability Insurance including, but not limited to, bodily

injury, property damage, products/completed operations, contractual and personal injury   
liability with a combined single limit of $2 million per occurrence, $5 million annual   
aggregate.

51

Attachment 8

Initial Synchronization Date

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid Attention: Director, Commercial Services

40 Sylvan Road

Waltham, MA 02541-1120

Re: Hilltop Solar Project Small Generating Facility

Dear :

On [Date] [Interconnection Customer] initially synchronized the Small Generating Facility [specify units, if applicable]. This letter confirms that [Interconnection Customer]’s Initial Synchronization Date was [specify].

Thank you.

[Signature]

[Interconnection Customer Representative]

52

Attachment 9

Commercial Operation Date

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid Attention: Director, Commercial Services

40 Sylvan Road

Waltham, MA 02541-1120

Re: Hilltop Solar Project Small Generating Facility

Dear \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_:

On [Date] [Interconnection Customer] has completed Trial Operation of Unit No. \_\_\_. This

letter confirms that [Interconnection Customer] commenced Commercial Operation of the Small Generating Facility [specify units, as applicable], effective as of [Date plus one day].

Thank you.

[Signature]

[Interconnection Customer Representative]

53