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This Second Amended and Restated Standard Small Generator Interconnection Agreement
(“Agreement” or “SGIA”) is made and entered into this 13th day of August, 2026, by and among
the New York Independent System Operator, Inc., a not-for-profit corporation organized and
existing under the laws of the State of New York (“NYISO”) and Niagara Mohawk Power
Corporation d/b/a National Grid, a corporation organized and existing under the laws of the State
of New York (“Connecting Transmission Owner”), and Hawthorn Solar, LLC a Limited
Liability Company organized and existing under the laws of the State of Delaware
(“Interconnection Customer”) each hereinafter sometimes referred to individually as “Party” or
referred to collectively as the “Parties.”
In consideration of the mutual covenants set forth herein, the Parties agree as follows:
1
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Article 1 Scope and Limitations of Agreement
1.1 Applicability
 This Agreement shall be used for all Interconnection Requests submitted under the Small
Generator Interconnection Procedures (SGIP) except for those submitted under the 10 kW
Inverter Process contained in SGIP Attachment 5.
1.2 Purpose
 This Agreement governs the terms and conditions under which the Interconnection
Customer’s Small Generating Facility will interconnect with, and operate in parallel with, the
New York State Transmission System or the Distribution System.
1.3 Scope of Interconnection Service
1.3.1 The NYISO will provide Energy Resource Interconnection Service and Capacity
 Resource Interconnection Service to Interconnection Customer at the Point of
 Interconnection.
1.3.2 This Agreement does not constitute an agreement to purchase or deliver the
 Interconnection Customer’s power. The purchase or delivery of power and other
 services that the Interconnection Customer may require will be covered under
 separate agreements, if any, or applicable provisions of NYISO’s or Connecting
 Transmission Owner’s tariffs. The Interconnection Customer will be responsible
 for separately making all necessary arrangements (including scheduling) for
 delivery of electricity in accordance with the applicable provisions of the ISO
 OATT and Connecting Transmission Owner’s tariff. The execution of this
 Agreement does not constitute a request for, nor agreement to, provide Energy,
 any Ancillary Services or Installed Capacity under the NYISO Services Tariff or
 any Connecting Transmission Owner’s tariff. If Interconnection Customer wishes
 to supply or purchase Energy, Installed Capacity or Ancillary Services, then
 Interconnection Customer will make application to do so in accordance with the
 NYISO Services Tariff or Connecting Transmission Owner’s tariff.
1.4 Limitations
 Nothing in this Agreement is intended to affect any other agreement by and among the
NYISO, Connecting Transmission Owner and the Interconnection Customer, except as otherwise
expressly provided herein.
1.5 Responsibilities of the Parties
1.5.1 The Parties shall perform all obligations of this Agreement in accordance with all
 Applicable Laws and Regulations, Operating Requirements, and Good Utility
 Practice.
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1.5.2 The Interconnection Customer shall construct, interconnect, operate and maintain
 its Small Generating Facility and construct, operate, and maintain its
 Interconnection Facilities in accordance with the applicable manufacturer’s
 recommended maintenance schedule, and in accordance with this Agreement, and
 with Good Utility Practice.
1.5.3 The Connecting Transmission Owner shall construct, operate, and maintain its
 Interconnection Facilities and Upgrades covered by this Agreement in accordance
 with this Agreement, and with Good Utility Practice. If all the Parties agree, the
 Interconnection Customer may construct the Connecting Transmission Owner’s
 Interconnection Facilities and Upgrades as specified in Attachment 2.
1.5.4 The Interconnection Customer agrees to construct its facilities or systems in
 accordance with applicable specifications that meet or exceed those provided by
 the National Electrical Safety Code, the American National Standards Institute,
 IEEE, Underwriter’s Laboratory, and Operating Requirements in effect at the time
 of construction and other applicable national and state codes and standards. The
 Interconnection Customer agrees to design, install, maintain, and operate its Small
 Generating Facility so as to reasonably minimize the likelihood of a disturbance
 adversely affecting or impairing the system or equipment of the Connecting
 Transmission Owner or Affected Systems.
1.5.5 The Connecting Transmission Owner and Interconnection Customer shall operate,
 maintain, repair, and inspect, and shall be fully responsible for the facilities that it
 now or subsequently may own unless otherwise specified in the Attachments to
 this Agreement. Each of those Parties shall be responsible for the safe
 installation, maintenance, repair and condition of their respective lines and
 appurtenances on their respective sides of the point of change of ownership. The
 Connecting Transmission Owner and the Interconnection Customer, as
 appropriate, shall provide Interconnection Facilities that adequately protect the
 Connecting Transmission Owner’s electric system, personnel, and other persons
 from damage and injury. The allocation of responsibility for the design,
 installation, operation, maintenance and ownership of Interconnection Facilities
 shall be delineated in the Attachments to this Agreement.
1.5.6 The NYISO shall coordinate with all Affected Systems to support the
 interconnection. The Connecting Transmission Owner shall cooperate with the
 NYISO in these efforts.
1.5.7 The Interconnection Customer shall ensure “frequency ride through” capability
 and “voltage ride through” capability of its Small Generating Facility. The
 Interconnection Customer shall enable these capabilities such that its Small
 Generating Facility shall not disconnect automatically or instantaneously from the
 system or equipment of the Connecting Transmission Owner and any Affected
 Systems for a defined under-frequency or over-frequency condition, or an under-
 voltage or over-voltage condition, as tested pursuant to section 2.1 of this
 agreement. The defined conditions shall be in accordance with Good Utility
3
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Practice and consistent with any standards and guidelines that are applied to other
generating facilities in the Balancing Authority Area on a comparable basis. The
Small Generating Facility’s protective equipment settings shall comply with the
Transmission Owner’s automatic load-shed program. The Transmission Owner
shall review the protective equipment settings to confirm compliance with the
automatic load-shed program. The term “ride through” as used herein shall mean
the ability of a Small Generating Facility to stay connected to and synchronized
with the system or equipment of the Transmission Owner and any Affected
Systems during system disturbances within a range of conditions, in accordance
with Good Utility Practice and consistent with any standards and guidelines that
are applied to other generating facilities in the Balancing Authority on a
comparable basis. The term “frequency ride through” as used herein shall mean
the ability of a Small Generating Facility to stay connected to and synchronized
with the system or equipment of the Transmission Owner and any Affected
Systems during system disturbances within a range of under-frequency and over-
frequency conditions, in accordance with Good Utility Practice and consistent
with any standards and guidelines that are applied to other generating facilities in
the Balancing Authority Area on a comparable basis. The term “voltage ride
through” as used herein shall mean the ability of a Small Generating Facility to
stay connected to and synchronized with the system or equipment of the
Transmission Owner and any Affected Systems during system disturbances
within a range of under-voltage and over-voltage conditions, in accordance with
Good Utility Practice and consistent with any standards and guidelines that are
applied to other generating facilities in the Balancing Authority Area on a
comparable basis.
1.6 Parallel Operation Obligations
 Once the Small Generating Facility has been authorized to commence parallel operation,
the Interconnection Customer shall abide by all rules and procedures pertaining to the parallel
operation of the Small Generating Facility in the applicable control area, including, but not
limited to: (1) the rules and procedures concerning the operation of generation set forth in the
NYISO tariffs or ISO Procedures or the Connecting Transmission Owner’s tariff; (2) any
requirements consistent with Good Utility Practice or that are necessary to ensure the safe and
reliable operation of the Transmission System or Distribution System; and (3) the Operating
Requirements set forth in Attachment 5 of this Agreement.
1.7 Metering
 The Interconnection Customer shall be responsible for the Connecting Transmission
Owner’s reasonable and necessary cost for the purchase, installation, operation, maintenance,
testing, repair, and replacement of metering and data acquisition equipment specified in
Attachments 2 and 3 of this Agreement. The Interconnection Customer’s metering (and data
acquisition, as required) equipment shall conform to applicable industry rules and Operating
Requirements.
1.8 Reactive Power and Primary Frequency Response
4
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1.8.1 Power Factor Design Criteria
1.8.1.1 Synchronous Generation. The Interconnection Customer shall design its
 Small Generating Facility to maintain a composite power delivery at
 continuous rated power output at the Point of Interconnection at a power
 factor within the range of 0.95 leading to 0.95 lagging, unless the NYISO
 or the Transmission Owner in whose Transmission District the Small
 Generating Facility interconnects has established different requirements
 that apply to all similarly situated generators in the New York Control
 Area or Transmission District (as applicable) on a comparable basis, in
 accordance with Good Utility Practice.
1.8.1.2 Non-Synchronous Generation. The Interconnection Customer shall design
 its Small Generating Facility to maintain a composite power delivery at
 continuous rated power output at the high-side of the generator substation
 at a power factor within the range of 0.95 leading to 0.95 lagging, unless
 the NYISO or the Transmission Owner in whose Transmission District the
 Small Generating Facility interconnects has established a different power
 factor range that applies to all similarly situated non-synchronous
 generators in the control area or Transmission District (as applicable) on a
 comparable basis, in accordance with Good Utility Practice. This power
 factor range standard shall be dynamic and can be met using, for example,
 power electronics designed to supply this level of reactive capability
 (taking into account any limitations due to voltage level, real power
 output, etc.) or fixed and switched capacitors, or a combination of the two.
 This requirement shall only apply to newly interconnecting non-
 synchronous generators that have not yet executed a Facilities Study
 Agreement as of September 21, 2016.
1.8.2 The NYISO is required to pay the Interconnection Customer for reactive power,
 or voltage support service, that the Interconnection Customer provides from the
 Small Generating Facility in accordance with Rate Schedule 2 of the NYISO
 Services Tariff.
1.8.3 Primary Frequency Response. Interconnection Customer shall ensure the primary
 frequency response capability of its Small Generating Facility by installing,
 maintaining, and operating a functioning governor or equivalent controls. The
 term “functioning governor or equivalent controls” as used herein shall mean the
 required hardware and/or software that provides frequency responsive real power
 control with the ability to sense changes in system frequency and autonomously
 adjust the Small Generating Facility’s real power output in accordance with the
 droop and deadband parameters and in the direction needed to correct frequency
 deviations. Interconnection Customer is required to install a governor or
 equivalent controls with the capability of operating: (1) with a maximum 5
 percent droop and ±0.036 Hz deadband; or (2) in accordance with the relevant
 droop, deadband, and timely and sustained response settings from an approved
 Applicable Reliability Standard providing for equivalent or more stringent
5
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parameters. The droop characteristic shall be: (1) based on the nameplate
capacity of the Small Generating Facility, and shall be linear in the range of
frequencies between 59 to 61 Hz that are outside of the deadband parameter; or
(2) based on an approved Applicable Reliability Standard providing for an
equivalent or more stringent parameter. The deadband parameter shall be: the
range of frequencies above and below nominal (60 Hz) in which the governor or
equivalent controls is not expected to adjust the Small Generating Facility’s real
power output in response to frequency deviations. The deadband shall be
implemented: (1) without a step to the droop curve, that is, once the frequency
deviation exceeds the deadband parameter, the expected change in the Small
Generating Facility’s real power output in response to frequency deviations shall
start from zero and then increase (for under-frequency deviations) or decrease (for
over-frequency deviations) linearly in proportion to the magnitude of the
frequency deviation; or (2) in accordance with an approved Applicable Reliability
Standard providing for an equivalent or more stringent parameter. Interconnection Customer shall notify NYISO that the primary frequency
response capability of the Small Generating Facility has been tested and
confirmed during commissioning. Once Interconnection Customer has
synchronized the Small Generating Facility with the New York State
Transmission System, Interconnection Customer shall operate the Small
Generating Facility consistent with the provisions specified in Articles 1.8.3.1 and
1.8.3.2 of this Agreement. The primary frequency response requirements
contained herein shall apply to both synchronous and non-synchronous Small
Generating Facilities.
1.8.3.1 Governor or Equivalent Controls. Whenever the Small Generating Facility
 is operated in parallel with the New York State Transmission System,
 Interconnection Customer shall operate the Small Generating Facility with
 its governor or equivalent controls in service and responsive to frequency.
 Interconnection Customer shall: (1) in coordination with NYISO, set the
 deadband parameter to: (1) a maximum of ±0.036 Hz and set the droop
 parameter to a maximum of 5 percent; or (2) implement the relevant droop
 and deadband settings from an approved Applicable Reliability Standard
 that provides for equivalent or more stringent parameters. Interconnection
 Customer shall be required to provide the status and settings of the
 governor and equivalent controls to NYISO and/or the Connecting
 Transmission Owner upon request. If Interconnection Customer needs to
 operate the Small Generating Facility with its governor or equivalent
 controls not in service, Interconnection Customer shall immediately notify
 NYISO and the Connecting Transmission Owner, and provide both with
 the following information: (1) the operating status of the governor or
 equivalent controls (i.e., whether it is currently out of service or when it
 will be taken out of service); (2) the reasons for removing the governor or
 equivalent controls from service; and (3) a reasonable estimate of when
 the governor or equivalent controls will be returned to service.
Interconnection Customer shall make Reasonable Efforts to return its
governor or equivalent controls into service as soon as practicable.
6
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Interconnection Customer shall make Reasonable Efforts to keep outages
of the Small Generating Facility’s governor or equivalent controls to a
minimum whenever the Small Generating Facility is operated in parallel
with the New York State Transmission System.
1.8.3.2 Timely and Sustained Response. Interconnection Customer shall ensure
 that the Small Generating Facility’s real power response to sustained
 frequency deviations outside of the deadband setting is automatically
 provided and shall begin immediately after frequency deviates outside of
 the deadband, and to the extent the Small Generating Facility has
 operating capability in the direction needed to correct the frequency
 deviation. Interconnection Customer shall not block or otherwise inhibit
 the ability of the governor or equivalent controls to respond and shall
 ensure that the response is not inhibited, except under certain operational
 constraints including, but not limited to, ambient temperature limitations,
 physical energy limitations, outages of mechanical equipment, or
 regulatory requirements. The Small Generating Facility shall sustain the
 real power response at least until system frequency returns to a value
 within the deadband setting of the governor or equivalent controls. An
 Applicable Reliability Standard with equivalent or more stringent
 requirements shall supersede the above requirements.
1.8.3.3 Exemptions. Small Generating Facilities that are regulated by the United
 States Nuclear Regulatory Commission shall be exempt from Articles
 1.8.3, 1.8.3.1, and 1.8.3.2 of this Agreement. Small Generating Facilities
 that are behind the meter generation that is sized-to-load (i.e., the thermal
 load and the generation are near-balanced in real-time operation and the
 generation is primarily controlled to maintain the unique thermal,
 chemical, or mechanical output necessary for the operating requirements
 of its host facility) shall be required to install primary frequency response
 capability requirements in accordance with the droop and deadband
 capability requirements specified in Article 1.8.3, but shall be otherwise
 exempt from the operating requirements in Articles 1.8.3, 1.8.3.1, 1.8.3.2,
 and 1.8.3.4 of this Agreement.
1.8.3.4 Electric Storage Resources. Interconnection Customer interconnecting an
 electric storage resource shall establish an operating range in Attachment 5
 of its SGIA that specifies a minimum state of charge and a maximum state
 of charge between which the electric storage resource will be required to
 provide primary frequency response consistent with the conditions set
 forth in Articles 1.8.3, 1.8.3.1, 1.8.3.2, and 1.8.3.3 of this Agreement.
 Attachment 5 shall specify whether the operating range is static or
 dynamic, and shall consider (1) the expected magnitude of frequency
 deviations in the interconnection; (2) the expected duration that system
 frequency will remain outside of the deadband parameter in the
interconnection; (3) the expected incidence of frequency deviations
outside of the deadband parameter in the interconnection; (4) the physical
7
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capabilities of the electric storage resource; (5) operational limitations of
the electric storage resources due to manufacturer specification; and (6)
any other relevant factors agreed to by the NYISO, Connecting
Transmission Owner, and Interconnection Customer. If the operating
range is dynamic, then Attachment 5 must establish how frequently the
operating range will be reevaluated and the factors that may be considered
during its reevaluation.
Interconnection Customer’s electric storage resource is required to provide timely
and sustained primary frequency response consistent with Article 1.8.3.2 of this
Agreement when it is online and dispatched to inject electricity to the New York
State Transmission System and/or receive electricity from the New York State
Transmission System. This excludes circumstances when the electric storage
resource is not dispatched to inject electricity to the New York State Transmission
System and/or dispatched to receive electricity from the New York State
Transmission System. If Interconnection Customer’s electric storage resource is
charging at the time of a frequency deviation outside of its deadband parameter, it
is to increase (for over-frequency deviations) or decrease (for under-frequency
deviations) the rate at which it is charging in accordance with its droop parameter.
Interconnection Customer’s electric storage resource is not required to change
from charging to discharging, or vice versa, unless the response necessitated by
the droop and deadband settings requires it to do so and it is technically capable
of making such a transition.
1.9 Capitalized Terms
 Capitalized terms used herein shall have the meanings specified in the Glossary of Terms
in Attachment 1 or the body of this Agreement. Capitalized terms used herein that are not so
defined shall have the meanings specified in Appendix 1 of Attachment Z, Section 25.1.2 of
Attachment S, or Section 30.1 of Attachment X of the ISO OATT.
8
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Article 2 Inspection, Testing, Authorization, and Right of Access
2.1 Equipment Testing and Inspection
2.1.1 The Interconnection Customer shall test and inspect its Small Generating Facility
 and Interconnection Facilities prior to interconnection. The Interconnection
 Customer shall notify the NYISO and the Connecting Transmission Owner of
 such activities no fewer than five Business Days (or as may be agreed to by the
 Parties) prior to such testing and inspection. Testing and inspection shall occur on
 a Business Day. The Connecting Transmission Owner may, at its own expense,
 send qualified personnel to the Small Generating Facility site to inspect the
 interconnection and observe the testing. The Interconnection Customer shall
 provide the NYISO and Connecting Transmission Owner a written test report
 when such testing and inspection is completed. The Small Generating Facility
 may not commence parallel operations if the NYISO, in consultation with the
 Connecting Transmission Owner, finds that the Small Generating Facility has not
 been installed as agreed upon or may not be operated in a safe and reliable
 manner.
2.1.2 The NYISO and Connecting Transmission Owner shall each provide the
 Interconnection Customer written acknowledgment that it has received the
 Interconnection Customer’s written test report. Such written acknowledgment
 shall not be deemed to be or construed as any representation, assurance,
 guarantee, or warranty by the NYISO or Connecting Transmission Owner of the
 safety, durability, suitability, or reliability of the Small Generating Facility or any
 associated control, protective, and safety devices owned or controlled by the
 Interconnection Customer or the quality of power produced by the Small
 Generating Facility.
2.2 Authorization Required Prior to Parallel Operation
2.2.1 The NYISO, in consultation with the Connecting Transmission Owner, shall use
 Reasonable Efforts to list applicable parallel Operating Requirements in
Attachment 5 of this Agreement. Additionally, the NYISO, in consultation with
the Connecting Transmission Owner, shall notify the Interconnection Customer of
any changes to these requirements as soon as they are known. The NYISO and
Connecting Transmission Owner shall make Reasonable Efforts to cooperate with
the Interconnection Customer in meeting requirements necessary for the Interconnection Customer to commence parallel operations by the in-service date.
2.2.2 The Interconnection Customer shall not operate its Small Generating Facility in
 parallel with the New York State Transmission System or the Distribution System
 without prior written authorization of the NYISO. The NYISO, in consultation
 with the Connecting Transmission Owner, will provide such authorization once
 the NYISO receives notification that the Interconnection Customer has complied
 with all applicable parallel Operating Requirements. Such authorization shall not
 be unreasonably withheld, conditioned, or delayed.
9
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2.3 Right of Access
2.3.1 Upon reasonable notice, the NYISO and/or Connecting Transmission Owner may
 send a qualified person to the premises of the Interconnection Customer at or
 immediately before the time the Small Generating Facility first produces energy
 to inspect the interconnection, and observe the commissioning of the Small
 Generating Facility (including any required testing), startup, and operation for a
 period of up to three Business Days after initial start-up of the unit. In addition,
 the Interconnection Customer shall notify the NYISO and Connecting
 Transmission Owner at least five Business Days prior to conducting any on-site
 verification testing of the Small Generating Facility.
2.3.2 Following the initial inspection process described above, at reasonable hours, and
 upon reasonable notice, or at any time without notice in the event of an
 emergency or hazardous condition, the NYISO and Connecting Transmission
 Owner each shall have access to the Interconnection Customer’s premises for any
 reasonable purpose in connection with the performance of the obligations
 imposed on them by this Agreement or if necessary to meet their legal obligation
 to provide service to their customers.
2.3.3 Each Party shall be responsible for its own costs associated with following this
 article.
10
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Article 3 Effective Date, Term, Termination, and Disconnection
3.1 Effective Date
 This Agreement shall become effective upon execution by the Parties subject to
acceptance by FERC (if applicable), or if filed unexecuted, upon the date specified by the FERC.
The NYISO and Connecting Transmission Owner shall promptly file, or cause to be filed, this
Agreement with FERC upon execution, if required. If the Agreement is disputed and the
Interconnection Customer requests that it be filed with FERC in an unexecuted form, the NYISO
shall file, or cause to be filed, this Agreement and the NYISO shall identify the disputed
language.
3.2 Term of Agreement
 This Agreement shall become effective on the Effective Date and shall remain in effect
for a period of twenty (20) years from the Effective Date and shall be automatically renewed for
each successive one-year period thereafter, unless terminated earlier in accordance with article
3.3 of this Agreement.
3.3 Termination
 No termination shall become effective until the Parties have complied with all Applicable
Laws and Regulations applicable to such termination, including the filing with FERC of a notice
of termination of this Agreement (if required), which notice has been accepted for filing by
FERC.
3.3.1 The Interconnection Customer may terminate this Agreement at any time by
 giving the NYISO and Connecting Transmission Owner 20 Business Days written
 notice. The NYISO may terminate this Agreement after the Small Generating
 Facility is Retired.
3.3.2 Any Party may terminate this Agreement after Default pursuant to article 7.6.
3.3.3 Upon termination of this Agreement, the Small Generating Facility will be
 disconnected from the New York State Transmission System or the Distribution
 System, as applicable. All costs required to effectuate such disconnection shall be
 borne by the terminating Party, unless such termination resulted from the non-
 terminating Party’s Default of this SGIA or such non-terminating Party otherwise
 is responsible for these costs under this SGIA.
3.3.4 The termination of this Agreement shall not relieve any Party of its liabilities and
 obligations, owed or continuing at the time of the termination. The
Interconnection Customer shall pay all amounts in excess of any deposit or other
security without interest within 30 calendar days after receipt of the invoice for
such amounts. If the deposit or other security exceeds the invoice, the Connecting
Transmission Owner shall refund such excess within 30 calendar days of the
invoice without interest. If the Interconnection Customer disputes an amount to
be paid the Interconnection Customer shall pay the disputed amount to the
11
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Connecting Transmission Owner or into an interest bearing escrow account,
pending resolution of the dispute in accordance with Article 10 of this Agreement.
To the extent the dispute is resolved in the Interconnection Customer’s favor, that
portion of the disputed amount will be returned to the Interconnection Customer
with interest at rates applicable to refunds under the Commission’s regulations.
To the extent the dispute is resolved in the Connecting Transmission Owner’s
favor, that portion of any escrowed funds and interest will be released to the
Connecting Transmission Owner.
3.3.5 The limitations of liability, indemnification and confidentiality provisions of this
 Agreement shall survive termination or expiration of this Agreement.
3.4 Temporary Disconnection
 Temporary disconnection shall continue only for so long as reasonably necessary under
Good Utility Practice.
3.4.1 Emergency Conditions
 “Emergency Condition” shall mean a condition or situation: (1) that in the judgment of
the Party making the claim is imminently likely to endanger life or property; or (2) that, in the
case of the NYISO or Connecting Transmission Owner, is imminently likely (as determined in a
non-discriminatory manner) to cause a material adverse effect on the security of, or damage to
the New York State Transmission System or Distribution System, the Connecting Transmission
Owner’s Interconnection Facilities or the electric systems of others to which the New York State
Transmission System or Distribution System is directly connected; or (3) that, in the case of the
Interconnection Customer, is imminently likely (as determined in a non-discriminatory manner)
to cause a material adverse effect on the security of, or damage to, the Small Generating Facility
or the Interconnection Customer’s Interconnection Facilities. Under Emergency Conditions, the
NYISO or Connecting Transmission Owner may immediately suspend interconnection service
and temporarily disconnect the Small Generating Facility. The NYISO or Connecting
Transmission Owner shall notify the Interconnection Customer promptly when it becomes aware
of an Emergency Condition that may reasonably be expected to affect the Interconnection
Customer’s operation of the Small Generating Facility. The Interconnection Customer shall
notify the NYISO and Connecting Transmission Owner promptly when it becomes aware of an
Emergency Condition that may reasonably be expected to affect the New York State
Transmission System or Distribution System or any Affected Systems. To the extent
information is known, the notification shall describe the Emergency Condition, the extent of the
damage or deficiency, the expected effect on the operation of each Party’s facilities and
operations, its anticipated duration, and the necessary corrective action.
3.4.2 Routine Maintenance, Construction, and Repair
 The NYISO or Connecting Transmission Owner may interrupt interconnection service or
curtail the output of the Small Generating Facility and temporarily disconnect the Small
Generating Facility from the New York State Transmission System or Distribution System when
necessary for routine maintenance, construction, and repairs on the New York State
12
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Transmission System or Distribution System. The NYISO or the Connecting Transmission
Owner shall provide the Interconnection Customer with five Business Days’ notice prior to such
interruption. The NYISO and Connecting Transmission Owner shall use Reasonable Efforts to
coordinate such reduction or temporary disconnection with the Interconnection Customer.
3.4.3 Forced Outages
 During any forced outage, the NYISO or Connecting Transmission Owner may suspend
interconnection service to the Interconnection Customer to effect immediate repairs on the New
York State Transmission System or the Distribution System. The NYISO shall use Reasonable
Efforts to provide the Interconnection Customer with prior notice. If prior notice is not given,
the NYISO shall, upon request, provide the Interconnection Customer written documentation
after the fact explaining the circumstances of the disconnection.
3.4.4 Adverse Operating Effects
 The NYISO or Connecting Transmission Owner shall notify the Interconnection
Customer as soon as practicable if, based on Good Utility Practice, operation of the Small
Generating Facility may cause disruption or deterioration of service to other customers served
from the same electric system, or if operating the Small Generating Facility could cause damage
to the New York State Transmission System, the Distribution System or Affected Systems, or if
disconnection is otherwise required under Applicable Reliability Standards or the ISO OATT.
Supporting documentation used to reach the decision to disconnect shall be provided to the
Interconnection Customer upon request. If, after notice, the Interconnection Customer fails to
remedy the adverse operating effect within a reasonable time, the NYISO or Connecting
Transmission Owner may disconnect the Small Generating Facility. The NYISO or Connecting
Transmission Owner shall provide the Interconnection Customer with five Business Day notice
of such disconnection, unless the provisions of article 3.4.1 apply.
3.4.5 Modification of the Small Generating Facility
 The Interconnection Customer must receive written authorization from the NYISO and
Connecting Transmission Owner before making any change to the Small Generating Facility that
may have a material impact on the safety or reliability of the New York State Transmission
System or the Distribution System. Such authorization shall not be unreasonably withheld.
Modifications shall be done in accordance with Good Utility Practice. If the Interconnection
Customer makes such modification without the prior written authorization of the NYISO and
Connecting Transmission Owner, the Connecting Transmission Owner shall have the right to
temporarily disconnect the Small Generating Facility. If disconnected, the Small Generating
Facility will not be reconnected until the unauthorized modifications are authorized or removed.
3.4.6 Reconnection
 The Parties shall cooperate with each other to restore the Small Generating Facility,
Interconnection Facilities, and the New York State Transmission System and Distribution
System to their normal operating state as soon as reasonably practicable following a temporary
disconnection.
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Article 4 Cost Responsibility for Interconnection Facilities and Distribution Upgrades
4.1 Interconnection Facilities
4.1.1 The Interconnection Customer shall pay for the cost of the Interconnection
 Facilities itemized in Attachment 2 of this Agreement. The NYISO, in
 consultation with the Connecting Transmission Owner, shall provide a best
 estimate cost, including overheads, for the purchase and construction of its
 Interconnection Facilities and provide a detailed itemization of such costs. Costs
 associated with Interconnection Facilities may be shared with other entities that
 may benefit from such facilities by agreement of the Interconnection Customer,
 such other entities, the NYISO, and the Connecting Transmission Owner.
4.1.2 The Interconnection Customer shall be responsible for its share of all reasonable
 expenses, including overheads, associated with (1) owning, operating,
 maintaining, repairing, and replacing its own Interconnection Facilities, and
 (2) operating, maintaining, repairing, and replacing the Connecting Transmission
 Owner’s Interconnection Facilities, as set forth in Attachment 2 to this
 Agreement.
4.2 Distribution Upgrades
 The Connecting Transmission Owner shall design, procure, construct, install, and own
the Distribution Upgrades described in Attachment 6 of this Agreement. If the Connecting
Transmission Owner and the Interconnection Customer agree, the Interconnection Customer may
construct Distribution Upgrades. The actual cost of the Distribution Upgrades, including
overheads, shall be directly assigned to the Interconnection Customer. The Interconnection
Customer shall be responsible for its share of all reasonable expenses, including overheads,
associated with owning, operating, maintaining, repairing, and replacing the Distribution
Upgrades, as set forth in Attachment 6 to this Agreement.
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Article 5 Cost Responsibility for System Upgrade Facilities and System Deliverability
Upgrades
5.1 Applicability
 No portion of this article 5 shall apply unless the interconnection of the Small Generating
Facility requires System Upgrade Facilities or System Deliverability Upgrades.
5.2 System Upgrades
 The Connecting Transmission Owner shall procure, construct, install, and own the
System Upgrade Facilities and System Deliverability Upgrades described in Attachment 6 of this
Agreement. To the extent that design work is necessary in addition to that already accomplished
in the Class Year Interconnection Facilities Study for the Interconnection Customer, the
Connecting Transmission Owner shall perform or cause to be performed such work. If all the
Parties agree, the Interconnection Customer may construct System Upgrade Facilities and
System Deliverability Upgrades.
5.2.1 As described in Section 32.3.5.3 of the SGIP in Attachment Z of the ISO OATT,
 the responsibility of the Interconnection Customer for the cost of the System
 Upgrade Facilities and System Deliverability Upgrades described in Attachment 6
 of this Agreement shall be determined in accordance with Attachment S of the
 ISO OATT, as required by Section 32.3.5.3.2 of Attachment Z. The
 Interconnection Customer shall be responsible for all System Upgrade Facility
 costs as required by Section 32.3.5.3.2 of Attachment Z or its share of any System
 Upgrade Facilities and System Deliverability Upgrades costs resulting from the
 final Attachment S process, as applicable, and Attachment 6 to this Agreement
 shall be revised accordingly.
5.2.2 Pending the outcome of the Attachment S cost allocation process, if applicable,
 the Interconnection Customer may elect to proceed with the interconnection of its
 Small Generating Facility in accordance with Section 32.3.5.3 of the SGIP.
5.3 Special Provisions for Affected Systems
 For the repayment of amounts advanced to the Affected System Operator for System
Upgrade Facilities or System Deliverability Upgrades, the Interconnection Customer and
Affected System Operator shall enter into an agreement that provides for such repayment, but
only if responsibility for the cost of such System Upgrade Facilities is not to be allocated in
accordance with Attachment S of the ISO OATT. The agreement shall specify the terms
governing payments to be made by the Interconnection Customer to the Affected System
Operator as well as the repayment by the Affected System Operator.
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Article 6 Billing, Payment, Milestones, and Financial Security
6.1 Billing and Payment Procedures and Final Accounting
6.1.1 The Connecting Transmission Owner shall bill the Interconnection Customer for
 the design, engineering, construction, and procurement costs of Interconnection
 Facilities and Upgrades contemplated by this Agreement on a monthly basis, or as
 otherwise agreed by those Parties and as set forth in Section 2 of Attachment 4.
 The Interconnection Customer shall pay all invoice amounts within 30 calendar
 days after receipt of the invoice.
6.1.2 Within three months of completing the construction and installation of the
 Connecting Transmission Owner’s Interconnection Facilities and/or Upgrades
 described in the Attachments to this Agreement, the Connecting Transmission
 Owner shall provide the Interconnection Customer with a final accounting report
 of any difference between (1) the Interconnection Customer’s cost responsibility
 for the actual cost of such facilities or Upgrades, and (2) the Interconnection
 Customer’s previous aggregate payments to the Connecting Transmission Owner
 for such facilities or Upgrades. If the Interconnection Customer’s cost
 responsibility exceeds its previous aggregate payments, the Connecting
 Transmission Owner shall invoice the Interconnection Customer for the amount
 due and the Interconnection Customer shall make payment to the Connecting
 Transmission Owner within 30 calendar days. If the Interconnection Customer’s
 previous aggregate payments exceed its cost responsibility under this Agreement,
 the Connecting Transmission Owner shall refund to the Interconnection Customer
 an amount equal to the difference within 30 calendar days of the final accounting
 report.
6.1.3 If the Interconnection Customer disputes an amount to be paid, the
 Interconnection Customer shall pay the disputed amount to the Connecting
 Transmission Owner or into an interest bearing escrow account, pending
 resolution of the dispute in accordance with Article 10 of this Agreement. To the
 extent the dispute is resolved in the Interconnection Customer’s favor, that portion
 of the disputed amount will be credited or returned to the Interconnection
 Customer with interest at rates applicable to refunds under the Commission’s
 regulations. To the extent the dispute is resolved in the Connecting Transmission
 Owner’s favor, that portion of any escrowed funds and interest will be released to
 the Connecting Transmission Owner.
6.2 Milestones
 Subject to the provisions of the SGIP, the Parties shall agree on milestones for which
each Party is responsible and list them in Attachment 4 of this Agreement. A Party’s obligations
under this provision may be extended by agreement. If a Party anticipates that it will be unable
to meet a milestone for any reason other than a Force Majeure event, it shall immediately notify
the other Parties of the reason(s) for not meeting the milestone and: (1) propose the earliest
reasonable alternate date by which it can attain this and future milestones, and (2) requesting
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appropriate amendments to Attachment 4. The Party affected by the failure to meet a milestone
shall not unreasonably withhold agreement to such an amendment unless: (1) it will suffer
significant uncompensated economic or operational harm from the delay, (2) attainment of the
same milestone has previously been delayed, or (3) it has reason to believe that the delay in
meeting the milestone is intentional or unwarranted notwithstanding the circumstances explained
by the Party proposing the amendment.
6.3 Financial Security Arrangements
 At least 20 Business Days prior to the commencement of the design, procurement,
installation, or construction of a discrete portion of the Connecting Transmission Owner’s
Interconnection Facilities and Upgrades, the Interconnection Customer shall provide the
Connecting Transmission Owner, at the Interconnection Customer’s option, a guarantee, a surety
bond, letter of credit or other form of security that is reasonably acceptable to the Connecting
Transmission Owner and is consistent with the Uniform Commercial Code of the jurisdiction
where the Point of Interconnection is located. Such security for payment shall be in an amount
sufficient to cover the costs for constructing, designing, procuring, and installing the applicable
portion of the Connecting Transmission Owner’s Interconnection Facilities and Upgrades and
shall be reduced on a dollar-for-dollar basis for payments made to the Connecting Transmission
Owner under this Agreement during its term. The Connecting Transmission Owner may draw
on any such security to the extent that the Interconnection Customer fails to make any payments
due under this Agreement. In addition:
6.3.1 The guarantee must be made by an entity that meets the creditworthiness
 requirements of the Connecting Transmission Owner, and contain terms and
 conditions that guarantee payment of any amount that may be due from the
 Interconnection Customer, up to an agreed-to maximum amount.
6.3.2 The letter of credit or surety bond must be issued by a financial institution or
 insurer reasonably acceptable to the Connecting Transmission Owner and must
 specify a reasonable expiration date.
6.3.3 Notwithstanding the above, Security posted for System Upgrade Facilities for a
 Small Generating Facility required to enter the Class Year process, or cash or
 Security provided for System Deliverability Upgrades, shall meet the
requirements for Security contained in Attachment S to the ISO OATT.
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Article 7 Assignment, Liability, Indemnity, Force Majeure, Consequential Damages,
and Default
7.1 Assignment
 This Agreement, and each and every term and condition hereof, shall be binding upon
and inure to the benefit of the Parties hereto and their respective successors and assigns. This
Agreement may be assigned by any Party upon 15 Business Days prior written notice and
opportunity to object by the other Parties; provided that:
7.1.1 A Party may assign this Agreement without the consent of the other Parties to any
 affiliate of the assigning Party with an equal or greater credit rating and with the
 legal authority and operational ability to satisfy the obligations of the assigning
 Party under this Agreement, provided that the Interconnection Customer promptly
 notifies the NYISO and the Connecting Transmission Owner of any such
 assignment. A Party may assign this Agreement without the consent of the other
 Parties in connection with the sale, merger, restructuring, or transfer of a
 substantial portion of all of its assets, including the Interconnection Facilities it
 owns, so long as the assignee in such a transaction directly assumes all rights,
 duties and obligation arising under this Agreement.
7.1.2 The Interconnection Customer shall have the right to assign this Agreement,
 without the consent of the NYISO or Connecting Transmission Owner, for
 collateral security purposes to aid in providing financing for the Small Generating
 Facility.
7.1.3 Any attempted assignment that violates this article is void and ineffective.
 Assignment shall not relieve a Party of its obligations, nor shall a Party’s
 obligations be enlarged, in whole or in part, by reason thereof. An assignee is
 responsible for meeting the same financial, credit, and insurance obligations as
 the Interconnection Customer. Where required, consent to assignment will not be
 unreasonably withheld, conditioned or delayed.
7.2 Limitation of Liability
 Each Party’s liability to the other Parties for any loss, cost, claim, injury, liability, or
expense, including reasonable attorney’s fees, relating to or arising from any act or omission in
its performance of this Agreement, shall be limited to the amount of direct damage actually
incurred. In no event shall any Party be liable to the other Parties for any indirect, special,
consequential, or punitive damages.
7.3 Indemnity
7.3.1 This provision protects each Party from liability incurred to third parties as a
 result of carrying out the provisions of this Agreement. Liability under this
 provision is exempt from the general limitations on liability found in article 7.2.
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7.3.2 Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and
 hold harmless the other Parties (each an “ Indemnified Party”) from, any and all
 damages, losses, claims, including claims and actions relating to injury to or death
 of any person or damage to property, the alleged violation of any Environmental
 Law, or the release or threatened release of any Hazardous Substance, demand,
 suits, recoveries, costs and expenses, court costs, attorney fees, and all other
 obligations by or to third parties (any and all of these a “Loss”), arising out of or
 resulting from: (i) the Indemnified Party’s performance under this Agreement on
 behalf of the Indemnifying Party, except in cases where the Indemnifying Party
 can demonstrate that the Loss of the Indemnified Party was caused by the gross
 negligence or intentional wrongdoing by the Indemnified Party, or (ii) the
 violation by the Indemnifying Party of any Environmental Law or the release by
 the Indemnifying Party of a Hazardous Substance.
7.3.3 If a Party is entitled to indemnification under this article as a result of a claim by a
 third party, and the Indemnifying Party fails, after notice and reasonable
 opportunity to proceed under this article, to assume the defense of such claim,
 such Indemnified Party may at the expense of the Indemnifying Party contest,
 settle or consent to the entry of any judgment with respect to, or pay in full, such
 claim.
7.3.4 If an Indemnifying Party is obligated to indemnify and hold any Indemnified
 Party harmless under this article, the amount owing to the Indemnified Party shall
 be the amount of such Indemnified Party’s actual loss, net of any insurance or
 other recovery.
7.3.5 Promptly after receipt by an Indemnified Party of any claim or notice of the
 commencement of any action or administrative or legal proceeding or
investigation as to which the indemnity provided for in this article may apply, the
Indemnified Party shall notify the Indemnifying Party of such fact. Any failure of
or delay in such notification shall not affect a Party’s indemnification obligation
unless such failure or delay is materially prejudicial to the Indemnifying Party.
7.4 Consequential Damages
 Other than as expressly provided for in this Agreement, no Party shall be liable under any
provision of this Agreement for any losses, damages, costs or expenses for any special, indirect,
incidental, consequential, or punitive damages, including but not limited to loss of profit or
revenue, loss of the use of equipment, cost of capital, cost of temporary equipment or services,
whether based in whole or in part in contract, in tort, including negligence, strict liability, or any
other theory of liability; provided, however, that damages for which a Party may be liable to
another Party under another agreement will not be considered to be special, indirect, incidental,
or consequential damages hereunder.
7.5 Force Majeure
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7.5.1 As used in this article, a “Force Majeure Event” shall mean “any act of God, labor
 disturbance, act of the public enemy, war, insurrection, riot, fire, storm or flood,
 explosion, breakage or accident to machinery or equipment, any order, regulation
 or restriction imposed by governmental, military or lawfully established civilian
 authorities, or any other cause beyond a Party’s control. A Force Majeure Event
 does not include an act of negligence or intentional wrongdoing.” For the
 purposes of this article, this definition of Force Majeure shall supersede the
 definitions of Force Majeure set out in Section 32.10.1 of the ISO OATT.
7.5.2 If a Force Majeure Event prevents a Party from fulfilling any obligations under
 this Agreement, the Party affected by the Force Majeure Event (“Affected Party”)
 shall promptly notify the other Parties, either in writing or via the telephone, of
 the existence of the Force Majeure Event. The notification must specify in
 reasonable detail the circumstances of the Force Majeure Event, its expected
 duration, and the steps that the Affected Party is taking to mitigate the effects of
 the event on its performance. The Affected Party shall keep the other Parties
 informed on a continuing basis of developments relating to the Force Majeure
 Event until the event ends. The Affected Party will be entitled to suspend or
 modify its performance of obligations under this Agreement (other than the
 obligation to make payments) only to the extent that the effect of the Force
 Majeure Event cannot be mitigated by the use of Reasonable Efforts. The
 Affected Party will use Reasonable Efforts to resume its performance as soon as
 possible.
7.6 Breach and Default
7.6.1 No Breach of this Agreement shall exist where such failure to discharge an
 obligation (other than the payment of money) is the result of a Force Majeure
 Event or the result of an act or omission of the other Parties. Upon a Breach, the
 non-breaching Party shall give written notice of such Breach to the Breaching
 Party. Except as provided in article 7.6.2, the Breaching Party shall have 60
 calendar days from receipt of the Breach notice within which to cure such Breach;
 provided however, if such Breach is not capable of cure within 60 calendar days,
 the Breaching Party shall commence such cure within 20 calendar days after
 notice and continuously and diligently complete such cure within six months from
 receipt of the Breach notice; and, if cured within such time, the Breach specified
 in such notice shall cease to exist.
7.6.2 If a Breach is not cured as provided in this article, or if a Breach is not capable of
 being cured within the period provided for herein, a Default shall exist and the
 non-defaulting Parties acting together shall thereafter have the right to terminate
 this Agreement, in accordance with article 3.3 hereof, by written notice to the
 defaulting Party at any time until cure occurs, and be relieved of any further
 obligation hereunder and, whether or not those Parties terminate this Agreement,
 to recover from the defaulting Party all amounts due hereunder, plus all other
 damages and remedies to which they are entitled at law or in equity. The
 provisions of this article shall survive termination of this Agreement.
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7.6.3 In cases where the Interconnection Customer has elected to proceed under
 Section 32.3.5.3 of the SGIP, if the Interconnection Request is withdrawn or
 deemed withdrawn pursuant to the SGIP during the term of this Agreement, this
 Agreement shall terminate.
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Article 8 Insurance
8.1 The Interconnection Customer shall, at its own expense, maintain in force general
 liability insurance without any exclusion for liabilities related to the interconnection
 undertaken pursuant to this Agreement. The amount of such insurance shall be sufficient
 to insure against all reasonably foreseeable direct liabilities given the size and nature of
 the generating equipment being interconnected, the interconnection itself, and the
 characteristics of the system to which the interconnection is made. Such insurance
 coverage is specified in Attachment 7 to this Agreement. The Interconnection Customer
 shall obtain additional insurance only if necessary as a function of owning and operating
 a generating facility. Such insurance shall be obtained from an insurance provider
 authorized to do business in New York State where the interconnection is located.
 Certification that such insurance is in effect shall be provided upon request of the
 Connecting Transmission Owner, except that the Interconnection Customer shall show
 proof of insurance to the Connecting Transmission Owner no later than ten Business
 Days prior to the anticipated commercial operation date. An Interconnection Customer
 of sufficient creditworthiness may propose to self-insure for such liabilities, and such a
 proposal shall not be unreasonably rejected.
8.2 The NYISO and Connecting Transmission Owner agree to maintain general liability
 insurance or self-insurance consistent with the existing commercial practice. Such
 insurance or self-insurance shall not exclude the liabilities undertaken pursuant to this
 Agreement.
8.3 The Parties further agree to notify one another whenever an accident or incident occurs
 resulting in any injuries or damages that are included within the scope of coverage of
 such insurance, whether or not such coverage is sought.
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Article 9 Confidentiality
9.1 Confidential Information shall mean any confidential and/or proprietary information
 provided by one Party to the other Party that is clearly marked or otherwise designated
 “Confidential.” For purposes of this Agreement all design, operating specifications, and
 metering data provided by the Interconnection Customer shall be deemed Confidential
 Information regardless of whether it is clearly marked or otherwise designated as such.
 Confidential Information shall include, without limitation, information designated as such
 by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.
9.2 Confidential Information does not include information previously in the public domain,
 required to be publicly submitted or divulged by Governmental Authorities (after notice
 to the other Party and after exhausting any opportunity to oppose such publication or
 release), or necessary to be divulged in an action to enforce this Agreement. Each Party
 receiving Confidential Information shall hold such information in confidence and shall
 not disclose it to any third party nor to the public without the prior written authorization
 from the Party providing that information, except to fulfill obligations under this
 Agreement, or to fulfill legal or regulatory requirements.
9.2.1 Each Party shall employ at least the same standard of care to protect Confidential
 Information obtained from the other Parties as it employs to protect its own
 Confidential Information.
9.2.2 Each Party is entitled to equitable relief, by injunction or otherwise, to enforce its
 rights under this provision to prevent the release of Confidential Information
 without bond or proof of damages, and may seek other remedies available at law
 or in equity for breach of this provision.
9.3 Notwithstanding anything in this article to the contrary, and pursuant to 18 CFR § lb.20,
 if FERC, during the course of an investigation or otherwise, requests information from
 one of the Parties that is otherwise required to be maintained in confidence pursuant to
 this Agreement, the Party shall provide the requested information to FERC, within the
 time provided for in the request for information. In providing the information to FERC,
 the Party may, consistent with 18 CFR § 388.112, request that the information be treated
 as confidential and non-public by FERC and that the information be withheld from public
 disclosure. Each Party is prohibited from notifying the other Parties to this Agreement
 prior to the release of the Confidential Information to FERC. The Party shall notify the
 other Parties to this Agreement when it is notified by FERC that a request to release
 Confidential Information has been received by FERC, at which time either of the Parties
 may respond before such information would be made public, pursuant to 18 CFR §
 388.112. Requests from a state regulatory body conducting a confidential investigation
 shall be treated in a similar manner if consistent with the applicable state rules and
 regulations.
9.4 Consistent with the provisions of this article 9, the Parties to this Agreement will
cooperate in good faith to provide each other, Affected Systems, Affected System
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Operators, and state and federal regulators the information necessary to carry out the
terms of the SGIP and this Agreement.
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Article 10 Disputes
10.1 The NYISO, Connecting Transmission Owner and Interconnection Customer agree to
 attempt to resolve all disputes arising out of the interconnection process according to the
 provisions of this article.
10.2 In the event of a dispute, the Parties will first attempt to promptly resolve it on an
 informal basis. The NYISO will be available to the Interconnection Customer and
 Connecting Transmission Owner to help resolve any dispute that arises with respect to
 performance under this Agreement. If the Parties cannot promptly resolve the dispute on
 an informal basis, then any Party shall provide the other Parties with a written Notice of
 Dispute. Such notice shall describe in detail the nature of the dispute.
10.3 If the dispute has not been resolved within two Business Days after receipt of the notice,
 any Party may contact FERC’s Dispute Resolution Service (“DRS”) for assistance in
 resolving the dispute.
10.4 The DRS will assist the Parties in either resolving their dispute or in selecting an
 appropriate dispute resolution venue (e.g., mediation, settlement judge, early neutral
 evaluation, or technical expert) to assist the Parties in resolving their dispute. The result
 of this dispute resolution process will be binding only if the Parties agree in advance.
 DRS can be reached at 1-877-337-2237 or via the internet at
http://www.ferc.gov/legal/adr.asp.
10.5 Each Party agrees to conduct all negotiations in good faith and will be responsible for
one-third of any costs paid to neutral third-parties.
10.6 If any Party elects to seek assistance from the DRS, or if the attempted dispute resolution
 fails, then any Party may exercise whatever rights and remedies it may have in equity or
 law consistent with the terms of this Agreement.
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Article 11 Taxes
11.1 The Parties agree to follow all applicable tax laws and regulations, consistent with FERC
policy and Internal Revenue Service requirements.
11.2 Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.
 Nothing in this Agreement is intended to adversely affect the tax status of any Party
 including the status of NYISO, or the status of any Connecting Transmission Owner with
 respect to the issuance of bonds including, but not limited to, Local Furnishing Bonds.
 Notwithstanding any other provisions of this Agreement, LIPA, NYPA and Consolidated
 Edison Company of New York, Inc. shall not be required to comply with any provisions
 of this Agreement that would result in the loss of tax-exempt status of any of their Tax-
 Exempt Bonds or impair their ability to issue future tax-exempt obligations. For
 purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long
 Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc.,
 the interest on which is not included in gross income under the Internal Revenue Code.
11.3 LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA,
 from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s
 general ratemaking authority.
11.4 Any payments due to the Connecting Transmission Owner under this Agreement shall be
 adjusted to include any tax liability incurred by the Connecting Transmission Owner with
 respect to the interconnection request which is the subject of this Agreement. Such
 adjustments shall be made in accordance with the provisions of Article 5.17 of the LGIA
 in Attachment X of the ISO OATT. Except where otherwise noted, all costs, deposits,
 financial obligations and the like specified in this Agreement shall be assumed not to
 reflect the impact of applicable taxes.
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Article 12 Miscellaneous
12.1 Governing Law, Regulatory Authority, and Rules
 The validity, interpretation and enforcement of this Agreement and each of its provisions
shall be governed by the laws of the state of New York, without regard to its conflicts of law
principles. This Agreement is subject to all Applicable Laws and Regulations. Each Party
expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, or
regulations of a Governmental Authority.
12.2 Amendment
 The Parties may amend this Agreement by a written instrument duly executed by the
Parties, or under article 12.12 of this Agreement.
12.3 No Third-Party Beneficiaries
 This Agreement is not intended to and does not create rights, remedies, or benefits of any
character whatsoever in favor of any persons, corporations, associations, or entities other than the
Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their
successors in interest and where permitted, their assigns. Notwithstanding the foregoing, any
subcontractor of the Connecting Transmission Owner or NYISO assisting either of those Parties
with the Interconnection Request covered by this Agreement shall be entitled to the benefits of
indemnification provided for under Article 7.3 of this Agreement and the limitation of liability
provided for in Article 7.2 of this Agreement.
12.4 Waiver
12.4.1 The failure of a Party to this Agreement to insist, on any occasion, upon strict
 performance of any provision of this Agreement will not be considered a waiver
 of any obligation, right, or duty of, or imposed upon, such Party.
12.4.2 Any waiver at any time by a Party of its rights with respect to this Agreement
 shall not be deemed a continuing waiver or a waiver with respect to any other
 failure to comply with any other obligation, right, duty of this Agreement.
 Termination or default of this Agreement for any reason by Interconnection
 Customer shall not constitute a waiver of the Interconnection Customer’s legal
 rights to obtain an interconnection from the NYISO. Any waiver of this
 Agreement shall, if requested, be provided in writing.
12.5 Entire Agreement
 This Agreement, including all Attachments, constitutes the entire agreement between the
Parties with reference to the subject matter hereof, and supersedes all prior and contemporaneous
understandings or agreements, oral or written, between the Parties with respect to the subject
matter of this Agreement. There are no other agreements, representations, warranties, or
covenants which constitute any part of the consideration for, or any condition to, any Party’s
compliance with its obligations under this Agreement.
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12.6 Multiple Counterparts
 This Agreement may be executed in two or more counterparts, each of which is deemed
an original but all constitute one and the same instrument.
12.7 No Partnership
 This Agreement shall not be interpreted or construed to create an association, joint
venture, agency relationship, or partnership between the Parties or to impose any partnership
obligation or partnership liability upon any Party. No Party shall have any right, power or
authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an
agent or representative of, or to otherwise bind, another Party.
12.8 Severability
 If any provision or portion of this Agreement shall for any reason be held or adjudged to
be invalid or illegal or unenforceable by any court of competent jurisdiction or other
Governmental Authority, (1) such portion or provision shall be deemed separate and
independent, (2) the Parties shall negotiate in good faith to restore insofar as practicable the
benefits to each Party that were affected by such ruling, and (3) the remainder of this Agreement
shall remain in full force and effect.
12.9 Security Arrangements
 Infrastructure security of electric system equipment and operations and control hardware
and software is essential to ensure day-to-day reliability and operational security. FERC expects
the NYISO, the Connecting Transmission Owner, Market Participants, and Interconnection
Customers interconnected to electric systems to comply with the recommendations offered by
the President’s Critical Infrastructure Protection Board and, eventually, best practice
recommendations from the electric reliability authority. All public utilities are expected to meet
basic standards for system infrastructure and operational security, including physical,
operational, and cyber-security practices.
12.10 Environmental Releases
 Each Party shall notify the other Parties, first orally and then in writing, of the release of
any hazardous substances, any asbestos or lead abatement activities, or any type of remediation
activities related to the Small Generating Facility or the Interconnection Facilities, each of which
may reasonably be expected to affect the other Parties. The notifying Party shall: (1) provide the
notice as soon as practicable, provided such Party makes a good faith effort to provide the notice
no later than 24 hours after such Party becomes aware of the occurrence, and (2) promptly
furnish to the other Parties copies of any publicly available reports filed with any governmental
authorities addressing such events.
12.11 Subcontractors
Nothing in this Agreement shall prevent a Party from utilizing the services of any subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,
28




[bookmark: br33]SERVICE AGREEMENT NO. 2756
however, that each Party shall require its subcontractors to comply with all applicable terms and
conditions of this Agreement in providing such services and each Party shall remain primarily
liable to the other Parties for the performance of such subcontractor.
12.11.1The creation of any subcontract relationship shall not relieve the hiring Party of
 any of its obligations under this Agreement. The hiring Party shall be fully
 responsible to the other Parties to the extent provided for in Articles 7.2 and 7.3
 above for the acts or omissions of any subcontractor the hiring Party hires as if no
 subcontract had been made; provided, however, that in no event shall the NYISO
 or Connecting Transmission Owner be liable for the actions or inactions of the
 Interconnection Customer or its subcontractors with respect to obligations of the
 Interconnection Customer under this Agreement. Any applicable obligation
 imposed by this Agreement upon the hiring Party shall be equally binding upon,
 and shall be construed as having application to, any subcontractor of such Party.
12.11.2The obligations under this article will not be limited in any way by any limitation
of subcontractor’s insurance.
12.12 Reservation of Rights
 Nothing in this Agreement shall alter the right of the NYISO or Connecting Transmission
Owner to make unilateral filings with FERC to modify this Agreement with respect to any rates,
terms and conditions, charges, classifications of service, rule or regulation under Section 205 or
any other applicable provision of the Federal Power Act and FERC’s rules and regulations
thereunder which rights are expressly reserved herein, and the existing rights of the Interconnection Customer to make a unilateral filing with FERC to modify this Agreement under
any applicable provision of the Federal Power Act and FERC’s rules and regulations are also
expressly reserved herein; provided that each Party shall have the right to protest any such filing
by another Party and to participate fully in any proceeding before FERC in which such
modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties
or of FERC under Sections 205 or 206 of the Federal Power Act and FERC’s rules and
regulations, except to the extent that the Parties otherwise agree as provided herein.
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Article 13 Notices
13.1 General
 Unless otherwise provided in this Agreement, any written notice, demand, or request
required or authorized in connection with this Agreement shall be deemed properly given if
delivered in person, delivered by recognized national courier service, or sent by first class mail,
postage prepaid, to the person specified below:
If to the Interconnection Customer:
Interconnection Customer: Hawthorn Solar, LLC
Attention: Patty Wright, EVP & COO, Generation
Address: 2445 M Street, NW, Suite 200
City: Washington State: DC Zip: 20037
Phone: 828-319-7939
With Copy to: Hawthorn Solar, LLC Attention: Legal Department
Address: 2445 M Street, NW, Suite 200 City: Washington State: DC Zip: 20037
Email: legal@cleanchoice.com with a copy to: interconnection@cleanchoice.com
If to the Connecting Transmission Owner:
Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration & Commercial Services NY
Address: 2 Hanson Place 12th Floor
City: Brooklyn State: NY Zip: 11217 Phone: 516-448-7171
Email: Vishal.Ahirrao@nationalgrid.com
If to the NYISO:
Before Commercial Operation of the Small Generating Facility
New York Independent System Operator, Inc.
Attention: Vice President, System and Resource Planning
Address: 10 Krey Boulevard
City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000
After Commercial Operation:
New York Independent System Operator, Inc.
Attention: Vice President, Operations
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Address: 10 Krey Boulevard
City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000
13.2 Billing and Payment
Billings and payments shall be sent to the addresses set out below:
Interconnection Customer: Hawthorn Solar, LLC
Attention: Patty Wright, EVP & COO, Generation
Address: 2445 M Street, NW, Suite 200
City: Washington State: DC Zip: 20037
Phone: 828-319-7939
With Copy to: Hawthorn Solar, LLC Attention: Legal Department
Address: 2445 M Street, NW, Suite 200
City: Washington State: DC Zip: 20037
Email: legal@cleanchoice.com
with a copy to: interconnection@cleanchoice.com
Connecting Transmission Owner:
Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration and Commercial Services NY
Address: 2 Hanson Place 12th Floor City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171
Email: Vishal.Ahirrao@nationalgrid.com
13.3 Alternative Forms of Notice
 Any notice or request required or permitted to be given by either Party to the other and
not required by this Agreement to be given in writing may be so given by telephone or e-mail to
the telephone numbers and e-mail addresses set out below:
If to the Interconnection Customer:
Hawthorn Solar, LLC
Attention: Patty Wright, EVP & COO, Generation
Address: 2445 M Street, NW, Suite 200
City: Washington State: DC Zip: 20037
Phone: 828-319-7939
With Copy to:
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Hawthorn Solar, LLC Attention: Legal Department
Address: 2445 M Street, NW, Suite 200 City: Washington State: DC Zip: 20037
Email: legal@cleanchoice.com
with a copy to: interconnection@cleanchoice.com
If to the Connecting Transmission Owner:
Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration & Commercial Services NY
Address:2 Hanson Place 12th Floor
City: Brooklyn State: NY Zip: 11217 Phone: 516-448-7171
E-mail: Vishal.Ahirrao@nationalgrid.com
If to the NYISO:
New York Independent System Operator, Inc.
Attention: Vice President, Operations
Address: 10 Krey Boulevard
City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000
E-mail: interconnectionsupport@nyiso.com
13.4 Designated Operating Representative
 The Parties may also designate operating representatives to conduct the communications
which may be necessary or convenient for the administration of this Agreement. This person
will also serve as the point of contact with respect to operations and maintenance of the Party’s
facilities.
Interconnection Customer’s Operating Representative:
Hawthorn Solar, LLC
Attention: Patty Wright, EVP & COO, Generation
Address: 2445 M Street, NW, Suite 200
City: Washington State: DC Zip: 20037
Phone: 828-319-7939
With Copy to: Hawthorn Solar, LLC Attention: Legal Department
Address: 2445 M Street, NW, Suite 200
City: Washington State: DC Zip: 20037
Email: legal@cleanchoice.com
with a copy to: interconnection@cleanchoice.com
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Connecting Transmission Owner’s Operating Representative:
Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration and Commercial Services NY
Address: 2 Hanson Place 12th Floor City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171
E-mail: Vishal.Ahirrao@nationalgrid.com
NYISO’s Operating Representative:
New York Independent System Operator, Inc.
Attention: Vice President, Operations
Address: 10 Krey Boulevard
City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000
E-mail: interconnectionsupport@nyiso.com
13.5 Changes to the Notice Information
 Either Party may change this information by giving five Business Days written notice
prior to the effective date of the change.
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Article 14 Signatures
IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their
respective duly authorized representatives.
For the New York Independent System Operator, Inc.
By:
Name: _________________________
Title: __________________________
Date: __________________________
For Niagara Mohawk Power Corporation d/b/a National Grid
By:
Name: _________________________
Title: __________________________
Date: __________________________
For Hawthorn Solar, LLC
By:
Name: __________________________
Title: ___________________________
Date: ___________________________
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Attachment 1
Glossary of Terms
Affected System – An electric system other than the transmission system owned, controlled or
operated by the Connecting Transmission Owner that may be affected by the proposed
interconnection.
Affected System Operator – Affected System Operator shall mean the operator of any Affected System.
Affected Transmission Owner –The New York public utility or authority (or its designated
agent) other than the Connecting Transmission Owner that: (i) owns facilities used for the
transmission of Energy in interstate commerce and provides Transmission Service under the
Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State
Transmission System where System Deliverability Upgrades or System Upgrade Facilities are
installed pursuant to Attachment Z and Attachment S to the ISO OATT.
Applicable Laws and Regulations – All duly promulgated applicable federal, state and local
laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or
administrative orders, permits and other duly authorized actions of any Governmental Authority,
including but not limited to Environmental Law.
Applicable Reliability Standards – The criteria, requirements and guidelines of the North
American Electric Reliability Council, the Northeast Power Coordinating Council, the New York
State Reliability Council and related and successor organizations, or the Transmission District to
which the Interconnection Customer’s Small Generating Facility is directly interconnected, as
those criteria, requirements and guidelines are amended and modified and in effect from time to
time; provided that no Party shall waive its right to challenge the applicability of or validity of
any criterion, requirement or guideline as applied to it in the context of Attachment Z to the ISO
OATT and this Agreement. For the purposes of this Agreement, this definition of Applicable
Reliability Standards shall supersede the definition of Applicable Reliability Standards set out in
Attachment X to the ISO OATT.
Base Case – The base case power flow, short circuit, and stability data bases used for the
Interconnection Studies by NYISO, Connecting Transmission Owner or Interconnection
Customer; described in Section 32.2.3 of the Large Facility Interconnection Procedures.
Breach - The failure of a Party to perform or observe any material term or condition of this Agreement.
Business Day – Monday through Friday, excluding federal holidays.
Capacity Resource Interconnection Service –The service provided by NYISO to
Interconnection Customers that satisfy the NYISO Deliverability Interconnection Standard or
that are otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT;
such service being one of the eligibility requirements for participation as a NYISO Installed
Capacity Supplier.
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Commercial Operation shall mean the status of the Small Generating Facility that has
commenced generating electricity for sale, excluding electricity generated during Trial
Operation, notice of which must be provided to the NYISO in the form of Attachment 9 to this
Agreement.
Commercial Operation Date of a unit shall mean the date on which the Large Generating
Facility commences Commercial Operation as agreed to by the Parties, notice of which must be
provided to the NYISO in the form of Attachment 9 to this Agreement.
Connecting Transmission Owner – The New York public utility or authority (or its designated
agent) that: (i) owns facilities used for the transmission of Energy in interstate commerce and
provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an
interest in the portion of the New York State Transmission System or Distribution System at the
Point of Interconnection, and (iii) is a Party to the Standard Small Generator Interconnection
Agreement.
Default – The failure of a Party in Breach of this Agreement to cure such Breach under the Small Generator Interconnection Agreement.
Distribution System – The Transmission Owner’s facilities and equipment used to distribute
electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s Large Facility
Interconnection Procedures in Attachment X to the ISO OATT or Small Generator
Interconnection Procedures in Attachment Z to the ISO OATT under FERC Order Nos. 2003
and/or 2006. For the purpose of this Agreement, the term Distribution System shall not include
LIPA’s distribution facilities.
Distribution Upgrades – The additions, modifications, and upgrades to the Connecting
Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate
interconnection of the Small Generating Facility and render the transmission service necessary to
effect the Interconnection Customer’s wholesale sale of electricity in interstate commerce.
Distribution Upgrades do not include Interconnection Facilities or System Upgrade Facilities or
System Deliverability Upgrades.
Energy Resource Interconnection Service – The service provided by NYISO to interconnect
the Interconnection Customer’s Small Generating Facility to the New York State Transmission
System or Distribution System in accordance with the NYISO Minimum Interconnection
Standard, to enable the New York State Transmission System to receive Energy and Ancillary
Services from the Small Generating Facility, pursuant to the terms of the ISO OATT.
Force Majeure – Any act of God, labor disturbance, act of the public enemy, war, insurrection,
riot, fire, storm or flood, explosion, breakage or accident to machinery or equipment, any order,
regulation or restriction imposed by governmental, military or lawfully established civilian
authorities, or any other cause beyond a Party’s control. A Force Majeure event does not include
an act of negligence or intentional wrongdoing. For the purposes of this Agreement, this
definition of Force Majeure shall supersede the definitions of Force Majeure set out in Section
32.2.11 of the NYISO Open Access Transmission Tariff.
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Good Utility Practice – Any of the practices, methods and acts engaged in or approved by a
significant portion of the electric industry during the relevant time period, or any of the practices,
methods and acts which, in the exercise of reasonable judgment in light of the facts known at the
time the decision was made, could have been expected to accomplish the desired result at a
reasonable cost consistent with good business practices, reliability, safety and expedition. Good
Utility Practice is not intended to be limited to the optimum practice, method, or act to the
exclusion of all others, but rather to be acceptable practices, methods, or acts generally accepted
in the region.
Governmental Authority – Any federal, state, local or other governmental regulatory or
administrative agency, court, commission, department, board, or other governmental subdivision,
legislature, rulemaking board, tribunal, or other governmental authority having jurisdiction over
the Parties, their respective facilities, or the respective services they provide, and exercising or
entitled to exercise any administrative, executive, police, or taxing authority or power; provided,
however, that such term does not include the Interconnection Customer, NYISO, Affected
Transmission Owner, Connecting Transmission Owner or any Affiliate thereof.
Initial Synchronization Date shall mean the date upon which the Small Generating Facility is
initially synchronized and upon which Trial Operation begins, notice of which must be provided
to the NYISO in the form of Attachment 9.
In-Service Date shall mean the date upon which the Developer reasonably expects it will be
ready to begin use of the Connecting Transmission Owner’s Interconnection Facilities to obtain
back feed power.
Interconnection Customer – Any entity, including the Transmission Owner or any of the
affiliates or subsidiaries, that proposes to interconnect its Small Generating Facility with the New
York State Transmission System or the Distribution System.
Interconnection Facilities – The Connecting Transmission Owner’s Interconnection Facilities
and the Interconnection Customer’s Interconnection Facilities. Collectively, Interconnection
Facilities include all facilities and equipment between the Small Generating Facility and the
Point of Interconnection, including any modification, additions or upgrades that are necessary to
physically and electrically interconnect the Small Generating Facility to the New York State
Transmission System or the Distribution System. Interconnection Facilities are sole use facilities
and shall not include Distribution Upgrades or System Upgrade Facilities.
Interconnection Request – The Interconnection Customer’s request, in accordance with the
Tariff, to interconnect a new Small Generating Facility, or to materially increase the capacity of,
or make a material modification to the operating characteristics of, an existing Small Generating
Facility that is interconnected with the New York State Transmission System or the Distribution
System. For the purposes of this Agreement, this definition of Interconnection Request shall
supersede the definition of Interconnection Request set out in Attachment X to the ISO OATT.
Interconnection Study – Any study required to be performed under Sections 32.2 or 32.3 of the SGIP.
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Material Modification – A modification that has a material impact on the cost or timing of any Interconnection Request with a later queue priority date.
New York State Transmission System – The entire New York State electric transmission
system, which includes: (i) the Transmission Facilities under ISO Operational Control; (ii) the
Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities
within the New York Control Area.
NYISO Deliverability Interconnection Standard – The standard that must be met, unless
otherwise provided for by Attachment S to the ISO OATT, by (i) any generation facility larger
than 2MW in order for that facility to obtain CRIS; (ii) any Class Year Transmission Project
proposing to interconnect to the New York State Transmission System and receive Unforced
Capacity Delivery Rights; (iii) any entity requesting External CRIS Rights, and (iv) any entity
requesting a CRIS transfer pursuant to Section 25.9.5 of Attachment S to the ISO OATT. To
meet the NYISO Deliverability Interconnection Standard, the Interconnection Customer must, in
accordance with the rules in Attachment S to the ISO OATT, fund or commit to fund any System
Deliverability Upgrades identified for its project in the Class Year Deliverability Study.
NYISO Minimum Interconnection Standard – The reliability standard that must be met by
any generation facility or Class Year Transmission Project that is subject to NYISO’s Large
Facility Interconnection Procedures in Attachment X to the ISO OATT or the NYISO’s Small
Generator Interconnection Procedures in this Attachment Z, that is proposing to connect to the
New York State Transmission System or Distribution System, to obtain ERIS. The Minimum
Interconnection Standard is designed to ensure reliable access by the proposed project to the
New York State Transmission System or to the Distribution System. The Minimum
Interconnection Standard does not impose any deliverability test or deliverability requirement on
the proposed interconnection.
Operating Requirements – Any operating and technical requirements that may be applicable
due to Regional Transmission Organization, Independent System Operator, control area, or the
Connecting Transmission Owner’s requirements, including those set forth in the Small Generator
Interconnection Agreement. Operating Requirements shall include Applicable Reliability
Standards.
Party or Parties – The NYISO, Connecting Transmission Owner, Interconnection Customer or any combination of the above.
Point of Interconnection – The point where the Interconnection Facilities connect with the New York State Transmission System or the Distribution System.
Reasonable Efforts – With respect to an action required to be attempted or taken by a Party
under this Agreement, efforts that are timely and consistent with Good Utility Practice and are
otherwise substantially equivalent to those a Party would use to protect its own interests.
Small Generating Facility – The Interconnection Customer’s facility, no larger than 20 MW for
the production and/or storage for later injection of electricity identified in the Interconnection
Request if proposing to interconnect to the New York State Transmission System or Distribution
System, but shall not include (i) facilities proposing to simply receive power from the New York
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State Transmission System or the Distribution System; (ii) facilities proposing to interconnect to
the New York State Transmission System or the Distribution System made solely for the purpose
of generation with no wholesale sale for resale nor to net metering; (iii) facilities proposing to the
New York State Transmission System or the Distribution System made solely for the purpose of
net metering; (iv) facilities proposing to interconnect to LIPA’s distribution facilities; and (v) the
Interconnection Customer’s Interconnection Facilities. A facility will be treated as a single Small
Generating Facility if all units within the facility are behind a single facility meter, even if such
units are different technology types.
System Deliverability Upgrades – The least costly configuration of commercially available
components of electrical equipment that can be used, consistent with Good Utility Practice and
Applicable Reliability Requirements, to make the modifications or additions to the existing New
York State Transmission System that are required for the proposed project to connect reliably to
the system in a manner that meets the NYISO Deliverability Interconnection Standard for
Capacity Resource Interconnection Service.
System Upgrade Facilities – The least costly configuration of commercially available
components of electrical equipment that can be used, consistent with Good Utility Practice and
Applicable Reliability Requirements to make the modifications to the existing transmission
system that are required to maintain system reliability due to: (i) changes in the system,
including such changes as load growth and changes in load pattern, to be addressed in the form
of generic generation or transmission projects; and (ii) proposed interconnections. In the case of
proposed interconnection projects, System Upgrade Facilities are the modification or additions to
the existing New York State Transmission System that are required for the proposed project to
connect reliably to the system in a manner that meets the NYISO Minimum Interconnection
Standard.
Tariff – The NYISO’s Open Access Transmission Tariff, as filed with the FERC, and as amended or supplemented from time to time, or any successor tariff.
Trial Operation shall mean the period during which Interconnection Customer is engaged in on-
site test operations and commissioning of the Small Generating Facility prior to Commercial
Operation.
Upgrades – The required additions and modifications to the Connecting Transmission Owner’s
portion of the New York State Transmission System or the Distribution System at or beyond the
Point of Interconnection. Upgrades may be System Upgrade Facilities or System Deliverability
Upgrades Distribution Upgrades. Upgrades do not include Interconnection Facilities.
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Attachment 2
Detailed Scope of Work, Including Description and Costs of the Small Generating Facility,
 Interconnection Facilities, and Metering Equipment
 Equipment, including the Small Generating Facility, Interconnection Facilities, and
metering equipment shall be itemized and identified as being owned by the Interconnection
Customer, or the Connecting Transmission Owner. The NYISO, in consultation with the
Connecting Transmission Owner, will provide a best estimate itemized cost, including
overheads, of its Interconnection Facilities and metering equipment, and a best estimate itemized
cost of the annual operation and maintenance expenses associated with its Interconnection
Facilities and metering equipment.
A. PROJECT DESCRIPTION
 The Interconnection Customer has proposed to construct a 20MW solar powered
electricity generation facility (the “Small Generating Facility”) located on Fords Road in
Hoosick Falls, New York, Rensselaer County. The Small Generating Facility will consist of
three (3) Sungrow SG3150UD-MV solar inverters coupled with 600V/34.5kV 3.150MVA step-
up transformers and four (4) Sungrow SG4400UD-MV solar inverters coupled with
645V/34.5kV 4.40MVA step-up transformers. The output of the five step-up transformers are
aggregated into a medium voltage collection circuit (“Collection Feeder Line”). The home run
of the Collection Feeder Line ties to the Interconnection Customer’s Collector Station
(“Hawthorn Solar Collector Substation”) where it is stepped up to 115kV via a 15/20/25MVA
115kV/34.5kV transformer.
 The Point of Interconnection (“POI”) for the Small Generating Facility is Connecting
Transmission Owner’s 115kV North Troy-Hoosick Line 5, located approximately 14.5 miles
from Connecting Transmission Owner’s North Troy Substation and approximately 3.21 miles
from Connecting Transmission Owner’s Hoosick Substation. Interconnection to the electric
power system will be via a tap. The Point of Change of Ownership (“PCO”) will be at the line
side connection of the Interconnection Customer’s disconnect switch located on the
Interconnection Customer’s termination structure inside the Hawthorn Solar Collector
Substation. The Connecting Transmission Owner will own the insulators, whips, and hardware
connections to the disconnect switch. The POI and PCO are detailed on the one-line diagram in
Attachment 3.
B. INTERCONNECTION CUSTOMER’S INTERCONNECTION FACILITIES
 The Interconnection Customer’s Interconnection Facilities (“ICIFs”) include all of the
facilities between the Interconnection Customer’s side of the PCO and the Small Generating
Facility, except the Connecting Transmission Owner-owned metering, remote terminal unit
(“RTU”), and telecommunications equipment described in Section C below. As depicted on the
one-line diagram in Attachment 3, the ICIFs consist of the following:
1. Hawthorn Solar Collector Substation
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 The Hawthorn Solar Collector Substation will be located approximately 100 feet
southeast of Line 5 and will be comprised of the following major equipment:
• one (1) three phase, three winding, 115-34.5kV grounded wye-grounded
 wye, step-up transformer rated 15/20/25MVA (ONAN/ONAF/ONAF),
 z=9%;
• six (6) single phase 76kV maximum continuous operating voltage
(“MCOV”) station class surge arresters;
• one (1) 115kV, 1200A, 550kV basic insulation level (“BIL”) group operated
air break switch;
• one (1) 115kV, 1200A, 550kV BIL, 40 kAIC SF-6 circuit breaker;
• three (3) 69kV-115/69V; capacitive voltage transformers 600/1000:1:1;
• six (6) single phase 24.4kV MCOV station class surge arresters;
• one (1) 38kV, 1200A, 200kV BIL, gang operated disconnect switch;
• one (1) 28kV, 1200A, 200kV BIL, 25kAIC vacuum circuit breaker;
• one (1) 38kV, 300A, 200kV BIL, fused hook stick switch;
• three (3) 38kV, 1200A, hook stick operated disconnect switches;
• three (3) 19.9kV voltage transformers 300:1; and
• one (1) 50kVA 19.9kV – 120/240V station service transformer.
2. System Protection Requirements
a) Line 5
 Direct transfer trip (“DTT”) will be used between the Hawthorn Solar Collector
Substation and the line terminals at the Connecting Transmission Owner’s North Troy and
Hoosick Substations to ensure removal of the generation. This will require installation of two (2)
RFL GARDPro tele-protection sets at the Hawthorn Solar Collector Substation. The Connecting
Transmission Owner will provide details on the GARDPro model number with the Connecting
Transmission Owner’s logic during detailed engineering design. The Interconnection Customer
will provide redundant 115kV line protection to remove the generation for line faults. Two sets
of C800 multi-ratio current transformers (“CTs”) shall be provided for these schemes.
b) Transformer
 The 115–34.5kV transformer shall be protected by two independent protection systems;
one must be a transformer differential. If overcurrent protection is used for the other system,
then both phase and ground time and instantaneous protection shall be provided. Each of the two
schemes must operate separate lockout relays to trip and block the necessary breakers.
c) Breaker
 Breaker failure protection shall be provided for the 115kV breaker R5; this protection
must trip the Interconnection Customer’s 115kV breaker and send DTT to North Troy and
Hoosick Substations. For loss of SF6, the breaker must trip and block close. (Note: When the
facility’s interrupter fails to interrupt for internal station faults and loss of SF6 condition, the
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Interconnection Customer is not to rely on the Connecting Transmission Owner’s 115kV system for remote backup.)
 DTT receive from North Troy and Hoosick Substations will be required to trip the
Interconnection Customer’s 115kV breaker for a line relay operation or breaker failure at the
North Troy and Hoosick substations. The Interconnection Customer shall provide on/off
switches for the DTT schemes.
3. Telecommunications Circuit
 The Interconnection Customer will coordinate with the CTO and FirstLight to bring
FirstLight dark fiber into the Hawthorn Solar Collector Substation. To establish the
teleprotection circuits required for DTT between the Hawthorn Solar Collector Station and the
CTO’s Hoosick and North Troy Station, Hawthorn Solar Collector Station will become a node
on the CTO’s private network.
 The Connecting Transmission Owner’s revenue meter will require a communications link
to its RTU. In accordance with the ESBs, the Interconnection Customer shall install a conduit
for the communication cables that will run between meter equipment enclosure and RTU
enclosure in the Hawthorn Solar Collector Substation control house. The Connecting
Transmission Owner will specify and run the communication cables between the meter
equipment and RTU enclosures. (Note: Third party telecommunications are potentially long lead
time items).
 To the extent the Small Generating Facility feeder lines, communication circuits, access
roads, and/or driveways cross Connecting Transmission Owner-owned transmission or
distribution circuits, such crossings must be reviewed by the Connecting Transmission Owner in
accordance with the Connecting Transmission Owner’s land use requirements. Per the
Hawthorn Solar Project Specifications (defined below), feeder line crossings shall be
underground so as to maintain the reliability of service provided by the Connecting Transmission
Owner to other customers via the impacted transmission and distribution facilities.
C. CONNECTING TRANSMISSION OWNER’S INTERCONNECTION FACILITIES
 As depicted in the one-line diagram in Attachment 3, the Connecting Transmission
Owner’s Interconnection Facilities (“CTOIFs”) consist of the following items constructed or
installed between the POI and PCO, as well as the revenue metering and a RTU located at the
Hawthorn Solar Collector Substation.
1. Revenue Metering
 The revenue metering shall be located in the Hawthorn Solar Collector Substation control
enclosure on the generator side of the 115kV breaker and shall consist of:
• three (3) combination current/potential transformer (CT/PT) units, also called
metering units, one for each phase. Manufacturer and model shall be
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ABB/Hitachi KXM-550 or other Connecting Transmission Owner specific equivalent;
• revenue meter; and • revenue socket.
 The ratios of CTs and PTs will be provided by the Connecting Transmission Owner upon
review of the Interconnection Customer’s design documents in accordance with the ESBs. (Note:
Connecting Transmission Owner’s revenue metering CTs and PTs cannot be used to feed the
Interconnection Customer’s check meter).
 The metering of any redundant or standby station service provisions (if required) at the
Hawthorn Solar Collector Substation shall be added in accordance with the Connecting
Transmission Owner’s retail tariff, PSC No. 220, and ESB 750.
2. EMS-RTU
 The Connecting Transmission Owner will procure and provide the RTU to the
Interconnection Customer for installation on the Interconnection Customer provided mounting
panel in the control house. The RTU cabinet is typically 42” H x 30” W x 12” D and shall be
wall-mounted with the bottom edge 36” above the floor with a 5-foot clear working space in
front of the mounting panel.
3. Telecommunications
 The Connecting Transmission Owner shall procure and provide a pre-wired telecom rack
for the Interconnection Customer to install in the Hawthorn Solar Collector Station control
enclosure. The pre-wired telecom rack will be comprised of:
• One (1) telecom rectifier rack with
 o Dedicated DC battery system
 o One (1) fuse panel
o One (1) SEL ICON
o One (1) DPS NETGAURDIAN TMON RTU o One (1) DCB Loop o One (1) DSX panel
o One (1) Fiber Distribution Panel (FDP)
4. Line 5 Tap
 The Small Generating Facility will interconnect to Connecting Transmission Owner’s
115kV system via a radial tap off the North Troy-Hoosick Line 5 between existing structures 141
and 142. The Hawthorn Solar Collector Substation is to be located approximately 100 feet
southeast of Line 5 and will be oriented perpendicular to the transmission lines. Based on the
location of the Hawthorn Solar Collector Substation, the radial tap will require:
Removal of:
• one (1) wood H-frame suspension structure.
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Installation of:
• one (1) 3-pole steel tapping structure with caisson foundations;
• one (1) H-frame light duty steel pole direct buried structure;
• two (2) direct bury H-frame steel flyover switch structure with switches;
• three (3) inline disconnect switches; and
• approximately 200 circuit feet of 795 MCM 36/1 “COOT” ACSR conductor.
 Note: at this time the Connecting Transmission Owner’s transmission control center
(“TCC”) does not anticipate the need for motor operated disconnect switches (“MODs”).
However, if during final engineering and outage planning TCC determines that MODs are
required to accommodate the interconnection, the Interconnection Customer shall be responsible
for the incremental cost.
 Take off structure heights and phase spacing will need to be established between
Interconnection Customer and Connecting Transmission Owner before final design and material
specifications are prepared. Soil borings for the line tap will be completed by the Connecting
Transmission Owner and all line phasing shall match the exiting Line 5.
 The Connection Transmission Owner and the Interconnection Customer agree that the
Connecting Transmission Owner shall endeavor in good faith to use commercially reasonable
efforts to design and site all components of the Line 5 Tap equipment, including vertical switch
structures, as close as reasonably practical to the Hawthorn Solar Collector Substation for the
purpose of simplifying any real estate or permitting needs, so long as the design and siting of
such equipment is in accordance with Good Utility Practice.
D. SCOPE OF WORK AND RESPONSIBILITIES
1. Interconnection Customer’s Scope of Work and Responsibilities
 The Interconnection Customer shall design, construct, operate, and maintain the ICIFs in
accordance with the following requirements, to the extent not inconsistent with the terms of this
Agreement, the ISO OATT, or applicable ISO procedures; the NYISO’s requirements; industry
standards and specifications; regulatory requirements; the Connecting Transmission Owner’s
applicable ESBs; and the Connecting Transmission Owner’s System Protection and Interconnection Customer Attachment Facilities Electric Installation Specification for Hawthorn
Solar Project (“Hawthorn Solar Project Specifications”) and Standards and Requirements
Relating to Third Party Acquisition and Transfer of Real Property Interests to Niagara Mohawk
Power Corporation for Electric Facilities and Survey Specifications, dated January 2019. The
Hawthorn Solar Project Specifications may be amended after receipt and review of the
Interconnection Customer’s final design and equipment specifications for the Small Generating
Facility and notice to proceed with funding under the terms of the Interconnection Agreement.
The Interconnection Customer shall furnish and install:
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• a billing meter panel in the Hawthorn Solar Collector Substation control
 building in accordance with ESB 756 and ESB 750 (the billing meter panel
 must be near the RTU);
• conduit for the wiring from the instrument transformers to the Connecting
 Transmission Owner supplied meter socket in accordance with ESB 758, ESB
 752, and ESB 750.
 The Interconnection Customer shall run the Connecting Transmission Owner provided
color-coded instrument transformer secondary cable from the instrument transformers to the
meter socket in accordance with the Hawthorn Solar Project Specifications.
 As per ESB 756 and ESB 752, the Interconnection Customer shall install the RTU
indoors and within 15 feet of the meter(s) and remote from:
• heavy traffic areas, work areas, and loading areas;
• heat producing or high electrostatic or electromagnetic field producing
 equipment; and
• station batteries.
The Interconnection Customer shall provide:
• a dedicated 20A, 120VAC single phase 60 hertz power circuit for the RTU;
• conduit and wiring (minimum No. 10 AWG copper) to the RTU cabinet, which
 shall enter the cabinet from the bottom (a 3 foot length of all conductors shall be
 provided for final connection); and
• a dedicated 10A, 48VDC or 125VDC circuit for the RTU from the station
battery.
 The Interconnection Customer shall coordinate with the Connecting Transmission Owner
to bring FirstLight dark fiber into the Hawthorn Solar Collector Station, and shall be responsible
for completing all make-ready work in accordance with the Connecting Transmission Owner’s
requirements, including, but not limited to:
• Construct two (2) 4” Schedule 80 conduits from the dark fiber meet point
 outside the Hawthorn Solar Collector Substation into the control house
• Install three (3) each 1.5” corrugated innerduct with mule tape in one of the 2 4”
 conduit.
• Install the pre-wired telecom rack with 3-foot of clearance in front and behind
the rack;
• Install four (4) each 120/240 VAC 20 amps circuits to power the telecom
rectifier rack;
• Install station ground #6 AWG green copper wire from station ground to the
telecom rack location;
• Extending circuits from telecom rack to relays and EMS RTU.
All make ready work must be completed 180 days prior to Initial Backfeed Date;
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 New right-of-way (“ROW”) will be required for the construction, operation, and
maintenance of the tap line and must accommodate the 125’ x 125’ work pads (temporary)
required for the installation of the new structures. The Interconnection Customer is responsible
for obtaining all real estate/easements and environmental permits for Connecting Transmission
Owner to construct, operate, and maintain the transmission infrastructure including all permanent
and temporary real estate for construction of the facilities and all access roads (permanent and
temporary). The Interconnection Customer shall acquire all required real estate in accordance
with the Connecting Transmission Owner’s Standards and Requirements Relating to Third Party
Acquisition and Transfer of Real Property Interests to Niagara Mohawk Power Corporation for
Electric Facilities and Survey Specifications.
 Permanent access roads are required for access to the new load break disconnect
switches. Property rights for the line tap and transmission line facilities and associated access
roads must be transferred to Connecting Transmission Owner at least two (2) months in advance
of construction initiation.
2. Connecting Transmission Owner’s Scope of Work and Responsibilities
The Connecting Transmission Owner shall:
• provide color-coded instrument transformer secondary cable and complete all
terminations of the cable in the control house;
• provide the meter socket for the Interconnection Customer to install on the
billing meter panel; and
• supply and install the revenue meter.
 The Connecting Transmission Owner will procure and provide the RTU to the
Interconnection Customer for installation on the Interconnection Customer provided mounting
panel in the control house.
 The Connecting Transmission Owner shall procure and install the Garrettcom DX-940E
gateway required for interfacing the RTU to the Connecting Transmission Owner’s EMS
network, and will complete all wiring, testing, and commissioning of the RTU.
 The Connecting Transmission Owner shall provide the pre-wired telecom rack to the
Interconnection Customer for installation in the Hawthorn Solar Collector Station. The
Connecting Transmission Owner will also:
• complete all secondary wiring for the telecom equipment;
• order Firstlight dark fiber from Hawthorn Solar Collector Station to Hoosick
 Station.
• Provision the following private network circuits;
o One (1) DS1 Teleprotection circuit for DTT from Hawthorn Solar
Collector Station to Hoosick Substation.
o One (1) DS1 Teleprotection circuit for DTT from Hawthorn Solar
Collector Station to North Troy Substation. o One (1) 10/100 EMS RTU Ethernet circuit.
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o One (1) 10/100 TMON network monitoring Ethernet circuit.
 The Connecting Transmission Owner shall engineer, design, construct, own, and
maintain the Line 5 Tap.
 The Connecting Transmission Owner shall engineer, design, and construct all System
Upgrade Facilities.
E. ESTIMATED COSTS OF INTERCONNECTION FACILITIES
 1. Facilities Study Cost Estimate
 The total estimated costs (+30%/-15%) of the work associated with the Interconnection
Facilities required for the interconnection of the Small Generating Facility are presented in the
table below.
 As described in the Facilities Study for the Small Generating Facility, the estimates
provided herein:
Assume:
• 5 x 10 construction work week; • outages are available;
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• all major material is delivered to site (i.e., no costs are included for transport
from storage);
• existing equipment to remain is functional; and
• mobile generation will be required for approximately seven (7) calendar days.
Exclude (as applicable):
• discussions and negotiations of issued interconnection study; • application fees;
• applicable surcharges;
• overall project sales tax; • property taxes; • line switching;
• property/easement acquisitions;
• access roads and associated matting;
• future operation and maintenance costs;
• recurring monthly communications circuits’ charges, if any, responsible by the
 Interconnection Customer to the communications utility;
• soil testing;
• adverse field conditions such as rock, water, weather, and Interconnection
Customer electrical equipment obstructions; • environmental mitigation;
• extended engineering to minimize outage time or Connecting Transmission
Owner’s public utility to serve;
• impacts resulting from modifications to the project and/or any variance to the
 assumptions, including the energization date and outage requirements;
• extended craft labor hours, to minimize outage and/or construction time, or;
• any required permits.
2. Cost Estimate Update
 Interconnection Customer requested an extension of its Commercial Operation Date
(“COD”) for the Small Generating Facility to June 2027 pursuant to the modification rules in
Section 40.6.3.5 of Attachment HH to the NYISO OATT. The NYISO determined, in
consultation with the Connecting Transmission Owner, that a Cost Estimate Update is required
in order for the requested extension of the Commercial Operation Date not to be a material
modification. Connecting Transmission Owner performed the Cost Estimate Update, and
Interconnection Customer accepted the revised cost estimates included above. The revised cost
estimates update the cost estimate amount for the Small Generating Facility determined in the
Facilities Study.
F. O&M EXPENSES FOR INTERCONNECTION FACILITIES
In accordance with Article 4.1.2 of this Agreement, the Interconnection Customer shall be responsible for all reasonable expenses associated with the operation, maintenance, repair and
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replacement of the Connecting Transmission Owner’s Interconnection Facilities, as such
facilities are detailed in this Attachment 2 (“O&M Expenses”).
 The Interconnection Customer shall have the option to pay such O&M Expenses either
under the procedure described in Option 1 or in Option 2 below.
Option 1: Fixed On-Going Charge Payment:
The Connecting Transmission Owner will invoice and Interconnection Customer
shall pay an annual payment to the Connecting Transmission Owner equal to the
product of the Gross Plant Investment associated with the Connecting
Transmission Owner’s Interconnection Facilities and the Annual Transmission
Ongoing Charge Factor, for the term of this Agreement.
For purposes of this Agreement, Gross Plant Investment shall mean the
investment from the plant account records associated with the Connecting
Transmission Owner’s Interconnection Facilities for the Small Generating
Facility.
All payments due to be made by the Interconnection Customer shall be made
within thirty (30) days after receiving an invoice from the Connecting
Transmission Owner. Connecting Transmission Owner will bill Interconnection
Customer for the O&M Expenses on a quarterly basis.
The Project’s Gross Plant Investment associated with the Connecting
Transmission Owner’s Interconnection Facilities shall be established in writing by
the Connecting Transmission Owner no later than 90 days following commercial
operation.
The Annual Transmission On-Going Charge Factor shall be calculated annually
each July based on the Connecting Transmission Owner’s most recent FERC
Form 1 data and will equal the sum of the Revenue Requirement Components as
identified in O&M Attachment 1 divided by the Total Gross Plant of the
Connecting Transmission Owner. Total Gross Plant shall equal the sum of Item
Nos. A (1)(a)(b)(c) in O&M Attachment 1.
Option 2: Quarterly Actual O&M Expenses
The Interconnection Customer shall pay for all actual O&M Expenses incurred by
the Connecting Transmission Owner, which expenses shall be billed by the
Connecting Transmission Owner quarterly as accumulated during the quarter for
which they were incurred.
All payments due to be made by the Interconnection Customer shall be made
within thirty (30) days after receiving an invoice from the Connecting
Transmission Owner, which invoice shall be issued after the end of each quarter
for the most recent quarter.
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Selection by Interconnection Customer
 The Interconnection Customer shall select which option for paying such O&M Expenses
by providing written notice to the Connecting Transmission Owner within thirty (30) days after
the Gross Connecting Transmission Owner’s Interconnection Facilities Plant Investment cost and
the most recent Annual Transmission Ongoing Charge Factor have been provided to the
Interconnection Customer. If the Interconnection Customer fails to provide timely notice to the
Connecting Transmission Owner of the option selected, the Interconnection Customer will be
deemed to have selected Option 2: Quarterly Actual O&M Expenses.
O&M ATTACHMENT 1
Capitalized terms used in this calculation will have the following definitions:
Allocation Factor
(1) General Plant Allocation Factor shall equal Electric General Plant divided by the sum of
Electric General Plant plus gas general plant as reported in the Annual Report filed with the New
York State Public Service Commission.
(2) Gross Transmission Plant Allocation Factor shall equal the total investment in
Transmission Plant in Service divided by the sum of the total Transmission Plant in Service plus
the total Distribution Plant in Service, excluding Intangible Plant, General Plant and Common
Plant.
(3) Transmission Wages and Salaries Allocation Factor shall equal the ratio of Connecting
Transmission Owner Transmission-related direct electric wages and salaries including any direct
wages or salaries charged to Connecting Transmission Owner by a Connecting Transmission
Owner Affiliate to Connecting Transmission Owner’s total electric direct wages and salaries
including any wages charged to Connecting Transmission Owner by a Connecting Transmission
Owner Affiliate excluding any electric administrative and general wages and salaries.
Ratebase and Expense items
(1) Administrative and General Expense shall equal electric expenses as recorded in FERC
Account Nos. 920-935.
(2) Amortization of Investment Tax Credits shall equal electric credits as recorded in FERC
Account No. 411.4.
(3) Distribution Plant in Service shall equal the gross plant balance as recorded in FERC Account Nos. 360 – 374.
(4) Electric Common Plant shall equal the balance of Common Plant recorded in FERC
Account Nos. 389-399 multiplied by the General Plant Allocation Factor.
(5) General Plant shall equal electric gross general plant balance recorded in FERC Account
Nos. 389-399.
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(6) Materials and Supplies shall equal electric materials and supplies balance as recorded in
FERC Account No. 154.
(7) Payroll Taxes shall equal those electric payroll tax expenses as recorded in FERC
Account Nos. 408.100, 408.110 and 408.130.
(8) Prepayments shall equal electric prepayment balance as recorded in FERC Account
No. 165.
(9) Real Estate Tax Expenses shall equal electric transmission-related real estate tax expense
as recorded in FERC Account No. 408.140 and 408.180.
(10) Transmission Operation and Maintenance Expense shall equal electric expenses as
recorded in FERC Account Nos. 560, 562-573.
(11) Transmission Plant in Service shall equal the gross plant balance as recorded in FERC
Account Nos. 350-359.
(12) Transmission Revenue Credits shall equal the revenue reported in Account 456
(13) Transmission Related Bad Debt Expense shall equal Bad Debt Expense as reported in
Account 904 related to transmission billing.
(14) Wholesale Metering Cost shall equal any costs associated with any Revenue or Remote
Terminal Unit (RTU) meters and associated equipment located at an internal or external tie at
voltages equal to or greater than 23V. The cost shall be determined by multiplying the number of
wholesale meters in FERC Account No. 370.3 by the average cost of the meters plus the average
costs of installation.
 In the event that the above-referenced FERC accounts are renumbered, renamed, or
otherwise modified, the above sections shall be deemed amended to incorporate such
renumbered, renamed, modified or additional accounts.
Revenue Requirement Components
 The Revenue Requirement Components shall be the sum of Connecting Transmission
Owner’s (A) Return and Associated Income Taxes, (B) Transmission Related Real Estate Tax
Expense, (C) Transmission Related Amortization of Investment Tax Credits, (D) Transmission
Related Payroll Tax Expense (E) Transmission Operation and Maintenance Expense, (F)
Transmission Related Administrative and General Expenses, less (G) Revenue Credits, plus (H)
Bad Debt Expense.
 A. Return and Associated Income Taxes shall equal the product of the Transmission
Investment Base as identified in A(1) below and the Cost of Capital Rate.
1. Transmission Investment Base shall be defined as
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Transmission Related General Plant plus Transmission Related Common
Plant plus Transmission Related Regulatory Assets plus Transmission
Related Prepayments plus Transmission Related Materials and Supplies
plus Transmission Related Cash Working Capital.
(a) Transmission Plant in Service shall equal the balance of Total
 investment in Transmission Plant plus Wholesale Metering Cost.
(b) Transmission Related General Plant shall equal the balance of
 investment in General Plant multiplied by the Transmission Wages
 and Salaries Allocation Factor.
(c) Transmission Related Common Plant shall equal Electric Common
 Plant multiplied by the Gross Transmission Plant Allocation Factor
 and multiplied by the Transmission Wages and Salaries Allocation
 Factor.
(d) Transmission Related Regulatory Assets shall equal balances in
 FERC Account Nos. 182.3 and 254 for state and federal regulatory
 assets and liabilities related to FAS109, and excess AFUDC
 multiplied by the Gross Transmission Plant Allocation Factor
(e) Transmission Related Prepayments shall equal the electric balance
 of Prepayments multiplied by the Gross Transmission Plant
 Allocation Factor.
(f) Transmission Related Materials and Supplies shall equal the
 balance of Materials and Supplies assigned to Transmission added
 to the remainder of Material and Supplies not directly assigned to
 either Transmission or Distribution multiplied by the Gross
 Transmission Plant Allocation Factor.
(g) Transmission Related Cash Working Capital shall be a 12.5%
 allowance (45 days/360 days) of the Transmission Operation and
 Maintenance Expense (less FERC Account 565: Transmission of
 Electricity by Others) and Transmission-Related Administrative
 and General Expense.
2. Cost of Capital Rate
The Cost of Capital Rate shall equal the proposed Weighted Costs of
Capital plus Federal Income Taxes and State Income Taxes.
(a) The Weighted Costs of Capital will be calculated for the
 Transmission Investment Base using Connecting Transmission
 Owner’s actual capital structure and will equal the sum of (i), (ii),
 and (iii) below:
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(i) the long-term debt component, which equals the product of
 the actual weighted average embedded cost to maturity of
 Connecting Transmission Owner’s long-term debt then
 outstanding and the actual long-term debt capitalization
 ratio.
(ii) the preferred stock component, which equals the product of
 the actual weighted average embedded cost to maturity of
 Connecting Transmission Owner’s preferred stock then
 outstanding and the actual preferred stock capitalization
 ratio;
(iii) the return on equity component, shall be the product of the
 allowed ROE of 10.30% or such value as most recently
 approved by the Commission plus a 50 basis point adder
 (per FERC Order 697 and 697-A, if authorized by the
 Commission for the Connecting Transmission Owner) and
 Connecting Transmission Owner’s actual common equity
 capitalization ratio.
(b) Federal Income Tax shall equal
A x Federal Income Tax Rate
(1 - Federal Income Tax Rate)
where A is the sum of the preferred stock component and the return
on equity component, each as determined in Sections 2.(a)(ii) and
for the ROE set forth in 2.(a)(iii) above
(c) State Income Tax shall equal
(A + Federal Income Tax) x State Income Tax Rate
(1 – State Income Tax Rate)
Where A is the sum of the preferred stock component and the return on
equity component as determined in A.2.(a)(ii) and A.2.(a)(iii) above and
Federal income Tax is determined in 2.(b) above.
 B. Transmission Related Real Estate Tax Expense shall equal the Real Estate Tax
Expenses multiplied by the Gross Plant Allocation Factor.
 C. Transmission Related Amortization of Investment Tax Credits shall equal the
electric Amortization of Investment Tax Credits multiplied by the Gross Transmission Plant
Allocation Factor.
 D. Transmission Related Payroll Tax Expense shall equal Payroll Taxes multiplied
by the Transmission Wages and Salaries Allocation Factor.
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 E. Transmission Operation and Maintenance Expense shall equal the Transmission
Operation and Maintenance Expense as previously defined.
 F. Transmission Related Administrative and General Expenses shall equal the sum
of the electric Administrative and General Expenses multiplied by the Transmission Wages and
Salaries Allocation Factor.
G. Revenue Credits shall equal all Transmission revenue recorded in FERC account 456.
 H. Transmission Related Bad Debt Expense shall equal Transmission Related Bad
Debt Expense as previously defined.
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Attachment 3
One-line Diagram Depicting the Small Generating Facility, Interconnection Facilities, Metering Equipment, and Upgrades
(see below)
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Attachment 4
Milestones
In-Service Date: 09/2027
1. Milestones
Critical milestones and responsibility as agreed to by the Parties:
MILESTONE DATE RESPONSIBLE
 PARTY
1. Execute Interconnection Interconnection
 Agreement Completed Customer/Connecting
 Transmission Owner
2. Complete Cost Estimate Update in
accordance with NYISO OATT
 Owner
Completed Connecting Transmission Section 40.6.3.5.3
3. Provide initial prepayment for Completed Interconnection
 engineering and procurement Customer
4. Issue written authorization to
Interconnection
proceed with engineering and Completed
Customer
procurement
5. Project initiation Completed Connecting Transmission
 Owner
6. Project management level kickoff Connecting Transmission
meeting Completed Owner/Interconnection
Customer 7. Provide property rights
documentation (i.e., options,
deeds, easements, etc.) to
 Customer
Completed Interconnection Connecting Transmission Owner
for review
8. Start engineering on
Interconnection Customer’s
 Customer
Completed Interconnection Interconnection Facilities
9. Provide final civil plans for
 Collector Station with surveyed
location and height of termination Interconnection
 Completed
structure, grading plan, access Customer
roads, and wetlands delineation
maps (in CAD format)
10. Start engineering on all System
Upgrade Facilities and Connecting Connecting Transmission
 Completed
Transmission Owner’s Owner Interconnection Facilities
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MILESTONE DATE RESPONSIBLE
PARTY 11. Start procurement for
Interconnection Customer’s
 Customer
Completed Interconnection Interconnection Facilities
12. Start procurement for System
Upgrade Facilities and Connecting Connecting Transmission
 Completed
Transmission Owner’s Owner Interconnection Facilities
13. Complete engineering on
Interconnection Customer’s Connecting Transmission
Interconnection Facilities Completed Owner/Interconnection
(including Connecting Customer
Transmission Owner approvals)
14. Complete procurement for
 Interconnection
Interconnection Customer’s 09/2026
 Customer
Interconnection Facilities
15. Start construction of
 Interconnection Customer’s
Interconnection Facilities 09/2026 Interconnection
(including but not limited to site Customer
civil preparation and foundation
work)
16. Provide prepayment/security for Completed Interconnection
 construction Customer
17. Complete Cost Estimate Update in
accordance with NYISO OATT
 Owner
10/2026 Connecting Transmission Section 40.6.3.5.3
18. Post additional security required in
accordance with NYISO OATT
 Customer
11/2026 Interconnection Section 40.6.3.5.3
19. Provide written authorization to
 proceed with construction of
 System Upgrade Facilities
(“SUF”) and Connecting
 Customer
12/2026 Interconnection Transmission Owner’s Interconnection Facilities
(“CTOIF”)
20. Complete engineering on SUF and Connecting Transmission
 CTOIF 02/2027
Owner
21. Deliver property rights to CTO for 02/2027 Interconnection
 SUF and CTOIF Customer
22. Start construction of SUF and 02/2027 Connecting Transmission
 CTOIF Owner
23. Complete procurement for SUF 07/2027 Connecting Transmission
 and CTOIF Owner
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MILESTONE DATE RESPONSIBLE
PARTY 24. Complete construction of
Interconnection Customer’s Interconnection Facilities
including all telecom circuits
 Customer
07/2027 Interconnection installation and provisioning, as well as all make ready work for revenue metering and RTU
25. Start construction of the Line 15 Connecting Transmission
 Tap (CTOIF) 07/2027
Owner 26. Provide Connecting Transmission
Owner the NYISO assigned PTID number and associated project
06/2027 Interconnection
name (must be provided at least 2 Customer
months in advance of
synchronization)
27. Complete construction and testing 08/2027 Connecting Transmission
 of SUF and CTOIF Owner
28. Field verification and witness
 Connecting Transmission
 testing of Interconnection
 08/2027 Owner/Interconnection
 Customer’s Interconnection
 Customer
Facilities
29. Initial Synchronization Date Interconnection
 08/2027 Customer/Connecting
Transmission Owner 30. Complete testing and Interconnection
 commissioning 09/2027
Customer
31. In-Service Date Interconnection
09/2027
Customer
32. Commercial Operations Date Interconnection
09/2027
Customer
33. Submit Interconnection
 Interconnection
Customer’s Interconnection 11/2027
 Customer
Facilities as builts
34. Complete as builts for SUF and Connecting Transmission
 CTOIF 02/2028
Owner
35. Complete review/acceptance of
 Connecting Transmission
Interconnection Customer’s 02/2028
 Owner
Interconnection Facilities as builts
36. Complete project closeout and Connecting Transmission
 final invoicing 04/2028
Owner
 These milestones are contingent upon, but not limited to, outage scheduling, and the
Interconnection Customer’s successful compliance with all interconnection requirements and
timely completion of its obligations in Appendix C to the Facilities Study for the Small
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Generating Facility. Due to the impact of the COVID-19 pandemic on equipment lead times, the ability to deliver the Small Generating Facility in accordance with these milestones may be at
risk.
2. Security
Security Arrangement
 As agreed upon by Connecting Transmission Owner and Interconnection Customer
pursuant to Article 6.1.1 of this Agreement, the Interconnection Customer shall, at the
Interconnection Customer’s discretion, either (i) make prepayments (in lieu of posting the
security contemplated by Article 6.3 of this Agreement), or (ii) provide security installments to
Connecting Transmission Owner in the form contemplated by Article 6.3 of this Agreement, in
each case for its estimated costs to design, engineer, procure, construct, and install Connecting
Transmission Owner’s Interconnection Facilities and Upgrades. Interconnection Customer shall
make such prepayment or security installments in accordance with the following schedule:
• $1,892,700 such prepayment amount or security amount to be provided at least
 twenty (20) Business Days prior to Interconnection Customer’s issuance of the
 written authorization to proceed with engineering and procurement. Such amount to
 be provided as contemplated by Milestones 2 and 3 in the table contained in Section 1
 of this Attachment 4; and
• $2,066,000 such prepayment or security amount to be provided at least twenty (20)
 Business Days prior to Interconnection Customer’s issuance of the written
 authorization to proceed with construction. Such amount to be provided as
 contemplated by Milestones 14 and 16 in the table contained in Section 1 of this
 Attachment 4; and
 The actual amount of the prepayment or security to be provided by Interconnection
Customer may be adjusted by Connecting Transmission Owner following completion of
engineering for Connecting Transmission Owner’s Interconnection Facilities and System
Upgrade Facilities; Connecting Transmission Owner shall provide written notice to
Interconnection Customer of the adjusted prepayment or security amount, together with
reasonable supporting documentation of the related cost estimates.
 If at any time after Interconnection Customer has made a prepayment of amounts due in
accordance with this Section 2 of Attachment 4, Interconnection Customer provides Connecting
Transmission Owner with security satisfying the requirements of Article 6.3 in an amount at
least equal to the amount required to be provided as of such date by this Section 2, Connecting
Transmission Owner will refund to Interconnection Customer any prepayment or portion thereof
that Interconnection Customer has made prior to the date such alternate security is provided and
that has not been applied against Interconnection Customer’s payment obligations as of such
date.
 The Connecting Transmission Owner shall not be obligated to commence engineering,
procurement, or construction, as applicable, unless the Connecting Transmission Owner has
received the corresponding prepayment or security installment as contemplated above.
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 As agreed to by Interconnection Customer and Connecting Transmission Owner, the
Connecting Transmission Owner shall issue Interconnection Customer an invoice on a monthly
basis detailing Interconnection Customer’s cost responsibility under this Agreement and
providing the net amount, if any, due to Connecting Transmission Owner after Connecting
Transmission Owner has applied any prepayment amounts towards settlement of the invoice.
For the avoidance of doubt, Connecting Transmission Owner shall apply the full amount of any
prepayment amount held by Connecting Transmission Owner against Interconnection
Customer’s cost responsibility under this Agreement before Interconnection Customer is
required to pay any amount in excess of such prepayment amount. If any amount is due from
Interconnection Customer, it shall make such payments pursuant to Article 6.1.1 of this
Agreement. The amount of any security provided by Interconnection Customer under this
Section 2 shall be reduced for payments made by Interconnection Customer as provided in
Article 6.3 of this Agreement.
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Attachment 5
Additional Operating Requirements for the New York State Transmission System, the
 Distribution System and Affected Systems Needed to Support the Interconnection
 Customer’s Needs
 The NYISO, in consultation with the Connecting Transmission Owner, shall also provide
requirements that must be met by the Interconnection Customer prior to initiating parallel
operation with the New York State Transmission System or the Distribution System.
 a. Interconnection Customer must comply with all applicable NYISO tariffs
and Procedures, as amended from time to time.
 b. To the extent not inconsistent with the terms of this Agreement, the ISO
OATT, or applicable NYISO procedures, Interconnection Customer must comply with
Connecting Transmission Owner’s operating instructions and requirements, which
requirements shall include the dedicated data circuits, including system protection
circuits, to be maintained by Interconnection Customer in accordance with Article 1.5 of
this Agreement. Interconnection Customer must also comply with the applicable
requirements as set out in the Connecting Transmission Owner’s ESBs, which have been
identified and provided to the Interconnection Customer as amended from time to time, to
the extent not inconsistent with the terms of this Agreement or applicable NYISO tariffs
and procedures. Upon the Connecting Transmission Owner’s notice to the
Interconnection Customer of amendments to the ESBs, the Interconnection Customer has
30 days to comply with such amendments.
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Attachment 6
Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of
 Upgrade Costs
 The NYISO, in consultation with the Connecting Transmission Owner, shall describe
Upgrades and provide an itemized best estimate of the cost, including overheads, of the
Upgrades and annual operation and maintenance expenses associated with such Upgrades. The
Connecting Transmission Owner shall functionalize Upgrade costs and annual expenses as either
transmission or distribution related.
 The cost estimate for System Upgrade Facilities and System Deliverability Upgrades
shall be taken from the ISO OATT Attachment S cost allocation process or applicable
Interconnection Study, as required by Section 32.3.5.3.2 of Attachment Z. The cost estimate for
Distribution Upgrades shall include the costs of Distribution Upgrades that are reasonably
allocable to the Interconnection Customer at the time the estimate is made, and the costs of any
Distribution Upgrades not yet constructed that were assumed in the Interconnection Studies for
the Interconnection Customer but are, at the time of the estimate, an obligation of an entity other
than the Interconnection Customer.
 The cost estimates for Distribution Upgrades, System Upgrade Facilities, and System
Deliverability Upgrades are estimates. The Interconnection Customer is ultimately responsible
for the actual cost of the Distribution Upgrades, System Upgrade Facilities, and System
Deliverability Upgrades needed for its Small Generating Facility, as that is determined under
Attachments S, X, and Z of the ISO OATT.
A. DISTRIBUTION UPGRADES
None.
B. SYSTEM UPGRADE FACILITIES (“SUF”)
 The interconnection of the Small Generating Facility to the North Troy-Hoosick Line 5
will require System Upgrades at the North Troy and Hoosick Substations.
1. North Troy Substation
a) Protection
 The existing Line 5 relays will be reused and reset for the addition of the Small
Generating Facility. The “A” package uses an ERLPhase LPRO 4000 and will be converted to a
permissive overreaching transfer tip scheme (“POTT”) with the addition of a RFL GardPro
communications package. The “B” package will remain step distance using an SEL-311C.
Breaker failure and protection will be incorporated in the line relays. DTT transmit and receive
will be added between the Hawthorn Solar Collector Station and the North Troy and Hoosick
substations. The GardPro installed for POTT to Hoosick will also be used for DTT to/from
Hoosick Substation and an additional RFL GARDPro will be added for the DTT to/from the
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Hawthorn Solar Collector Substation. The existing reclosing relay is an SEL-351 and will need
to be rewired to add DTL for DTT receive.
b) Controls and Integration
 The existing RTU is sufficient for the scope of this project. Spare I/O points will be used
to accommodate the additions required.
c) Telecommunications
 Two (2) new DS1 circuits will be provisioned by the CTO on its private network for the
protection schemes between the Hawthorn Collector Station and North Troy Substation and
Hoosick Station and North Troy Substation . North Troy Substation is currently connected to the
private network. The new circuits will require the installation of one (1) new SEL ICON in the
existing telecom rack at North Troy Station.
2. Hoosick Substation
a) Protection
 The existing Line 5 relays will be reused and reset for the addition of the Small
Generating Facility. The “A” package uses an ABB RED670 relay which will be converted to a
POTT scheme and the “B” package will remain step distance using an GE D60 relay. DTT
transmit and receive will be added between the Hawthorn Solar Collector Station and the North
Troy and Hoosick substations. A GARDPro communications package will be installed for
POTT and DTT signals to/from North Troy and an additional RFL GARDPro communications
package will be added for the DTT to/from the Hawthorn Solar Collector Substation. (Note:
Since Hoosick is an IEC61850 station, the new RFL equipment must be IEC61850 compliant.)
Breaker reclosing will be done by the System 1 breaker control which is a GE C60 relay. The
System 2 breaker control will be an ABB REC670 relay. Both System 1 and System 2 breaker
controllers will be used for breaker failure protection. Drive to lockout for DTT will be added to
the GE C60 relay.Both System 1 and System 2 breaker control relays will be used for DTT send
and receive.
b) Controls and Integration
 Since Hoosick Substation is an IEC61850 station, it has an SEL-3355 station controller
interfaced to EMS through a GarrettcomDX940E industrial router. The new relays will be
interfaced to the station controller via the station bus. Spare ports on the relay panel’s ethernet
switch(es) will be used for new relays. Additional ethernet port modules will be added to the
relays or switches to the relay panels, as required. The HMI and station controller will need to
be reprogrammed to interface the new relays to EMS and may require third-party support. (Note:
the cost estimate in this Agreement is based on the assumption that no third party support is
required. If it is determined to be required during final engineering and/or construction, the
Interconnection Customer shall be responsible for the incremental costs.)
c) Telecommunications
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 New Dark fiber facilities will be installed between the Hawthorn Solar Collector Station
and Hoosick Substation for the teleprotection circuits required for DTT between the stations. To
establish the circuits on the CTO’s private network, Hoosick Substation and Hawthorne
Collector Stations will be added to the CTO’s private network via FirstLight’s existing dark fiber
network between Hoosick Station and the CTO’s Battenkill Station.
 To implement the new circuits the following equipment and facilities will be installed by
the CTO at Hoosick Substation:
• two (2) 4” Schedule 80 conduits from the  dark fiber meet point outside Hoosick
Substation into the control.
• one (1) 19”x84”x12” telecom rectifier rack with dedicated batteries and the following
telecom equipment:
o SEL ICON
o DPS NetGuardian TMON RTU o DCB Loop CB
o DSX pannel
o Telect Fuse panel
o Fiber Distribution Panel (FDP)
o Telecom Rectifier Rack with dedicated batteries
• four (4) each 120VAC/240 volts 20A AC circuits to power the telecom rectifier rack.
The CTO will provision the following private network circuits:
1. One (1) DS1 Teleprotection circuit for DTT from Hoosick Substation to Hawthorn Solar
Collector Station.
2. One (1) DS1 Teleprotection circuit for DTT from Hoosick Substation to North Troy
Substation.
3. Battenkill Substation
 Connection of the Hoosick Station to the CTO’s private telecom network shall be made
via First Light’s existing dark fiber network between Battenkill Substation and Hoosick Station.
This will require the installation of one (1) new SEL ICON in the existing telecom rack at
Battenkill Station.
(Note: Due to the addition of the Small Generating Facility, an area coordination study will be
completed during final engineering and may result in resetting of relays in the area. The cost of
the coordination study is included in the cost estimates provided in this Agreement. If the area
coordination study determines that additional relays in the area must be reset, the costs
associated with resetting the relays will be the responsibility of the Interconnection Customer.)
C. ELECTIVE SYSTEM UPGRADE FACILITIES (“ELECTIVE SUFS”)
None.
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D. COST ESTIMATES RELATED TO DISTRIBUTION UPGRADES AND SYSTEM
 UPGRADE FACILITIES
 The total estimated costs (+30%/-15%) of the work associated with the System Upgrade
Facilities required for the interconnection of the Small Generating Facility (in 2025 dollars) are
presented in the table below.
 Interconnection Customer requested an extension of its Commercial Operation Date
(“COD”) for the Small Generating Facility to June 2027 pursuant to the modification rules in
Section 40.6.3.5 of Attachment HH to the NYISO OATT. The NYISO determined, in
consultation with the Connecting Transmission Owner, that a Cost Estimate Update is required
in order for the requested extension of the Commercial Operation Date not to be a material
modification. Connecting Transmission Owner performed the Cost Estimate Update, and
Interconnection Customer accepted the revised cost estimates included above. The revised cost
estimates update the cost estimate amount for the Small Generating Facility determined in the
Facilities Study.
 The Parties acknowledge that the cost estimate tables set forth in this Agreement were
prepared prior to revisions to the telecommunications scope. Therefore, the above cost estimate
does not include costs associated with Dark Fiber Telecommunications scope described in
Sections B.1(c), B.2(c), and B.3 of this Attachment 6. An additional estimated cost of $2,310,115
applies to such work and is incorporated into this Agreement.
 As described in the Facilities Study for the Small Generating Facility, the estimates
provided herein:
Assume:
• 5 x 10 construction work week; • outages are available;
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• all major material is delivered to site (i.e., no costs are included for transport
from storage);
• existing equipment to remain is functional; and
• mobile generation will be required for approximately seven (7) calendar days.
Exclude (as applicable):
• discussions and negotiations of issued interconnection study; • application fees;
• applicable surcharges;
• overall project sales tax; • property taxes; • line switching;
• property/easement acquisitions;
• access roads and associated matting;
• future operation and maintenance costs;
• recurring monthly communications circuits’ charges, if any, responsible by the
 Interconnection Customer to the communications utility;
• soil testing;
• adverse field conditions such as rock, water, weather, and Interconnection
Customer electrical equipment obstructions; • environmental mitigation;
• extended engineering to minimize outage time or Connecting Transmission
Owner’s public utility to serve;
• extended craft labor hours, to minimize outage and/or construction time, • any required permits, or
• any modifications to the project and/or any variance to the assumptions,
 including the energization date and outage requirements, which may impact this
 cost estimates.
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Attachment 7
Insurance Coverage
 Interconnection Customer shall, at its own expense, maintain in force throughout the
period of this Agreement, the following minimum insurance coverage, with insurers authorized
to do business in the State of New York.
 Commercial General Liability Insurance including, but not limited to, bodily injury,
property damage, products/completed operations, contractual and personal injury liability with a
combined single limit of $2 million per occurrence, $5 million annual aggregate.
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Attachment 8
Initial Synchronization Date
[Date]
New York Independent System Operator, Inc.
Attn: Vice President, Operations
10 Krey Boulevard Rensselaer, NY 12144
Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration and Commercial Services
Address: 2 Hanson Place, 12th Floor City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171
E-mail: Vishal.Ahirrao@nationalgrid.com
Re: Hawthorn Solar Small Generating Facility
Dear :
On [Date] [Interconnection Customer] initially synchronized the Small Generating Facility
[specify units, if applicable]. This letter confirms that [Interconnection Customer]’s Initial
Synchronization Date was [specify].
Thank you.
[Signature]
[Interconnection Customer Representative]
8-1




[bookmark: br74]SERVICE AGREEMENT NO. 2756
Attachment 9
Commercial Operation Date
[Date]
New York Independent System Operator, Inc.
Attn: Vice President, Operations
10 Krey Boulevard Rensselaer, NY 12144
Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration and Commercial Services
Address: 2 Hanson Place, 12th Floor City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171
E-mail: Vishal.Ahirrao@nationalgrid.com
Re: Hawthorn Solar Small Generating Facility
Dear __________________:
On [Date] [Interconnection Customer] has completed Trial Operation of Unit No. ___. This
letter confirms that [Interconnection Customer] commenced Commercial Operation of the
Small Generating Facility [specify units, as applicable], effective as of [Date plus one day].
Thank you.
[Signature]
[Interconnection Customer Representative]
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Interconnection Customer Interconnection Facilities (ICIFs]

Engineering review and compliance verification of the ICIF, including
all required drawings and equipment specifications reviews, relay

settings, construction and testing assistance by engineering, field $152,000
verification, and witness testing

Connecting Transmission Owner Interconnection Facilities (CTO IFs)

Engineering, design, construction, testing and commissioning for:
Revenue Metering & RTU $214,700

Line Tap $2,400,800

CTO IF Subtotal $2,615,500

Subtotal| $2,767,500

Contingency $569,400

IF TOTAL| $3,336,900
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System Upgrade Facilities (SUFs)

Engineering, design, construction, testing and commissioning of:

North Troy Station $430,000
Hoosick Station $209,200
SUF Subtotal $639,200

Subtotal $639,200

Contingency $134,600

SUF TOTAL $773,800
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