SERVICE AGREEMENT NO. 2880

SERVICE AGREEMENT NO. 2880

STANDARD UPGRADE CONSTRUCTION AGREEMENT

AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.,

AND

NIAGARA MOHAWK POWER CORPORATION D/B/A NATIONAL GRID

AND

SITHE/INDPENDENCE POWER PARTNERS, L.P.

Dated as of March 12, 2025

Project Name: Scriba-Volney Series Reactor Project

Queue Position No(s): 899

SERVICE AGREEMENT NO. 2880

TABLE OF CONTENTS

ARTICLE 1. DEFINITIONS.........................................................................................................1

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION .............................................5
 2.1 Effective Date. .........................................................................................................5
 2.2 Term of Agreement..................................................................................................6
 2.3 Termination..............................................................................................................6
 2.4 Termination Costs....................................................................................................6
 2.5 Survival....................................................................................................................7
 2.6 No Annexation.........................................................................................................7

ARTICLE 3. CONSTRUCTION SERVICES...............................................................................8
 3.1 Performance of Construction Services.....................................................................8
 3.2 General Conditions Applicable to Interconnection Customer’s

Performance of the Construction Services...............................................................8

3.3 Design and Equipment Procurement. ......................................................................9

3.4 Construction Commencement..................................................................................9

3.5 Work Progress........................................................................................................10

3.6 Information Exchange............................................................................................10

3.7 Ownership and Control of Upgrades. ....................................................................10

3.8 Access Rights.........................................................................................................10

3.9 Lands of Other Property Owners. ..........................................................................11

3.10 Permits. ..................................................................................................................11

3.11 Suspension. ............................................................................................................11

3.12 Taxes......................................................................................................................12

3.13 Tax Status; Non-Jurisdictional Entities. ................................................................14

3.14 Modification...........................................................................................................14

ARTICLE 4. TESTING AND INSPECTION.............................................................................15
 4.1 Initial Testing and Modifications...........................................................................15
 4.2 Right to Observe Testing. ......................................................................................15

ARTICLE 5. PERFORMANCE OBLIGATIONS ......................................................................15
 5.1 Cost Responsibilities..............................................................................................15
 5.2 Provision and Application of Security...................................................................15

ARTICLE 6. INVOICE ...............................................................................................................16
 6.1 General...................................................................................................................16
 6.2 Final Invoice and Refund of Remaining Security/Overpayment Amount.............16
 6.3 Payment..................................................................................................................16
 6.4 Disputes..................................................................................................................17

ARTICLE 7. REGULATORY REQUIREMENTS AND GOVERNING LAW........................17
 7.1 Regulatory Requirements.......................................................................................17
 7.2 Governing Law. .....................................................................................................17

ARTICLE 8. NOTICES...............................................................................................................17

i

SERVICE AGREEMENT NO. 2880

8.1 General...................................................................................................................17

8.2 Billings and Payments............................................................................................18

8.3 Alternative Forms of Notice. .................................................................................18

ARTICLE 9. FORCE MAJEURE ...............................................................................................18

ARTICLE 10. DEFAULT .............................................................................................................18
 10.1 General...................................................................................................................18
 10.2 Right to Terminate.................................................................................................19

ARTICLE 11. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE ...............19
 11.1 Indemnity...............................................................................................................19
 11.2 No Consequential Damages...................................................................................20
 11.3 Insurance................................................................................................................20

ARTICLE 12. ASSIGNMENT......................................................................................................23
 12.1 Assignment. ...........................................................................................................23

ARTICLE 13. SEVERABILITY...................................................................................................23
ARTICLE 14. COMPARABILITY...............................................................................................23

ARTICLE 15. CONFIDENTIALITY............................................................................................23
 15.1 Confidentiality. ......................................................................................................23
 15.2 Term.......................................................................................................................24
 15.3 Confidential Information. ......................................................................................24
 15.4 Scope......................................................................................................................24
 15.5 Release of Confidential Information......................................................................24
 15.6 Rights.....................................................................................................................25
 15.7 No Warranties. .......................................................................................................25
 15.8 Standard of Care. ...................................................................................................25
 15.9 Order of Disclosure................................................................................................25
 15.10 Termination of Agreement.....................................................................................25
 15.11 Remedies................................................................................................................26
 15.12 Disclosure to FERC, its Staff, or a State................................................................26
 15.13 Required Notices Upon Requests or Demands for Confidential

Information. ...........................................................................................................26

ARTICLE 16. INTERCONNECTION CUSTOMER AND SYSTEM OWNER
 NOTICES OF ENVIRONMENTAL RELEASES ................................................27

ARTICLE 17. INFORMATION REQUIREMENT......................................................................27
 17.1 Information Acquisition.........................................................................................27
 17.2 Information Submission Concerning the Upgrades...............................................27
 17.3 Information Submission Concerning the Transmission Project. ...........................27
 17.4 Information Supplementation. ...............................................................................28

ARTICLE 18. INFORMATION ACCESS AND AUDIT RIGHTS.............................................28

ii

SERVICE AGREEMENT NO. 2880

18.1 Information Access. ...............................................................................................28

18.2 Reporting of Non-Force Majeure Events...............................................................28

18.3 Audit Rights...........................................................................................................28

18.4 Audit Rights Periods..............................................................................................29

18.5 Audit Results..........................................................................................................29

ARTICLE 19. SUBCONTRACTORS ..........................................................................................29
 19.1 General...................................................................................................................29
 19.2 Responsibility of Principal.....................................................................................29
 19.3 No Limitation by Insurance. ..................................................................................29

ARTICLE 20. DISPUTES.............................................................................................................30
 20.1 Submission.............................................................................................................30
 20.2 External Arbitration Procedures. ...........................................................................30
 20.3 Arbitration Decisions.............................................................................................30
 20.4 Costs.......................................................................................................................30
 20.5 Termination............................................................................................................31

ARTICLE 21. REPRESENTATIONS, WARRANTIES AND COVENANTS ...........................31
 21.1 General...................................................................................................................31

ARTICLE 22. MISCELLANEOUS ..............................................................................................32
 22.1 Binding Effect........................................................................................................32
 22.2 Conflicts.................................................................................................................32
 22.3 Rules of Interpretation. ..........................................................................................32
 22.4 Compliance. ...........................................................................................................32
 22.5 Joint and Several Obligations. ...............................................................................33
 22.6 Entire Agreement...................................................................................................33
 22.7 No Third Party Beneficiaries. ................................................................................33
 22.8 Waiver....................................................................................................................33
 22.9 Headings. ...............................................................................................................33
 22.10 Multiple Counterparts............................................................................................33
 22.11 Amendment............................................................................................................34
 22.12 Modification by the Parties....................................................................................34
 22.13 Reservation of Rights.............................................................................................34
 22.14 No Partnership. ......................................................................................................34
 22.15 Other Transmission Rights. ...................................................................................34
 22.16 Modifications Related to NYISO’s Compliance with Order No. 2023.................34

iii

SERVICE AGREEMENT NO. 2880

STANDARD UPGRADE CONSTRUCTION AGREEMENT

THIS STANDARD UPGRADE CONSTRUCTION AGREEMENT (“Agreement”) is made
and entered into this 12th day of March 2025, by and among: Sithe/Independence Power
Partners, L.P., a limited partnership organized and existing under the laws of State of Delaware
(“Interconnection Customer”), Niagara Mohawk Power Corporation d/b/a National Grid, a
corporation organized and existing under the laws of State of New York (“System Owner”), and
the New York Independent System Operator, Inc., a not-for-profit corporation organized and
existing under the laws of the State of New York (“NYISO”). Interconnection Customer, the
NYISO, or System Owner each may be referred to as a “Party” or collectively referred to as the
“Parties.”

RECITALS

WHEREAS, Interconnection Customer wishes to develop a Transmission Project that will
interconnect to the New York State Transmission System in order to relieve local thermal
overloads under operating conditions identified on System Owner’s system;

WHEREAS, the Transmission Project was evaluated in the NYISO’s Transmission Interconnection Procedures located in Attachment P of the ISO OATT;

WHEREAS, the NYISO determined that certain Network Upgrade Facilities were required on
the System Owner’s system for the Transmission Project to connect reliably to the system in a
manner that meets the NYISO Transmission Interconnection Standard;

WHEREAS, the NYISO has determined the cost estimate for the engineering, procurement, and
construction of the Network Upgrade Facilities (together with Transmission Project costs, the
“Upgrades Estimated Total Cost Amount”);

WHEREAS, Interconnection Customer and System Owner desire to have System Owner
perform, and System Owner is willing to perform, the engineering, procurement, and
construction services (“Construction Services”) required to construct and place in service the
Transmission Project and Upgrades (collectively, the “Upgrades”) in accordance with the terms
and conditions hereinafter set forth; and

WHEREAS, Interconnection Customer, System Owner, and the NYISO have agreed to enter
into this Agreement for the purpose of allocating the responsibilities for the performance and
oversight of the Construction Services required to construct the Upgrades;

NOW, THEREFORE, in consideration of and subject to the mutual covenants contained herein, it is agreed:

ARTICLE 1. DEFINITIONS

Whenever used in this Agreement with initial capitalization, the following terms shall have the
meanings specified in this Article 1. Terms used in this Agreement with initial capitalization that
are not defined in this Article 1 shall have the meanings specified in Section 1 of the OATT,

1

SERVICE AGREEMENT NO. 2880

Section 22.1 of Attachment P of the ISO OATT, the body of the Transmission Interconnection
Procedures, or the body of this Agreement.

Affiliate shall mean, with respect to a person or entity, any individual, corporation, partnership,
firm, joint venture, association, joint-stock company, trust or unincorporated organization,
directly or indirectly controlling, controlled by, or under common control with, such person or
entity. The term “control” shall mean the possession, directly or indirectly, of the power to
direct the management or policies of a person or an entity. A voting interest of ten percent or
more shall create a rebuttable presumption of control.

Applicable Laws and Regulations shall mean all duly promulgated applicable federal, state and
local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or
administrative orders, permits and other duly authorized actions of any Governmental Authority,
including but not limited to Environmental Law.

Applicable Reliability Councils shall mean the Electric Reliability Organization, the NPCC and the NYSRC.

Applicable Reliability Requirements shall mean the NYSRC Reliability Rules, and other
criteria, standards and procedures, as described in Section 40.12.1.2 of this Attachment HH,
applied when conducting the Cluster Baseline Assessment and the Cluster Project Assessment;
provided that no Party shall waive its right to challenge the applicability or validity of any
requirement or guideline as applied to it in the context of the Standard Interconnection
Procedures. The Applicable Reliability Requirements applied are those in effect when the
particular assessment is commenced.

Applicable Reliability Standards shall mean the requirements and guidelines of the Applicable
Reliability Councils, and the Transmission District to which the Interconnection Customer’s
Transmission Project is directly interconnected, as those requirements and guidelines are
amended and modified and in effect from time to time; provided that no Party shall waive its
right to challenge the applicability or validity of any requirement or guideline as applied to it in
the context of this Agreement.

Breach shall mean the failure of a Party to perform or observe any material term or condition of this Agreement.

Breaching Party shall mean a Party that is in Breach of this Agreement.

Business Day shall mean Monday through Friday, excluding federal holidays.

Calendar Day shall mean any day including Saturday, Sunday or a federal holiday.

Completion Date shall mean the date on which, as applicable, the System Owner or Interconnection Customer has completed the Construction Services, as set forth in Appendix A.

Confidential Information shall mean any information that is defined as confidential by Article 15 of this Agreement.

2

SERVICE AGREEMENT NO. 2880

Construction Services shall have the meaning set forth in the recitals and shall consist of the services described in Appendix A.

Default shall mean the failure of a Party in Breach of this Agreement to cure such Breach in accordance with Article 10 of this Agreement.

Distribution System shall mean the Connecting Transmission Owner’s facilities and equipment
used to distribute electricity that are subject to FERC jurisdiction, and are subject to the
NYISO’s Standard Interconnection Procedures in Attachment HH under FERC Order Nos. 2003
and/or 2006. The term Distribution System shall not include LIPA’s distribution facilities.

Effective Date shall mean the date on which this Agreement becomes effective in accordance with Article 2.1 of this Agreement.

Electric Reliability Organization (“ERO”) shall mean the North American Electric Reliability Corporation or its successor organization.

Environmental Law shall mean Applicable Laws and Regulations relating to pollution or protection of the environment or natural resources.

Facilities Study shall mean the study conducted pursuant to Section 22.9 of Attachment P to the
ISO OATT to determine a list of facilities required to reliably interconnect the Transmission
Project (including Network Upgrade Facilities) as identified in the System Impact Study, the cost
of those facilities and the time required to interconnect the Transmission Project with the New
York State Transmission System.

Federal Power Act shall mean the Federal Power Act, as amended, 16 U.S.C. §§ 791a et seq. (“FPA”).

FERC shall mean the Federal Energy Regulatory Commission (“Commission”) or its successor.

Force Majeure shall mean any act of God, labor disturbance, act of the public enemy, war,
insurrection, riot, fire, storm or flood, explosion, breakage or accident to machinery or
equipment, any order, regulation or restriction imposed by governmental, military or lawfully
established civilian authorities, or any other cause beyond a Party’s control. A Force Majeure
event does not include acts of negligence or intentional wrongdoing by the Party claiming Force
Majeure.

Good Utility Practice shall mean any of the practices, methods and acts engaged in or approved
by a significant portion of the electric industry during the relevant time period, or any of the
practices, methods and acts which, in the exercise of reasonable judgment in light of the facts
known at the time the decision was made, could have been expected to accomplish the desired
result at a reasonable cost consistent with good business practices, reliability, safety and
expedition. Good Utility Practice is not intended to be limited to the optimum practice, method,
or act to the exclusion of all others, but rather to delineate acceptable practices, methods, or acts
generally accepted in the region.

3

SERVICE AGREEMENT NO. 2880

Governmental Authority shall mean any federal, state, local or other governmental regulatory
or administrative agency, court, commission, department, board, or other governmental
subdivision, legislature, rulemaking board, tribunal, or other governmental authority having
jurisdiction over any of the Parties, their respective facilities, or the respective services they
provide, and exercising or entitled to exercise any administrative, executive, police, or taxing
authority or power; provided, however, that such term does not include Interconnection
Customer, the NYISO, Affected Transmission Owner, Affected System Operator, Connecting
Transmission Owner, or any Affiliate thereof.

Hazardous Substances shall mean any chemicals, materials or substances defined as or
included in the definition of “hazardous substances,” “hazardous wastes,” “hazardous materials,”
“hazardous constituents,” “restricted hazardous materials,” “extremely hazardous substances,”
“toxic substances,” “radioactive substances,” “contaminants,” “pollutants,” “toxic pollutants” or
words of similar meaning and regulatory effect under any applicable Environmental Law, or any
other chemical, material or substance, exposure to which is prohibited, limited or regulated by
any applicable Environmental Law.

In-Service Date shall mean the date upon which the Upgrades are energized consistent with the
provisions of this Agreement, notice of which must be provided to the other Parties by, as
applicable, the Interconnection Customer or System Owner in the form of Appendix C.

Interconnection Customer shall mean the Transmission Developer for the Transmission Project
as defined in Attachment P to the ISO OATT. For purposes of this Agreement, the
Interconnection Customer shall have the meaning set forth in the introductory paragraph.

IRS shall mean the Internal Revenue Service.

ISO Services Tariff shall mean the NYISO’s Market Administration and Control Area Services
Tariff, as filed with the Commission, and as amended or supplemented from time to time, or any
successor tariff thereto.

ISO OATT shall mean the NYISO’s Open Access Transmission Tariff, as filed with the Commission, and as amended or supplemented from time to time, or any successor tariff.

Milestones shall mean the milestones for the performance of the Construction Services, as set forth in Appendix A.

Network Upgrade Facilities shall mean the least costly configuration of commercially available
components of electric equipment that can be used, consistent with good utility practice and
Applicable Reliability Requirements, to make the modifications or additions to the New York
State Transmission System that are required for the proposed Transmission Project to connect
reliably to the system in a manner that meets the NYISO Transmission Interconnection Standard.

New York State Transmission System shall mean the entire New York State electric
transmission system, which includes (i) the Transmission Facilities under NYISO Operational
Control; (ii) the Transmission Facilities Requiring ISO Notification; and (iii) all remaining
transmission facilities within the New York Control Area.

4

SERVICE AGREEMENT NO. 2880

Notice of Dispute shall mean a written notice of a dispute or claim pursuant to Article 20 of this Agreement that arises out of or in connection with this Agreement or its performance.

NPCC shall mean the Northeast Power Coordinating Council or its successor organization.

NYISO Tariffs shall mean the ISO OATT and ISO Services Tariff.

NYSRC shall mean the New York State Reliability Council or its successor organization.

Party or Parties shall have the meaning set forth in the introductory paragraph.

Reasonable Efforts shall mean, with respect to an action required to be attempted or taken by a
Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and
are otherwise substantially equivalent to those a Party would use to protect its own interests.

Standard Upgrade Construction Agreement shall mean this Agreement.

System Owner shall mean, as applicable, the Affected System Operator, Affected Transmission
Owner, or Connecting Transmission Owner. For purposes of this Agreement, the System Owner
shall be defined in the introductory paragraph.

Transmission Interconnection Application shall mean Transmission Developer’s request, in
the form of Appendix 1 to the Transmission Interconnection Procedures, to interconnect a
Transmission Project to the New York State Transmission System.

Transmission Interconnection Procedures (“TIP”) shall mean the interconnection procedures
applicable to a Transmission Interconnection Application pertaining to a Transmission Project
that are included in Attachment P to the ISO OATT.

Transmission Interconnection Studies shall mean any of the following studies: the Optional
Feasibility Study, the System Impact Study, and the Facilities Study described in the
Transmission Interconnection Procedures.

Transmission Project shall be the Transmission Developer’s proposed transmission facility or
facilities that collectively satisfy the definition of Transmission Project in Section 22.3.1 of
Attachment P of the NYISO OATT.

Upgrades shall have the meaning set forth in the recitals and shall be described in Appendix A.

Upgrades Estimated Total Cost Amount shall have the meaning set forth in the recitals, which costs are specified in Appendix A.

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION

2.1 Effective Date.

This Agreement shall become effective upon the date of execution by the Parties, subject
to acceptance by FERC, or if filed unexecuted, upon the date specified by FERC. The NYISO,
and if applicable, the System Owner, shall promptly file this Agreement with FERC upon

5

SERVICE AGREEMENT NO. 2880

execution, if required, in accordance with the requirements in the OATT. Interconnection
Customer and System Owner shall reasonably cooperate with the NYISO with respect to the
filing of this Agreement with FERC and provide any information reasonably requested by the
NYISO needed for such filing.

2.2 Term of Agreement.

Subject to the provisions of Article 2.3, this Agreement shall remain in effect until the
later of: (i) the Completion Date, and (ii) the date on which the final payment of all invoices
issued under this Agreement have been made pursuant to Articles 6.1 and 6.3 and any remaining
Security has been released or refunded pursuant to Article 6.2.

2.3 Termination.

2.3.1 Completion of Term of Agreement.

This Agreement shall terminate upon the completion of the term of the Agreement
pursuant to Article 2.2.

2.3.2 Written Notice.

This Agreement may be terminated by the mutual agreement in writing of all of the
Parties.

2.3.3 Default.

Any Party may terminate this Agreement to the extent permitted under Article 10 and
Article 20.

2.3.4 Compliance.

Notwithstanding Articles 2.3.1, 2.3.2, and 2.3.3, no termination of this Agreement shall
become effective until the Parties have complied with all Applicable Laws and Regulations
applicable to such termination, including the filing with FERC of a notice of termination of this
Agreement, which notice has been accepted for filing by FERC.

2.4 Termination Costs.

If this Agreement is terminated pursuant to Articles 2.3.2 or 2.3.3 above, the
Interconnection Customer shall be responsible for all costs that are the responsibility of the
Interconnection Customer under this Agreement that are incurred by the Interconnection
Customer or other Parties through the date the Parties agree in writing to terminate the
agreement. Such costs include any cancellation costs relating to orders or contracts concerning
the Construction Services or Upgrades. In the event of termination, all Parties shall use
commercially Reasonable Efforts to mitigate the costs, damages and charges arising as a
consequence of termination. Upon termination of this Agreement, unless otherwise ordered or
approved by FERC:

6

SERVICE AGREEMENT NO. 2880

2.4.1 With respect to any portion of the Upgrades for which the System Owner or
Interconnection Customer (the “Constructing Party”) are responsible for constructing or
installing under this Agreement and that have not yet been constructed or installed, the
Constructing Party shall, to the extent possible and with the other Party’s (i.e., the System Owner
or Interconnection Customer, as applicable) authorization, cancel any pending orders of, or
return, any materials or equipment for, or contracts for construction of, the Upgrades; provided
that in the event the other Party elects not to authorize such cancellation, the other Party shall
assume all payment obligations with respect to such materials, equipment, and contracts, and the
Constructing Party shall deliver such material and equipment, and, if necessary, assign such
contracts, to the other Party as soon as practicable, at the other Party’s expense. To the extent
that the other Party has already paid the Constructing Party for any or all such costs of materials
or equipment not taken by the other Party, the Constructing Party shall promptly refund such
amounts to the other Party, less any costs, including penalties incurred by the Constructing Party
to cancel any pending orders of or return such materials, equipment, or contracts.

2.4.2 The Constructing Party may, at its option, retain any portion of such materials
or equipment that the other Party chooses not to accept delivery of, in which case the
Constructing Party shall be responsible for all costs associated with procuring such materials or
equipment.

2.4.3 With respect to any portion of the Construction Services already performed
pursuant to the terms of this Agreement, Interconnection Customer shall be responsible for all
costs associated with the removal, relocation or other disposition or retirement of such related
materials, equipment, or facilities and such other expense actually incurred by System Owner to
return its system to safe and reliable operation.

2.5 Survival.

This Agreement shall continue in effect after termination to the extent necessary to
provide for final billings and payments and for costs incurred hereunder; including billings and
payments pursuant to this Agreement; to permit the determination and enforcement of liability
and indemnification obligations arising from acts or events that occurred while this Agreement
was in effect; and to permit Interconnection Customer and System Owner each to have access to
the lands of the other pursuant to this Agreement or other applicable agreements, to disconnect,
remove or salvage its own facilities and equipment.

2.6 No Annexation.

Any and all equipment placed on the premises of a Party shall be and remain the property
of the Party providing such equipment regardless of the mode and manner of annexation or
attachment to real property, unless otherwise mutually agreed by the Party providing such
equipment and the Party receiving such equipment.

7

SERVICE AGREEMENT NO. 2880

ARTICLE 3. CONSTRUCTION SERVICES

3.1 Performance of Construction Services.

System Owner shall be responsible for performing the Construction Services. At System
Owner’s sole discretion, System Owner may agree with Interconnection Customer for
Interconnection Customer to perform such services. System Owner’s and Interconnection
Customer’s respective obligations concerning the Construction Services shall be set forth in
Appendix A hereto. System Owner and Interconnection Customer shall each use Reasonable
Efforts to complete the Construction Services for which it has responsibility by the Milestone
dates set forth in Appendix A hereto. The System Owner shall not be required to undertake any
action which is inconsistent with the System Owner’s standard safety practices, its material and
equipment specifications, its design criteria and construction procedures, its labor agreements,
and Applicable Laws and Regulations. The NYISO has no responsibility, and shall have no
liability, for the performance of any of the Construction Services under this Agreement.

3.2 General Conditions Applicable to Interconnection Customer’s Performance of the

Construction Services.

If System Owner and Interconnection Customer agree pursuant to Section 3.1 for
Interconnection Customer to be responsible for the design, procurement, and/or construction of
any Upgrades as set forth in Appendix A, the following conditions apply:

3.2.1 Interconnection Customer shall engineer, procure equipment, and construct
the Upgrades (or portions thereof) using Good Utility Practice and using standards and
specifications provided in advance by System Owner;

3.2.2 Interconnection Customer’s engineering, procurement and construction of the
Upgrades shall comply with all requirements of law to which System Owner would be subject in
the engineering, procurement or construction of the Upgrades;

3.2.3 System Owner shall review and approve the engineering design, equipment acceptance tests, and the construction of the Upgrades;

3.2.4 Prior to the commencement of construction, Interconnection Customer shall
provide System Owner and NYISO a schedule for construction of the Upgrades, and shall
promptly respond to requests for information from System Owner or NYISO;

3.2.5 At any time during construction, System Owner shall have the right to gain unrestricted access to the Upgrades and to conduct inspections of the same;

3.2.6 At any time during construction, should any phase of the engineering,
equipment procurement, or construction of the Upgrades not meet the standards and
specifications provided by System Owner, Interconnection Customer shall be obligated to
remedy deficiencies in that portion of the Upgrades;

8

SERVICE AGREEMENT NO. 2880

3.2.7 Interconnection Customer shall indemnify System Owner and NYISO for
claims arising from Interconnection Customer’s construction of Upgrades under procedures
applicable to Article 11.1 Indemnity;

3.2.8 Interconnection Customer shall transfer control of Upgrades to System Owner;

3.2.9 Unless Interconnection Customer and System Owner otherwise agree, Interconnection Customer shall transfer ownership of Upgrades to System Owner;

3.2.10 System Owner shall approve and accept for operation and maintenance the Upgrades to the extent engineered, procured, and constructed in accordance with this Article 3.2;

3.2.11 Interconnection Customer shall deliver to NYISO and System Owner “as
built” drawings, information, and any other documents that are reasonably required by NYISO or
System Owner to assure that the Upgrades are built to the standards and specifications required
by System Owner; and

3.2.12 Interconnection Customer shall pay the System Owner the agreed upon
amount of [$ PLACEHOLDER] for the System Owner to execute the responsibilities
enumerated to System Owner under Article 3.2. System Owner shall invoice Interconnection
Customer for this total amount to be divided on a monthly basis pursuant to Article 6.

3.3 Design and Equipment Procurement.

If responsibility for construction of the Upgrades is to be borne by the System Owner,
then the System Owner shall commence the design and procurement of the Upgrades for which it
is responsible as soon as practicable after all of the following conditions are satisfied, unless the
Interconnection Customer and System Owner otherwise agree in writing:

3.3.1 NYISO has completed the Facilities Study for the Transmission Project;

3.3.2 The NYISO has completed the required cost allocation analyses, and
Interconnection Customer has accepted its Project Cost Allocation for the Upgrades in
accordance with the provisions of Attachment P of the ISO OATT.

3.3.3 System Owner has received written authorization to proceed with design and
procurement of the Upgrades from the Interconnection Customer by the date specified in
Appendix A hereto; and

3.3.4 Interconnection Customer has provided Security to the System Owner for the
design and procurement of the Upgrades in accordance with Article 5 by the date(s) specified in
Appendix A hereto.

3.4 Construction Commencement.

System Owner shall commence construction of the Upgrades for which it is responsible
as soon as practicable after the following additional conditions are satisfied.

9

SERVICE AGREEMENT NO. 2880

3.4.1 Approval of the appropriate Governmental Authority has been obtained for any facilities requiring regulatory approval;

3.4.2 Necessary real property rights and rights-of-way have been obtained, to the extent required, for the construction of a discrete aspect of the Upgrades;

3.4.3 System Owner has received written authorization to proceed with construction from the Interconnection Customer by the date specified in Appendix A hereto; and

3.4.4 Interconnection Customer has provided security to the System Owner for the
construction of the applicable facilities in accordance with Article 5.2 by the date(s) specified in
Appendix A hereto.

3.5 Work Progress.

The Interconnection Customer and System Operator will keep each other, and NYISO,
advised periodically as to the progress of its respective design, procurement and construction
efforts. Any Party may, at any time, request a progress report from the Interconnection
Customer or System Owner.

3.6 Information Exchange.

As soon as reasonably practicable after the Effective Date, Interconnection Customer and
System Owner shall exchange information, and provide NYISO the same information, regarding
the design of the Upgrades and compatibility of the Upgrades with the New York State
Transmission System and shall work diligently and in good faith to make any necessary design
changes.

3.7 Ownership and Control of Upgrades.

System Owner shall own the Upgrades as described in Appendix A. The System
Owner’s and, if applicable, NYISO’s operational control of the Upgrades upon the completion of
the facilities shall be described in Appendix A.

3.8 Access Rights.

Upon reasonable notice and supervision by the Granting Party, and subject to any
required or necessary regulatory approvals, either the System Owner or Interconnection
Customer (“Granting Party”) shall furnish to the other of those two Parties (“Access Party”) at
no cost any rights of use, licenses, rights of way and easements with respect to lands owned or
controlled by the Granting Party, its agents (if allowed under the applicable agency agreement),
or any Affiliate, that are necessary to enable the Access Party to obtain the ingress and egress
required for the performance of the Construction Services, including to construct, repair, test (or
witness testing), inspect, replace or remove the Upgrades. In exercising such licenses, rights of
way and easements, the Access Party shall not unreasonably disrupt or interfere with normal
operation of the Granting Party’s business and shall adhere to the safety rules and procedures
established in advance, as may be changed from time to time, by the Granting Party and provided
to the Access Party. The Access Party shall indemnify the Granting Party against all claims of

10

SERVICE AGREEMENT NO. 2880

injury or damage from third parties resulting from the exercise of the access rights provided for
herein.

3.9 Lands of Other Property Owners.

If any part of the Upgrades will be installed on property owned by persons other than the
Interconnection Customer or System Owner, the System Owner shall at Interconnection
Customer’s expense use efforts, similar in nature and extent to those that it typically undertakes
for its own or affiliated generation, including use of its eminent domain authority, and to the
extent consistent with state law, to procure from such persons any rights of use, licenses, rights
of way and easements that are necessary for the performance of the Construction Services upon
such property by the System Owner or Interconnection Customer, including to construct, repair,
operate, maintain, test (or witness testing), inspect, replace or remove the Upgrades.

3.10 Permits.

NYISO, Interconnection Customer, and System Owner shall cooperate with each other in
good faith in obtaining all permits, licenses and authorizations that are necessary to accomplish
the Construction Services in compliance with Applicable Laws and Regulations. With respect to
this paragraph, System Owner shall provide permitting assistance to the Interconnection
Customer comparable to that provided to System Owner’s own, or an Affiliate’s generation
facilities, if any.

3.11 Suspension.

Interconnection Customer reserves the right, upon written notice to System Owner and
NYISO, to suspend at any time all work by System Owner or Interconnection Customer, as
applicable, associated with the construction and installation of the Upgrades required for only
that Interconnection Customer’s Transmission Project, with the condition that the New York
State Transmission System shall be left in a safe and reliable condition in accordance with Good
Utility Practice and the safety and reliability criteria of System Owner and NYISO. In such
event, such Interconnection Customer shall be responsible for all reasonable and necessary costs
and/or obligations in accordance with Attachment P to the ISO OATT including those which
System Owner (i) has incurred pursuant to this Agreement prior to the suspension and (ii) incurs
as a result of the suspension of such work, including any costs incurred by System Owner to
perform such work as may be necessary to ensure the safety of persons and property and the
integrity of the New York State Transmission System during such suspension and, if applicable,
any costs incurred by System Owner in connection with the cancellation or suspension of
material, equipment and labor contracts which System Owner cannot reasonably avoid;
provided, however, that prior to canceling or suspending any such material, equipment or labor
contract, System Owner shall obtain such Interconnection Customer’s authorization to do so.

System Owner shall invoice Interconnection Customer for such costs pursuant to
Article 6 and shall use due diligence to minimize its costs. If Interconnection Customer suspends
work required under this Agreement pursuant to this Article 3.11, and has, as applicable, either
not recommenced work or requested System Owner to recommence its work required under this
Agreement on or before the expiration of three (3) years following commencement of such

11

SERVICE AGREEMENT NO. 2880

suspension, this Agreement shall be deemed terminated. The three-year period shall begin on the
date the suspension is requested, or the date of the written notice to System Owner and NYISO,
if no effective date is specified.

3.12 Taxes.

3.12.1 Indemnification for Contributions in Aid of Construction.

With regard only to payments made by Interconnection Customer to System Owner for
the installation of the Upgrades, System Owner shall not include a gross-up for income taxes in
the amounts it charges Interconnection Customer for the installation of the Upgrades unless
(1) System Owner has determined, in good faith, that the payments or property transfers made by
Interconnection Customer to System Owner should be reported as income subject to taxation, or
(2) any Governmental Authority directs System Owner to report payments or property as income
subject to taxation. Interconnection Customer shall reimburse System Owner for such costs on a
fully grossed-up basis, in accordance with this Article, within thirty (30) Calendar Days of
receiving written notification from System Owner of the amount due, including detail about how
the amount was calculated.

The indemnification obligation shall terminate at the earlier of (1) the expiration of the
ten (10)-year testing period and the applicable statute of limitation, as it may be extended by
System Owner upon request of the Internal Revenue Service, to keep these years open for audit
or adjustment, or (2) the occurrence of a subsequent taxable event and the payment of any related
indemnification obligations as contemplated by this Article. Notwithstanding the foregoing
provisions of this Article 3.12.1, and to the extent permitted by law, to the extent that the receipt
of such payments by System Owner is determined by any Governmental Authority to constitute
income by System Owner subject to taxation, Interconnection Customer shall protect, indemnify,
and hold harmless System Owner and its Affiliates, from all claims by any such Governmental
Authority for any tax, interest, and/or penalties associated with such determination. Upon
receiving written notification of such determination from the Governmental Authority, System
Owner shall provide Interconnection Customer with written notification within thirty (30)
Calendar Days of such determination and notification. System Owner, upon the timely written
request by Interconnection Customer and at Interconnection Customer’s expense, shall appeal,
protest, seek abatement of, or otherwise oppose such determination. System Owner reserves the
right to make all decisions with regard to the prosecution of such appeal, protest, abatement or
other contest, including the compromise or settlement of the claim; provided that System Owner
shall cooperate and consult in good faith with Interconnection Customer regarding the conduct of
such contest. Interconnection Customer shall not be required to pay System Owner for the tax,
interest, and/or penalties prior to the seventh (7th) Calendar Day before the date on which
System Owner (1) is required to pay the tax, interest, and/or penalties or other amount in lieu
thereof pursuant to a compromise or settlement of the appeal, protest, abatement, or other
contest; (2) is required to pay the tax, interest, and/or penalties as the result of a final, non
appealable order by a Governmental Authority; or (3) is required to pay the tax, interest, and/or
penalties as a prerequisite to an appeal, protest, abatement, or other contest. In the event such
appeal, protest, abatement, or other contest results in a determination that System Owner is not
liable for any portion of any tax, interest, and/or penalties for which Interconnection Customer
has already made payment to System Owner, System Owner shall promptly refund to

12

SERVICE AGREEMENT NO. 2880

Interconnection Customer any payment attributable to the amount determined to be non-taxable,
plus any interest (calculated in accordance with 18 CFR 35.19a(a)(2)(iii)) or other payments
System Owner receives or which System Owner may be entitled with respect to such payment.
Interconnection Customer shall provide System Owner with credit assurances sufficient to meet
Interconnection Customer’s estimated liability for reimbursement of System Owner for taxes,
interest, and/or penalties under this Article 3.12.1. Such estimated liability shall be stated in
Appendix A.

To the extent that System Owner is a limited liability company and not a corporation, and
has elected to be taxed as a partnership, then the following shall apply: System Owner
represents, and the Parties acknowledge, that System Owner is a limited liability company and is
treated as a partnership for federal income tax purposes. Any payment made by Interconnection
Customer to System Owner for Upgrades is to be treated as an upfront payment. It is anticipated
by the Parties that any amounts paid by Interconnection Customer to System Owner for the
Upgrades will be reimbursed to Interconnection Customer in accordance with the terms of this
Agreement, provided Interconnection Customer fulfills its obligations under this Agreement.

3.12.2 Private Letter Ruling.

At Interconnection Customer’s request and expense, System Owner shall file with the
Internal Revenue Service a request for a private letter ruling as to whether any property
transferred or sums paid, or to be paid, by Interconnection Customer to System Owner under this
Agreement are subject to federal income taxation. Interconnection Customer will prepare the
initial draft of the request for a private letter ruling and will certify under penalties of perjury that
all facts represented in such request are true and accurate to the best of Interconnection
Customer’s knowledge. System Owner and Interconnection Customer shall cooperate in good
faith with respect to the submission of such request.

3.12.3 Other Taxes.

Upon the timely request by Interconnection Customer, and at Interconnection Customer’s
sole expense, System Owner shall appeal, protest, seek abatement of, or otherwise contest any
tax (other than federal or state income tax) asserted or assessed against System Owner for which
Interconnection Customer may be required to reimburse System Owner under the terms of this
Agreement. Interconnection Customer shall pay to System Owner on a periodic basis, as
invoiced by System Owner, System Owner’s documented reasonable costs of prosecuting such
appeal, protest, abatement, or other contest. Interconnection Customer and System Owner shall
cooperate in good faith with respect to any such contest. Unless the payment of such taxes is a
prerequisite to an appeal or abatement or cannot be deferred, no amount shall be payable by
Interconnection Customer to System Owner for such taxes until they are assessed by a final, non-
appealable order by any court or agency of competent jurisdiction. In the event that a tax
payment is withheld and ultimately due and payable after appeal, Interconnection Customer will
be responsible for all taxes, interest and penalties, other than penalties attributable to any delay
caused by System Owner. Each Party shall cooperate with the other Party to maintain each
Party’s tax status. Nothing in this Agreement is intended to adversely affect any Party’s tax-
exempt status with respect to the issuance of bonds including, but not limited to, local furnishing
bonds, as described in section 142(f) of the Internal Revenue Code.

13

SERVICE AGREEMENT NO. 2880

3.13 Tax Status; Non-Jurisdictional Entities.

3.13.1 Tax Status.

Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.
Nothing in this Agreement is intended to adversely affect the tax status of any Party including
the status of NYISO, or the status of System Owner with respect to the issuance of bonds
including, but not limited to, Local Furnishing Bonds. Notwithstanding any other provisions of
this Agreement, LIPA, NYPA and Consolidated Edison Company of New York, Inc. shall not be
required to comply with any provisions of this Agreement that would result in the loss of tax-
exempt status of any of their Tax-Exempt Bonds or impair their ability to issue future tax-exempt
obligations. For purposes of this provision, Tax-Exempt Bonds shall include the obligations of
the Long Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc.,
the interest on which is not included in gross income under the Internal Revenue Code.

3.13.2 Tax Status.

LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA,
from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general
ratemaking authority.

3.14 Modification.

3.14.1 General.

If, prior to the In-Service Date, the System Owner proposes to modify the Upgrades, the
System Owner must provide to the NYISO at least ninety (90) Calendar Days in advance of the
commencement of the work, or such shorter period upon which the Parties may agree, sufficient
information for the NYISO to evaluate the impact of the proposed modification on, as
applicable: (i) the reliable interconnection of Interconnection Customer’s Transmission Project
to the New York State Transmission System or (ii) the reliability of the New York State
Transmission System due to the Transmission Project’s interconnection to another region’s
transmission system. The NYISO’s agreement to the proposed modification shall not be
unreasonably withheld, conditioned, or delayed if the proposed modification is reasonably
related to the interconnection of the Transmission Project and will enable Interconnection
Customer’s Transmission Project to reliably interconnect to the New York State Transmission
System or ensure the reliability of the New York State Transmission System of the Transmission
Project’s interconnection to another region’s transmission system. If the cost of the modified
Upgrades is greater than the estimated cost identified in the Facilities Study, the additional cost
will be allocated in accordance with Sections 40.12.1.5.1 and 40.16.3 of Attachment HH of the
ISO OATT.

3.14.2 Standards.

Any additions, modifications, or replacements made to a Party’s facilities shall be
designed, constructed and operated in accordance with this Agreement, NYISO requirements and
Good Utility Practice.

14

SERVICE AGREEMENT NO. 2880

3.14.3 Modification Costs.

Interconnection Customer shall not be assigned the costs of any additions, modifications,
or replacements that System Owner makes to the Upgrades or the New York State Transmission
System to facilitate the interconnection of a third party to the Upgrades or the New York State
Transmission System, or to provide Transmission Service to a third party under the ISO OATT,
except in accordance with the cost allocation procedures in Attachment P of the ISO OATT.

ARTICLE 4. TESTING AND INSPECTION

4.1 Initial Testing and Modifications.

Prior to the In-Service Date of the Upgrades, the System Owner or Interconnection
Customer, as specified in Appendix A, shall test the Upgrades to ensure their safe and reliable
operation. The Party responsible for constructing the Upgrades shall make any modifications to
the Upgrades that are found to be necessary as a result of such testing. Interconnection Customer
shall bear the cost of all such testing and modifications

4.2 Right to Observe Testing.

The Party performing the testing shall notify the other Parties in advance of its
performance of tests of the Upgrades. Each of the other Parties shall have the right, at its own
expense, to observe such testing.

ARTICLE 5. PERFORMANCE OBLIGATIONS

5.1 Cost Responsibilities.

Interconnection Customer and/or System Owner, as specified in Appendix A, shall
perform the Construction Services at Interconnection Customer’s sole expense up to the
Upgrades Estimated Total Cost Amount. Interconnection Customer’s and System Owner’s
respective responsibilities for the cost of the Construction Services greater than the Upgrades
Estimated Total Costs Amount shall be determined in accordance with Section 40.16.3 of
Attachment HH to the OATT.

5.2 Provision and Application of Security.

5.2.1 If Interconnection Customer accepted its Project Cost Allocation and posted to
System Owner the Security for its Upgrades at the conclusion of the Facilities Study, then
Interconnection Customer shall not be responsible for posting additional Security under this
Agreement. Interconnection Customer’s Security shall be subject to the requirements of
Attachment P to the ISO OATT.

5.2.2 If Interconnection Customer was not required to post Security to the System
Owner at the conclusion of the Facilities Study, then at least thirty (30) Calendar Days prior to
the System Owner’s commencement of the procurement, installation, or construction of a
discrete portion of the Upgrades as such portion(s) are detailed in the Milestones in Appendix A,
Interconnection Customer shall provide System Owner, at Interconnection Customer’s option, a

15

SERVICE AGREEMENT NO. 2880

guarantee, a surety bond, letter of credit or other form of security that is reasonably acceptable to
System Owner and is consistent with the Uniform Commercial Code of the jurisdiction identified
in Article 7.2 of this Agreement. Such security for payment shall be in an amount sufficient to
cover the costs for Interconnection Customer’s share of constructing, procuring and installing the
applicable portion of the Upgrades, and shall be reduced on a dollar-for-dollar basis for
payments made to System Owner for these purposes.

In addition:

5.2.2.1 The guarantee must be made by an entity that meets the commercially
reasonable creditworthiness requirements of System Owner, and contains terms and conditions
that guarantee payment of any amount that may be due from Interconnection Customer, up to an
agreed-to maximum amount.

5.2.2.2 The letter of credit must be issued by a financial institution reasonably acceptable to System Owner and must specify a reasonable expiration date.

5.2.2.3 The surety bond must be issued by an insurer reasonably acceptable to System Owner and must specify a reasonable expiration date.

ARTICLE 6. INVOICE

6.1 General.

To the extent that any amounts are due to the Interconnection Customer or System Owner
under this Agreement, the Interconnection Customer and System Owner, as applicable, shall
submit to the other Party, on a monthly basis, invoices of amounts due for the preceding month.
Each invoice shall state the month to which the invoice applies and fully describe the services
and equipment provided. The Interconnection Customer and System Owner may discharge
mutual debts and payment obligations due and owing to each other on the same date through
netting, in which case all amounts one Party owes to the other Party under this Agreement,
including interest payments or credits, shall be netted so that only the net amount remaining due
shall be paid by the owing Party.

6.2 Final Invoice and Refund of Remaining Security/Overpayment Amount.

Within one hundred eighty (180) Calendar Days of the Completion Date, Interconnection
Customer or System Owner, as applicable, shall provide a final invoice to the other Party of any
remaining amounts due associated with the Construction Services. Within thirty (30) Calendar
Days of the later of: (i) Interconnection Customer’s payment of any final invoice to the System
Owner, and (ii) the completion of the Construction Services, System Owner shall release or
refund to the Interconnection Customer any remaining portions of its Security and any amount
that Interconnection Customer has overpaid under this Article 6.

6.3 Payment.

Invoices shall be rendered to the paying Party at the address specified in Appendix B hereto. The Party receiving the invoice shall pay the invoice within thirty (30) Calendar Days of

16

SERVICE AGREEMENT NO. 2880

receipt. All payments shall be made in immediately available funds payable to the other Party,
or by wire transfer to a bank named and account designated by the invoicing Party. Payment of
invoices will not constitute a waiver of any rights or claims the paying Party may have under this
Agreement.

6.4 Disputes.

In the event of a billing dispute between Parties, the Party owed money shall continue to
perform under this Agreement as long as the other Party: (i) continues to make all payments not
in dispute; and (ii) pays to the Party owed money or into an independent escrow account the
portion of the invoice in dispute, pending resolution of such dispute. If the Party that owes
money fails to meet these two requirements for continuation of service, then the Party owed
money may provide notice to the other Party of a Default pursuant to Article 10. Within thirty
(30) Calendar Days after the resolution of the dispute, the Party that owes money to the other
Party shall pay the amount due with interest calculated in accord with the methodology set forth
in FERC’s Regulations at 18 C.F.R. § 35.19a(a)(2)(iii).

ARTICLE 7. REGULATORY REQUIREMENTS AND GOVERNING LAW

7.1 Regulatory Requirements.

Each Party’s obligations under this Agreement shall be subject to its receipt of any
required approval or certificate from one or more Governmental Authorities in the form and
substance satisfactory to the applying Party, or the Party making any required filings with, or
providing notice to, such Governmental Authorities, and the expiration of any time period
associated therewith. Each Party shall in good faith seek and use its Reasonable Efforts to obtain
such other approvals. Nothing in this Agreement shall require a Party to take any action that
could result in its inability to obtain, or its loss of, status or exemption under the Federal Power
Act or the Public Utility Holding Company Act of 2005 or the Public Utility Regulatory Policies
Act of 1978, as amended.

7.2 Governing Law.

7.2.1 The validity, interpretation and performance of this Agreement and each of its
provisions shall be governed by the laws of the state of New York, without regard to its conflicts
of law principles.

7.2.2 This Agreement is subject to all Applicable Laws and Regulations.

7.2.3 Each Party expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, rules, or regulations of a Governmental Authority.

ARTICLE 8. NOTICES

8.1 General.

Unless otherwise provided in this Agreement, any notice, demand or request required or
permitted to be given by a Party to the other Parties and any instrument required or permitted to

17

SERVICE AGREEMENT NO. 2880

be tendered or delivered by a Party in writing to the other Parties shall be effective when
delivered and may be so given, tendered or delivered, by recognized national courier, or by
depositing the same with the United States Postal Service with postage prepaid, for delivery by
certified or registered mail, addressed to the Party, or personally delivered to the Party, at the
address set out in Appendix B hereto.

A Party may change the notice information in this Agreement by giving five (5) Business
Days written notice prior to the effective date of the change.

8.2 Billings and Payments.

Billings and payments shall be sent to the addresses set out in Appendix B hereto.

8.3 Alternative Forms of Notice.

Any notice or request required or permitted to be given by a Party to the other Parties and
not required by this Agreement to be given in writing may be so given by telephone or email to
the telephone numbers and email addresses set out in Appendix B hereto.

ARTICLE 9. FORCE MAJEURE

Economic hardship is not considered a Force Majeure event. A Party shall not be
responsible or liable, or deemed, in Default with respect to any obligation hereunder, other than
the obligation to pay money when due, to the extent the Party is prevented from fulfilling such
obligation by Force Majeure. A Party unable to fulfill any obligation hereunder (other than an
obligation to pay money when due) by reason of Force Majeure shall give notice and the full
particulars of such Force Majeure to the other Parties in writing or by telephone as soon as
reasonably possible after the occurrence of the cause relied upon. Telephone notices given
pursuant to this Article shall be confirmed in writing as soon as reasonably possible and shall
specifically state full particulars of the Force Majeure, the time and date when the Force Majeure
occurred and when the Force Majeure is reasonably expected to cease. The Party affected shall
exercise due diligence to remove such disability with reasonable dispatch, but shall not be
required to accede or agree to any provision not satisfactory to it in order to settle and terminate a
strike or other labor disturbance.

ARTICLE 10. DEFAULT

10.1 General.

No Breach shall exist where such failure to discharge an obligation (other than the
payment of money) is the result of Force Majeure as defined in this Agreement or the result of an
act or omission of the other Parties. Upon a Breach, the non-Breaching Parties shall give written
notice of such to the Breaching Party. The Breaching Party shall have thirty (30) Calendar Days
from receipt of the Breach notice within which to cure such Breach; provided however, if such
Breach is not capable of cure within thirty (30) Calendar Days, the Breaching Party shall
commence such cure within thirty (30) Calendar Days after notice and continuously and
diligently complete such cure within ninety (90) Calendar Days from receipt of the Breach
notice; and, if cured within such time, the Breach specified in such notice shall cease to exist.

18

SERVICE AGREEMENT NO. 2880

10.2 Right to Terminate.

If a Breach is not cured as provided in this Article 10, or if a Breach is not capable of
being cured within the period provided for herein, the non-Breaching Parties acting together shall
thereafter have the right to declare a Default and terminate this Agreement by written notice at
any time until cure occurs, and be relieved of any further obligation hereunder and, whether or
not those Parties terminate this Agreement, to recover from the defaulting Party all amounts due
hereunder, plus all other damages and remedies to which they are entitled at law or in equity.
The provisions of this Article will survive termination of this Agreement.

ARTICLE 11. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE

11.1 Indemnity.

Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and save
harmless, as applicable, the other Parties (each an “Indemnified Party”) from, any and all
damages, losses, claims, including claims and actions relating to injury to or death of any person
or damage to property, the alleged violation of any Environmental Law, or the release or
threatened release of any Hazardous Substance, demand, suits, recoveries, costs and expenses,
court costs, attorney fees, and all other obligations by or to third parties (any and all of these a
“Loss”), arising out of or resulting from (i) the Indemnified Party’s performance of its
obligations under this Agreement on behalf of the Indemnifying Party, except in cases where the
Indemnifying Party can demonstrate that the Loss of the Indemnified Party was caused by the
gross negligence or intentional wrongdoing of the Indemnified Party or (ii) the violation by the
Indemnifying Party of any Environmental Law or the release by the Indemnifying Party of any
Hazardous Substance.

11.1.1 Indemnified Party.

If a Party is entitled to indemnification under this Article 11 as a result of a claim by a
third party, and the Indemnifying Party fails, after notice and reasonable opportunity to proceed
under Article 11.1.3, to assume the defense of such claim, such Indemnified Party may at the
expense of the Indemnifying Party contest, settle or consent to the entry of any judgment with
respect to, or pay in full, such claim.

11.1.2 Indemnifying Party.

If an Indemnifying Party is obligated to indemnify and hold any Indemnified Party
harmless under this Article 11, the amount owing to the Indemnified Party shall be the amount of
such Indemnified Party’s actual Loss, net of any insurance or other recovery.

11.1.3 Indemnity Procedures.

Promptly after receipt by an Indemnified Party of any claim or notice of the
commencement of any action or administrative or legal proceeding or investigation as to which
the indemnity provided for in Article 11.1 may apply, the Indemnified Party shall notify the
Indemnifying Party of such fact. Any failure of or delay in such notification shall not affect a

19

SERVICE AGREEMENT NO. 2880

Party’s indemnification obligation unless such failure or delay is materially prejudicial to the Indemnifying Party.

Except as stated below, the Indemnifying Party shall have the right to assume the defense
thereof with counsel designated by such Indemnifying Party and reasonably satisfactory to the
Indemnified Party. If the defendants in any such action include one or more Indemnified Parties
and the Indemnifying Party and if the Indemnified Party reasonably concludes that there may be
legal defenses available to it and/or other Indemnified Parties which are different from or
additional to those available to the Indemnifying Party, the Indemnified Party shall have the right
to select separate counsel to assert such legal defenses and to otherwise participate in the defense
of such action on its own behalf. In such instances, the Indemnifying Party shall only be
required to pay the fees and expenses of one additional attorney to represent an Indemnified
Party or Indemnified Parties having such differing or additional legal defenses.

The Indemnified Party shall be entitled, at its expense, to participate in any such action,
suit or proceeding, the defense of which has been assumed by the Indemnifying Party.
Notwithstanding the foregoing, the Indemnifying Party (i) shall not be entitled to assume and
control the defense of any such action, suit or proceedings if and to the extent that, in the opinion
of the Indemnified Party and its counsel, such action, suit or proceeding involves the potential
imposition of criminal liability on the Indemnified Party, or there exists a conflict or adversity of
interest between the Indemnified Party and the Indemnifying Party, in such event the
Indemnifying Party shall pay the reasonable expenses of the Indemnified Party, and (ii) shall not
settle or consent to the entry of any judgment in any action, suit or proceeding without the
consent of the Indemnified Party, which shall not be unreasonably withheld, conditioned or
delayed.

11.2 No Consequential Damages.

Other than the indemnity obligations set forth in Article 11.1, in no event shall any Party
be liable under any provision of this Agreement for any losses, damages, costs or expenses for
any special, indirect, incidental, consequential, or punitive damages, including but not limited to
loss of profit or revenue, loss of the use of equipment, cost of capital, cost of temporary
equipment or services, whether based in whole or in part in contract, in tort, including
negligence, strict liability, or any other theory of liability; provided, however, that damages for
which a Party may be liable to another Party under separate agreement will not be considered to
be special, indirect, incidental, or consequential damages hereunder.

11.3 Insurance.

The System Owner and, if applicable, Interconnection Customer shall, at its own
expense, procure and maintain in force throughout the period of this Agreement and until
released by the other Parties, the following minimum insurance coverages, with insurance
companies licensed to write insurance or approved eligible surplus lines carriers in the state of
New York with a minimum A.M. Best rating of A or better for financial strength, and an A.M.
Best financial size category of VIII or better:

20

SERVICE AGREEMENT NO. 2880

11.3.1 Employers’ Liability and Workers’ Compensation Insurance providing statutory benefits in accordance with the laws and regulations of New York State.

11.3.2 Commercial General Liability (“CGL”) Insurance including premises and
operations, personal injury, broad form property damage, broad form blanket contractual liability
coverage products and completed operations coverage, coverage for explosion, collapse and
underground hazards, independent contractors coverage, coverage for pollution to the extent
normally available and punitive damages to the extent normally available using Insurance
Services Office, Inc. Commercial General Liability Coverage (“ISO CG”) Form CG 00 01 04 13
or a form equivalent to or better than CG 00 01 04 13, with minimum limits of Two Million
Dollars ($2,000,000) per occurrence and Two Million Dollars ($2,000,000) aggregate combined
single limit for personal injury, bodily injury, including death and property damage.

11.3.3 Comprehensive Automobile Liability Insurance for coverage of owned and
non-owned and hired vehicles, trailers or semi-trailers designed for travel on public roads, with a
minimum, combined single limit of One Million Dollars ($1,000,000) per occurrence for bodily
injury, including death, and property damage.

11.3.4 If applicable, the Commercial General Liability and Comprehensive
Automobile Liability Insurance policies should include contractual liability for work in
connection with construction or demolition work on or within 50 feet of a railroad, or a separate
Railroad Protective Liability Policy should be provided.

11.3.5 Excess Liability Insurance over and above the Employers’ Liability,
Commercial General Liability and Comprehensive Automobile Liability Insurance coverages,
with a minimum combined single limit of Twenty Million Dollars ($20,000,000) per occurrence
and Twenty Million Dollars ($20,000,000) aggregate. The Excess policies should contain the
same extensions listed under the Primary policies.

11.3.6 The Commercial General Liability Insurance, Comprehensive Automobile
Insurance and Excess Liability Insurance policies of System Owner and, if applicable,
Interconnection Customer shall name the other Party, its parent, associated and Affiliate
companies and their respective directors, officers, agents, servants and employees (“Other Party
Group”) as additional insureds using ISO CG Endorsements: CG 20 33 04 13, and CG 20 37 04
13 or CG 20 10 04 13 and CG 20 37 04 13 or equivalent to or better forms. All policies shall
contain provisions whereby the insurers waive all rights of subrogation in accordance with the
provisions of this Agreement against the Other Party Group and provide thirty (30) Calendar
Days advance written notice to the Other Party Group prior to anniversary date of cancellation or
any material change in coverage or condition.

11.3.7 The Commercial General Liability Insurance, Comprehensive Automobile
Liability Insurance and Excess Liability Insurance policies shall contain provisions that specify
that the policies are primary and non-contributory. System Owner and, if applicable,
Interconnection Customer shall each be responsible for its respective deductibles or retentions.

11.3.8 The Commercial General Liability Insurance, Comprehensive Automobile Liability Insurance and Excess Liability Insurance policies, if written on a Claims First Made

21

SERVICE AGREEMENT NO. 2880

Basis, shall be maintained in full force and effect for at least three (3) years after termination of
this Agreement, which coverage may be in the form of tail coverage or extended reporting period
coverage if agreed by the Interconnection Customer and System Owner.

11.3.9 If applicable, Pollution Liability Insurance in an amount no less than
$7,500,000 per occurrence and $7,500,000 in the aggregate. The policy will provide coverage
for claims resulting from pollution or other environmental impairment arising out of or in
connection with work performed on the premises by the other party, its contractors and and/or
subcontractors. Such insurance is to include coverage for, but not be limited to, cleanup, third
party bodily injury and property damage and remediation and will be written on an occurrence
basis. The policy shall name the Other Party Group as additional insureds, be primary and
contain a waiver of subrogation.

11.3.10 The requirements contained herein as to the types and limits of all insurance
to be maintained by the System Owner and, if applicable, Interconnection Customer are not
intended to and shall not in any manner, limit or qualify the liabilities and obligations assumed
by those Parties under this Agreement.

11.3.11 Within thirty (30) Calendar Days following execution of this Agreement, and
as soon as practicable after the end of each fiscal year or at the renewal of the insurance policy
and in any event within ninety (90) Calendar Days thereafter, Interconnection Customer and
System Owner, as applicable, shall provide certificate of insurance for all insurance required in
this Agreement, executed by each insurer or by an authorized representative of each insurer.

11.3.12 Notwithstanding the foregoing, either of System Owner and, if applicable,
Interconnection Customer may each self-insure to meet the minimum insurance requirements of
Articles 11.3.1 through 11.3.9 to the extent it maintains a self-insurance program; provided that,
such Party’s senior debt is rated at investment grade, or better, by Standard & Poor’s and that its
self-insurance program meets the minimum insurance requirements of Articles 11.3.1 through

11.3.9. In the event that a Party is permitted to self-insure pursuant to this Article 11.3.12, it
shall notify the other Party that it meets the requirements to self-insure and that its self-insurance
program meets the minimum insurance requirements in a manner consistent with that specified
in Articles 11.3.1 through 11.3.9 and provide evidence of such coverages. For any period of
time that a Party’s senior debt is unrated by Standard & Poor’s or is rated at less than investment
grade by Standard & Poor’s, such Party shall comply with the insurance requirements applicable
to it under Articles 11.3.1 through 11.3.9.

11.3.13 Interconnection Customer and System Owner agree to report to each other in
writing as soon as practical all accidents or occurrences resulting in injuries to any person,
including death, and any property damage arising out of this Agreement.

11.3.14 Subcontractors of each party must maintain the same insurance requirements
stated under Articles 11.3.1 through 11.3.9 and comply with the Additional Insured requirements
herein. In addition, their policies must state that they are primary and non-contributory and
contain a waiver of subrogation.

22

SERVICE AGREEMENT NO. 2880

ARTICLE 12. ASSIGNMENT

12.1 Assignment.

This Agreement may be assigned by a Party only with the written consent of the other
Parties; provided that a Party may assign this Agreement without the consent of the other Parties
to any Affiliate of the assigning Party with an equal or greater credit rating and with the legal
authority and operational ability to satisfy the obligations of the assigning Party under this
Agreement; provided further that a Party may assign this Agreement without the consent of the
other Parties in connection with the sale, merger, restructuring, or transfer of a substantial
portion or all of its assets, so long as the assignee in such a transaction directly assumes in
writing all rights, duties and obligations arising under this Agreement; and provided further that
the Interconnection Customer shall have the right to assign this Agreement, without the consent
of the NYISO or System Owner, for collateral security purposes to aid in providing financing for
the Transmission Project, provided that the Interconnection Customer will promptly notify the
NYISO and System Owner of any such assignment. Any financing arrangement entered into by
Interconnection Customer pursuant to this Article will provide that prior to or upon the exercise
of the secured party’s, trustee’s or mortgagee’s assignment rights pursuant to said arrangement,
the secured creditor, the trustee or mortgagee will notify the NYISO and System Owner of the
date and particulars of any such exercise of assignment right(s) and will provide the NYISO and
System Owner with proof that it meets the requirements of Articles 5.2 and 11.3. Any attempted
assignment that violates this Article is void and ineffective. Any assignment under this
Agreement shall not relieve a Party of its obligations, nor shall a Party’s obligations be enlarged,
in whole or in part, by reason thereof. Where required, consent to assignment will not be
unreasonably withheld, conditioned or delayed.

ARTICLE 13. SEVERABILITY

If any provision in this Agreement is finally determined to be invalid, void or
unenforceable by any court or other Governmental Authority having jurisdiction, such
determination shall not invalidate, void or make unenforceable any other provision, agreement or
covenant of this Agreement.

ARTICLE 14. COMPARABILITY

The Parties will comply with all applicable comparability and code of conduct laws, rules
and regulations, as amended from time to time.

ARTICLE 15. CONFIDENTIALITY

15.1 Confidentiality.

Certain information exchanged by the Parties during the term of this Agreement shall
constitute confidential information (“Confidential Information”) and shall be subject to this
Article 15.

If requested by a Party receiving information, the Party supplying the information shall provide in writing, the basis for asserting that the information referred to in this Article warrants

23

SERVICE AGREEMENT NO. 2880

confidential treatment, and the requesting Party may disclose such writing to the appropriate
Governmental Authority. Each Party shall be responsible for the costs associated with affording
confidential treatment to its information.

15.2 Term.

During the term of this Agreement, and for a period of three (3) years after the expiration
or termination of this Agreement, except as otherwise provided in this Article 15, each Party
shall hold in confidence and shall not disclose to any person Confidential Information.

15.3 Confidential Information.

The following shall constitute Confidential Information: (1) any non-public information
that is treated as confidential by the disclosing Party and which the disclosing Party identifies as
Confidential Information in writing at the time, or promptly after the time, of disclosure; or (2)
information designated as Confidential Information by the NYISO Code of Conduct contained in
Attachment F to the OATT.

15.4 Scope.

Confidential Information shall not include information that the receiving Party can
demonstrate: (1) is generally available to the public other than as a result of a disclosure by the
receiving Party; (2) was in the lawful possession of the receiving Party on a non-confidential
basis before receiving it from the disclosing Party; (3) was supplied to the receiving Party
without restriction by a third party, who, to the knowledge of the receiving Party after due
inquiry, was under no obligation to the disclosing Party to keep such information confidential;
(4) was independently developed by the receiving Party without reference to Confidential
Information of the disclosing Party; (5) is, or becomes, publicly known, through no wrongful act
or omission of the receiving Party or Breach of this Agreement; or (6) is required, in accordance
with Article 15.9 of this Agreement, Order of Disclosure, to be disclosed by any Governmental
Authority or is otherwise required to be disclosed by law or subpoena, or is necessary in any
legal proceeding establishing rights and obligations under this Agreement. Information
designated as Confidential Information will no longer be deemed confidential if the Party that
designated the information as confidential notifies the other Party that it no longer is
confidential.

15.5 Release of Confidential Information.

No Party shall release or disclose Confidential Information to any other person, except to
its Affiliates (limited by FERC Standards of Conduct requirements), subcontractors, employees,
consultants, or to parties who may be considering providing financing to or equity participation
with Interconnection Customer, or to potential purchasers or assignees of a Party, on a need-to-
know basis in connection with this Agreement, unless such person has first been advised of the
confidentiality provisions of this Article 15 and has agreed to comply with such provisions.
Notwithstanding the foregoing, a Party providing Confidential Information to any person shall
remain primarily responsible for any release of Confidential Information in contravention of this
Article 15.

24

SERVICE AGREEMENT NO. 2880

15.6 Rights.

Each Party retains all rights, title, and interest in the Confidential Information that each
Party discloses to the other Party. The disclosure by each Party to the other Parties of
Confidential Information shall not be deemed a waiver by any Party or any other person or entity
of the right to protect the Confidential Information from public disclosure.

15.7 No Warranties.

By providing Confidential Information, no Party makes any warranties or representations
as to its accuracy or completeness. In addition, by supplying Confidential Information, no Party
obligates itself to provide any particular information or Confidential Information to the other
Parties nor to enter into any further agreements or proceed with any other relationship or joint
venture.

15.8 Standard of Care.

Each Party shall use at least the same standard of care to protect Confidential Information
it receives as it uses to protect its own Confidential Information from unauthorized disclosure,
publication or dissemination. Each Party may use Confidential Information solely to fulfill its
obligations to the other Parties under this Agreement or its regulatory requirements, including the
OATT and Services Tariff. The NYISO shall, in all cases, treat the information it receives in
accordance with the requirements of Attachment F to the OATT.

15.9 Order of Disclosure.

If a court or a Government Authority or entity with the right, power, and apparent
authority to do so requests or requires any Party, by subpoena, oral deposition, interrogatories,
requests for production of documents, administrative order, or otherwise, to disclose Confidential
Information, that Party shall provide the other Parties with prompt notice of such request(s) or
requirement(s) so that the other Parties may seek an appropriate protective order or waive
compliance with the terms of this Agreement. Notwithstanding the absence of a protective order
or waiver, the Party may disclose such Confidential Information which, in the opinion of its
counsel, the Party is legally compelled to disclose. Each Party will use Reasonable Efforts to
obtain reliable assurance that confidential treatment will be accorded any Confidential
Information so furnished.

15.10 Termination of Agreement.

Upon termination of this Agreement for any reason, each Party shall, within ten (10)
Calendar Days of receipt of a written request from the other Parties, use Reasonable Efforts to
destroy, erase, or delete (with such destruction, erasure, and deletion certified in writing to the
other Parties) or return to the other Parties, without retaining copies thereof, any and all written
or electronic Confidential Information received from the other Parties pursuant to this
Agreement.

25

SERVICE AGREEMENT NO. 2880

15.11 Remedies.

The Parties agree that monetary damages would be inadequate to compensate a Party for
another Party’s Breach of its obligations under this Article 15. Each Party accordingly agrees
that the other Parties shall be entitled to equitable relief, by way of injunction or otherwise, if the
first Party Breaches or threatens to Breach its obligations under this Article 15, which equitable
relief shall be granted without bond or proof of damages, and the receiving Party shall not plead
in defense that there would be an adequate remedy at law. Such remedy shall not be deemed an
exclusive remedy for the Breach of this Article 15, but shall be in addition to all other remedies
available at law or in equity. The Parties further acknowledge and agree that the covenants
contained herein are necessary for the protection of legitimate business interests and are
reasonable in scope. No Party, however, shall be liable for indirect, incidental, or consequential
or punitive damages of any nature or kind resulting from or arising in connection with this
Article 15.

15.12 Disclosure to FERC, its Staff, or a State.

Notwithstanding anything in this Article 15 to the contrary, and pursuant to 18 C.F.R.
section 1b.20, if FERC or its staff, during the course of an investigation or otherwise, requests
information from one of the Parties that is otherwise required to be maintained in confidence
pursuant to this Agreement or the OATT, the Party shall provide the requested information to
FERC or its staff, within the time provided for in the request for information. In providing the
information to FERC or its staff, the Party must, consistent with 18 C.F.R. section 388.112,
request that the information be treated as confidential and non-public by FERC and its staff and
that the information be withheld from public disclosure. Parties are prohibited from notifying
the other Parties to this Agreement prior to the release of the Confidential Information to the
Commission or its staff. The Party shall notify the other Parties to the Agreement when it is
notified by FERC or its staff that a request to release Confidential Information has been received
by FERC, at which time the Parties may respond before such information would be made public,
pursuant to 18 C.F.R. section 388.112. Requests from a state regulatory body conducting a
confidential investigation shall be treated in a similar manner if consistent with the applicable
state rules and regulations. A Party shall not be liable for any losses, consequential or otherwise,
resulting from that Party divulging Confidential Information pursuant to a FERC or state
regulatory body request under this paragraph.

15.13 Required Notices Upon Requests or Demands for Confidential Information.

Except as otherwise expressly provided herein, no Party shall disclose Confidential
Information to any person not employed or retained by the Party possessing the Confidential
Information, except to the extent disclosure is (i) required by law; (ii) reasonably deemed by the
disclosing Party to be required to be disclosed in connection with a dispute between or among
the Parties, or the defense of litigation or dispute; (iii) otherwise permitted by consent of the
other Party, such consent not to be unreasonably withheld; or (iv) necessary to fulfill its
obligations under this Agreement, the OATT or the Services Tariff. Prior to any disclosures of a
Party’s Confidential Information under this subparagraph, or if any third party or Governmental
Authority makes any request or demand for any of the information described in this subparagraph, the disclosing Party agrees to promptly notify the other Party in writing and agrees

26

SERVICE AGREEMENT NO. 2880

to assert confidentiality and cooperate with the other Party in seeking to protect the Confidential
Information from public disclosure by confidentiality agreement, protective order or other
reasonable measures.

ARTICLE 16. INTERCONNECTION CUSTOMER AND SYSTEM OWNER
NOTICES OF ENVIRONMENTAL RELEASES

Interconnection Customer and System Owner shall notify the other Parties, first orally
and then in writing, of the release of any Hazardous Substances, any asbestos or lead abatement
activities, or any type of remediation activities related to the Upgrades, each of which may
reasonably be expected to affect the other Parties. The notifying Party shall: (i) provide the
notice as soon as practicable, provided such Party makes a good faith effort to provide the notice
no later than twenty-four hours after such Party becomes aware of the occurrence; and
(ii) promptly furnish to the other Parties copies of any publicly available reports filed with any
Governmental Authorities addressing such events.

ARTICLE 17. INFORMATION REQUIREMENT

17.1 Information Acquisition.

Interconnection Customer and System Owner shall each submit specific information
regarding the electrical characteristics of its facilities to the other Parties as described below and
in accordance with Applicable Reliability Requirements.

17.2 Information Submission Concerning the Upgrades.

The initial information submission by System Owner shall occur as specified in the
Milestones in Appendix A and shall include New York State Transmission System information
necessary to allow the Interconnection Customer to select equipment for its Transmission Project
and meet any system protection and stability requirements, unless otherwise mutually agreed to
by the Interconnection Customer and System Owner. On a monthly basis, System Owner and
Interconnection Customer shall each provide the other Parties a status report on the construction
and installation of the Upgrades, including, but not limited to, the following information:
(1) progress to date; (2) a description of the activities since the last report; (3) a description of the
action items for the next period; and (4) the delivery status of equipment ordered.

17.3 Information Submission Concerning the Transmission Project.

The updated information submission by the Interconnection Customer, including
manufacturer information, shall occur as specified in the Milestones in Appendix A.
Interconnection Customer shall submit a completed copy, if applicable, of the Transmission
Project data requirements contained in the Transmission Interconnection Application to the
Transmission Interconnection Procedures. It shall also include any additional information
provided to System Owner, as applicable, for the Facilities Study. Information in this
submission shall be the most current Transmission Project design or expected performance data.
Information submitted for stability models shall be compatible with NYISO standard models. If
there is no compatible model, the Interconnection Customer will work with a consultant mutually
agreed to by the Parties to develop and supply a standard model and associated information.

27

SERVICE AGREEMENT NO. 2880

If the Interconnection Customer’s data is different from what was originally provided to
System Owner and NYISO in its Transmission Interconnection Application and this difference
may be reasonably expected to affect the other Parties’ facilities or the New York State
Transmission System, but does not require the submission of a new Transmission
Interconnection Application, then Interconnection Customer will notify the NYISO and System
Owner of such modifications.

17.4 Information Supplementation.

The Interconnection Customer and System Owner shall supplement its information
submissions described above in this Article 17 with any and all “as built” information or “as
tested” performance information that differs from the initial submissions or, alternatively, written
confirmation that no such differences exist.

ARTICLE 18. INFORMATION ACCESS AND AUDIT RIGHTS

18.1 Information Access.

Each Party (“Disclosing Party”) shall make available to another Party (“Requesting
Party”) information that is in the possession of the Disclosing Party and is necessary in order for
the Requesting Party to: (i) verify the costs incurred by the Disclosing Party for which the
Requesting Party is responsible under this Agreement; and (ii) carry out its obligations and
responsibilities under this Agreement. The Parties shall not use such information for purposes
other than those set forth in this Article 18.1 and to enforce their rights under this Agreement.

18.2 Reporting of Non-Force Majeure Events.

Each Party (the “Notifying Party”) shall notify the other Parties when the Notifying Party
becomes aware of its inability to comply with the provisions of this Agreement for a reason other
than a Force Majeure event. The Parties agree to cooperate with each other and provide
necessary information regarding such inability to comply, including the date, duration, reason for
the inability to comply, and corrective actions taken or planned to be taken with respect to such
inability to comply. Notwithstanding the foregoing, notification, cooperation or information
provided under this Article shall not entitle the Party receiving such notification to allege a cause
for anticipatory breach of this Agreement.

18.3 Audit Rights.

Subject to the requirements of confidentiality under Article 15 of this Agreement, each
Party shall have the right, during normal business hours, and upon prior reasonable notice to
another Party, to audit at its own expense the other Party’s accounts and records pertaining to the
other Party’s performance or satisfaction of its obligations under this Agreement. Such audit
rights shall include audits of the other Party’s costs and calculation of invoiced amounts. Any
audit authorized by this Article shall be performed at the offices where such accounts and
records are maintained and shall be limited to those portions of such accounts and records that
relate to the Party’s performance and satisfaction of obligations under this Agreement. Each
Party shall keep such accounts and records for a period equivalent to the audit rights periods
described in Article 18.4 of this Agreement.

28

SERVICE AGREEMENT NO. 2880

18.4 Audit Rights Periods.

18.4.1 Audit Rights Period for Construction-Related Accounts and Records.

Accounts and records related to the design, engineering, procurement, and construction of
the Upgrades shall be subject to audit for a period of twenty-four months following the issuance
of a final invoice in accordance with Article 6.1 of this Agreement.

18.4.2 Audit Rights Period for All Other Accounts and Records.

Accounts and records related to a Party’s performance or satisfaction of its obligations
under this Agreement other than those described in Article 18.4.1 of this Agreement shall be
subject to audit as follows: (i) for an audit relating to cost obligations, the applicable audit rights
period shall be twenty-four months after the auditing Party’s receipt of an invoice giving rise to
such cost obligations; and (ii) for an audit relating to all other obligations, the applicable audit
rights period shall be twenty-four months after the event for which the audit is sought.

18.5 Audit Results.

If an audit by a Party determines that an overpayment or an underpayment has occurred, a
notice of such overpayment or underpayment shall be given to the other Party together with
those records from the audit which support such determination.

ARTICLE 19. SUBCONTRACTORS

19.1 General.

Nothing in this Agreement shall prevent a Party from utilizing the services of any
subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,
however, that each Party shall require its subcontractors to comply with all applicable terms and
conditions of this Agreement in providing such services and each Party shall remain primarily
liable to the other Parties for the performance of such subcontractor.

19.2 Responsibility of Principal.

The creation of any subcontract relationship shall not relieve the hiring Party of any of its
obligations under this Agreement. The hiring Party shall be fully responsible to the other Parties
for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been
made; provided, however, that in no event shall the NYISO or System Owner be liable for the
actions or inactions of Interconnection Customer or its subcontractors with respect to obligations
of Interconnection Customer under Article 3 of this Agreement. Any applicable obligation
imposed by this Agreement upon the hiring Party shall be equally binding upon, and shall be
construed as having application to, any subcontractor of such Party.

19.3 No Limitation by Insurance.

The obligations under this Article 19 will not be limited in any way by any limitation of subcontractor’s insurance.

29

SERVICE AGREEMENT NO. 2880

ARTICLE 20. DISPUTES

20.1 Submission.

In the event any Party has a dispute, or asserts a claim, that arises out of or in connection
with this Agreement or its performance (a “Dispute”), such Party shall provide the other Parties
with written notice of the Dispute (“Notice of Dispute”). Such Dispute shall be referred to a
designated senior representative of each Party for resolution on an informal basis as promptly as
practicable after receipt of the Notice of Dispute by the other Parties. In the event the designated
representatives are unable to resolve the Dispute through unassisted or assisted negotiations
within thirty (30) Calendar Days of the other Parties’ receipt of the Notice of Dispute, such
Dispute may, upon mutual agreement of the Parties, be submitted to arbitration and resolved in
accordance with the arbitration procedures set forth below. In the event the Parties do not agree
to submit such Dispute to arbitration, each Party may exercise whatever rights and remedies it
may have in equity or at law consistent with the terms of this Agreement.

20.2 External Arbitration Procedures.

Any arbitration initiated under this Agreement shall be conducted before a single neutral
arbitrator appointed by the Parties. If the Parties fail to agree upon a single arbitrator within ten
(10) Calendar Days of the submission of the Dispute to arbitration, each Party shall choose one
arbitrator who shall sit on a three-member arbitration panel. In each case, the arbitrator(s) shall
be knowledgeable in electric utility matters, including electric transmission and bulk power
issues, and shall not have any current or past substantial business or financial relationships with
any party to the arbitration (except prior arbitration). The arbitrator(s) shall provide each of the
Parties an opportunity to be heard and, except as otherwise provided herein, shall conduct the
arbitration in accordance with the Commercial Arbitration Rules of the American Arbitration
Association (“Arbitration Rules”) and any applicable FERC regulations or RTO rules; provided,
however, in the event of a conflict between the Arbitration Rules and the terms of this Article 20,
the terms of this Article 20 shall prevail.

20.3 Arbitration Decisions.

Unless otherwise agreed by the Parties, the arbitrator(s) shall render a decision within
ninety (90) Calendar Days of appointment and shall notify the Parties in writing of such decision
and the reasons therefor. The arbitrator(s) shall be authorized only to interpret and apply the
provisions of this Agreement and shall have no power to modify or change any provision of this
Agreement in any manner. The decision of the arbitrator(s) shall be final and binding upon the
Parties, and judgment on the award may be entered in any court having jurisdiction. The
decision of the arbitrator(s) may be appealed solely on the grounds that the conduct of the
arbitrator(s), or the decision itself, violated the standards set forth in the Federal Arbitration Act
or the Administrative Dispute Resolution Act. The final decision of the arbitrator(s) must also be
filed with FERC if it affects jurisdictional rates, terms and conditions of service, or Upgrades.

20.4 Costs.

Each Party shall be responsible for its own costs incurred during the arbitration process
and for the following costs, if applicable: (1) the cost of the arbitrator chosen by the Party to sit

30

SERVICE AGREEMENT NO. 2880

on the three member panel; or (2) one-third the cost of the single arbitrator jointly chosen by the
Parties.

20.5 Termination.

Notwithstanding the provisions of this Article 20, any Party may terminate this
Agreement in accordance with its provisions or pursuant to an action at law or equity. The issue
of whether such a termination is proper shall not be considered a Dispute hereunder.

ARTICLE 21. REPRESENTATIONS, WARRANTIES AND COVENANTS

21.1 General.

Each Party makes the following representations, warranties and covenants:

21.1.1 Good Standing.

Such Party is duly organized, validly existing and in good standing under the laws of the
state in which it is organized, formed, or incorporated, as applicable; that it is qualified to do
business in the State of New York; and that it has the corporate power and authority to own its
properties, to carry on its business as now being conducted, to enter into this Agreement and
carry out the transactions contemplated hereby, and to perform and carry out all covenants and
obligations on its part to be performed under and pursuant to this Agreement.

21.1.2 Authority.

Such Party has the right, power and authority to enter into this Agreement, to become a
Party hereto and to perform its obligations hereunder. This Agreement is a legal, valid and
binding obligation of such Party, enforceable against such Party in accordance with its terms,
except as the enforceability thereof may be limited by applicable bankruptcy, insolvency,
reorganization or other similar laws affecting creditors’ rights generally and by general equitable
principles (regardless of whether enforceability is sought in a proceeding in equity or at law).

21.1.3 No Conflict.

The execution, delivery and performance of this Agreement does not violate or conflict
with the organizational or formation documents, or bylaws or operating agreement, of such
Party, or any judgment, license, permit, order, material agreement or instrument applicable to or
binding upon such Party or any of its assets.

21.1.4 Consent and Approval.

Such Party has sought or obtained, or, in accordance with this Agreement will seek or
obtain, each consent, approval, authorization, order, or acceptance by any Governmental
Authority in connection with the execution, delivery and performance of this Agreement, and the
Party will provide to any Governmental Authority notice of any actions under this Agreement
that are required by Applicable Laws and Regulations.

31

SERVICE AGREEMENT NO. 2880

ARTICLE 22. MISCELLANEOUS

22.1 Binding Effect.

This Agreement and the rights and obligations hereof, shall be binding upon and shall
inure to the benefit of the successors and permitted assigns of the Parties hereto.

22.2 Conflicts.

If there is a discrepancy or conflict between or among the terms and conditions of the
body of this Agreement and the Appendices hereto, the terms and conditions of the body of this
Agreement shall be given precedence over the Appendices, except as otherwise expressly agreed
to in writing by the Parties.

22.3 Rules of Interpretation.

This Agreement, unless a clear contrary intention appears, shall be construed and
interpreted as follows: (1) the singular number includes the plural number and vice versa;
(2) reference to any person includes such person’s successors and assigns but, in the case of a
Party, only if such successors and assigns are permitted by this Agreement, and reference to a
person in a particular capacity excludes such person in any other capacity or individually;
(3) reference to any agreement (including this Agreement), document, instrument or tariff means
such agreement, document, instrument, or tariff as amended or modified and in effect from time
to time in accordance with the terms thereof and, if applicable, the terms hereof; (4) reference to
any Applicable Laws and Regulations means such Applicable Laws and Regulations as
amended, modified, codified, or reenacted, in whole or in part, and in effect from time to time,
including, if applicable, rules and regulations promulgated thereunder; (5) unless expressly stated
otherwise, reference to any Article, Section or Appendix means such Article of this Agreement
or such Appendix to this Agreement, or such Section to the Transmission Interconnection
Procedures or such Appendix to the Transmission Interconnection Procedures as the case may
be; (6) “hereunder,” “hereof,” “herein,” “hereto” and words of similar import shall be deemed
references to this Agreement as a whole and not to any particular Article or other provision
hereof or thereof; (7) “including” (and with correlative meaning “include”) means including
without limiting the generality of any description preceding such term; and (8) relative to the
determination of any period of time, “from” means “from and including,” “to” means “to but
excluding” and “through” means “through and including.”

22.4 Compliance.

Each Party shall perform its obligations under this Agreement in accordance with
Applicable Laws and Regulations, Applicable Reliability Standards, the OATT and Good Utility
Practice. To the extent a Party is required or prevented or limited in taking any action by such
regulations and standards, such Party shall not be deemed to be in Breach of this Agreement for
its compliance therewith. When any Party becomes aware of such a situation, it shall notify the
other Parties promptly so that the Parties can discuss the amendment to this Agreement that is
appropriate under the circumstances.

32

SERVICE AGREEMENT NO. 2880

22.5 Joint and Several Obligations.

Except as otherwise stated herein, the obligations of NYISO, Interconnection Customer,
and System Owner are several, and are neither joint nor joint and several.

22.6 Entire Agreement.

This Agreement, including all Appendices and Schedules attached hereto, constitutes the
entire agreement among the Parties with reference to the subject matter hereof, and supersedes
all prior and contemporaneous understandings or agreements, oral or written, among the Parties
with respect to the subject matter of this Agreement. There are no other agreements,
representations, warranties, or covenants that constitute any part of the consideration for, or any
condition to, either Party’s compliance with its obligations under this Agreement.

22.7 No Third Party Beneficiaries.

This Agreement is not intended to and does not create rights, remedies, or benefits of any
character whatsoever in favor of any persons, corporations, associations, or entities other than the
Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their
successors in interest and permitted their assigns.

22.8 Waiver.

The failure of a Party to this Agreement to insist, on any occasion, upon strict
performance of any provision of this Agreement will not be considered a waiver of any
obligation, right, or duty of, or imposed upon, such Party. Any waiver at any time by any Party
of its rights with respect to this Agreement shall not be deemed a continuing waiver or a waiver
with respect to any other failure to comply with any other obligation, right, duty of this
Agreement. Termination or Default of this Agreement for any reason by an Interconnection
Customer shall not constitute a waiver of such Interconnection Customer’s legal rights to obtain
Capacity Resource Interconnection Service and Energy Resource Interconnection Service from
the NYISO and the relevant System Owner in accordance with the relevant Interconnection
Agreement and the provisions of the OATT. Any waiver of this Agreement shall, if requested,
be provided in writing.

22.9 Headings.

The descriptive headings of the various Articles of this Agreement have been inserted for
convenience of reference only and are of no significance in the interpretation or construction of
this Agreement.

22.10 Multiple Counterparts.

This Agreement may be executed in two or more counterparts, each of which is deemed
an original but all constitute one and the same instrument.

33

SERVICE AGREEMENT NO. 2880

22.11 Amendment.

The Parties may by mutual agreement amend this Agreement, by a written instrument
duly executed by all three of the Parties.

22.12 Modification by the Parties.

The Parties may by mutual agreement amend the Appendices to this Agreement, by a
written instrument duly executed by all three of the Parties. Such an amendment shall become
effective and a part of this Agreement upon satisfaction of all Applicable Laws and Regulations.

22.13 Reservation of Rights.

NYISO and the System Owner shall have the right to make unilateral filings with FERC
to modify this Agreement with respect to any rates, terms and conditions, charges, classifications
of service, rule or regulation under section 205 or any other applicable provision of the Federal
Power Act and FERC’s rules and regulations thereunder, and Interconnection Customer shall
have the right to make a unilateral filing with FERC to modify this Agreement pursuant to
section 206 or any other applicable provision of the Federal Power Act and FERC’s rules and
regulations thereunder; provided that each Party shall have the right to protest any such filing by
another Party and to participate fully in any proceeding before FERC in which such
modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties
or of FERC under sections 205 or 206 of the Federal Power Act and FERC’s rules and
regulations thereunder, except to the extent that the Parties otherwise mutually agree as provided
herein.

22.14 No Partnership.

This Agreement shall not be interpreted or construed to create an association, joint
venture, agency relationship, or partnership among the Parties or to impose any partnership
obligation or partnership liability upon any Party. No Party shall have any right, power or
authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an
agent or representative of, or to otherwise bind, any other Party.

22.15 Other Transmission Rights.

Notwithstanding any other provision of this Agreement, nothing herein shall be construed
as relinquishing or foreclosing any rights, including but not limited to firm transmission rights,
capacity rights, or transmission congestion rights that Interconnection Customer shall be entitled
to, now or in the future under any other agreement or tariff as a result of or otherwise associated
with, the transmission capacity, if any, created by the Upgrades.

22.16 Modifications Related to NYISO’s Compliance with Order No. 2023.

If, as part of the NYISO’s compliance proceeding at the Commission in response to
Order No. 2023, the Commission directs that the NYISO modify the pro forma Standard
Upgrade Construction Agreement located in Appendix 16 of Attachment HH to the ISO OATT,
the Parties shall amend and restate this Agreement to incorporate the modifications; provided,

34

SERVICE AGREEMENT NO. 2880

however, the Parties may agree to include in the amended and restated agreement non-
conforming changes to any terms of the pro forma Standard Upgrade Construction Agreement
that have been modified to comply with the Commission’s order, which non-conforming
modifications must be filed with the Commission for its acceptance.

35

SERVICE AGREEMENT NO. 2880

IN WITNESS WHEREOF, the Parties have executed this Agreement in duplicate
originals, each of which shall constitute and be an original effective Agreement between the
Parties.

New York Independent System Operator, Inc.

By:

Name:

Title:

Date:

Niagara Mohawk Power Corporation d/b/a National Grid

By:

Name:

Title:

Date:

Sithe/Independence Power Partners, L.P.

By:

Name:

Title:

Date:

36

SERVICE AGREEMENT NO. 2880

APPENDICES

Appendix A

Construction Services

Appendix B

Addresses for Delivery of Notices and Billings

Appendix C

In-Service Date

SERVICE AGREEMENT NO. 2880

APPENDIX A

CONSTRUCTION SERVICES

1. Upgrades

System Owner will design, install, and implement the Upgrades set forth in this
Appendix A.

The Upgrades consist of the installation of a series reactor (4.9 Ohms (0.0041pu) on the
345 kV Scriba-Volney Line 20 (“Line 20”) at System Owner’s Volney Substation, as well as
Upgrades at System Owner’s Scriba Station and to Line 20, which will include the following
major electrical equipment and facilities to be designed, installed, and implemented by System
Owner:

A. Volney Substation

Three (3) single phase 345kV series reactors will be installed between breakers R925 and R200 at System Owner’s Volney Substation.

i. Site/Civil/Structure

To accommodate the reactors, the substation yard will need to be expanded by
approximately 49,000 SF to the northeast. Due to the nature of the substation expansion, soil
borings will be required for the foundation design. The location at which the station is being
expanded is approximately 15’-20’ below the finish grade of the station at the lowest point. Fill
will be required to be imported to raise the grade. A new access road will be needed along the
outside of the station expansion for access to the transmission lines to the east of the station. The
station expansion will exceed 1 acre and impact the existing drainage swale around the station
therefore a SWPPP will be needed as well as new storm water remedial measures.

Civil and structural work at Connecting Transmission Owner’s Volney Substation will include installation of:

• three (3) galvanized steel A-frame takeoff structures with caisson foundations;

• one (1) galvanized steel motor operated disconnect switch support structure with

caisson foundation;

• one (1) galvanized steel 1-phase coupling capacitor voltage transformer

(“CCVT”) support structure with caisson foundation;

• three (3) galvanized steel security poles;

• miscellaneous steel on two (2) new A-frame structures required for the disconnect

switches;

A-1

SERVICE AGREEMENT NO. 2880

• additional bus supports with associated foundations; and
• three (3) reinforced concrete pad foundations for the reactors.
 ii. Primary Electrical

The following primary electrical equipment shall be installed at the Volney Substation:

• three (3) 345 KV, 1200MVA, 13mH series reactors;
• three (3) 345 KV 2000A, 3-phase motor operated disconnect switches;
• approximately 1944 ft of 5” inch aluminum bus;
• one (1) 345 KV, CCVT;

• one (1) 345 KV line tuner; and

• one (1) 345 kV, 3K amps, line trap.

The ground grid will be extended to accommodate the reactors and switches. System
Owner will complete a lightning and ground grid study during final engineering to determine if
any additional protection is required.

iii. Secondary Electrical

a. Protection

Due to the addition of the series reactors, an additional CCVT needs to be installed in
order to maintain the power line carrier system currently used for the system ‘B’ protection
package. The existing RFL 9780 carrier used for permissive overreaching transfer trip (“POTT”)
and direct transfer trip (“DTT”) will be modified to accommodate a dual coaxial line tuner by
installing an external hybrid. Both line relay packages will be reset to accommodate the addition
of the reactors.

System Owner will perform an area coordination study.

b. Controls and Integration

The existing remote terminal unit (“RTU”) is sufficient for the scope of the project. New
I/O points will be installed to accommodate the additions required. There is no available space in
the existing cabinet for the additional points therefore a new enclosure cabinet containing a new
Telvent digital input card will be installed to the left of the existing RTU cabinets. RE-01
Control Switch Relays (“CSRs”) with associated test switches will be installed for each of the
motor-operated disconnect switches.

A-2

SERVICE AGREEMENT NO. 2880

c. Telecommunications

A There is no telecommunications scope as the powerline carrier (PLC) communications
system will be maintained.

B. Scriba Station

Line tuning will be required at Scriba Station.

C. Line 20

To accommodate installation of the series reactors at the Volney Substation, the section
of Line 20 from structure 74 into System Owner’s Volney Substation must be reconductored as
depicted in Appendix B. Reconductoring this section of line will require:

• removal of approximately 510 circuit feet (1,530 linear feet) of 2167 ACSR 72/7
 KIWI” and 510 linear feet of 7/16” shield wire between Volney Substation and
 Structure #74 on LN20 circuit; and

• installation of approximately 310 circuit feet (930 linear feet) of 2167 ACSR 72/7

“KIWI” and 310 linear feet of 7/16” EHS Steel shield wire.

2. Upgrades Estimated Total Cost Amount

Interconnection Customer has accepted, and has provided Security to the System Owner
to cover, the following Upgrades Estimated Total Costs identified in the Facilities Study for the
Upgrades: $8,759,800.

The cost estimates provided in this report are in 2022 dollars and are based on the results
of this study and assumptions listed below. Any modifications to the project, as defined herein
and in the FSA, may impact the study results and associated cost estimates and/or schedule.

The estimates provided herein exclude the following, as applicable:

• discussions of issued interconnection study;

• negotiation and execution of agreements;

• overall project sales tax;

• property acquisition;

• property taxes;

• future operation and maintenance costs;

A-3

SERVICE AGREEMENT NO. 2880

• recurring monthly communications circuits’ charges;

• allowance for funds used during construction (AFUDC) assuming Interconnection

Customer upfront payment;

• adverse field conditions such as water, weather, and Interconnection Customer

electrical equipment obstructions; or

• the cost of any temporary construction service.

3. Milestones

Item Milestone Date Responsible Party

1. Execute EPC Agreement Completed System
 Owner/Interconnection

Customer/NYISO

|  | 2. Provide initial prepayment/security for engineering and procurement |  | Completed Interconnection Customer |
| --- | --- | --- | --- |
|  | 3. Issue written authorization to proceed with engineering |  | Completed Interconnection Customer |

4. Project initiation Completed System Owner

|  | 5. Project management level kickoff meeting |  | Completed System Owner/Developer |
| --- | --- | --- | --- |

6. Start engineering Completed System Owner

7. Start procurement Completed System Owner

|  | 8. Provide remainder of Transmission Project Security |  | 03/2025 Developer |
| --- | --- | --- | --- |

9. Complete engineering 03/2025 System
 Owner/Developer

10. Start construction 08/2025 System Owner

11. Complete procurement 02/2025 System Owner

12. Complete construction and testing 03/2026 System Owner

13. In-Service Date 03/2026 System Owner

14. Complete as-builts 07/2026 System Owner

|  | 15. Complete project closeout and final invoicing |  | 10/2026 System Owner |
| --- | --- | --- | --- |

A-4

SERVICE AGREEMENT NO. 2880

4. Security

Interconnection Customer has provided $3,558,200 in cash as security for its Project Cost
Allocation for Network Upgrade Facilities. Interconnection Customer has also provided
$2,900,000 in cash as security for Transmission Project costs under an Engineering and
Procurement Agreement with System Owner.

Interconnection Customer is responsible for providing an additional $2,301,600 in security for
the remainder of its Transmission Project costs. Interconnection Customer has agreed to provide
the remaining Security under this Agreement in the form of cash. Any excess funds of the
Estimated Total Cost Amount will be returned to Interconnection Customer within ten (10)
business days following completion.

A-5

SERVICE AGREEMENT NO. 2880

APPENDIX B

ADDRESSES FOR DELIVERY OF NOTICES AND BILLINGS

Notices:

NYISO:

New York Independent System Operator, Inc.
Attn: Vice President, System and Resource Planning
10 Krey Boulevard Rensselaer, NY 12144 Phone: (518) 356-6000

Email: interconnectionsupport@nyiso.com

System Owner:

Niagara Mohawk Power Corporation d/b/a National Grid

Attn: Vishal Ahirrao, Director, Customer Energy Integration and Commercial Services, NY

2 Hanson Place 12th Floor
Brooklyn, NY 11217 Fax: (781) 907-3002

Email: Vishal.Ahirrao@nationalgrid.com

Interconnection Customer:

Sithe Independence Power Partners, L.P.
Ben Elliott, SVP Renewables / Battery Storage / Fossil Operations
Vistra Corp.

6555 Sierra Drive Irving, TX 75039

Email: ben.elliott@vistracorp.com
 lume.compliance@vistracorp.com

Billings and Payments:

System Owner:

Niagara Mohawk Power Corporation d/b/a National Grid

Attn: Vishal Ahirrao, Director, Customer Energy Integration and Commercial Services, NY

2 Hanson Place 12th Floor
Brooklyn, NY 11217 Phone: (781) 907-3002

B-1

SERVICE AGREEMENT NO. 2880

Interconnection Customer:

Sithe Independence Power Partners, L.P.
Attn: Plant Manager 76 Independence Way Oswego, NY 13126 Phone: (315) 349-5117

Email: eric.pahl@vistracorp.com

With copy to:

Ben Elliott, SVP Renewables / Battery Storage / Fossil Operations
Vistra Corp.

6555 Sierra Drive Irving, TX 75039

Email: ben.elliott@vistracorp.com
 lume.compliance@vistracorp.com

Alternative Forms of Delivery of Notices (telephone, facsimile or email):

NYISO:

New York Independent System Operator, Inc.
Attn: Vice President, System and Resource Planning
10 Krey Boulevard Rensselaer, NY 12144 Phone: (518) 356-6000

Email: interconnectionsupport@nyiso.com

System Owner:

Niagara Mohawk Power Corporation d/b/a National Grid

Attn: Vishal Ahirrao, Director, Customer Energy Integration and Commercial Services, NY

2 Hanson Place 12th Floor
Brooklyn, NY 11217 Fax: (781) 907-3002

Email: Vishal.Ahirrao@nationalgrid.com

Interconnection Customer:

Sithe Independence Power Partners, L.P.
Ben Elliott, SVP Renewables / Battery Storage / Fossil Operations
Vistra Corp.

6555 Sierra Drive Irving, TX 75039

Email: ben.elliott@vistracorp.com

B-2

SERVICE AGREEMENT NO. 2880

lume.compliance@vistracorp.com

B-3

SERVICE AGREEMENT NO. 2880

APPENDIX C

IN-SERVICE DATE

[Date]

New York Independent System Operator, Inc.
Attn: Vice President, System and Resource Planning
10 Krey Boulevard Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid

Attn: Vishal Ahirrao, Director, Customer Energy Integration and Commercial Services, NY

12 Hanson Place, 12th Floor
Brooklyn, NY 11217

Sithe Independence Power Partners, L.P.
Ben Elliott, SVP Renewables / Battery Storage / Fossil Operations
Vistra Corp.

6555 Sierra Drive

Re: Scriba-Volney Series Reactor Project Upgrades
Dear :

On [Date] [System Owner/Interconnection Customer] has completed the Upgrades. This
letter confirms that [describe Upgrades] have commenced service, effective as of [Date plus
one day].

Thank you.

[Signature]

[Interconnection Customer’s/System Owner’s Representative]

C-1