UNITED STATES OF AMERICA 
	BEFORE THE

FEDERAL ENERGY REGULATORY COMMISSION

)

Air Energy TCI, Inc.	)	Docket No. ER13-296-000

)

MOTION TO INTERVENE AND COMMENTS OF

THE NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.

Pursuant to Rules 212 and 213 of the Federal Energy Regulatory Commission’s

(“Commission”) Rules of Practice and Procedure,1 the New York Independent System Operator, Inc. (“NYISO”) moves to intervene and submits comments in the above-referenced proceeding. The NYISO requests that the Commission consider these comments in the event the Commission grants the relief requested.

I.	Background

On November 1, 2012, Air Energy TCI, Inc. (“TCI”), the developer of Crown City Wind 
Farm,2 filed a request for waiver of a tariff-imposed deadline so that the developer may have 
additional time to meet its regulatory milestone.  TCI specifically requests waiver of the 
requirement in Attachment S of the NYISO Open Access Transmission Tariff (“OATT”) that 
requires a project to satisfy the regulatory milestone described in Section 25.6.3.2.1.1 within two 
years from the later of January 17, 2010 or the date the NYISO’s Operating Committee approved

1 18 C.F.R. §§ 385.212 and 385.214 (2012).

2  TCI refers to the project in its waiver request as the “Crown City Wind Energy Project,” however the

Interconnection Request for the project referred to the project as the “Crown City Wind Farm,” which is how the

project was listed on the NYISO interconnection queue.  The project was listed in the NYISO interconnection queue at Queue Position 276.

of the Interconnection System Reliability Impact Study for the project.”3  A project that fails to satisfy the regulatory milestone within this period “will be deemed to be withdrawn in 
accordance with Section 30.3.6 of the Large Facility Interconnection Procedures (“LFIP”) 
contained in Attachment X.”4

Under the NYISO’s OATT, Large Facilities such as the Crown City Wind Energy Project 
are required to enter a Class Year Interconnection Facilities Study (“Class Year Study”).  A 
project becomes eligible to enter a Class Year Study when it has satisfied the two developmental 
milestones identified in Attachment S of the OATT.  As described in the waiver request, the 
Crown City Wind Energy Project satisfied one of its two milestones by securing Operating 
Committee approval of its Interconnection System Reliability Impact Study.  The 
Interconnection System Reliability Impact Study for the Crown City Project was approved by the 
NYISO’s Operating Committee on October 7, 2010.  Therefore, TCI was required to complete 
its second milestone - the regulatory milestone required by Attachment S, Section 25.6.2.3.1.15

- by October 7, 2012 in order to remain in the NYISO interconnection queue and be eligible to enter into a Class Year.6

TCI, however, failed to complete the regulatory milestone by October 7, 2012.  NYISO 
issued a withdrawal notice to TCI on October 11, 2012 pursuant to Section 325.6.2.3.2 deeming

3  See Section 25.6.2.3.2 of Attachment S to the OATT.  While TCI provides incorrect citations to the relevant

section of Attachment S, these appear to be mere typographical errors, as it is clear from the context of TCI’s waiver request that the section for which it is requesting a waiver is 25.6.2.3.2 of Attachment S.

4  See Id.

5 TCI asserts that the two-year timeline expired October 9, 2012 because October 7, 2012 was a Sunday and October 8, 2012 was a federal holiday.

6 With respect to TCI’s representation that the next Class Year will not form “until March 1, 2013, at the earliest,”

the NYISO provides the following clarification:  Under the NYISO’s current OATT, the next Class Year would start on March 1, 2013; however, NYISO’s stakeholders recently approved proposed revisions to the NYISO’s OATT that would provide for a later start date for the Class Year subsequent to Class Year 2012.  The NYISO will file 
these proposed tariff revisions with the Commission shortly.

2

the project withdrawn in accordance with Section 30.3.6 of Attachment X.  Under Section 30.3.6 of the LFIP, the Project has fifteen business days from receipt of the withdrawal letter “to either respond with information or actions that cure the deficiency or to notify the NYISO of its intent to pursue Dispute Resolution.”  The NYISO received no notice within this fifteen day cure 
period -- that expired on November 1, 2012 -- curing the deficiency.  By letter dated November 5, 2012, the NYISO advised TCI that the Crown City Wind Farm had been withdrawn from the NYISO interconnection queue.7

II.	Motion to Intervene

The NYISO is the independent body responsible for providing open access transmission 
service, maintaining reliability, and administering competitive wholesale markets for electricity, 
capacity, and ancillary services in New York State.  Additionally, the NYISO administers the 
interconnection process pursuant to its Commission-approved tariffs.  In this proceeding, TCI is 
requesting waiver of a requirement of the interconnection process established by the NYISO OATT.

The NYISO, therefore, has a unique interest in this proceeding that cannot be adequately

represented by any other entity and, therefore, should be permitted to intervene with all the rights of a party.

III.	Comments

The NYISO takes no position on the merits of TCI’s request for a waiver, but notes that 
the Crown City Wind Farm is free to submit a new Interconnection Request in the event the 
Commission does not grant the requested waiver.  In addition, the NYISO respectfully requests

7 The withdrawal of the Q276 Crown City Wind Farm from the interconnection queue will be reflected on the public 
queue posted on the NYISO website in the next regularly scheduled update to the queue posting in early December 
2012.

3

that the Commission address the following in any Order granting the County’s requested relief in 
order for the NYISO to properly implement any relief the Commission may order. 
	The NYISO understands TCI’s request as requesting (1) that the tariff-mandated deadline for meeting the regulatory milestone not apply to the Crown City Wind Farm; (2) that the Crown City Wind Farm be provided a forty-five (45) day extension within which to complete the 
regulatory milestone required by Section 25.6.2.3.1.1 of Attachment S  -- until December 17, 
2012 (forty-five (45) days from November 1, 2012 expiration of the cure period for the 
withdrawal letter the NYISO issued on October 11, 2012); and (3) that upon satisfaction of the 
Section 25.6.2.3.1.1 milestone within this extended time period, NYISO reinstate the Crown City 
Wind Farm in the NYISO interconnection queue.  Should the Commission grant TCI’s request, 
the NYISO requests that such Order clarify whether the extension until December 17, 2012 is the 
maximum time permitted for TCI to satisfy the regulatory milestone or whether the fifteen (15) 
business day cure period provided in Section 30.3.6 of Attachment X will apply to further extend 
the requested extension in the event the Crown City Wind Farm is unable to satisfy the requisite 
milestone by December 17, 2012.

Furthermore, the NYISO is concerned that a waiver in this proceeding may raise

questions regarding the applicability of the same regulatory milestone requirement to other projects.8  This is particularly true given that this is a substantive milestone reflecting the progress of the project, rather than an administrative deadline.

8  As the Commission emphasized in one of the few instances in which it has granted a waiver of tariff-mandated 
deadlines in the NYISO’s interconnection procedures, “we emphasize the importance of meeting [ ] deadlines and

note that in the future, we expect parties to arrange for [compliance with such deadlines] to be submitted in

sufficient time to meet the requirements of their tariffs.”  See Innovative Energy Systems, LLC, 131 FERC ¶ 61,066 (2010) (waiver of developer’s obligation as a  Class Year 2008 project  to submit a security deposit to its Connecting Transmission Owner within a date prescribed by Attachment S).

4

IV.	Communications and Correspondence

All communications and service with regard to this filing should be directed to:

Robert E. Fernandez, General Counsel

Raymond Stalter, Director of Regulatory Affairs Karen Georgenson Gach, Deputy General Counsel Sara B. Keegan, Senior Attorney*

New York Independent System Operator, Inc.

10 Krey Boulevard

Rensselaer, NY 12144 
Tel:  (518) 356-8554 
Fax:  (518) 356-7678

* Persons designated for receipt of service.

V.	Conclusion

WHEREFORE, for the foregoing reasons, the NYISO respectfully requests that the

Commission (i) grant this motion to intervene, and (ii) consider these comments in making its decision on the TCI’s request.

Respectfully submitted,

/s/ Sara B. Keegan

Sara B. Keegan 
Senior Attorney

New York Independent System Operator, Inc.

November 21, 2012

5

CERTIFICATE OF SERVICE

I hereby certify that I have this day served the foregoing document upon each person

designated on the official service list compiled by the Secretary in this proceeding in accordance with the requirements of Rule 2010 of the Rules of Practice and Procedure, 18 C.F.R. §385.2010. 
	Dated at Rensselaer, NY this 21st day of November, 2012.

/s/ Joy A. Zimberlin

Joy A. Zimberlin

New York Independent System Operator, Inc.

10 Krey Blvd.

Rensselaer, NY 12144 (518) 356-6207