UNITED STATES OF AMERICA 
	BEFORE THE

FEDERAL ENERGY REGULATORY COMMISSION

)

New York Independent System Operator, Inc.	)	Docket No. ER13-102-006

)

REQUEST FOR LEAVE TO ANSWER AND ANSWER OF 
NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.

Pursuant to Rule 213 of the Commission’s1 Rules of Practice and Procedure,2 the New 
York Independent System Operator, Inc. (“NYISO”) respectfully submits this request for leave 
to answer and answer (“Answer”) of the protest of LS Power (“Protest”).3  LS Power’s Protest of 
the Filing Parties’ September 15, 2014, supplemental compliance filing (“Compliance Filing”)4 
fundamentally mischaracterizes the Filing Parties’ proposal.  The Protest also impermissibly 
collaterally attacks an issue that the Commission has already resolved.  The Commission should, 
therefore, reject LS Power’s Protest in its entirety, accept the Compliance Filing, and find that 
the Filing Parties have fully complied with the regional transmission planning and cost allocation 
requirements of Order No. 10005 and the Commission’s July 17, 2014, order in this proceeding 
(“July 2014 Order”).6

1 Capitalized terms not defined in this Answer shall have the meaning set forth in Section 31.1.1 of Attachment Y of the NYISO OATT, and if not therein, in Section 1 of the OATT.

2 18 C.F.R. § 385.213 (2013).

3 New York Independent System Operator, Inc. and New York Transmission Owners, Protest of LS Power Transmission, LLC and LSP Transmission Holdings, LLC, Docket No. ER13-102-006 
(October 6, 2014) (“LS Power Protest”).  In the Answer, “LS Power” refers to LS Power Transmission, LLC and LSP Transmission Holdings, LLC.

4 New York Independent System Operator, Inc. and New York Transmission Owners, Compliance Filing, Docket No. ER13-102-006 (September 15, 2014) (“Compliance Filing”).  The “Filing Parties” are the NYISO and the New York Transmission Owners.

5 Transmission Planning and Cost Allocation by Transmission Owning and Operating Public 
Utilities, Order No. 1000, 136 FERC ¶ 61,051 (2011) (“Order No. 1000”), order on reh’g and 
clarification, Order No. 1000-A, 139 FERC ¶ 61,132 (2012) (“Order No. 1000-A”), order on reh’g and 
clarification, 141 FERC ¶ 61,044 (2012) (“Order No. 1000-B”).  For convenience, unless otherwise

1

I.  REQUEST FOR LEAVE TO ANSWER

The Commission has discretion to, and routinely accepts, answers to protests where, as here, they help to clarify complex issues, provide additional information, are otherwise helpful in the development of the record in a proceeding, or assist in the decision-making process.7  The NYISO’s Answer to LS Power’s Protest satisfies those standards and should be accepted because it addresses inaccurate or misleading statements, and provides additional information that will help the Commission fully evaluate the arguments in this proceeding.

II.  BACKGROUND

The July 2014 Order accepted that the NYISO may direct a Responsible Transmission 
Owner to proceed with the development of a regulated backstop solution8 in parallel with an 
alternative regulated transmission solution selected by the NYISO as the more efficient or cost-
effective transmission solution to ensure that a Reliability Need is satisfied.9  However, the July

specified, references in this filing to “Order No. 1000” should be understood to encompass Order Nos. 1000, 1000-A, and 1000-B.

6 New York Independent System Operator, Inc., Order on Rehearing and Compliance, 148 FERC ¶ 61,044 (2014) (“July 2014 Order”).

7 See, e.g., Southern California Edison Co., 135 FERC ¶ 61,093 at P 16 (2011) (accepting

answers to protests “because those answers provided information that assisted  [the Commission] in [its] decision-making process”); New York Independent System Operator, Inc., 134 FERC ¶ 61,058 at P 24 (2011) (accepting the answers to protests and answers because they provided information that aided the Commission in better understanding the matters at issue in the proceeding); New York Independent 
System Operator, Inc., 140 FERC ¶ 61,160 at P 13 (2012) and PJM Interconnection, LLC, 132 FERC ¶ 61,217 at P 9 (2010) (accepting answers to answers and protests because they assisted in the 
Commission’s decision-making process).

8 The NYTOs have a legal obligation to prepare a regulated backstop solution to an identified

Reliability Need if designated by the NYISO as the Responsible Transmission Owner.  This obligation is 
set forth in Attachment Y of the OATT and was memorialized by the NYTOs in a contract with the 
NYISO, which was accepted for filing by the Commission.  Section 31.2.4.3.1 of Attachment Y of the 
OATT; Agreement Between the New York Independent System Operator, Inc. and the New York 
Transmission Owners on the Comprehensive Planning Process for Reliability Needs (June 10, 2010), 
available at:

http://www.nyiso.com/public/webdocs/markets_operations/documents/Legal_and_Regulatory/Agreements 
/NYISO/Comprehensive_Planning_Process_for_Reliability_Needs_Agreement.pdf

9 July 2014 Order at PP 72-75.

2

2014 Order indicated that Sections 31.2.8.1.3 and 31.2.8.2.1 of Attachment Y of the NYISO

Open Access Transmission Tariff (“OATT”) were unclear regarding the circumstances in which the NYISO would determine, prior to or at the Trigger Date10 of the regulated backstop solution, that it was necessary to direct the Responsible Transmission Owner to proceed with the regulated backstop solution.11  The July 2014 Order, therefore, directed the Filing Parties to propose tariff revisions to explain the process by which the NYISO will make its determination.12

In response, the Compliance Filing proposed revisions to Section 31.2.8.1.3 of the

OATT.  Section 31.2.8.1.3 addresses the scenario in which the Trigger Date for the selected

alternative regulated transmission solution precedes the Trigger Date for the regulated backstop 
solution.  It sets forth that the NYISO will direct an Other Developer or Transmission Owner to 
proceed to develop its selected alternative regulated transmission solution at its project’s Trigger 
Date.

The proposed compliance revisions specify that, prior to the Trigger Date of the regulated 
backstop solution, the NYISO will review the status of the development of the selected solution 
to determine its ability to timely enter service to satisfy a Reliability Need.  The revised Section

31.2.8.1.3 sets forth a non-exhaustive list of factors the NYISO will consider in reviewing the 
status of the selected solution, including whether the Other Developer or Transmission Owner 
developing that solution: (i) has executed a development agreement with the NYISO, (ii) has 
provided important milestone data to the NYISO, and (iii) has received its siting permits and 
authorizations under Article VII of the New York State Public Service Law or other applicable

10  As defined in Section 31.1.1 of Attachment Y of the OATT, Trigger Date means “[t]he date by which the ISO must request implementation of a regulated backstop solution or an alternative regulated solution pursuant to Section 31.2.8 in order to meet a Reliability Need.”

11 July 2014 Order at P 75.

12 Id.

3

New York State law.  Based on its review, the NYISO will determine prior to or at the Trigger 
Date of the regulated backstop solution whether it is necessary to direct the Responsible 
Transmission Owner to proceed with the development of its regulated backstop solution to 
ensure that the identified Reliability Need can be satisfied by the need date.  The NYISO will 
report to stakeholders the reasons for its determination based upon the conclusions of its review.

III.  ANSWER

A. 	LS Power Incorrectly Describes the NYISO’s Process for Determining

Whether to Trigger a Regulated Backstop Solution.

LS Power incorrectly states that the NYISO will not make an actual determination

regarding the need to trigger a regulated backstop solution, but would instead focus solely on 
whether or not the selected alternative regulated transmission solution has received its required 
permits, resulting in a mere “check-the-box” exercise.13  In actuality, the Filing Parties’ tariff 
revisions provide that the NYISO will consider the totality of the circumstances regarding the 
status of the selected solution.14  If the NYISO determines, based on this review, that the selected 
solution has not progressed sufficiently to ensure that the Reliability Need will be satisfied by the 
need date, and that it is necessary to trigger the regulated backstop solution, it will report to 
stakeholders the reasons for its determination.  The extent to which the selected solution has 
satisfied the factors explicitly listed in Section 31.2.8.1.3, including whether the project has 
received the necessary permits, will certainly inform the NYISO’s analysis.  However, as a plain 
reading of the revised language in Section 31.2.8.1.3 makes clear, the proposed tariff revisions in 
no way limit the factors that the NYISO can consider in making its determination, nor does

13 LS Power Protest at pp 3, 5-7.

14 As the NYISO has previously informed the Commission, a non-incumbent developer, unlike a Responsible Transmission Owner, does not have an obligation to construct its selected alternative 
regulated transmission solution and is free to discontinue its proposed project at any time.

4

Section 31.2.8.1.3 provide that the NYISO will automatically trigger the regulated backstop 
solution simply because the selected solution has not yet received its necessary permits.

B. 	LS Power Incorrectly Suggests that the NYISO Could Reasonably Determine

that a Project Will Actually Be Constructed and Satisfy the Reliability Need Based Solely on the Results of the NYISO’s Viability, Sufficiency, and 
Selection Processes.

LS Power incorrectly suggests that the NYISO does not need to take any steps beyond its 
evaluation of an alternative regulated transmission solution in the viability, sufficiency, and 
selection phases of the reliability planning process to have a reasonable assurance that the 
selected solution will actually be able to complete permitting, construction and commissioning to 
satisfy the Reliability Need by the need date.15  The NYISO’s analysis in the initial sufficiency 
and viability phase of the reliability planning process, however, enables it to make only a 
preliminary determination regarding a proposed project’s ability to satisfy the Reliability Need. 
This phase of the planning process will occur years before the actual project begins construction 
and is based on initial project information that is subject to further development and revision by 
the developer.  Given that bulk power system reliability is at stake, the NYISO naturally will 
monitor the progress of the selected solution to ensure that it will be able to complete and enter 
service in time.

Similarly, the NYISO’s review of the alternative regulated transmission solution using 
the selection metrics referenced by LS Power does not provide reasonable assurance that the 
selected project will be in service in time to satisfy the Reliability Need.  For example Section

31.2.6.5.1.6 concerns whether the developer has obtained the property rights required to

implement the project.  This metric does not, however, require the developer to possess those

rights at the time of selection.  The NYISO could determine that a developer satisfies this metric

15  LS Power Protest at pp 5-6.

5

because it “has specified a plan or approach for determining routing and acquiring property 
rights.”16  A developer’s plan for addressing the acquisition of property rights under Section

31.2.6.5.1.6 or addressing potential issues with delays under Section 31.2.6.5.1.7 does not

provide reasonable assurance that the developer will be able to satisfy the Reliability Need or

take into account changes in circumstances that occur between the NYISO’s selection of a

project and its decision to trigger a regulated project to proceed.  The NYISO will re-evaluate the developer’s progress in carrying out its plan to obtain property rights, as well as other 
milestones, in deciding whether to trigger a regulated backstop solution to proceed in parallel 
with the selected solution.

C. 	The Commission Must Reject LS Power’s Collateral Attack on the

Commission’s Acceptance of the NYISO’s Ability to Trigger a Regulated Backstop Solution in Parallel with a Selected Alternative Regulated 
Transmission Solution.

The Commission must reject LS Power’s argument that the NYISO’s triggering of a

regulated backstop solution shifts project selection from the NYISO to the New York State

Public Service Commission.17  The argument is nothing more than a collateral attack on the July 
2014 Order’s determinations that: (i) the NYISO has satisfied the requirement to have a process 
to evaluate and select the more efficient or cost-effective transmission solutions to meet regional 
transmission needs,18 and (ii) the NYISO’s process to trigger a regulated backstop solution in 
parallel with a selected alternative regulated transmission solution under certain circumstances is

16 OATT, Attachment Y, Section 31.2.6.5.1.6.

17 LS Power Protest at p 7.

18 July 2014 Order at P 73.

6

permissible under Order No. 1000.19  The July 2014 Order firmly rejected LS Power’s protests 
regarding the NYISO’s ability to trigger a regulated backstop solution.20 
	Nothing in the Compliance Filing changes the NYISO’s process for selecting the more efficient or cost-effective transmission solution for purposes of cost allocation under the 
NYISO’s tariffs.  The Compliance Filing simply clarifies, as directed by the Commission, the 
circumstances under which the NYISO determines whether to trigger a regulated backstop 
solution.

D.	The Commission Should Reject LS Power’s Suggested Revisions to Section

31.2.8.1.4 of Attachment Y that Were Not Required under the July 2014

Order.

The Commission should reject LS Power’s challenge to the requirement for triggering the 
regulated backstop solution set forth in Section 31.2.8.1.4 of Attachment Y.21  Section 31.2.8.1.4 
concerns the scenario in which the Trigger Date for the regulated backstop solution precedes the 
Trigger Date for the selected alternative regulated transmission solution.  Under these 
circumstances, the NYISO will trigger both the regulated backstop solution and the selected 
solution at the earlier Trigger Date for the regulated backstop solution. 
	The July 2014 Order did not direct the NYISO to revise the requirements in Section

31.2.8.1.4, and there is no cause for doing so.  Unlike the scenario addressed in Section

31.2.8.1.3 in which the Trigger Date for the selected alternative regulated transmission solution 
comes first, the NYISO will not have the opportunity under the scenario addressed in Section

31.2.8.1.4 to perform a meaningful review of the status of the selected solution before

determining whether to trigger a regulated backstop solution at its earlier Trigger Date.  The

19 July 2014 Order at PP 72-75.

20 July 2014 Order at PP 72-75.

21 LS Power Protest at pp 3-4.

7

Other Developer or Transmission Owner will not have made significant progress in developing the selected solution at the time the NYISO makes its decision on the project or projects to be triggered.  Accordingly, at the time of its triggering decision, the NYISO will not have sufficient information regarding whether the selected solution will timely progress to be constructed and satisfy the Reliability Need.  If the NYISO were to wait until sufficient information becomes available regarding the selected solution, it could be too late to trigger the regulated backstop solution that is required to satisfy the Reliability Need.

Any legitimate concern that LS Power might have that triggering the regulated backstop solution at its earlier Trigger Date could disadvantage the selected alternative regulated 
transmission solution has already been addressed.  Section 31.2.8.1.4 already provides that the NYISO will also trigger the selected solution at the same time as the regulated backstop solution. Moreover, the NYISO will halt the regulated backstop solution once the selected solution 
satisfies the conditions set forth in Section 31.2.8.2.2 of Attachment Y.

IV.  CONCLUSION

WHEREFORE, the New York Independent System Operator, Inc. respectfully requests that the Commission accept this Answer and accept the Compliance Filing in the abovereferenced docket without requiring any modifications.

Respectfully submitted,

/s/ Carl F. Patka

Carl F. Patka

Assistant General Counsel

New York Independent System Operator, Inc.

10 Krey Boulevard

Rensselaer, New York 12144 (518) 356-6220

cpatka@nyiso.com

8

/s/ Michael J. Messonnier, Jr.

Michael J. Messonnier, Jr. Ted J. Murphy

Hunton & Williams LLP Counsel for

New York Independent System Operator, Inc.

October 20, 2014

cc:	Michael Bardee

Gregory Berson

Anna Cochrane

Jignasa Gadani

Morris Margolis

Michael McLaughlin 
David Morenoff 
Daniel Nowak

9

CERTIFICATE OF SERVICE

I hereby certify that I have this day served the foregoing document upon each person

designated on the official service list compiled by the Secretary in this proceeding in accordance with the requirements of Rule 2010 of the Rules of Practice and Procedure, 18 C.F.R. §385.2010. 
	Dated at Rensselaer, NY this 20th day of October, 2014.

/s/ Mohsana Akter

Mohsana Akter

New York Independent System Operator, Inc.

10 Krey Blvd.

Rensselaer, NY 12144 (518) 356-7560