THIS FILING LETTER DOES NOT CONTAIN ANY PRIVILEGED OR

CONFIDENTIAL INFORMATION.  THE BODIES OF THE REPORTS, INCLUDING TABLE 2 IN ATTACHMENT II (MARKED PUBLIC) DO NOT CONTAIN ANY 
PRIVILEGED OR CONFIDENTIAL INFORMATION.  CONFIDENTIAL EXHIBIT A (ATTACHMENT III) INCLUDES UNREDACTED TABLES 2, 4, AND 5 WHICH 
CONTAIN PRIVILEGED AND CONFIDENTIAL INFORMATION, AND ARE 
SUBMITTED SEPARATELY.

June 1, 2017

By Electronic Delivery

Honorable Kimberly D. Bose, Secretary Federal Energy Regulatory Commission 888 First Street, NE

Washington, DC 20426

Re:    New York Independent System Operator, Inc. Semi-Annual Reports on 
	New Generation Projects and Demand Response Programs; Docket Nos. 
	ER03-647-000 and ER01-3001-000

Dear Secretary Bose:

Enclosed for filing in the above-referenced dockets are the New York Independent

System Operator, Inc.’s (“NYISO”) Semi-Annual Reports to the Federal Energy Regulatory

Commission (“Commission”) on the NYISO’s New Generation Projects and Demand Response 
programs in the New York Control Area.  This filing is made for informational purposes only in 
accordance with the Commission’s delegated order issued February 23, 2010 in these dockets.1

I.	Documents Submitted

The NYISO respectfully submits the following documents with this filing letter:

1.	NYISO Semi-Annual Compliance Report on New Generation Projects (including

its Exhibits A and B), June 1, 2017 (“Attachment I”);

1 New York Indep. Sys. Operator, Inc., Docket Nos. ER01-3001 and ER03-647 (Feb. 23,

2010).

Honorable Kimberly D. Bose June 1, 2017

Page 2

2. 	NYISO Semi-Annual Compliance Report on Demand Response Programs, June

1, 2017 - Public (redacted) (“Attachment II”); and

3. 	Confidential Exhibit A to the NYISO Semi-Annual Compliance Report on

Demand Response Programs, June 1, 2017 - CONFIDENTIAL (unredacted) (“Confidential Exhibit A”) (“Attachment III”).

II. 	Request for Confidential Treatment of Confidential Exhibit A to the NYISO

Semi-Annual Compliance Report on Demand Response Programs

The attached Semi-Annual Compliance Report on Demand Response Programs

(“Demand Response Report,” filing Attachment II) summarizes the current status of demand

response participation in the NYISO’s markets as of May 2017.  The Demand Response Report 
redacts confidential, commercially sensitive information in Table 2, and omits Tables 4 and 5 in 
their entirety.  The confidential, unredacted versions of Table 2, as well as the entirety of Tables

4 and 5 are in Confidential Exhibit A (Attachment III), which is labeled as confidential and is being filed separately.

In accordance with Sections 388.107 and 388.112 of the Commission’s regulations,2

Article 6 of the NYISO’s Market Administration and Control Area Services Tariff, and Sections

1.0(4) and 4.0 of the NYISO’s Code of Conduct, the NYISO requests Privileged and

Confidential treatment of the contents of Confidential Exhibit A.  The NYISO also requests that the Confidential Exhibit A be exempted from public disclosure under the Freedom of 
Information Act (“FOIA”), 5 U.S.C. § 522.3

Confidential Exhibit A contains commercially sensitive, trade secret information that is 
not made public by the NYISO.  Disclosure of such information could cause competitive harm to 
the affected Market Participants,4 and could adversely affect competition in the markets 
administered by the NYISO.  This information includes a very limited number of demand 
response Resources in certain Load Zones.  Confidential Exhibit A also contains information on 
NYISO’s Demand Side Ancillary Services Program, and total enrollment for the entire program 
is very limited.  With such a small number of Resources participating in the program, the 
aggregation of the data reported would not sufficiently mask confidential and commercially 
sensitive Market Participant Information.  Further, because this confidential, commercially 
sensitive information is exempt from disclosure under 5 U.S.C. § 522(b)(4), the NYISO requests 
that the contents of Confidential Exhibit A receive Privileged and Confidential treatment and be 
exempt from FOIA disclosure.  Confidential Exhibit A is identified and marked in accordance

2 18 C.F.R. §§ 388.107 and 388.112 (2016).

3 The information provided by the NYISO, for which the NYISO claims an exemption from FOIA disclosure, is labeled “Contains Privileged Information - Do Not Release.”

4 Capitalized terms not otherwise defined herein have the meaning set forth in Section 2 of the NYISO’s Market Administration and Control Area Services Tariff.

Honorable Kimberly D. Bose June 1, 2017

Page 3

with the Commission’s regulations and rules published by the Secretary’s Office for submitting privileged information.5

III.	Communications and Correspondence

All communications and service in this proceeding should be directed to:

Robert E. Fernandez, General Counsel

Raymond Stalter, Director, Regulatory Affairs Gloria Kavanah, Senior Attorney

*Gregory J. Campbell, Attorney

10 Krey Boulevard

Rensselaer, NY 12144 
Tel:  (518) 356-8540 
GCampbell@nyiso.com

*Person designated for receipt of service.

Respectfully submitted,

/s/ Gregory J. Campbell

Gregory J. Campbell Attorney

New York Independent System Operator, Inc.

10 Krey Blvd.

Rensselaer, New York 12144 (518) 356-8540

GCampbell@nyiso.com

cc:	Michael Bardee

Nicole Buell

Anna Cochrane 
Kurt Longo

David Morenoff 
Daniel Nowak 
Larry Parkinson

J. Arnold Quinn 
Douglas Roe

Kathleen Schnorf 
Jamie Simler 
Gary Will

5 Notice of Document Labeling Guidance for Documents Submitted to or Filed with the Commission or Commission Staff (Apr. 14, 2017).

Attachment I

ATTACHMENT I

NYISO June 1, 2017 Report on New Generation Projects

In an October 23, 2006 order, the Commission ordered the NYISO to submit “a list of 
investments in new generation projects in New York (including a description and current status of each such project), regardless of the stage of project development at the time of the filing.”1 The NYISO keeps a list of Interconnection Requests and Transmission Projects for the New 
York Control Area that includes information about all generation projects in the State that have requested interconnection.

The NYISO interconnection process is described in two attachments of the NYISO Open Access Transmission Tariff:  Attachment X entitled, “Standard Large Facility Interconnection Procedures,” and Attachment Z entitled, “Small Generator Interconnection Procedures.” 
Attachment X applies to Generating Facilities that exceed 20 MW in size and to Merchant 
Transmission Facilities, collectively referred to as “Large Facilities.”  Attachment Z applies to Generating Facilities no larger than 20 MW.

Under Attachment X, Developers of Large Facilities must submit an Interconnection 
Request to the NYISO.  The NYISO assigns a Queue Position to all valid Interconnection 
Requests.  Under Attachment X, proposed generation and merchant transmission projects 
undergo up to three studies: the Feasibility Study, the System Reliability Impact Study, and the 
Class Year Interconnection Facilities Study.  The Class Year Interconnection Facilities Study is 
performed on a Class Year basis for a group of eligible projects pursuant to the requirements of 
Attachment S of the NYISO OATT.  Under Attachment Z, proposed small generators undergo a 
process that is similar, but with different paths and options that are dependent on the specific 
circumstances of the project.

Proposed generation and transmission projects currently in the NYISO interconnection 
process are listed on the list of Interconnection Requests and Transmission Projects for the New 
York Control Area (“NYISO Interconnection Queue”).  The generation projects on that list are 
shown in Exhibit A to this Attachment I, which is dated April 30, 2017.  The NYISO updates its 
Interconnection Queue on at least a monthly basis and posts the most recent list on the NYISO’s 
public web site at

http://www.nyiso.com/public/markets_operations/services/planning/documents/index.jsp (in the 
“Interconnection Studies” section).

The status of each project on the NYISO Interconnection Queue is shown in the column 
labeled “S.”  An explanation of this column is provided in Exhibit B to this Attachment I.  Also, 
note that the proposed In-Service Date for each project is the date provided to the NYISO by the 
respective Owner/Developer, is updated only on a periodic basis, and is subject to change.

1 New York Indep. Sys. Operator, Inc., 117 FERC ¶ 61,086, at P 14 (2006).

Interconnection Requests and Transmission Projects

Page 1 of 4

Queue 
	Pos. Owner/Developer

Date 
Project Name 	of IR

SP	WP	Type/ 
(MW) 	(MW) 	Fuel

Location	Interconnection 
County/State 	Z 	Point

Last 
Utility 	S 	Update

Availability  FS Complete/ 
of Studies 	SGIA Tender

Proposed  Proposed 
In-Service 	COD

251	CPV Valley, LLC	CPV Valley Energy Center	7/5/07	677.6	690.6	CC-D	Orange, NY	G	Coopers - Rock Tavern 345kV	NYPA	11	7/31/16	FES, SRIS, FS	10/15/13	2017/06	2018/02

276	Air Energie TCI, Inc.	Crown City Wind Farm	1/30/08	90	90	W	Cortland, NY	C	Cortland - Fenner 115kV	NM-NG	7	1/31/15	FES, SRIS	2018/12	2018/12

331	National Grid	Northeast NY Reinforcement	4/22/09	N/A	N/A    AC	Saratoga, NY	F	NGrid 230kV	NM-NG	12,14	5/31/16	SIS	2010-2019	N/A

333	National Grid	Western NY Reinforcement	5/5/09	N/A	N/A    AC	Cattaraugus, NY	A	NGrid 115kV	NM-NG	12,14	5/31/16	SIS	2015-2019	N/A

338	RG&E	Brown's Race II	8/11/09	6.3	6.3	H	Monroe, NY	B	Station 137 11kV	RG&E	11	11/30/15	None	2018/09	2018/09

339	RG&E	Transmission Reinforcement	8/17/09	N/A	N/A    AC	Monroe, NY	B	Niagara - Kintigh 345kV	RG&E	12	12/31/16	SIS	2019/W	N/A

347	Franklin Wind Farm, LLC	Franklin Wind	12/2/09	50.4	50.4	W	Delaware, NY	E	Oakdale - Delhi 115kV	NYSEG	7	4/30/16	FES, SRIS	2019/10	2019/12

349	Taylor Biomass Energy-Montgomery, LLC	Taylor Biomass	12/30/09	19	22.5	SW	Orange, NY	G	Maybrook - Rock Tavern 69kV	CHGE	12	11/30/16	SRIS, FS	10/15/13	2017/12	2018/04

358	West Point Partners, LLC	West Point Transmission	9/13/10	1000	1000	DC	Greene, Westchester, NY	F, H	Leeds - Buchanan North 345kV	NM-NG/ConEd	7	4/30/17	FES, SRIS	2021/01	2021/05

361	US PowerGen Co.	Luyster Creek Energy	2/15/11	401	444	CC-D	Queens, NY	J	Astoria West Substation 138kV	CONED	7	1/31/15	FES, SRIS	2017/06	2017/06

363	Poseidon Transmission 1, LLC	Poseidon Transmission	4/27/11	500	500	DC	NJ - Suffolk, NY	K	Ruland Rd. 138kV	LIPA	10	2/28/17	FES, SRIS, FS	2/2/2017	2020/03	2020/06

367	Orange & Rockland	North Rockland Transformer	9/14/11	N/A	N/A    AC	Rockland, NY	G	Line Y94 345kV	ConEd	6	5/31/16	SIS	2018/06	N/A

371	South Mountain Wind, LLC	South Mountain Wind	10/31/11	18	18	W	Delaware, NY	E	River Rd Substation 46kV	NYSEG	7	10/31/14	None	2017/12	2017/12

372	Dry Lots Wind, LLC	Dry Lots Wind	10/31/11	33	33	W	Herkimer, NY	E	Schuyler - Whitesboro 46kV	NM-NG	7	1/31/15	FES, SRIS	2017/11	2017/11

382	Astoria Generating Co.	South Pier Improvement	5/30/12	91.2	95.5	CT-NG  Kings, NY	J	Gowanus Substation 138kV	ConEd	7	4/30/16	SRIS	2018/06	2018/06

383	NRG Energy, Inc.	Bowline Gen. Station Unit #3	5/30/12	775	814	CC-NG Rockland, NY	G	Ladentown Subsation 345kV	O&R/ConEd	7	6/30/16	SRIS	2022/01	2022/06

386	Vermont Green Line Devco, LLC	Grand Isle Intertie	6/28/12	400	400	DC	Clinton, NY - VT	D	Plattsburgh 230kV-New Haven, VT 345kV	NYPA	7	9/30/16	FES, SRIS	2018/06	2018/06

387	Cassadaga Wind, LLC	Cassadaga Wind	7/19/12	126	126	W	Chautauqua, NY	A	Dunkirk - Moon Station 115 kV	NM-NG	9	4/30/17	FES, SRIS	2019/09	2019/12

393	NRG Berrians East Development, LLC	Berrians East Repower	10/16/12	102.3	53	CC-D	Queens , NY	J	Astoria East Substation 138kV	CONED	9	4/30/17	FES, SRIS	2018/06	2018/06

395	Copenhagen Wind Farm, LLC	Copenhagen Wind	11/12/12	79.9	79.9	W	Lewis, NY	E	Black River-Lighthouse Hill 115kV   NM-NG	10	2/28/17	FES, SRIS, FS	2/2/2017	2018/05	2018/05

396	Baron Winds, LLC	Baron Winds	11/30/12	300	300	W	Steuben, NY	C	Hillside - Meyer 230kV	NYSEG	7	4/30/17	FES, SRIS	2019/09	2019/12

396A	New York State Electric & Gas	Wood Street Transformer	12/14/12	N/A	N/A    AC	Putnum, NY	G	Wood St. 345/115kV	NYSEG	6	5/31/16	SIS	2021/12	N/A

398	Black Oak Wind Farm, LLC	Black Oak Wind	1/10/13	12.5	12.5	W	Tompkins, NY	C	Montour - Coddington 115kV	NYSEG	10	11/30/16	None	8/28/15	2018/01	2018/03

401	Caithness Long Island II, LLC	Caithness Long Island II	3/22/13	744	807	CC-D	Suffolk, NY	K	Sills Road Substation 138kV	LIPA	8	1/31/17	SRIS	2018/04	2019/05

403	PSEG Power New York	Bethlehem Energy Center Up	5/28/13	72	51.2	CC-D	Albany, NY	F	Bethlehem Energy Center	NM-NG	10	2/28/17	FES, SRIS, FS	2/2/2017	2017-2019	2017-2019

414	North America Transmission, LLC Segment B Enhanced	9/5/13	N/A	N/A    AC	Albany-Dutchess, NY F, G	New Scotland - P. Valley 345kV	NM-NG/ConEd	5	3/31/17	None	2019	2019

421	EDP Renewables North America	Arkwright Summit	11/1/13	78	78	W	Chautauqua, NY	A	Dunkirk - Falconer 115 kV	NM-NG	9	11/30/16	SRIS	2017/10	2017/11

422	NextEra Energy Resources, LLC	Eight Point Wind Energy Center	11/7/13	101.2	101.2	W	Steuben-Allegany, NY  B	Bennett 115kV	NYSEG	9	4/30/17	FES, SRIS	2018/12	2018/12

429	Orange & Rockland	North Rockland Station	2/12/14	N/A	N/A    AC	Rockland, NY	G	Line Y88 345kV	ConEd	6	5/31/16	SIS	2018/06	N/A

430	H.Q. Energy Services U.S. Inc.	Cedar Rapids Transmission	3/5/14	N/A	N/A    AC	St. Lawrence, NY	E	Dennison - Alcoa 115kV	NM-NG	7	2/28/17	SIS	2017/Q1	N/A

431	Greenidge Generation	Greenidge Unit #4	4/11/14	106.3	106.3	ST-NG  Yates, NY	C	Greenidge Substation 115kV	NYSEG	14	3/31/17	SRIS, FS	I/S	I/S

432	New York State Electric & Gas	South Perry Transformer	4/15/14	N/A	N/A    AC	Wyoming, NY	B	South Perry Substation 115kV	NYSEG	5	4/30/17	None	2019/07	N/A

440	Erie Power, LLC	Erie Power	6/2/14	79.4	88	CC-NG Chautauqua, NY	A	South Ripley Substation 230kV	NM-NG	9	11/30/16	SRIS	2017/08	2017/08

444	Cricket Valley Energy Center, LLCCricket Valley Energy Center II	6/18/14	1020	1132	CC-NG Dutchess, NY	G	Pleasant Valley - Long Mt. 345kV	ConEd	9, 11	3/31/17	SRIS	2017/12	2019/08

445	Lighthouse Wind, LLC	Lighthouse Wind	6/30/14	201.3	201.3	W	Niagara, NY	A	AES Somerset Substation 345kV    NYSEG	7	8/31/16	FES, SRIS	2017/09	2017/12

448	Alps Interconnector, LLC	Alps HVDC	8/12/14	600	600	DC	NE-Rensselaer, NY	F	Alps Substation 345kV	NM-NG	5	1/31/16	FES	2019/06	2019/06

449	Stockbridge Wind, LLC	Stockbridge Wind	8/13/14	72.6	72.6	W	Madison, NY	E	Whitman - Oneida 115kV	NM-NG	7	11/30/16	FES	2019/08	2019/12

458	TDI-USA Holdings, Inc.	CH Interconnection	10/24/14	1000	1000	DC	Quebec - NY, NY	J	Astoria Annex Substation 345kV	NYPA	7	4/30/17	FES, SRIS	2021/Q1	2021/Q2

461	Consolidated Edison Co. of NY   East River 1 Uprate	12/1/14	2	2	CT-NG  New York, NY	J	East River Complex	ConEd	9, 14	4/30/17	SRIS, FS	2/2/2017	I/S	I/S

462	Consolidated Edison Co. of NY   East River 2 Uprate	12/1/14	2	2	CT-NG  New York, NY	J	East River Complex	ConEd	9, 14	4/30/17	SRIS, FS	2/2/2017	I/S	I/S

465	Hudson Transmssion Partners    Hudson Transmission NY to PJM	12/15/14	675	675	DC/AC  New York, NY	J	W49th St 345kV - Bergen 230kV	ConEd	7	7/31/16	SRIS	2017/06	2017/06

466	Atlantic Wind, LLC	Bone Run Win	12/16/14	132	132	W	Cattaraugus, NY	A	Falconer - Homer Hill 115kV	NM-NG	7	11/30/16	FES, SRIS	2019/12	2019/12

467	Invenergy Solar Development, LLCShoreham Solar	12/22/14	25	25	S	Suffolk, NY	K	Ridge - Wildwood 69kV	LIPA	9	3/31/17	SRIS	2018/06	2018/06

468	Apex Clean Energy LLC	Galloo Island Wind	12/30/14	110.4	110.4	W	Oswego, NY	C	Hammermill - Wine Creek 115kV    NM-NG	7	4/30/17	FES, SRIS	2019/10	2019/12

473	Calverton Solar LLC	Calverton Solar	1/21/15	10	10	S	Suffolk, NY	K	Riverhead - Wildwood 69kV	LIPA	5	12/31/16	FES	2017/Q3	2017/Q3

474	EDP Renewables North America	North Slope Wind	1/30/15	200	200	W	Franklin-Clinton, NY	D	Patnode 230kV	NYPA	7	3/31/17	FES, SRIS	2021/10	2021/10

477	Riverhead Solar Farm LLC	Riverhead Solar	2/18/15	20	20	S	Suffolk, NY	K	Edwards Substation 138kV	LIPA	7	4/30/17	FES, SIS	2018/10	2018/10

487	LI Energy Storage System	Far Rockaway Battery Storage	3/9/15	20	20	ES	Suffolk, NY	K	Far Rockaway Substation 69kV	LIPA	3	4/30/16	None	2018/10	2018/10

20170601_NYISONewGnrtnRprt_ExhibitA.xlsx	Updated: 04/30/2017

Interconnection Requests and Transmission Projects

Page 2 of 4

Queue 
	Pos. Owner/Developer

Date 
Project Name 	of IR

SP	WP	Type/ 
(MW) 	(MW) 	Fuel

Location	Interconnection 
County/State 	Z 	Point

Last 
Utility 	S 	Update

Availability  FS Complete/ 
of Studies 	SGIA Tender

Proposed  Proposed 
In-Service 	COD

494	Alabama Ledge Wind Farm LLC

495	Mohawk Solar LLC

496	Renovo Energy Center, LLL

497	Invenergy Wind Development LLC

498	ESC Tioga County Power, LLC

505	RES America Devlopments Inc.

506	Empire State Connector Corp.

510	Bayonne Energy Center

511	AG Energy, LP

512	Northbrook Lyons Falls

513	Stony Creek Energy LLC

514	RES Americas Developments Inc.

515	North Bergen Liberty Energy Center LLC

516	East Coast Power LLC

518	PPL Electric Utilities

519	Canisteo Wind Energy LLC

520	EDP Renewables North America

521	Invenergy NY, LLC

522	NYC Energy LLC

523	Dunkirk Power LLC

524	Dunkirk Power LLC

525	New York Power Authority

526	Atlantic Wind, LLC

527	Atlantic Wind, LLC

528	National Grid

529	National Grid

530	NextEra Energy New York

531	Invenergy Wind Development LLC

532	RES America Devlopments LLC

533	Delano Management LLC

534	OneEnergy Development, LLC

535	FTS DevCo LLC

536	Empire Interconnection LLC

537	NextEra Energy New York

Alabama Ledge Wind Mohawk Solar

Renovo Energy Center Bull Run Wind

Tioga County Power Ball Hill Wind

Empire State Connector Bayonne Energy Center II Ogdensburg

Lyons Fills Mill Hydro Orangeville

Empire Wind

Liberty Generation 
Linden Cogen Uprate Compass

Canisteo Wind

Rolling Upland Wind Bull Run II Wind

NYC Energy 
Dunkirk Unit 2

Dunkirk Unit 3 & 4

Western NY Energy Link North Ridge Wind

Horse Creek Wind

Moderate Power Transfer High Power Transfer

Empire State Line 
Number 3 Wind Energy Allegany Wind

Empire Interconnection Great Valley Solar

Riverhead Expansion Glenwood

Segment A

3/31/15	79.8	79.8

4/2/15	98	98

4/13/15	480	504

4/24/15	303.6	303.6

4/29/15	550	550

6/2/15	100	100

6/10/15	1000	1000

8/3/15	120.4	129.4

9/4/15	79	90.1

9/11/15	14.1	14.1

9/21/15	20	20

10/1/15	120	120

10/7/15	1000	1000

10/12/15	230	234

10/27/15	N/A	N/A

11/2/15	290.7	290.7

12/3/15	72.6	72.6

12/15/15	145.4	145.4

12/16/15	79.9	79.9

12/17/15	75	75

12/17/15	370	370

12/18/15	N/A	N/A

12/23/15	100	100

12/23/15	250	250

12/30/15	N/A	N/A

12/30/15	N/A	N/A

1/4/16	N/A	N/A

1/11/16	105.8	105.8

2/1/16	100	100

2/3/16	275	275

2/3/16	20	20

2/23/16	60	60

4/19/16	275	275 
4/25/16 	N/A 	N/A

W	Genesee, NY	A

S	Montgomery, NY	F

CC	Chemung, NY - PA	C

W	Clinton, NY	D 
CC-NG Chemung, NY - PA     C

W	Chautauqua, NY	A

DC	Onondaga-New York, NY	C, J

CT-D	Bayonne, NJ	J

CT-NG  St. Lawrence, NY	E

H	Lewis, NY	E

ES	Wyoming, NY	A

W	Rensselaer, NY	F

CC-NG New York, NY	J

CT-NG  Linden, NJ-NY,NY	J

AC	PA-Rockland, NY	G

W	Steuben, NY	C

W	Madison, NY	E

W	Clinton, NY	D

CT	New York, NY	J

ST	Chautauqua, NY	A

ST	Chautauqua, NY	A

AC	Niagara, NY	A

W	St. Lawrence, NY	E

W	Jefferson, NY	E

AC	Niagara-Erie, NY	A

AC	Niagara-Erie, NY	A

AC	Niagara-Erie, NY	A

W	Lewis, NY	E

W	Allegany, NY	B

DC	Nassau, NY	K

S	Washington, NY	F

S	Suffolk, NY	K

AC	Suffolk, NY	K 
AC 	Oneida-Albany NY 	E, F

Oakfield - Lockport 115kV	NM-NG

St. Johnsville - Marshville 115kV	NM-NG

Homer City - Watercure 345kV	NYSEG

Patnode 230kV	NYPA

Homer City - Watercure 345kV	NYSEG

Dunkirk - Gardenville 230kV	NM-NG

NYPA/NM-NG/

Clay - Gowanus 345kV	ConEd

Gowanus Substation 345kV	ConEd

North Ogdensburg Substation	NM-NG

Taylorville- Boonville 115 kV	NM-NG

Stony Creek 230kV	NYSEG 
Stephentown - Greenbush 115kV   NM-NG

W49th St 345kV	ConEd

Linden Cogen 345kV	ConEd

Lackawanna - Ramapo 345kV	ConEd

Bennett 115kV	NYSEG

County Line - Bothertown 115kV	NYSEG

Patnode 230kV	NYPA

Hudson Avenue East 138kV	ConEd

Dunkirk 115kV	NM-NG

Dunkirk 230kV	NM-NG

Niagara - Stolle - Gardenville	NYPA/NYSEG

Colton - Malone 115kV	NM-NG

Indian River 115kV	NM-NG

Niagara, Erie, Stolle, Gardenville	NM-NG

Niagara, Erie, Stolle, Gardenville	NM-NG

Dysinger - Stolle 345kV	NYPA/NYSEG

Lowville - Bremen 115kV	NM-NG

Freedom Substation	Village of Arcade

Far Rockaway Substation 69kV	LIPA

Battenkill Substation	NM-NG

Edwards Substation 138kV	LIPA

Glenwood/Far Rockaway Station 69kV	LIPA

Edic - New Scotland 345kV	NM-NG/NYPA

NM-NG/NYSEG/

7	4/30/17	SRIS	2020/07	2020/10

5	11/30/16	FES	2018/09	2018/12

9	4/30/17	FES, SRIS	2019/09	2020/06

5	6/30/16	FES	2018/10	2018/12

9	4/30/17	FES, SRIS	2020/06	2021/05

9	4/30/17	SRIS	2018/09	2018/12

3	10/31/15	None	2021/10	2022/01

9	1/31/17	SRIS	2017/11	2018/03

9	4/30/17	SRIS	2017/05	2017/06

7	11/30/16	SIS	2018/03	2018/03

5	10/31/16	None	2017/08	2017/08

4	2/28/17	FES	2019/10	2019/10

3	8/31/16	None	2019/06	2019/06

9	4/30/17	SRIS	2020/05	2020/05

4	4/30/17	FES	2023/12	2023/12

5	10/31/16	FES	2019/10	2019/12

4	4/30/17	FES	2019/07	2019/10

4	4/30/17	FES	2018/10	2018/12

4	2/28/17	FES	2017/10	2017/10

9	4/30/17	SRIS	2018/08	2018/12

9	4/30/17	SRIS	2018/08	2018/12

5	5/31/16	None	2020	N/A

5	2/28/17	FES	2019/11	2019/12

3	5/31/16	None	2019/11	2019/12

5	3/31/17	None	2020/12	2020/12

5	3/31/17	None	2020/12	2020/12

5	3/31/17	None	2020/05	2020/05

5	2/28/17	FES	2019/10	2019/12

5	4/30/17	None	2018/09	2018/12

3	10/31/16	None	2020/04	2020/05

4	4/30/17	FES	2018/02	2018/02

3	11/30/16	None	2020/11	2020/12

3	1/31/17	None	2020/04	2020/06 
5 	10/31/16 	None 	2018/11 	2018/11

538	NextEra Energy New York

539	NextEra Energy New York

Segment B	4/25/16

Segment B Alt	4/25/16

N/A	N/A	AC	Albany-Dutchess, NY F, G 
N/A 	N/A 	AC 	Albany-Dutchess, NY F, G

Greenbush - PV 345kV 
Greenbush - PV 345kV

CHGE/ConEd	5	12/31/16

NM-NG/NYSEG/

CHGE/ConEd	5	12/31/16

NM-NG/NYSEG/

None	2018/11	2018/11 
None 	2018/11 	2018/11

540	AVANGRID	Connect NY Edic - PV

541	AVANGRID	Connect NY Edic - Ramapo

4/28/16	1000	1000	DC 
4/28/16 	1000 	1000 	DC

Oneida-Dutchess, NY E, G Edic - PV 345kV 
Oneida-Dutchess, NY E, G Edic - Ramapo 345kV

ConEd	5	12/31/16

NM-NG/NYSEG/ 
	O&R 	5 	10/31/16

None	2020/12	2020/12 
None 	2020/12 	2020/12

542	National Grid

543	National Grid

544	Invenergy Wind Development LLC

545	Sky High Solar, LLC

545A  NextEra Energy New York

546	Atlantic Wind, LLC

547	North America Transmission, LLC

548	North America Transmission, LLC

549	North America Transmission, LLC

550	North America Transmission, LLC

20170601_NYISONewGnrtnRprt_ExhibitA.xlsx

Segment A Edic-New Scotland Segment B Knickerbocker-PV Alle Catt Wind

Sky High Solar

Empire State Line Alt Roaring Brook Wind Dysinger-Stolle

Dysinger-Stolle-Gardenville

Niagara-Dysinger-Stolle-Gardenville

Dysinger-Stolle-Gardenville II

5/4/16	N/A	N/A	AC

5/4/16	N/A	N/A	AC

5/4/16	100.5	100.5	W

5/10/16	20	20	S

5/17/16	N/A	N/A	AC

5/19/16	78	78	W

5/25/16	N/A	N/A	AC

5/25/16	N/A	N/A	AC

5/25/16	N/A	N/A	AC 
	6/2/16 	N/A 	N/A 	AC

Oneida-Albany NY    E, F 
Albany-Dutchess, NY F, G 
Cattaraugus, NY 	A

Onondaga, NY	C

Niagara-Erie, NY	A

Lewis, NY	E

Niagara-Erie, NY	A

Niagara-Erie, NY	A

Niagara-Erie, NY	A 
Niagara-Erie, NY 	A

Edic - New Scotland 345kV Greenbush - PV 345kV

Freedom Substation 115kV 115kV

Dysinger - Stolle 345kV 
Chases Lake Substation 
Dysinger - Stolle 345kV

Dysinger - Gardenville 345kV 
Niagara - Gardenville 345kV 
Dysinger - Gardenville 345kV

NM-NG	5	11/30/16

NM-NG/NYSEG/

CHGE/ConEd	5	11/30/16

Village of Arcade

4	9/30/16

NM-NG	3	4/30/17

NYPA/NYSEG	5	3/31/17

NM-NG	3	10/31/16

NYPA/NYSEG/

NM-NG	5	3/31/17

NYPA/NYSEG/

NM-NG	5	3/31/17

NYPA/NYSEG/

NM-NG	5	3/31/17

NYPA/NYSEG/ 
	NM-NG 	5 	3/31/17

None	2021/12	2021/12

None	2021/12	2021/12

None	2020/10	2020/12

None	2018/12	2018/12

None	2020/06	2020/06

None	2019/11	2019/12

None	2020/06	2020/06

None	2021/04	2021/04

None	2021/06	2021/06

None	2020/12	2020/12

Updated: 04/30/2017

Interconnection Requests and Transmission Projects

Page 3 of 4

Queue 
	Pos. Owner/Developer

Date 
Project Name 	of IR

SP	WP	Type/ 
(MW) 	(MW) 	Fuel

Location	Interconnection 
County/State 	Z 	Point

Last 
Utility 	S 	Update

Availability  FS Complete/ 
of Studies 	SGIA Tender

Proposed  Proposed 
In-Service 	COD

551	OneEnergy Development, LLC

552	OneEnergy Development, LLC

555	North America Transmission, LLC

556	North America Transmission, LLC

557	North America Transmission, LLC

558	North America Transmission, LLC

559	North America Transmission, LLC

560	Atlantic Wind, LLC

561	Astoria Generating Co. LP

563	Double Lock Solar, LLC

564	Rock Distric Solar, LLC

565	Tayandenga Solar, LLCe

566	New York Power Authority

567	Tribes Hill Solar, LLC

568	Turkey Hollow Solar, LLC

570	Hecate Energy, LLC

571	Heritage Renewables, LLC

572	Hecate Energy, LLC

573	Hecate Energy, LLC

574	Atlantic Wind, LLC

575	Little Pond Solar, LLC

576	Astoria Generating Company

577	Greene County Energy Properties, LLC

578	Sharon Solar LLC

579	Bluestone Wind, LLC

580	Genesee County Economic Devel.

581	GCSD NY Solar, LLC

582	Sunny Knoll Solar LLC

583	Erie Boulevard Hydropower, LP

584	GCSD NY Solar, LLC

585	Community Energy Solar Development LLC

586	GCSD NY Solar, LLC

587	Community Energy Solar Development LLC

Caprock Solar 
Flotilla Solar

Segment A Base

Segment A Double Circuit Segment A Enhanced

Segment A 765

Segmant B Base 
Deer River Wind

Astoria Generating Unit 4 Double Lock Solar

Rock District Solar 
Tayandenega Solar 
MA 1 & 2 Rebuild 
Tribes Hill Solar

Turkey Hollow Solar Albany County

Heritage Wind 
Greene County I 
Greene County II 
Mad River Wind 
Little Pond Solar

Astoria Generating Unit 4 Greene County Energy Sharon Solar

Bluestone Wind WNY STAMP Hills Solar

Sunny Knoll Solar Fulton

Dog Corners Solar 
Caledonia I Solar 
Watkins Rd Solar 
Fork Valley Solar

6/24/16	20	20

6/24/16	20	20

7/6/16	N/A	N/A

7/6/16	N/A	N/A

7/6/16	N/A	N/A

7/6/16	N/A	N/A

7/6/16	N/A	N/A

7/8/16	100	100

7/18/16	385	385

7/25/16	20	20

7/25/16	20	20

7/25/16	20	20

8/4/16	N/A	N/A

8/10/16	20	20

8/16/16	20	20

8/17/16	20	20

9/1/16	200.1	200.1

9/6/16	20	20

9/6/16	10	10

9/16/16	450	450

9/16/16	20	20

9/16/16	385	385

9/20/16	20	20

9/20/16	20	20

9/21/16	124.2	124.2

9/27/16	500	500

10/6/16	20	20

10/18/16	20	20

10/31/16	1.3	1.3

11/2/16	20	20

11/7/16	20	20

11/8/16	20	20 
11/8/16 	20 	20

S	Monroe, NY	B

S	Monroe, NY	B

AC	Oneida-Albany NY	E, F

AC	Oneida-Albany NY	E, F

AC	Oneida-Albany NY	E, F

AC	Oneida-Albany NY	E, F

AC	Oneida-Albany NY	E, F

W	Lewis, NY	E

ST	New York, NY	J

S	Herkimer, NY	E

S	Schoharie, NY	F

S	Herkimer, NY	E

AC	St. Lawrence-Lewis, NY	D, E

S	Mongomery, NY	F

S	Delaware, NY	F

S	Albany, NY	F

W	Genesee, NY	A

S	Greene, NY	G

S	Greene, NY	G

W	Jefferson-Oswego, NY	C

S	Rockland, NY	G

St	New York, NY	J

S	Greene, NY	G

S	Schoharie, NY	F

W	Broome, NY	E

L	Genesee, NY	A

S	Herkimer, NY	E

S	Schoharie, NY	F

H	Oswego, NY	C

S	Cayuga, NY	C

S	Livingston, NY	A

S	Herkimer, NY	E 
S 	Steuben, NY 	C

South Union - Sweden 115kV	NM-NG

Brockport - Hamlin 115kV	NM-NG

NM-NG/NYSEG/

Edic - New Scotland 345kV	CHGE/ConEd

NM-NG/NYSEG/

Edic - New Scotland 345kV	CHGE/ConEd

NM-NG/NYSEG/

Edic - New Scotland 345kV	CHGE/ConEd

NM-NG/NYSEG/

Edic - New Scotland 345kV	NYPA/CHGE/ConEd

NM-NG/NYSEG/

Knickerbocker - PV 345kV	CHGE/ConEd

Black River-Lighthouse Hill 115kV	NM-NG

Astoria West Substation 138 kV	ConEd

Marshville 115kV	NM-NG

Sharon - Cobleskill 69kV	NM-NG

St. Johnsville - Inghams 115kV	NM-NG

Moses & Adirondack 230kV	NYPA

Church St. 69KV	NM-NG

Grand Gorge - Axtell Road 115kV	NYSEG

Long Lane - Lafarge 115kV	NM-NG

Shelby - Sweden 115kV	NM-NG

Coxsackie - North Catskill 69kV	CHGE

Coxsackie Substation 13.2kV	CHGE

Volney - Marcy 345kV	NM-NG

Mongaup - Shoemaker 69kV	O&R

Astoria East Substation 138kV	ConEd

New Baltimore - Coxsackie 69 kV	CHGE

Sharon Substation 69kV	NM-NG

Afton - Stilesville 115kV	NYSEG 
Kintigh/Niagara - Rochester 345kV   NYPA

Salisbury Station 115kV	NM-NG

Cobbleskill - Schoharie 69kV	NM-NG

Fay St. 34.5kV	NM-NG

Aurora Substation 34.5kV	NYSEG

Golah - York 69kV	NM-NG

Watkins Rd 115kV	NM-NG

Eelpot Rd Substation	NYSEG

NYPA/NYSEG/

3	10/31/16	None	2018/06	2018/06

3	10/31/16	None	2018/06	2018/06

5	1/31/17	None	2020/01	2020/01

5	1/31/17	None	2020/06	2020/06

5	1/31/17	None	2020/01	2020/01

5	12/31/16	None	2020/01	2020/01

5	1/31/17	None	2019/09	2019/09

3	11/30/16	None	2019/11	2019/12

5	2/28/17	None	2018/05	2018/05

4	4/30/17	None	2018/12	2018/12

4	4/30/17	None	2018/12	2018/12

4	4/30/17	None	2018/12	2018/12

5	10/31/16	None	2022/12	2022/12

4	4/30/17	None	2018/12	2018/12

4	4/30/17	None	2018/12	2018/12

5	2/28/17	None	2017/12	2017/12

3	3/31/17	None	2019/08	2019/12

4	11/30/16	None	2017/12	2017/12

4	11/30/16	None	2017/12	2017/12

3	4/30/17	None	2020/11	2020/12

3	2/28/17	None	2017/06	2017/06

5	2/28/17	None	2018/05	2018/05

4	4/30/17	None	2018/08	2018/08

2	4/30/17	None	2018/12	2018/12

3	2/28/17	None	2020/08	2020/11

5	2/28/17	None	2020/06	2020/06

2	1/31/17	None	2018/06	2018/06

4	4/30/17	None	2018/12	2018/12

9	3/31/17	None	2017/04	2017/04

4	4/30/17	None	201806	2018/06

2	1/31/17	None	2018/09	2018/09

4	4/30/17	None	201806	2018/06 
2 	1/31/17 	None 	2018/09 	2018/09

588	Exelon Transmission Co., LLC

589	RES America Devlopments LLC

590	RES America Devlopments LLC

591	RES America Devlopments LLC

592	RES America Devlopments LLC

594	North Park Energy, LLC

595	North Park Energy, LLC

596	Invenergy Wind Development LLC

597	Hecate Energy, LLC

598	Hecate Energy, LLC

600	Conti Solar

601	HP Hood LLC

602	Cypress Creek Renewables

603	Hecate Energy Riverhead, LLC

20170601_NYISONewGnrtnRprt_ExhibitA.xlsx

Niagara Transmission Expansion

Boonville Solar Scipio Solar

South Perry Solar Bennington Solar NW Energy

SW Energy

Alle Catt II Wind 
Greene County III 
Albany County II 
Johnson Solar 
Hood Cogen

Keesog Solar Riverhead

11/15/16	N/A	N/A

12/2/16	20	20

12/2/16	20	20

12/2/16	20	20

12/2/16	20	20

12/29/16	64.8	64.8

12/29/16	110.1	110

1/4/17	381.1	381.1

1/10/17	20	20

1/10/17	20	20

1/12/17	20	20

1/20/17	4	4

1/30/17	50	50 
	2/3/17 	7.5 	7.5

AC	Niagara-Erie, NY	A

S	Lewis, NY	E

S	Cayuga, NY	C

S	Wyoming, NY	B

S	Wyoming, NY	B

ES	Wyoming, NY	B

ES	Cattaraugus, NY	A

W	Cattaraugus, NY	A

S	Greene, NY	G

S	Albany, NY	F

S	Washington, NY	G

Madison, NY	C

S	Franklin, NY	D 
S 	Suffolk, NY 	K

Niagara - Gardenville Boonville Substation Scipio Substation

South Perry Substation 
Bennington Substation

Wethersfield Substation 230kV Five Mile Rd Substation 115kV Stolle - SW 345kV

North Catskill - Coxsackie 69kV Long Lane - Lafarge 115kV

Mechanicville - Schaghticoke 34.5kV

Onedia - Fenner 115kV Moses - Willis 230kV

Wildwood - Riverhead 69kV

NM-NG	4	1/31/17

NM-NG	2	3/31/17

NYSEG	2	3/31/17

NYSEG	2	3/31/17

NYSEG	2	3/31/17

NYSEG	2	1/31/17

NM-NG	2	1/31/17

NM-NG	2	3/31/17

CHGE	4	4/30/17

NGrid	4	4/30/17

NGrid	2	4/30/17

NGrid	2	2/28/17

NYPA	2	4/30/17 
	LIPA 	2 	3/31/17

None	2024/07	2024/07

None	2018/06	2018/09

None	2018/06	2018/09

None	2018/06	2018/09

None	2018/06	2018/09

None	2019/10	2019/12

None	2019/10	2019/12

None	2021/10	2021/12

None	2018/06	2018/06

None	2018/06	2018/06

None	2018/04	2018/04

None	2017/12	2017/12

None	2020/08	2020/08

None	2018/06	2018/06

Updated: 04/30/2017

Interconnection Requests and Transmission Projects

Page 4 of 4

Queue 
	Pos. Owner/Developer

Date 
Project Name 	of IR

SP	WP	Type/ 
(MW) 	(MW) 	Fuel

Location	Interconnection 
County/State 	Z 	Point

Last 
Utility 	S 	Update

Availability  FS Complete/ 
of Studies 	SGIA Tender

Proposed  Proposed 
In-Service 	COD

604	Hecate Energy Columbia County 1, LLC   Columbia County 1

605	Hecate Energy Columbia County 2, LLC   Columbia County 2

606	Hecate Energy Craryville 3, LLC	Columbia County 3

608	ITC New York Development, LLC	Segment A

609	ITC New York Development, LLC	Segment B

610	Woodruff Solar, LLC	Woodruff Solar

611	Badra Solar, LLC	Badra Solar

612	Deepwater Wind South Fork, LLC	South Fork Wind Farm

614	Sabertooth Solar, LLC	Sabertooth Solar

615	West Point Partners, LLC	West Point II HVDC

616	RES America Developments Inc.	Mohawk Solar

617	North Park Solar, LLC	Watkins Glen Solar

618	North Park Solar, LLC	High River Solar

619	North Park Solar, LLC	East Point Solar

620	North Park Solar, LLC	North Side Solar

621	Geronimo Solar Energy, LLC	Saugerties Solar

622	Geronimo Solar Energy, LLC	Alcoa Solar

2/7/17	20	20	S

2/7/17	20	20	S

2/7/17	10	10	S

2/8/17	N/A	N/A    AC

2/8/17	N/A	N/A    AC

2/10/17	20	20	S

2/10/17	20	20	S

2/14/17	95.5	95.5	W

2/22/17	20	20	S

3/2/17	1000	1000	DC

3/23/17	20	20	S

3/27/17	80	80	S

3/27/17	100	100	S

3/27/17	80	80	S

3/27/17	180	180	S

3/27/17	20	20	S 
3/27/17 	20 	20 	S

Columbia, NY	G

Columbia, NY	G

Columbia, NY	G

Oneida-Albany NY	E, F

Oneida-Albany NY	E, F

Livingston, NY	A

Franklin, NY	D

Suffolk, NY	K

Cortland, NY	B 
Albany, Westchester, F, H

Herkimer, NY	E

Schuyler, NY	C

Schenectady, NY	F

Schoharie, NY	F

St. Lawrence, NY	E

Ulster, NY	G 
St. Lawrence, NY 	E

Craryville Substation 34.5kV Craryville Substation 34.5kV Craryville Substation 34.5kV Edic - New Scotland 345kV Knickerbocker - PV 345kV Golah - York 69kV

Nicholville - Malone 115kV East Hampton 69kV

Willett - Lapeer 115kV

New Scotland - Buchanan South 345kV

Watkins Rd 115kV

Bath - Montour Falls 115kV Amsterdam Substation 115kV Sharon Substation 69kV

Massena Substation 203kV Saugerties Substation

13.8kV

NYSEG	2	4/30/17

NYSEG	2	4/30/17

NYSEG	2	4/30/17

NM-NG	4	3/31/17

NM-NG/NYSEG/

CHGE/ConEd	4	3/31/17

NM-NG	2	4/30/17

NM-NG	2	3/31/17

LIPA	4	3/31/17

NYSEG	2	4/30/17

NM-NG/ConEd	2	4/30/17

NM-NG	1	4/30/17

NYSEG	1	4/30/17

NM-NG	1	4/30/17

NM-NG	1	4/30/17

NYPA	1	4/30/17

CHGE	1	4/30/17 
NM-NG 	1 	4/30/17

None	2018/06	2018/06

None	2018/06	2018/06

None	2018/06	2018/06

None	2020/04	2020/04

None	2021/04	2021/04

None	2018/12	2018/12

None	2018/12	2018/12

None	2022/08	2022/12

None	2019/02	2019/02

None	2022/01	2022/05

None	2018/06	2018/06

None	2020/07	2020/12

None	2020/07	2020/12

None	2020/07	2020/12

None	2020/07	2020/12

None	2019	2019 
None 	2019 	2019

Number of new projects during April	8

Number of new projects year to date	35

Number withdrawn during April	4

Number withdrawn year to date	12

NOTES:  ● The column labeled 'SP' refers to the maximum summer megawatt electrical output.  The column labeled 'WP' refers to the maximum winter megawatt electrical output.

● Type / Fuel.  Key: ST=Steam Turbine, CT=Combustion Turbine, CC=Combined Cycle, CS= Steam Turbine & Combustion Turbine, H=Hydro, PS=Pumped Storage, W=Wind, NU=Nuclear, NG=Natural Gas, M=Methane, SW=Solid Waste, S=Solar, Wo=Wood, F=Flywheel ES=Energy Storage, O=Oil, C=Coal, D=Dual Fuel, AC=AC Transmission, DC=DC Transmission, L=Load, FC=Fuel Cell

● The column labeled 'Z' refers to the zone

● The column labeled 'S' refers to the status of the project in the  NYISO's LFIP.  Key: 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress, 11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn

● Availability of Studies  Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available ● FS Complete/SGIA Tender refers to the Attachment X milestone used to apply the 4-year COD limitation.

● Proposed in-service dates and Commerical Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.

20170601_NYISONewGnrtnRprt_ExhibitA.xlsx	Updated: 04/30/2017

ATTACHMENT I

New Generation Report - Exhibit B

1=	Scoping Meeting Pending

2=	FESA Pending

3=	FES in Progress

4=	SRIS/SIS Pending

5=	SIS/SRIS in Progress

6=	SIS/SRIS Approved

7=	FS Pending

8=	Rejected Cost Allocation/ Next

FS Pending--

9=	FS in Progress

10=	Accepted Cost Allocation/ IA in

Progress

11=	IA Completed

12=	Under Construction

13=	In Service for Test

14=	In Service Commercial

Interconnection Request has been received, but scoping meeting has not yet occurred

Awaiting execution of Feasibility Study Agreement

Feasibility Study is in Progress

Awaiting execution of System Impact Study (SIS) Agreement or System Reliability Impact Study (SRIS) Agreement and/or Operating Committee approval of SIS/SRIS scope

SIS/SRIS is in Progress

SIS/SRIS report has been approved by NYISO Operating Committee

Awaiting execution of Facilities Study Agreement

Project was in prior Class Year, but rejected cost allocation—Awaiting Developer’s decision to elect to enter next Class Year Study

Class Year Facilities Study or Small Generator Facilities Study is in Progress

Project accepted its System Upgrade Facilities 
Project Cost Allocation in a Class Year Study, if

applicable, and Interconnection Agreement is under negotiation

Interconnection Agreement is fully executed or filed unexecuted with FERC

Project is under construction

Project is In-Service and is in Trial Operations

Project is in Commercial Operation

Attachment II

ATTACHMENT II 
	PUBLIC

New York Independent System Operator, Inc.

Semi-Annual Compliance Report on Demand Response Programs 
	June 1, 2017

This report summarizes the status of demand response participation in the New York

Independent System Operator Inc.’s (“NYISO’s”) markets as of the Installed Capacity (“ICAP”) auction month of May 2017.  As in previous years, this report focuses on enrolled demand 
response participation in preparation for the Summer Capability Period.1  An overview of the status of the NYISO’s several demand response initiatives is provided below.

Deployments of the NYISO’s two reliability-based programs (the Emergency Demand Response Program (“EDRP”) and the Installed Capacity - Special Case Resource program 
(“ICAP/SCR”)) during the Summer 2016 Capability Period were reported in the NYISO’s 2017 Demand Response Annual Report (“January 2017 Report”).2

The NYISO also has two economic programs (the Day-Ahead Demand Response

Program (“DADRP”) and the Demand-Side Ancillary Services Program (“DSASP”)).  DADRP enrollment has been static for several years and enrolled resources have not participated in the energy market for more than four years. Given the lack of activity during the analysis period, there is no market participation to report.

Demand Response Enrollment

This report presents statistical data on demand response enrollment.  Demand response 
providers include individual retail electricity consumers that participate directly in the NYISO’s 
market as a Customer, as well as curtailment service providers, which is a general term used to 
identify the NYISO Customers that represent retail customers in the NYISO’s demand response 
programs.3

1 Capitalized terms not otherwise defined herein have the meaning set forth in Section 2 of the NYISO’s Market Administration and Control Area Services Tariff (“Services Tariff”).

2 New York Indep. Sys. Operator, Inc. Jan. 15, 2017Annual Report on Demand Response Programs, Docket No. ER01-3001-021.

3 The term “curtailment service providers” as used in this report refers to Responsible Interface Parties (RIPs) as

defined in Services Tariff Section 2.18 and as used therein and in the Installed Capacity Manual, Demand Reduction Providers (DRPs) as defined in Services Tariff Section 2.4 and used in the DADRP Manual, and the four types of Market Participants identified in the EDRP Manual.  A retail customer participating directly in a NYISO demand response program with its own Load must be a NYISO Customer, and it acts as its own curtailment service provider. The Services Tariff defines Curtailment Services Provider solely in relation to the EDRP (see Services Tariff 
Section 2.3), which is narrower than as used in this report.

- 1 -

ATTACHMENT II 
	PUBLIC

Table 1 identifies the number of curtailment service providers by the following organizational categories:

•   Aggregator - an entity that enrolls individual retail electricity consumers within the same 
	Load Zone that may be aggregated to form a single demand response resource;

•   Competitive Load Serving Entity4 (“LSE”) - an entity authorized to supply Energy, Capacity 
	and/or Ancillary Services to retail customers located within the New York Control Area 
	(“NYCA”);

•   Transmission Owner5/LSE -  the public utility or authority that owns facilities used for the 
	transmission of Energy in interstate commerce and provides Transmission Service under the 
	Services Tariff; and

•   Direct Customer - an entity that registers as a Market Participant with the NYISO to 
	participate on their own behalf in any of the NYISO’s demand response programs.

Table 1:  Demand Response Service Providers by Provider Type

Provide r Type	Numbe r as of May 2017

Aggregator	13

Competitive LSE*	7

TO/LSE	2

Direct Customer	3

Total	25

* Competitive LSEs are LSEs that are not also TOs.

Since the NYISO’s 2016 Semi-Annual Demand Response Report (“June 2016 Report”),6 the number of curtailment service providers participating in the NYISO’s demand response 
programs has decreased by three.

Tables 2 and 3 present enrollment statistics by Load Zone for EDRP and ICAP/SCR

respectively.  Each table presents the total number of resources, total MW enrolled, and the

enrolled MW of eligible Local Generators, or other behind-the-meter supply sources, facilitating load reduction.  In addition, changes in the number of resources and enrolled MW since the June 2016 Report are shown by Load Zone.

4 See Services Tariff Section 2.12.

5 See Services Tariff Section 2.20.

6 New York Indep. Sys. Operator, Inc. June 1, 2016 Semi-Annual Reports on Demand Response Programs and New Generation Projects, Docket No. ER03-647, et al.

- 2 -

ATTACHMENT II 
	PUBLIC

Table 2 shows EDRP Enrollment and ICAP Unsold.  Of the 92 end-use locations, 87 participated in the EDRP program and 5 were ICAP/SCRs with unsold capacity.7  Enrolled 
EDRP MW and ICAP Unsold increased 164% and end-use locations increased 43.8% since the June 2016 Report.  The largest increase in enrolled MW occurred in Load Zone A (West) and the largest increase in end-use locations occurred in Zone J (New York City).

Table 2:  EDRP Enrollment and ICAP Unsold (as of May 2017)

Zone

No. of End-Use 
	Locations

MW of Load	MW of Local 
	Reduction 	Generators

Change in No.

of End-Use Total MW

Locations from 
	May 2016

Change in 
	Total MW 
from May 2016

A	9	41.6	0.0	41.6	*	37.7

B	*	0.4	0.0	0.4	0	-0.2

C	20	11.1	0.0	11.1	0	0.0

D	7	3.4	0.0	3.4	0	0.0

E	11	5.4	0.0	5.4	0	0.0

F	*	7.0	0.0	7.0	*	6.7

G	*	0.0	0.0	0.0	0	0.0

H	*	1.6	0.1	1.7	0	-0.3

I	*	0.1	0.0	0.1	*	0.1

J	32	0.3	0.0	0.3	22	0.1

K	*	0.0	0.0	0.0	0	0.0

Total	92	70.9	0.1	71.0	28	44.1

* When the number of end-use locations is less than 5, the value has been masked in this public version of  the table.

Table 3 reflects ICAP/SCR MW sold in the May 2017 ICAP Spot Market Auction (May is the first month of the Summer Capability Period).  Historical data shows that enrollment in the ICAP/SCR program changes monthly throughout the Summer Capability Period.  The data shows ICAP/SCR enrolled MW decreased 1.3% compared with the same period reported in the June 2016 Report and the number of end-use locations decreased 0.6%.

7 ICAP/SCRs with unsold capacity are those resources that did not sell their full available capacity.

- 3 -

ATTACHMENT II 
	PUBLIC

Table 3:  ICAP/SCR Sold (as of May 2017)

Zone

No. of End-Use 
	Locations

MW of Load	MW of Local 
	Reduction 	Generators

Change in No.

Total	of End-Use

MW	Locations from

May 2016

Change in

Total MW from 
	May 2016

A	254	257.7	2.9	260.6	-48	-24.1

B	196	49.3	7.4	56.7	-40	-16.7

C	225	123.8	1.4	125.2	-39	7.4

D	23	57.1	0.2	57.3	0	-5.4

E	117	31.8	2.2	34.1	-20	-3.6

F	170	83.2	17.1	100.2	-13	9.5

G	143	35.0	14.2	49.2	-12	-6.1

H	23	6.4	0.9	7.3	-9	-0.3

I	96	13.3	5.2	18.5	-9	-5.3

J	1881	326.7	61.8	388.5	222	29.8

K	323	37.3	9.9	47.3	-53	0.4

Total	3451	1021.7	123.2	1144.9	-21	-14.5

* Depending upon the meter configuration of an individual resource the MW available from Local Generators may be greater than the MW of  Load Reduction (i.e.,curtailment).

For the majority of the analysis period of November 2016 through April 2017, there were three Demand Side Resources actively participating in the DSASP as providers of Operating Reserves.  The resources represented 106.5 MW of capability and had an average performance of 106.0% during this analysis period.

Tables 4 and 5, not presented in this public report, describe enrollment in the DSASP.  Due 
to the limited participation in this program, those tables are provided only in Confidential Exhibit

A.

Update on 2017 Demand Response Initiatives

This section provides an update on the projects that the NYISO has planned for its demand response programs for 2017.

Demand Response in the Real-Time Energy Market via the NYISO’s Distributed Energy Resources Roadmap for New York’s Wholesale Electricity Markets

The NYISO initiated a project in 2016 to develop a roadmap to integrate Distributed 
Energy Resources (DER), including demand response, into its real-time Energy markets.  The 
primary outcome of this initiative will be the integration of dispatchable DER.8  The NYISO has 
developed a DER Roadmap describing NYISO’s vision for integrating these resources into the

8 The NYISO’s initiative to integrate distributed energy resources will also include concepts for participation in the NYISO’s capacity and ancillary services markets.

- 4 -

ATTACHMENT II 
	PUBLIC

wholesale markets and made the Roadmap available to stakeholders in February 2017.9  The

integration of DER into the NYISO’s markets will continue to be the main driver in demand response innovation for 2017. The NYISO is continuing to work with its stakeholders through its shared governance process to develop a detailed market design concept and market rules.

9 New York Indep. Sys. Operator, Inc., Distributed Resources Roadmap for New York’s Wholesale Electricity Markets (Feb. 2017),

http://www.nyiso.com/public/webdocs/markets_operations/market_data/demand_response/Distributed_Energy_Res 
ources/Distributed_Energy_Resources_Roadmap.pdf.

- 5 -