December 19, 2019

By Electronic Delivery

Honorable Kimberly D. Bose, Secretary Federal Energy Regulatory Commission 888 First Street, NE

Washington, DC 20426

Re:    New York Independent System Operator, Inc., Proposed Tariff Revisions 
	Regarding Interconnection Process Improvements; Docket No. ER20-___-
	000

Dear Ms. Bose:

In accordance with Section 205 of the Federal Power Act1 and Part 35 of the regulations of the Federal Energy Regulatory Commission (“Commission”),2 the New York Independent 
System Operator, Inc. (“NYISO”) respectfully submits proposed revisions to its Open Access 
Transmission Tariff (“OATT”) and its Market Administration and Control Area Services Tariff (“Services Tariff”) to further expedite and enhance the efficiency of its interconnection processes and related tariff requirements, particularly the performance of its Class Year Interconnection 
Facilities Study (“Class Year Study”).3

The NYISO has a longstanding commitment to work with its stakeholders to identify

opportunities to enhance and improve its interconnection processes.4  Based on its experience in administering its interconnection processes and on stakeholders’ and Developers’ input, the 
NYISO developed, and proposes in this filing, further enhancements to its interconnection 
processes that build off of other recent, successful enhancements and that will further expedite and enhance these processes.  These proposed enhancements create additional options and 
flexibility to accommodate Developers seeking for their projects to be studied for deliverability, while maintaining and creating additional efficiencies in the Class Year Study structure that is favored by the NYISO’s stakeholders.  Collectively, these revisions will enable the NYISO to expedite the performance of Class Year Studies and to conduct studies for deliverability more often, along with providing additional process enhancements.

1 See 16 U.S.C. § 824d (2017).

2 18 C.F.R § 35 et seq. (2017).

3 Capitalized terms not otherwise defined in this letter have the meaning set forth in the NYISO’s OATT and Services Tariff.

4 See, e.g., New York Indep. Sys. Operator, Inc., Interconnection Process Improvements, Docket No. ER18-
80-000 (October 16, 2017); New York Indep. Sys. Operator, Inc., Proposed Tariff Revisions Regarding 
Interconnection Process Improvements, Docket No. ER16-1627-000 (May 5, 2016); New York Indep. Sys. Operator, 
Inc., Proposed Tariff Revisions Regarding Interconnection Process Improvements, Docket No. ER13-588-000 
(December 19, 2012).

10 Krey Boulevard, Rensselaer, New York 12144 | www.nyiso.com

Honorable Kimberly D. Bose December 19, 2019

Page 2

In particular, the proposed revisions will enhance the NYISO’s processes for evaluating a 
project’s deliverability by advancing elements of the deliverability analysis earlier in the 
interconnection process, creating additional opportunities and flexibility for the evaluation of a 
project’s deliverability outside of the Class Year Study, and addressing process elements that 
have resulted in delays due to issues applicable to only a single or a few projects.  In addition, 
the NYISO proposes various conforming revisions to the buyer-side mitigation rules (“BSM 
Rules”) for the NYISO-administered capacity market that are closely integrated with the revised 
interconnection procedures.  The proposed revisions also clarify and revise the requirements for 
the maintenance and expiration of a facility’s Capacity Resource Interconnection Service 
(“CRIS”) to address facilities retaining but not using CRIS for extended periods of time to 
prevent facilities from retaining CRIS without using it for extended periods of time.  Finally, the 
proposed revisions will enhance the efficiency of the NYISO’s interconnection processes by 
eliminating duplicative or unnecessary analysis in interconnection studies, amending the timing 
and process for enrolling in a Class Year, revising and clarifying the requirements for satisfying 
a regulatory milestone as part of this enrollment, and making additional process enhancements 
and clean-ups.  The revisions are described in detail in Part IV of this letter.

The proposed tariff revisions modify the interconnection procedures set forth in

Attachment S to the OATT (Rules to Allocate Responsibility for the Cost of New

Interconnection Facilities), Attachment X to the OATT (Standard Large Facility Interconnection 
Procedures or “LFIP”), and Attachment Z to the OATT (Small Generator Interconnection 
Procedures or “SGIP”), along with related tariff provisions.  The NYISO is also making changes 
to the BSM Rules, which are set forth in Section 23, Attachment H of the Services Tariff, so that 
they will continue to accurately and clearly describe the NYISO’s mitigation procedures in light 
of the proposed changes to the NYISO interconnection process.  In addition to these conforming 
changes the NYISO is also proposing certain clarifying and organizational adjustments to the 
BSM Rules that are ministerial in nature.  No substantive changes are being proposed to the 
BSM Rules at this time. The improvements proposed in this filing, however, should help to 
ameliorate concerns5 that interconnection process schedule may result in delayed determinations 
under the BSM Rules and delays that could unnecessarily impact small projects.

As discussed herein, all of the proposed revisions presented in this filing are just and 
reasonable both on their individual merits and as a cohesive package.  Further, the revisions 
would advance the policies set forth in Orders Nos. 2003 and 20066 and related orders.7  The

5 See, e.g., Complaint on Behalf of the New York State Public Service Commission and the New York State 
Energy Research and Development Authority and Request for Fast Track Processing, Docket No. EL19-86-000 
(July 29, 2019) (claiming that the combination of interconnection process delays and the BSM Rules discourages 
entry.)

6 Standardization of Generator Interconnection Agreements and Procedures, Order No. 2003, FERC Stats. & Regs. 31,146 (2003), order on reh’g, Order No. 2003-A, FERC Stats. & Regs. 31,160 (2004), order on reh’g, Order No. 2003-B, FERC Stats.& Regs. 31,171 (2004), order on reh’g, Order No. 2003-C, FERC Stats. & Regs. 131,190 (2005), affirmed sub nom. Nat’l Ass’n of Regulatory Util. Com’rs v. FERC, 475 F.3d 1277 (D.C. Cir. 2007) (“Order No. 2003”); Standardization of Small Generator Interconnection Agreements and Procedures, Order No. 2006, 70 Fed. Reg. 34190 (June 13, 2005), 111 FERC ¶ 61,220 (2005), order on reh'g, Order No. 2006-A, 113 
FERC ¶ 61,195, 70 Fed. Reg. 71760 (Nov. 30, 2005) (“Order No. 2006”).

7 See, e.g., Reactive Power Requirements for Non-Synchronous Generation, Order No. 827, FERC Stats. & 
Regs. ¶ 31,385, 155 FERC ¶ 61,277 (2016); Essential Reliability Services and the Evolving Bulk-Power System -

Honorable Kimberly D. Bose December 19, 2019

Page 3

tariff revisions were developed to address particular areas for improvement identified by

stakeholders and developers and carefully balance the interests of different stakeholder sectors, along with Developers.  The tariff revisions were approved by the NYISO’s stakeholder 
Management Committee and its Board of Directors.  Accordingly, all of the NYISO’s proposed tariff revisions should be accepted without modification or condition.  However, if the 
Commission were to decline to accept any part of this filing, it should nevertheless accept the remaining parts rather than rejecting the filing as a whole.

The NYISO respectfully requests that the proposed tariff revisions become effective the day immediately following the end of the statutory sixty-day notice period under Section 205 of the Federal Power Act (i.e., February 18, 2020).

I.	DOCUMENTS SUBMITTED

The NYISO submits the following documents with this filing letter:

•	Figure regarding “Overview of Additional SDU Studies in Relation to the Class Year

Study” (Attachment I);

•	Figure regarding “Illustrative Interaction Between the Class Year Study and Expedited

Deliverability Study” (Attachment II);

•	Figure regarding “Comparison of Current Class Year Enrollment Process and Proposed

Revisions” (Attachment III);

•	A clean version of the proposed revisions to the OATT (Attachment IV);

•	A blacklined version of the proposed revisions to the OATT (Attachment V);

•	A clean version of the proposed revisions to the Services Tariff (Attachment VI);

•	A blacklined version of the proposed revisions to the Services Tariff (Attachment VII);

• 	A clean version of the proposed revisions to Section 23.4.5 of the Services Tariff made to

a comprehensive version of the Section that includes all proposed revisions currently pending before the Commission, which is being provided for informational purposes (Attachment VIII); and

• 	A blacklined version of the proposed revisions to Section 23.4.5 of the Service Tariff

made to a comprehensive version of the Section that includes all proposed revisions

Primary Frequency Response, Order No. 842, 83 Fed. Reg. 9,636 (Mar. 6, 2018), 162 FERC ¶ 61,128, order on 
clarification and reh’g, 164 FERC ¶ 61,135 (2018); Reform of Generator Interconnection Procedures and 
Agreements, Order No. 845, 83 Fed. Reg. 21342 (May 9, 2018), 163 FERC ¶ 61,043 (2018) (“Order No. 845”), 
order on clarification and reh’g, Order No. 845-A, 166 FERC ¶ 61,137 (2019) (“Order No. 845-A”).

Honorable Kimberly D. Bose December 19, 2019

Page 4

currently pending before the Commission, which is being provided for informational purposes (Attachment IX).

II.	COMMUNICATIONS AND CORRESPONDENCE8

Communications regarding this pleading should be directed to:

Robert E. Fernandez, Executive Vice President & General Counsel

Karen Georgenson Gach, Deputy General Counsel

Raymond Stalter, Director of Regulatory Affairs

* Sara B. Keegan, Senior Attorney * Brian R. Hodgdon, Senior Attorney David Allen, Senior Attorney

New York Independent System Operator, Inc.

10 Krey Boulevard

Rensselaer, NY 12144 
Tel: (518) 356-6000 
Fax: (518) 356-4702 
rfernandez@nyiso.com 
kgach@nyiso.com

rstalter@nyiso.com 
skeegan@nyiso.com 
bhodgdon@nyiso.com 
dallen@nyiso.com

*Designated to receive service.

III.	BACKGROUND

* Ted J. Murphy

Hunton Andrews Kurth LLP 2200 Pennsylvania Avenue, NW Washington, D.C. 20037 
Tel: (202) 955-1500

Fax: (202) 778-2201 
tmurphy@huntonak.com

* Michael J. Messonnier Jr. Hunton Andrews Kurth LLP 951 East Byrd Street

Richmond, VA 23219 
Tel: (804) 788-8200 
Fax: (804) 344-7999

mmessonnier@huntonak.com

A.	NYISO Interconnection Processes

i.  General Outline of NYISO’s Interconnection Processes

Attachments S, X, and Z to the OATT establish the rights and obligations of all parties

concerning the NYISO’s interconnection processes related to the interconnection or modification

8 The NYISO respectfully requests waiver of 18 C.F.R. § 385.203(b)(3) (2014) to permit service on counsel in multiple locations.

Honorable Kimberly D. Bose December 19, 2019

Page 5

of Large Facilities9 and Small Generating Facilities, including the rights and obligations of the project’s Developer,10 the Transmission Owner, and the NYISO.

A Developer that seeks to interconnect its Large Facility or Small Generating Facility to 
the New York State Transmission System or Distribution System must obtain Energy Resource 
Interconnection Service (“ERIS”).11  The Interconnection Studies in the LFIP and SGIP identify 
and allocate the costs of any Attachment Facilities and System Upgrade Facilities (“SUFs”) 
required to reliably interconnect the Developer’s proposed project to the New York State 
Transmission System or Distribution System.  In addition, if a Developer wants its Large Facility 
or Small Generating Facility to qualify as an Installed Capacity Supplier and to participate in the 
NYISO-administered Installed Capacity market, the Developer must also obtain CRIS.12  In such 
case, the NYISO will, with limited exception, study the deliverability of the proposed project in a 
Class Year Study and identify and allocate the costs of any System Deliverability Upgrades 
(“SDUs”) required for the proposed project to meet deliverability requirements.

Attachment X contains the procedures for processing the interconnection or modification 
of Large Facilities.  Large Facilities include both Large Generating Facilities (i.e., generating 
facilities greater than 20 MW) and Class Year Transmission Projects (i.e., transmission projects 
that are eligible for and request CRIS).13  Attachment X provides for potentially three successive 
Interconnection Studies of each proposed project.  These studies analyze proposed projects in 
varying levels of detail.  First is the Optional Interconnection Feasibility Study, which is a high-
level evaluation of the project’s configuration and local system impacts.14  The second study is 
the Interconnection System Reliability Impact Study (“SRIS”), which is a detailed single-project 
study that evaluates the project’s impact on transfer capability and system reliability.15  The final 
study in the LFIP is the Class Year Study, which is further described below.16

Attachment Z contains the procedures for processing the interconnection or modification 
of Small Generating Facilities (i.e., generating facilities 20 MW or smaller).  Like the LFIP, the

9 With the exception of Class Year Transmission Projects and transmission facilities proposed by a

Transmission Owner as part of its local transmission plan, the interconnection of transmission facilities are

addressed through the NYISO’s separate Transmission Interconnection Procedures located in Attachment P to the 
OATT.

10 The term “Developer” is a tariff-defined term referring to a project developer for a Large Facility versus 
a Small Generating Facility, which uses the term “Interconnection Customer.”  For ease of reference, the filing letter 
uses the term “Developer” to refer to both project developers of Large Facility projects and Small Generating 
Facility projects.

11 ERIS is basic interconnection service that allows a Developer to interconnect its generating facility to the New York State Transmission System or Distribution System in accordance with the NYISO Minimum 
Interconnection Standard to enable the New York State Transmission System or Distribution System to receive 
electric energy from the facility.

12 CRIS is interconnection service that allows a Developer to interconnect its generating facility to the New York State Transmission System or Distribution System in accordance with the NYISO Deliverability 
Interconnection Standard, which allows participation in the NYISO’s Installed Capacity market to the extent of the facility’s deliverable capacity.

13 OATT Section 30.1 (definition of Large Facility).

14 OATT Section 30.6.

15 OATT Section 30.7.

16 OATT Section 30.8.

Honorable Kimberly D. Bose December 19, 2019

Page 6

SGIP in Attachment Z provides for potentially three successive Interconnection Studies of each proposed project of varying levels of detail: an optional feasibility study,17 a system impact study,18 and a facilities study or participation in a Class Year Study.19  The facilities study 
determines the binding cost estimates and allocates the costs of Local SUFs.

ii.  Class Year Study Requirements

The Class Year Study process is unique to the NYISO’s interconnection processes.  The Class Year Study evaluates the cumulative impact of a group of projects—a “Class Year” of 
projects.20  All Large Facilities studied under the LFIP are required to participate in the Class 
Year Study.  Certain Small Generating Facilities studied under the SGIP are also required to 
participate in the Class Year Study,21 and Small Generating Facilities requesting CRIS of greater than 2 MW must participate in the deliverability elements of the Class Year Study to obtain 
CRIS.22  The Class Year Study procedures are primarily contained in Attachment S,23 which sets forth the eligibility requirements for Class Year entry, establishes the Class Year Start Date and schedule, describes the obligations of Class Year Projects once they enter a Class Year Study,24 and details the scope and the cost allocation methodology for the interconnection of new 
generation facilities and Class Year Transmission Facilities.

A Class Year is comprised of projects that have met specified Class Year Study eligibility 
requirements by the time the study begins.  The hallmark of the Class Year Study process is that 
it is performed for a group of projects that have achieved similar interconnection milestones to 
determine the cumulative impact of such projects in order to equitably allocate upgrade costs and 
generate detailed cost estimates that provide reasonable accuracy on upgrade costs.  The Class

17 OATT Section 32.3.3.

18 OATT Section 32.3.4.

19 OATT Section 32.3.5.

20 The Class Year Study is divided into two parts.  The first part of the study (“Part 1 Facilities Study”) is a 
design and engineering study performed for an individual Class Year Project that identifies the Connecting 
Transmission Owner’s Attachment Facilities, the Local System Upgrade Facilities (“Local SUF”), and related 
metering, protection, and telecommunications facilities required to reliably interconnect the project.  The second part 
of the study—the Class Year Study—is a combined study of the projects participating in the Class Year to identify 
the remainder of the SUFs required to reliably interconnect the aggregate of projects in the Class Year Study.

21 As described in Section 32.3.5.3 of Attachment Z, if any Interconnection Study determines that a Small Generating Facility requires a non-Local SUF to interconnect, then that Small Generating Facility is required to 
enter in the next Class Year Study, and cost responsibility is allocated to the Small Generating Facility in accordance with the procedures and methodologies in Attachment S.  See also NYISO Transmission Interconnection and 
Expansion Manual (Issued: August 2, 2019) at Section 3.4.4.

22 A Developer of a generating facility that is requesting 2 MW or less of CRIS may obtain this amount 
without being evaluated for deliverability under the NYISO Deliverability Interconnection Standard.  See OATT, 
Sections 25.3.1, 32.1.1.7.  If a Developer requests greater than 2 MW of CRIS, its proposed generating facility must 
be evaluated for deliverability as part of a Class Year Study for a Class Year of projects.  See OATT Sections 25.3.1,

32.1.1.7.

23 Attachment X details the obligations related to execution of a Class Year Study Agreement and provides a high-level scope of the Class Year Study and Class Year Study procedures, but it incorporates by reference the terms of Attachment S, which provide more detailed Class Year Study procedures.

24 Attachment X also details Developers’ obligations related to the execution of the Class Year Study Agreement and Class Year Study procedures, generally.

Honorable Kimberly D. Bose December 19, 2019

Page 7

Year Study identifies and allocates the costs of the SUFs needed to reliably interconnect all of the projects in a Class Year.

As part of the Class Year Study, the NYISO also performs a Class Year Deliverability 
Study to determine whether any Class Year Projects that request CRIS are deliverable and to 
identify and allocate the costs of any SDUs required to make these projects deliverable.  If a new 
SDU is identified (i.e., a SDU not previously identified and cost allocated in a Class Year Study 
and not substantially similar to one previously identified and cost allocated in a Class Year 
Study), the NYISO will perform an additional SDU study for the study of and development of 
cost estimates of the SDU.

Attachment S also provides for a decision and settlement process toward the completion 
of the Class Year Study during which the Developers of Class Year Projects accept or reject their 
Project Cost Allocations (i.e., the costs allocated to a Class Year Project for SUFs and/or SDUs, 
as applicable) and satisfy their Security and Headroom obligations.  The process may go through 
several decision and settlement rounds until all remaining Developers accept their Project Cost 
Allocations.

If the NYISO identified new SDUs in its Class Year Deliverability Study for which an 
additional SDU study is required, the Class Year Study is bifurcated into two separate decision 
and settlement phases.  This creates an exit ramp from the Class Year Study that allows projects 
to elect to complete the Class Year Study prior to the completion of the additional SDU studies. 
Developers of projects requiring additional SDU studies may elect to complete the Class Year 
early (without having additional SDUs identified that would make the project fully deliverable, 
limiting their ability to sell capacity) or to remain in the Class Year for additional SDU studies. 
The Developers of all other Class Year Projects may either complete the Class Year early

(allowing them to proceed to commercial operation with both energy and, potentially, capacity rights) or remain in the Class Year until the completion of the additional SDU studies.

The Class Year will be completed when all remaining Developers have accepted their Project Cost Allocation and posted the related Security in the decision and settlement phase of the Class Year or, if there was a bifurcated study, in the decision and settlement phase of the bifurcated study.  The NYISO will then commence the next Class Year process thirty days after the first Business Day following the completion of the prior Class Year.25

iii.  Coordination of BSM Rules with Class Year Study

In addition to the Class Year Study process to determine project cost allocation for SUFs 
and SDUs, the NYISO is directed by Section 23.4.5 of Attachment H to the Services Tariff to 
coordinate its determinations under the BSM Rules with the Class Year Study.  Section 23.4.5.7 
of the Services Tariff requires the NYISO to conduct the appropriate analysis to determine the 
Offer Floors for the projects seeking to become Installed Capacity Suppliers in Mitigated 
Capacity Zones (“Examined Facilities”) currently within the Class Year Study process.  Upon 
the completion of the Class Year Studies the NYISO issues its Offer Floor determinations for

25 See OATT Section 25.5.9.

Honorable Kimberly D. Bose December 19, 2019

Page 8

each Examined Facility or otherwise finds that the Examined Facility qualifies for an exemption 
from mitigation.  Currently, the NYISO must conduct its analysis and provide its determination 
to Examined Facilities during each of the decision and settlement rounds that are conducted at 
the end of both phases of a bifurcated Class Year Study.  The NYISO conducts these 
determinations for Examined Facilities that are in the Class Year Deliverability Studies.

B.	NYISO’s Stakeholder Process to Review and Improve Interconnection

Processes

The NYISO works with its stakeholders on an ongoing basis to review its interconnection 
processes and to identify and implement process enhancements.  In recent years, the NYISO has 
adopted a number of comprehensive revisions to its interconnection processes driven by both 
stakeholder and Developer input and the NYISO’s experience in administering these processes.26 
These revisions were the result of the NYISO’s active engagement with its stakeholders and 
Developers in identifying process elements that could benefit from further improvement.  The 
revisions have resulted in significant improvements in the performance of the NYISO’s 
interconnection processes and the NYISO’s coordination with Developers, Transmission 
Owners, and other process participants.  Most recently, the NYISO conducted a comprehensive 
improvement effort in 2017 through which the NYISO enhanced numerous aspects of the 
interconnection process, involving revisions to over thirty tariff sections.27

Beginning in early 2019, the NYISO began an initiative with its stakeholders with a

particular focus on the performance of previous Class Year Studies for purposes of identifying 
potential areas for improvement that build on prior comprehensive revisions.28  Overall, 
stakeholders and the NYISO recognized the numerous benefits of the Class Year structure, but 
identified key areas that would benefit from additional enhancements, including the need to 
expedite the interconnection study processes and to facilitate the start of new Class Years more 
often by limiting the potential for delays in the process that can result from unique issues related 
to a single or a few projects.  Such delays were largely the result of evaluating the deliverability 
of a small subset of projects.  The NYISO and stakeholders also observed a growing need for an 
expedited process for evaluating deliverability (and administering the associated BSM Rules) for 
those project just seeking CRIS.  This need has arisen in part due to an increase in the number of 
small, distributed resources seeking to participate in the NYISO-administered markets.  In 
response to this stakeholder feedback, the NYISO proposed a number of process improvements 
for their consideration.

The NYISO and its stakeholders then developed in joint working group meetings 
improvements to its tariffs and procedures, including revisions to the interconnection

26 See supra note 4.

27 See generally, New York Indep. Sys. Operator, Inc., Interconnection Process Improvements, Docket No. ER18-80-000 (October 16, 2017).

28 The NYISO brought an initial presentation to commence discussions on lessons learned and potential

process improvements to the March 6, 2019, Transmission Planning Advisory Subcommittee.  The NYISO

subsequently provided presentations to stakeholders that summarized their input, and the NYISO’s proposed process improvements based on that input.

Honorable Kimberly D. Bose December 19, 2019

Page 9

requirements in Attachments S, X, and Z to the OATT and related tariff provisions.29  The same stakeholder process reviewed and approved the proposed tariff revisions to maintain the close integration of the BSM Rules and the interconnection process (especially in light of the separate decision and settlement phases of each separate study that evaluates the deliverability of 
projects).  The proposed tariff revisions are discussed in detail in Part IV below.

C. 	Modifications to Pro Forma Interconnection Procedures

A number of the NYISO’s proposed revisions to Attachments S, X, and Z would modify 
tariff language that the Commission adopted in Order Nos. 2003 and 2006 or their successors as 
part of the pro forma interconnection procedures.  The Commission has accepted other 
modifications and improvements to the NYISO interconnection procedures,30 recognizing that 
where changes to pro forma interconnection procedures “are clarifying and/or ministerial in 
nature and/or NYISO has supplied sufficient justification,” such modifications are acceptable 
under the “independent entity variation” standard.31  The Commission has explained that under 
this standard, “the Commission will review the proposed variations to ensure they do not provide 
an unwarranted opportunity for undue discrimination or produce an interconnection process that 
is unjust and unreasonable.”32

The revisions to Attachments S, X, and Z that are proposed herein are fully justified 
under the Commission’s “independent entity variation” standard.  The proposed revisions are 
just and reasonable and do not provide for unwarranted opportunities for undue discrimination. 
In addition, the proposed revisions have been approved by the NYISO’s stakeholders after an 
extensive and open process.  They were the product of discussions with stakeholders in the 
NYISO’s governance process over a period of eight months beginning in March 2019.  These 
proposed changes to the NYISO’s tariffs were approved by the Business Issues Committee on 
November 6, 2019 with one abstention, by a unanimous vote of the Operating Committee on 
November 8, 2019, and by a unanimous vote of the Management Committee on November 20, 
2019.  The NYISO’s Board of Directors also approved the filing of these proposed changes at its 
December meeting.  As discussed in detail in Part IV below, the tariff revisions are intended to 
improve upon and clarify the NYISO’s current interconnection process.  In addition, the 
proposed tariff revisions enhance, revise, and clarify the meaning of tariff provisions that have 
proven to be ambiguous or unduly difficult to implement in the NYISO’s experience.  The 
NYISO and its stakeholders believe that the proposed tariff modifications can provide 
considerable improvements to the existing process.

29 Meetings to review and discuss these interconnection process improvements took place in the following working groups and advisory subcommittees of the stakeholder Business Issues Committee and Operating 
Committee: the Transmission Planning Advisory Subcommittee, the Installed Capacity Working Group, the Market Issues Working Group, and the Electric System Planning Working Group.

30 See, e.g., New York Indep. Sys. Operator, Inc., 135 FERC ¶ 51,014 (2011); New York Indep. Sys. Operator, Inc., 124 FERC ¶ 61,238 (2008).

31 New York Indep. Sys. Operator, Inc., 124 FERC ¶ 61,238 at PP 17-18 (2008).

32 See id. at P 18.

Honorable Kimberly D. Bose December 19, 2019

Page 10

IV.    DESCRIPTION OF PROPOSED TARIFF REVISIONS

In response to comments provided by stakeholders concerning the interconnection

process, particularly with respect to the duration of the Class Year Study and the ability to start new Class Years more often, the NYISO took the opportunity to engage its stakeholders in 
identifying and potentially implementing additional improvements its interconnection processes. This initiative was intended to complement and bolster previous comprehensive improvement efforts.  Through this re-design initiative, the NYISO seeks to enhance and expedite the 
interconnection study process overall, particularly the Class Year Study and evaluation of 
deliverability.  The revisions generally fall into two categories.

The first category of proposed revisions focus on re-designing the process for evaluating 
a project’s deliverability by providing Developers with more frequent opportunities and 
flexibility for their projects to be evaluated for deliverability outside of the Class Year process; 
increasing administrative efficiencies largely related to the Class Year Study; and updating and 
enhancing the process for retaining CRIS.  As described in Part IV.A below, the NYISO 
proposes to require the performance of a deliverability evaluation earlier in the process during a 
project’s SRIS for Large Facilities that request CRIS.  This evaluation will provide information 
concerning a project’s deliverability and required SDUs, which information will then be used 
and refined in the Class Year Study.

In addition, as described in Part IV.B, the NYISO proposes to replace its existing

bifurcated study process, which sought to limit the number of projects that needed to remain in 
the Class Year Study for the deliverability evaluation, with an approach that would perform 
additional studies for projects requiring new SDUs outside of the Class Year Process.  The new 
Additional SDU Study process will enable a Developer or subset of Developers that require a 
new SDU in order for its project to be fully deliverable to have the SDU determined and cost 
allocated in a separate study without delaying the completion of the Class Year Study for all 
other Developers and the commencement of a subsequent Class Year.  As described in Part IV.C, 
the NYISO also proposes to establish a new Expedited Deliverability Study process by which 
Developers that are only seeking CRIS for their projects may be studied without having to 
participate in a Class Year to obtain CRIS for deliverable MWs that do not require an SDU.  This 
new process will provide Developers with more frequent opportunities and flexibility to obtain 
CRIS by not requiring their projects’ participation in a Class Year.

The proposed revisions described above will both individually and collectively provide opportunities to expedite the Class Year Study process, provide for the commencement of more frequent Class Years, and provide Developers with additional flexibility within the NYISO’s 
interconnection processes.  Moreover, as detailed in Part IV.D, the NYISO proposes conforming revisions to its existing BSM Rule to reflect the revisions in the interconnection processes, 
including the introduction of Additional SDU Studies and Expedited Deliverability Studies. 
Additionally, as detailed in Part IV.E, the proposed revisions also clarify and revise the 
requirements for the maintenance and expiration of a facility’s CRIS to address facilities 
retaining but not using CRIS for extended periods of time.

Honorable Kimberly D. Bose December 19, 2019

Page 11

The second category of proposed revisions concern revisions to streamline and further 
increase the efficiency of the Class Year Study process by improving or reducing administrative 
requirements.  As described in Part IV.F, the NYISO proposes to revise the scope of its analysis 
under the SRIS and Class Year Study to eliminate duplicative or unnecessary analysis.  In 
addition, as described in Part IV.G, the NYISO proposes revisions to amend the timing and 
process for enrolling in a Class Year to minimize delays at the start of the Class Year Study.  As 
described in Part IV.H, the NYISO also proposes to clarify the regulatory milestones that a 
Developer must satisfy in the interconnection process to account for certain project types (e.g., 
offshore wind generation projects) and to introduce additional alternatives that a Developer can 
satisfy in lieu of the regulatory milestone for purposes of entering a Class Year Study.  Finally, 
as described in Parts IV.I through IV.K, the NYISO proposes several additional revisions and 
clean-ups, including, among other things, revising the treatment of refunded deposits to interest 
actually earned on the deposit, revising the definition of the transmission projects that are subject 
to the LFIP, and other minor process enhancements and clean-ups.

The following table lists each of these proposals, with the corresponding Part and page number at which they are described in this filing letter.

Part

IV.A 
IV.B 
IV.C 
IV.D 
IV.E 
IV.F

IV.G

IV.H 
IV.I 
IV.J 
IV.K

Proposal

Require Deliverability Evaluation in SRIS

Remove Additional SDU Studies from Class Year Study Expedited Deliverability Study for CRIS-Only Projects Conforming Revisions to BSM Rules

CRIS Expiration Rules

Eliminate Duplication in SRIS and Class Year

Require Class Year Study Agreements, Deposits, and Project Data Earlier in Class Year Process

Revise and Clarify Regulatory Milestones Requirements Revise Treatment of Deposits

Revise Definition of Class Year Transmission Project Minor Clarifications and Ministerial Errors

Page

11

15

20

27

35

38

39

43

46

47

48

A.	Require Deliverability Evaluation in the System Impact Reliability Study

i.  Background

As described in Part III.A.i above, Attachment X provides for potentially three successive 
Interconnection Studies for a Large Facility—an Optional Interconnection Feasibility Study, an 
SRIS, and a Class Year Study.  The SRIS is conducted early in the interconnection study 
process.  Its purposes is to evaluate the Large Facility’s impact on transfer capability and system 
reliability of the New York State Transmission System and, if applicable, an Affected System, to 
preliminarily determine what upgrades may be required under the NYISO Minimum 
Interconnection Standard.

Honorable Kimberly D. Bose December 19, 2019

Page 12

A Developer may also currently request, at its option and expense, a preliminary

deliverability evaluation of the Large Facility under the NYISO Deliverability Interconnection Standard as part of the SRIS.33  The Developer must provide an additional $30,000 deposit for this evaluation.34  The preliminary deliverability evaluation will state the assumptions upon 
which it is based, state the results of the preliminary deliverability analyses, identify potential SDUs at a high level, and provide preliminary SDU cost estimates, which may be based on 
generic information.35  The results of this preliminary deliverability evaluation are neither 
binding nor final, but the information and analyses serve as a groundwork that will be updated and refined in the Class Year Study.

ii.  Revisions to Require Deliverability Evaluation in SRIS

The NYISO proposes to revise the SRIS requirements to make it a requirement, rather 
than an option, to perform a deliverability evaluation in the SRIS in cases in which a Developer 
of a Large Facility requests CRIS.36  A Large Facility for which the NYISO does not require a 
deliverability evaluation may, at its option, request that a deliverability evaluation of the Large 
Facility be performed in the SRIS for informational purposes.37  If the need for any SDU is 
identified as part of the deliverability evaluation in the SRIS, the SRIS will identify potential 
SDUs at a high level and provide preliminary SDU cost estimates.  In addition, the NYISO 
proposes to revise its SRIS and Class Year Study requirements to detail how any high-level SDU 
designs and cost estimates developed in the deliverability evaluation in the SRIS will be used in 
the Class Year process.

The NYISO’s proposed tariff revisions will provide opportunities to shorten the overall 
duration of the interconnection process, by performing certain deliverability work as part of the 
SRIS, rather than waiting to start the analysis in the Class Year Study.  The deliverability 
evaluations that are performed in the SRIS will provide Developers with deliverability 
information earlier in the interconnection process that will be used and refined in the Class Year 
Study.  In addition, the information developed in the SRIS will enable Developers to consider 
changes to their projects that could make their projects more deliverable before proceeding into 
the Class Year Study.38  The NYISO does not anticipate that the proposed revisions will 
significantly extend the duration of the SRIS, as the NYISO is also proposing to narrow the 
scope of other analysis currently performed in the SRIS, as described in Part IV.F below. 
Accordingly, as described below, the NYISO is only proposing to extend the time frame within 
which to perform the SRIS by thirty days when a deliverability evaluation is performed and 
anticipates an overall shortening of the duration of the interconnection process.  A detailed 
description of the specific tariff amendments necessary to implement the deliverability 
evaluation in the SRIS is set forth below.

33 OATT Sections 30.7.3.

34 OATT Sections 30.7.2.1, 30.7.3.

35 OATT Section 30.7.3.

36 Proposed revisions to OATT Section 30.7.3; proposed OATT Section 30.7.3.2.

37 Proposed OATT Section 30.7.3.2.

38 Proposed changes to a project after the completion of the SRIS will still be subject to the modification provisions contained in Section 30.4.4 of the OATT.

Honorable Kimberly D. Bose December 19, 2019

Page 13

iii.  Proposed Tariff Modifications

The NYISO proposes to revise the scope of the SRIS to require that the NYISO perform 
a deliverability evaluation as part of the SRIS under the NYISO Deliverability Interconnection 
Standard if either: (i) the Developer of a Large Facility has requested CRIS, or (ii) at the 
Developer’s request.39  This deliverability evaluation will be a preliminary, non-binding 
evaluation of deliverability.40  It will state the assumptions upon which it is based and state the 
results of the preliminary analysis.41  If the evaluation determines that a Large Facility is not 
deliverable for its full amount of requested CRIS, the NYISO will identify, at a high level, the 
potential conceptual SDUs to make the facility fully deliverable for the amount of its requested 
CRIS and provide preliminary non-binding cost estimates for the SDUs.42  The NYISO will 
perform the deliverability evaluation in accordance with the deliverability requirements currently 
used for the Class Year Study as set forth in Attachment S to the OATT.  However, the NYISO 
will evaluate the Large Facility on an individual basis rather than together with other proposed 
projects.43

In performing the subsequent Class Year Study, including the Class Year Deliverability 
Study component of that study, the NYISO will continue its current practice of using existing 
studies to the extent practicable, including any deliverability analysis performed in the SRIS.44 
Any potential SDUs identified in the deliverability evaluation in the SRIS will be refined in the 
Class Year Study prior to the NYISO’s performance of the Class Year Deliverability Study.45 
The SDUs will be subsequently revised, as necessary, based on the results of the Class Year 
Deliverability Study, which may alleviate the need for or require alternative SDUs.46

The Developer will be responsible for the additional study costs related to the

deliverability evaluation as part of the SRIS.47  These study costs are reasonable as the

performance of this deliverability evaluation in the SRIS will offset work and related costs in the 
Class Year Study and will also expedite the performance of the Class Year Study.  The NYISO

39 Proposed revisions to OATT Section 30.7.3; proposed OATT Section 30.7.3.2.  As part of the proposed revisions, the NYISO proposes to separate out the SRIS requirements for evaluating the project for ERIS under the NYISO Minimum Interconnection Standard in new Section 30.7.3.1 of the OATT and for deliverability under the NYISO Deliverability Interconnection Standard in new Section 30.7.3.2 of the OATT.  In addition, the NYISO 
proposes to make conforming changes concerning this study work to the terms and conditions applicable to the 
study agreement for the SRIS.  Proposed OATT Section 30.14, Attachment A to Appendix 1 (Terms and Conditions of Interconnection Study(ies)), Section 6.0.

40 Proposed OATT Section 30.7.3.2.

41 Proposed OATT Section 30.7.3.2.

42 Proposed OATT Section 30.7.3.2.  Consistent with the current requirements, the identification and cost estimates of potential SDUs may be based on generic information.

43 Proposed OATT Section 30.7.3.2.  However, consistent with the NYISO’s current practices, a Developer may request for informational purposes and at its cost certain non-binding sensitivities to study relevant assumptions of future system conditions.

44 Proposed revisions to OATT Sections 25.7.7.1, 30.8.3.

45 Proposed OATT Sections 30.7.3.2; proposed revisions to OATT Section 30.8.2.  If the deliverability

evaluation in the SRIS identified alternative potential SDUs, the Developer may elect which SDUs to be evaluated in the Class Year Study.  Id.

46 Proposed OATT Sections 30.7.3.2; proposed revisions to OATT Section 30.8.2.

47 Proposed OATT Sections 30.7.3.2 and 30.14, Attachment A to Appendix 1.

Honorable Kimberly D. Bose December 19, 2019

Page 14

also proposes to remove the existing requirement that the Developer provide an additional

$30,000 deposit for the costs of the optional deliverability evaluation in the SRIS.48  The

additional deposit is no longer required as the scope of the other analyses performed in the SRIS is being narrowed as described in Part IV.F below.

If the NYISO is required to perform a deliverability evaluation in the SRIS, it will use

Reasonable Efforts to complete the SRIS within 120 days, instead of 90 days for other projects.49 While the NYISO proposes to extend the SRIS by thirty days, it anticipates that the performance of this preliminary deliverability evaluation in the SRIS will expedite the overall interconnection study process by advancing study work that would have been previously performed in the Class Year Study and building on such results in the Class Year Study.

A Developer that has not requested CRIS will be exempt from the requirement that a

deliverability evaluation be performed in the SRIS.  The Developer, however, will not be able to request CRIS in the Class Year Study greater than the CRIS amount evaluated in the SRIS.  A revision to the Developer’s project that requests CRIS or an increase of CRIS that was not 
evaluated in the SRIS shall constitute a material modification to its project.50

iv.  Transition Rule

The NYISO’s stakeholder Operating Committee is responsible for approving the specific 
study scope for each SRIS.51  The SRIS scope will include any required deliverability 
evaluation.52  The revised SRIS deliverability requirements will apply to all proposed Large 
Facilities that have not had an SRIS scope approved by the Operating Committee within thirty 
days after the effective date of the tariff revisions described in this Part IV.A.  This limited 
thirty-day transition period ensures that those projects that have already finalized their SRIS 
scopes and are awaiting review by the Transmission Planning Advisory Subcommittee and 
approval by the Operating Committee are not required to re-open their study scopes, which 
would delay their progress in the interconnection process.  In all other cases, the SRIS scope for 
the Large Facility will be revised to include any required deliverability evaluation under the new 
tariff requirements.  The NYISO presented these transition requirements as a part of multiple 
stakeholder presentations, and has been advising Developers that are in the process of preparing 
the SRIS scope of the proposed tariff revisions and when they are intended to go into effect 53

48 Proposed revisions to OATT Sections 30.7.2.1, 30.7.3, 30.7.3.2.

49 Proposed revisions to OATT Section 30.7.4.

50 Proposed revisions to OATT Section 30.4.4.3.

51 OATT Section 30.7.3.

52 Proposed OATT Section 30.7.3.2.

53 The NYISO has been encouraging Developers that are preparing their SRIS scopes and seeking CRIS to proactively elect to perform a deliverability evaluation in the SRIS.

Honorable Kimberly D. Bose December 19, 2019

Page 15

B. 	Removal of Additional SDU Studies from the Rest of the Class Year Study

i.  Background

As part of its Class Year Study process, the NYISO is currently required to perform 
additional studies of SDUs identified in the study that were not previously identified and cost 
allocated in a Class Year Study and are not substantially similar to an SDU that was previously 
identified and cost allocated in a Class Year Study.54  The OATT provides for the NYISO to use 
Reasonable Efforts to perform the additional SDU study within an additional six-month period.55

As described in Part III.A.ii above, a Developer of a project participating in the Class

Year Study is required to accept in the decision and settlement phase of the study the Project

Cost Allocation and provide related Security for any SUFs identified in the study to obtain ERIS 
and to interconnect its project.56  In addition, if the Developer wants to obtain CRIS, it must 
accept in the decision and settlement phase of the Class Year Study the Project Cost Allocation 
and provide Security for any required SDUs identified in the Class Year Deliverability Study.57 
A Developer that elects not to accept its responsibility for any SDUs may proceed with its 
project, but it will not obtain CRIS for the amount of MWs that are not deliverable without the 
SDU.

Starting with its Class Year 2017, the NYISO uses a bifurcated Class Year process to

implement the performance of additional SDU studies.  If the NYISO identifies new SDUs in its Class Year Deliverability Study that require additional study, the Class Year Study is bifurcated into two separate decision and settlement phases, which creates an exit ramp from the Class Year Study that allow Developers to elect for their projects to complete the Class Year Study without having to wait for the completion of the additional SDU studies.58  In the event of a bifurcated study, the Class Year cannot be completed (and the subsequent Class Year started) until the end of the decision and settlement phase of the results of the additional SDU study (i.e., completion of the final round of the decision and settlement phase, by which all remaining Developers have accepted their Project Cost Allocation and posted related Security).

The NYISO created this bifurcated process to expedite the Class Year Study process for 
Developers that previously could not complete the process until the additional SDUs required for 
only a subset of projects was completed.  While the new rules accelerated the Class Year Study 
by allowing the majority of the projects to complete earlier at the bifurcation point, the rules, in

54 OATT Section 25.5.9.

55 OATT Section 25.5.9.

56 OATT Sections 25.8.2-25.8.4.

57 OATT Sections 25.8.2-25.8.4.

58 OATT Section 25.5.10.  As described in Part III.A.ii above, the bifurcated Class Year provides

Developers of Class Year Projects with several options.  Developers of projects requiring additional SDU studies may elect to complete the Class Year early (without having additional SDUs identified that would make the project fully deliverable, limiting their ability to sell capacity) or to remain in the Class Year for additional SDU studies. 
The Developers of all other Class Year Projects may either complete the Class Year early (allowing them to proceed to commercial operation with both energy and, potentially, capacity rights) or remain in the Class Year until the 
completion of the additional SDU studies.

Honorable Kimberly D. Bose December 19, 2019

Page 16

practice, did not expedite the commencement of the next Class Year due to the need to complete the additional SDU studies.  For Class Year 2017, the delay associated with the completion of the additional SDU study component of the bifurcated study was over twelve months and was 
due to additional SDU studies associated with only a few projects.  As a result, there were 
numerous projects that wished to enter a Class Year, but had to wait for the conclusion of the 
additional SDU studies.  Accordingly, the NYISO identified an opportunity to further improve its process and worked with its stakeholders to develop an alternative approach for performing the additional SDU studies that does not create unnecessary delays for Developers with projects that do not require the additional studies to complete the Class Year Study and enables the 
NYISO to conduct more frequent Class Year Studies.

ii.  Proposed Revisions to Additional SDU Study Requirements

The NYISO proposes to revise the Class Year Study requirements to perform additional 
SDU studies outside of the Class Year process.  Under this approach, if a Developer’s project 
requires a new SDU that necessitates an additional SDU study, the Developer may elect to 
proceed with the cost allocation of that SDU in studies performed outside of the Class Year 
process.59  The path for the Developer to then complete a Class Year Study process and accept 
its SUFs and SDUs will depend on when the additional SDU study is completed.  The 
Developers of all other Class Year Projects may proceed to the decision and settlement phase for 
the ongoing Class Year and, following the conclusion of that Class Year, the subsequent Class 
Year will commence, regardless of whether there are any ongoing additional SDU studies.  A 
detailed description of the NYISO’s proposed approach is set forth below.

The NYISO’s revised approach for the performance of additional SDU studies will 
replace the current bifurcated study approach.60  The NYISO expects that this approach will 
shorten the duration of Class Year Studies and will also expedite the commencement of 
subsequent Class Year Studies, which will enable the NYISO to conduct more frequent Class 
Years.

The NYISO intends to implement this new approach as part of its currently ongoing 
Class Year 2019 and has notified Market Participants of this intention in stakeholder working 
groups, including the Class Year-specific Interconnection Projects Facilities Study Working 
Group.  The NYISO anticipates that the Commission’s order on the proposed tariff revisions will 
predate the point in the Class Year Study process for Class Year 2019 at which projects must 
elect whether to proceed with additional SDU studies under the current rules.  As a result, the 
additional SDU study, if applicable, will be able to be implemented without any adverse impact 
or restudy in Class Year 2019.

59 As revised, an Additional SDU Study will not impact the completion of the Class Year Study for

purposes of determining the Class Year Start Date for the next Class Year Study.  Proposed revisions to OATT 
Section 25.5.10.2.  A Class Year Study will be complete on the date upon which the Final Decision Round in the 
study process is completed for the decision period.  Id.  The date for completing any Additional SDU Study will not 
impact this date, and the next Class Year Study may commence prior to the completion of an Additional SDU Study.

Id.

60 The NYISO proposes to delete the bifurcated study rules set forth throughout Attachment S of the OATT, including in Sections 25.5.9, 25.8.2, 25.8.3, 25.8.4, and 25.5.10 of the OATT.

Honorable Kimberly D. Bose December 19, 2019

Page 17

iii.  Proposed Tariff Modifications

a.  Definition and Commencement of Additional SDU Study 
The NYISO proposes to define an “Additional SDU Study” as follows:

A study that a Developer may elect to pursue if the Class Year Deliverability

Study identifies the need for a new System Deliverability Upgrade (i.e., a System 
Deliverability Upgrade not previously identified and cost allocated in a Class 
Year Study and not substantially similar to a System Deliverability Upgrade 
previously identified and cost allocated in a Class Year Study) that requires 
additional study.61

In addition, the NYISO proposes to revise the requirements concerning the commencement and implementation of such studies.62

Under the current bifurcated Class Year Study process, the NYISO issues a formal

“Notice of SDUs Requiring Additional Studies” to all members of its Interconnection Projects Facilities Study Working Group after the Operating Committee has approved the Class Year Study.63  The NYISO proposes to revise this requirement to provide such notice earlier in the Class Year Study process.  Specifically, the NYISO will provide such notice as soon as it has identified as part of the preliminary Class Year Deliverability Study the need for an SDU that would require an Additional SDU Study.64

At the same time, the NYISO will issue a separate notice to only those Developers of

Class Year Projects for which the NYISO identified SDUs requiring additional studies.65  Those 
Developers will then have ten calendar days to inform the NYISO whether they want to proceed 
or not proceed with an Additional SDU Study for the identified SDUs.66  If a Developer does not 
elect to pursue an Additional SDU Study, it will only have the option in the Class Year Study to 
accept or reject the number of megawatts of Installed Capacity, if any, that were determined in 
the Class Year Deliverability Study to be deliverable without the need for the SDU (“Deliverable 
MWs”).  If the NYISO has not received the Developer’s election within the ten-day period, the 
Developer will be deemed to have elected to not proceed with an Additional SDU Study and will 
only be permitted to accept or reject its Deliverable MW, if any.67  The NYISO will notify

stakeholders if an Additional SDU Study will be conducted as soon as practicable after receiving notice from a Developer.68  Finally, the NYISO has proposed revisions to the Class Year

61 Proposed revisions to OATT Sections 25.1.2, 30.1.

62 See proposed revisions to OATT Section 25.5.10.

63 OATT Section 25.5.10.1.

64 Proposed revisions to OATT Section 25.5.10.1.

65 Proposed revisions to OATT Section 25.5.10.1.

66 Proposed revisions to OATT Section 25.5.10.1.  The Developer may pursue one of the SDU alternatives identified by the NYISO, which will be evaluated in the Additional SDU Study.  Id.

67 Proposed revisions to OATT Section 25.5.10.1.

68 Proposed revisions to OATT Section 25.7.7.1.

Honorable Kimberly D. Bose December 19, 2019

Page 18

Interconnection Facilities Study Agreement (“Class Year Study Agreement”) to incorporate the schedule for conducting the study work associated with an Additional SDU Study.69

b.  Alignment of Additional SDU Studies and Class Year Study

If the NYISO identifies the need for an Additional SDU Study for an SDU associated

with a project, the Developer will have a number of options for how to proceed with its project in 
the Class Year process and have its project modeled in the base case for subsequent Class 
Years.70  The different options are described below and are illustrated in the figure provided as 
Attachment I.

If no Developer that requires an Additional SDU Study for an SDU elects to proceed with 
such study, the Class Year Study will proceed to the normal decision and settlement phase for all 
projects participating in the Class Year.71  A Developer that requires an Additional SDU Study 
for an SDU but elects not to proceed with the Additional SDU Study may only accept or reject 
the Deliverable MWs, if any, for its project, provided that it accepts its SUF Project Cost 
Allocation for ERIS.72  Such project will not have the option to accept a cost related to the SDU 
that is identified as necessary to obtain its full requested CRIS in that Class Year Study.

If, on the other hand, one or more Developers elect to proceed with an Additional SDU 
Study for their projects, the Class Year Study will proceed to the decision and settlement phase 
for the remaining projects.  The Additional SDU Study will be performed separate and apart 
from the remaining Class Year Study work, and the Developer’s options for the decision and 
settlement concerning any SUFs and SDUs associated with its project will be addressed in one of 
the following ways.73

First, if the Additional SDU Study is completed prior to the completion of the Class Year (i.e., the Operating Committee’s approval of the Class Year Study), a project subject to the 
Additional SDU Study will participate in the same decision and settlement phase for both SUFs and SDUs with the remainder of the original Class Year’s members.  If the Developer accepts 
the Project Cost Allocation for any required SUFs and SDUs and satisfies the related Security 
requirements, the proposed project, its SUFs, and its SDUs will all be modeled in the base case 
for the subsequent Class Year.

Second, if the Additional SDU Study is not completed prior to the completion of the 
Class Year, the project may, but is not required, to accept the cost allocation for its SUFs and

69 Proposed revisions to OATT Section 30.14, Appendix 2 (Class Year Study Agreement), Attachment A.

70 As the NYISO will be performing the Additional SDU Study outside of the normal Class Year Study 
process, the NYISO has deleted the requirement for a six-month period for the performance of an additional SDU 
study in the existing Class Year Study process.  See proposed revisions to OATT Section 25.5.9 (revised as Section

25.5.9.1).

71 Proposed revisions to OATT Section 25.5.10.2.  The NYISO proposes to make conforming changes to the decision and settlement tariff requirements to remove the requirements for bifurcated studies, and to insert 
requirements for Additional SDU Studies and Expedited Deliverability Studies.  See proposed revisions to OATT Sections 25.8.2−25.8.2.4.

72 Proposed revisions to OATT Section 25.5.10.1.

73 Proposed revisions to OATT Section 25.5.10.2.

Honorable Kimberly D. Bose December 19, 2019

Page 19

Deliverable MWs, if any, as part of the decision and settlement phase for its original Class

Year.74  The Developer may settle its SUFs and continue with the Additional SDU Study for the 
SDUs.75  A Developer may wish to take such action, so that its Point of Interconnection is 
modeled in the subsequent Class Year’s base case.  This will lock in its SUFs and Deliverable 
MWs so that the Developer would not be required to share in the potential costs of larger 
upgrades that may be triggered in subsequent Class Years.  Alternatively, a Developer may defer 
making its determination concerning any SUFs and Deliverable MWs until the Additional SDU 
Study is completed in accordance with the process steps described below.  If the Developer does 
not accept its SUFs and the Additional SDU Study does not complete until after the lockdown 
date for the Annual Transmission Baseline Assessment for the subsequent Class Year, its project 
will be treated the same as any other project that does not accept its SUF Project Cost Allocation 
in the Class Year with respect to the other Class Year Projects—i.e., the project will not be 
modeled in the base case for the next Class Year.

Third, if the Additional SDU Study is completed after the completion of its Class Year, 
but before the lockdown date for the Annual Transmission Baseline Assessment for the 
subsequent Class Year,76 the projects participating in an Additional SDU Study will have their 
own separate decision and settlement period, which may be an iterative process if multiple 
Developers are participating.77  If a Developer participating in this separate decision and 
settlement period had already accepted the SUF Project Cost Allocation and/or Deliverable 
MWs, if any, for its project during the decision and settlement process for its Class Year, it will 
only be required to accept or reject its SDU cost allocation in this period.  If, on the other hand, 
the Developer deferred making its determination concerning the SUF Project Cost Allocation 
and/or Deliverable MWs, it will have to decide in this separate decision and settlement period 
whether to accept its SUFs and SDUs cost allocations.  In the latter case, the SUF Project Cost 
Allocation will be based on a post-Class Year base case that reflects the decisions from the Class 
Year projects that previously settled in the normal decision and settlement period.78  If the 
Developer elects to reject its SDU in this period, it may still proceed with its accepted SUFs 
and/or any Deliverable MWs.

Finally, if the Additional SDU Study is not completed until after the lockdown date for 
the Annual Transmission Baseline Assessment for the subsequent Class Year, the Developer can 
elect to either continue the Additional SDU Study in the next Class Year or enter a later Class

74 Proposed revisions to OATT Sections 25.5.10.2, 25.8.2.

75 Proposed revisions to OATT Section 25.8.2.

76 If the Developer accepts its SUF Project Cost Allocation prior to the completion of the Annual

Transmission Baseline Assessment study cases for the subsequent Class Year Study, the Developer’s project and its SUF will be included in the Existing System Representation for the subsequent Class Year Study.  The Annual 
Transmission Baseline Assessment serves as the baseline pre-project study cases for the Class Year Study.  Once complete, the NYISO studies the Class Year Projects against the Annual Transmission Baseline Assessment study cases to determine the impact of the Class Year Projects.  The NYISO proposes this point in time as the deadline because the NYISO finalizes the study cases for the subsequent Class Year Study.

77 Proposed revisions to OATT Section 25.5.10.2.  The NYISO proposes revisions to the decision and 
settlement requirements to clarify that they apply for decision and settlement periods applicable to a Class Year 
Study and an Additional SDU Study.  Proposed revisions to OATT Sections 25.8.2, 25.8.2.1, 25.8.2.2, 25.8.2.4,

25.8.3, 25.8.4, 25.8.5, 25.8.6.4.

78 Proposed revisions to OATT Section 25.8.2.

Honorable Kimberly D. Bose December 19, 2019

Page 20

Year in which it may begin a new deliverability evaluation of its project.79  The continuing

Additional SDU Study or new deliverability evaluation performed in the subsequent Class Year 
will be updated based on the subsequent Class Year’s deliverability base case.80  If the 
subsequent deliverability evaluation finds that the project does not require new SDUs, the 
Additional SDU Studies would not be required (or would not continue if the changes to the 
system obviated the need for the new SDU being studied in the ongoing Additional SDU Study).

A Developer seeking to enter into a subsequent Class Year Study for purposes of

continuing its deliverability evaluation must satisfy anew the entry requirements applicable to

Developers to enter into a Class Year.81  A Developer’s election to enter into the next Class Year under these circumstances will not count as one of the project’s two opportunities permitted by the OATT to enter a Class Year Study.82

c.  Cost Allocation of SDU If Multiple Projects Contribute to Need

If multiple projects contribute to the need for an SDU for which an Additional SDU

Study is required, the Additional SDU Study will study the projects collectively and will allocate 
the costs among the projects requiring the SDU in the Class Year Study.83  However, if the 
projects require different, unrelated SDUs (e.g., one project in Long Island requiring an SDU and 
another project in NYC requiring a different SDU), they will proceed in separate Additional 
SDU Studies.

C.	Perform “Expedited Deliverability Study” Outside the Class Year Process

for CRIS-Only Projects

The NYISO proposes to establish a new Expedited Deliverability Study process pursuant to which a Developer that is only seeking CRIS for its project in the NYISO’s interconnection process may be studied outside the Class Year Study process to obtain CRIS for Deliverable MW that do not require an SDU.84  This proposed option will afford more frequent opportunities and an abbreviated study process for qualifying projects to obtain CRIS.

In an Expedited Deliverability Study, the Developer may obtain full or partial CRIS

based on the deliverability of its project.  If the study determines that the Developer’s project is

79 Proposed revisions to OATT Section 25.5.10.2.

80 Proposed revisions to OATT Section 25.5.10.2.

81 Proposed revisions to OATT Section 25.5.10.2.  If the Developer elects to enter the first subsequent

Class Year, it may provide notice of this election on or before the completion of the Annual Transmission Baseline Assessment study cases for that subsequent Class Year Study.  Id.

82 Proposed revisions to OATT Section 25.5.10.2.  If the Developer, however, enters into a subsequent

Class Year Study and rejects its SDU Project Cost Allocation, such action will constitute one of its two Class Years.

Id.

83 See proposed OATT Section 25.5.10.2.

84 The NYISO proposes to insert a definition of an “Expedited Deliverability Study” in OATT Section

25.1.2.  Pursuant to this definition, an Expedited Deliverability Study will mean: “A study conducted by the ISO or a 
third party consultant to determine the extent to which an existing or proposed facility satisfies the NYISO 
Deliverability Interconnection Standard at its requested CRIS level without the need for System Deliverability 
Upgrades.  The schedule and scope of the study is defined in Sections 25.5.9.2.1 and 25.7.1.2 of this Attachment S.”

Honorable Kimberly D. Bose December 19, 2019

Page 21

not deliverable or fully deliverable, the Developer may enter into the next Open Class Year for the evaluation or identification of any SDUs required to make the project deliverable.  The 
Developer may also enter into a subsequent Expedited Deliverability Study for a new 
determination of its requested CRIS based on changed circumstances, such as changes to the system since the last study.

The Expedited Deliverability Study will provide Developers that are only seeking CRIS 
with an expedited opportunity to obtain those CRIS rights without having to participate in a full Class Year Study.  Generally, projects that seek CRIS only include, among others, Large 
Facilities and Small Generating Facilities that already have ERIS but subsequently seek to obtain CRIS or increase their CRIS and generating facilities that do not interconnect pursuant to 
NYISO’s FERC jurisdictional requirements (e.g. distributed resources connecting to 
distribution).  Currently, a significant number of Developers participate in the Class Year Study solely for purposes of obtaining CRIS.  In the current Class Year 2019, 52 of the 91 projects are solely requesting CRIS.  In addition, the NYISO anticipates that a significant number of 
Developers will continue to request only CRIS in the interconnection process, particularly as 
distributed energy resources that are not subject to the NYISO’s interconnection procedures for 
ERIS begin to enter the NYISO-administered markets.

The Expedited Deliverability Study process will benefit a large number of Developers by 
lowering the barriers and time frame to their obtaining CRIS and providing them with additional 
flexibility in their participation in the NYISO’s interconnection process.  This includes a faster 
study process and lower study deposits than those required to participate in the Class Year CRIS-
only evaluation.  In addition, by addressing a large number of CRIS requests in a separate study, 
the NYISO may have opportunities to expedite the analysis for those Developers participating in 
the Class Year Study.

i.  Overview of Expedited Deliverability Study

A Developer that is requesting only CRIS for a project larger than 2 MW and meets the 
eligibility requirements described below may elect to enter an Expedited Deliverability Study in 
place of a Class Year Study for its deliverability evaluation.85  A Class Year Study deliverability 
evaluation first evaluates whether a facility satisfies the NYISO Deliverability Interconnection 
Standard at its full amount of requested CRIS.86  If a facility is not deliverable for its full amount 
of requested CRIS, the Class Year Study proceeds to identify and cost allocate SDUs required to 
make the facility fully deliverable for the full amount of requested CRIS.87  An Expedited

Deliverability Study, on the other hand, will only evaluate whether an existing or new facility

85 Proposed OATT Section 25.7.1; proposed revisions to OATT Section 25.7.4.  A Small Generating Facility 2 MW or smaller may obtain CRIS without being evaluated for deliverability under the NYISO 
Deliverability Interconnection Standard.  See OATT Section 25.3.1.

86 Proposed OATT Sections 25.7.1, 25.7.4.

87 Proposed OATT Sections 25.7.1, 25.7.4.

Honorable Kimberly D. Bose December 19, 2019

Page 22

satisfies the NYISO Deliverability Interconnection Standard at its full amount of requested CRIS without the need for SDUs.88  It will not identify or cost allocate SDUs.89

If the requested CRIS of a Developer’s project evaluated in an Expedited Deliverability 
Study is determined to be fully or partially deliverable, the Developer can obtain CRIS rights in 
the amount of the full or partial CRIS that are Deliverable MW.90  If the requested CRIS of a 
Developer’s project evaluated in an Expedited Deliverability Study is deemed undeliverable at 
its full amount of requested CRIS, a Developer that wants the full amount of its requested CRIS 
may enter its project in the next Open Class Year for a determination of the required SDUs or 
enter into a subsequent Expedited Deliverability Study or Class Year Study with the same or 
different CRIS request.91

ii.  Expedited Deliverability Study Eligibility Requirements

A Developer that is only requesting CRIS through the NYISO’s interconnection process 
and satisfies the other eligibility requirements described below is eligible to use the Expedited 
Deliverability Study.  This includes a Developer requesting CRIS for: (i) new or existing 
facilities with no CRIS, (ii) for small generators that are subject to the NYISO’s SGIP, (iii) for 
facilities that were not subject to the NYISO’s interconnection procedures, and (iv) for requests 
to increase CRIS for facilities with existing CRIS.  The NYISO does not propose to cap the 
collective amount of CRIS that may be evaluated in the Expedited Deliverability Study or to 
limit the projects eligible to participate in the study to those under a specified MW level.

To become a member of an Expedited Deliverability Study, a Developer that is only

requesting CRIS must satisfy the following requirements.  The Developer must provide notice to 
the NYISO by the start date of the Expedited Deliverability Study.92  The Developer’s project 
must be in service or have completed one of the following studies, as applicable: a Class Year 
Study for ERIS, a System Impact Study under the SGIP, or a utility interconnection study if the 
facility is not subject to the NYISO’s interconnection procedures.93  In addition, the Developer 
must, if applicable, have satisfied the data submission requirements for Class Year Projects

requesting CRIS in a Mitigated Capacity Zone and have such data submission deemed completed 
by the NYISO by the study start date, as detailed in Part IV.C.iv below.94  Finally, the Developer 
must also satisfy the requirements for the completion of a pro forma Expedited Deliverability 
Study Agreement, submit the required deposit, and submit the required technical data.95

As soon as practicable after a Developer has notified the NYISO of its request to enter 
the next Expedited Deliverability Study, the NYISO will tender to the Developer and the

88 Proposed OATT Section 25.7.1; proposed revisions to OATT Section 25.1 (definition of “Expedited Deliverability Study”) and OATT Section 25.7.4.

89 Proposed OATT Section 25.7.1.

90 Proposed OATT Section 25.7.6; proposed revisions to OATT Section 25.7.4.

91 Proposed OATT Section 25.7.1; proposed revisions to OATT Section 25.7.4.

92 Proposed OATT Section 25.5.9.2.1.

93 Proposed OATT Section 25.5.9.2.1.

94 Proposed OATT Section 25.5.9.2.1.

95 Proposed OATT Sections 25.5.9.2.1, 25.5.9.2.2.

Honorable Kimberly D. Bose December 19, 2019

Page 23

applicable Connecting Transmission Owner an Expedited Deliverability Study Agreement.96

When the NYISO tenders the agreement, it will provide the Developer with a non-binding good faith estimate of the cost and time frame for completing the study.97

The pro forma Expedited Deliverability Study Agreement is set forth in Appendix 2 of 
Attachment S.  The pro forma agreement is based on and consistent with the pro forma Class 
Year Study Agreement located in Appendix 2 of Attachment S.  It includes limited modifications 
from the Class Year Study Agreement to clarify that the agreement addresses the performance of 
the Expedited Deliverability Study, concerns the determination of Deliverable MW, and 
concerns a request for CRIS—not ERIS and/or CRIS, and to make related conforming revisions 
based on the difference between the Class Year Study and the Expedited Deliverability Study.

Within ten Business Days of receiving the agreement, the Developer must complete the agreement and deliver it to the NYISO.98  Along with the completed agreement, the Developer must provide the NYISO with the technical data required by the agreement and a study deposit of $30,000.99  The Developer, the NYISO, and the Connecting Transmission Owner must then execute the agreement within ten calendar days of the NYISO’s confirmation that it has received the completed agreement, required technical data, and deposit.100

The NYISO will invoice the Developer on a monthly basis for the work conducted for the Expedited Deliverability Study.101  The Developer’s responsibility to pay the actual costs of the study is set forth in the pro forma Expedited Deliverability Study Agreement.102  Each 
Developer will be responsible for an equal share of the actual costs of a combined Expedited Deliverability Study.103  The Developers must pay the invoiced amounts within thirty calendar days of receipt of the invoice.104  The NYISO will hold the deposit in an interest bearing account associated with the Developer until settlement of the final invoice.105

iii.  Expedited Deliverability Study Process

The start date for the first Expedited Deliverability Study will be the first Business Day after 30 calendar days following the effective date of these requirements.106  Following the initial study, subsequent Expedited Deliverability Studies will commence on the first Business Day after 30 calendar days following the completion of the prior study.107

96 Proposed OATT Section 25.5.9.2.2.

97 Proposed OATT Section 25.5.9.2.2.

98 Proposed OATT Section 25.5.9.2.2.

99 Proposed OATT Section 25.5.9.2.2.

100 Proposed OATT Section 25.5.9.2.2.  The NYISO will provide a copy of the fully executed agreement to the Developer and Connecting Transmission Owner.

101 Proposed OATT Section 25.5.9.2.2.

102 Proposed OATT Section 25.5.9.2.2; Appendix 2 to Attachment S (Expedited Deliverability Study Agreement) at Section 5.0.

103 Proposed OATT Section 25.5.9.2.2. 
104 Proposed OATT Section 25.5.9.2.2. 
105 Proposed OATT Section 25.5.9.2.2. 
106 Proposed OATT Section 25.5.9.2.1. 
107 Proposed OATT Section 25.5.9.2.1.

Honorable Kimberly D. Bose December 19, 2019

Page 24

The NYISO, however, will not commence an Expedited Deliverability Study during the 
decision and settlement window of an ongoing Class Year Study—that is, the period between the 
posting of the Class Year Study for approval by the stakeholder Operating Committee and the 
commencement of the following Class Year Study.108  The NYISO will not commence an 
Expedited Deliverability Study in this window because the base case could be subject to changes 
during this period based on decisions in the Class Year and Buyer-Side Mitigation 
determinations could be impacted.  If the start date for the next Expedited Deliverability Study 
falls in this decision window, the study will instead begin on the first Business Day after ten 
calendar days following the next Class Year Start Date.109  The NYISO will notify interested 
parties of the start date of the Expedited Deliverability Study.110  The interaction between the 
Expedited Deliverability Study and the Class Year Study is illustrated in the figure provided as 
Attachment II.

The NYISO will perform the Expedited Deliverability Study concurrently for all projects 
that meet the eligibility requirements described above.111  There will be no prioritization of the 
projects grouped and studied together.112  Each project participating in the study will, with the 
other projects in the same study, share in the then currently available functional or electrical 
capability of the transmission system currently available in the applicable base case.113

The NYISO’s requirements for performing the Expedited Deliverability Studies mirror 
the requirements for performing Class Year Deliverability Studies.  Among other things, these 
include the requirement that only the NYISO has decisional control over the study, that the 
NYISO may use outside expert services to conduct the study, and that the NYISO will use 
existing studies to the extent practicable, including deliverability analysis from an SRIS.114  The 
NYISO may request additional information from the Developer and Connecting Transmission 
Owner as may reasonably become necessary during the course of the study, which information 
the Developer and Connecting Transmission Owner shall provide in a prompt manner.115  The 
NYISO will provide status reports and materials to the stakeholder Operating Committee or one 
of its subcommittees to provide opportunities for Market Participant input.116  Within ten 
Business Days of the NYISO providing a draft Expedited Deliverability Study report to a 
Developer, the NYISO, Connecting Transmission Owner, and any Affected System Operator 
will meet with the Developer to discuss the results.117  The completed Expedited Deliverability

108 Proposed OATT Section 25.5.9.2.1.

109 Proposed OATT Section 25.5.9.2.1.

110 Proposed OATT Section 25.5.9.2.1.  The NYISO will post notice on its website and send notices to those registered on the distribution list for its Operating Committee and its subcommittees.  Id. 
	111 Proposed OATT Section 25.7.1.2.

112 Proposed OATT Section 25.5.8.

113 Proposed revisions to OATT Section 25.5.8.

114 See proposed OATT Sections 25.5.9.2.3, 25.7.7.2; cf. OATT Section 25.7.7.1 (previously OATT Section 25.7.7) (establishing the Class Year Study procedures).

115 Proposed OATT Section 25.5.9.2.3.

116 Proposed OATT Section 25.7.7.2.

117 Proposed OATT Section 25.5.9.2.3. Upon request, the NYISO will provide the Developer with

supporting documentation, workpapers, and databases or data developed in preparing the study, subject to nondisclosure arrangements.  Id.

Honorable Kimberly D. Bose December 19, 2019

Page 25

Study will be reviewed and approved by the Operating Committee.118  In addition, the study is reviewable by the NYISO Board.119

Entities participating in the study must use Reasonable Efforts to complete and provide 
the draft Expedited Deliverability Study report to the stakeholder Operating Committee for its 
approval within four months of the NYISO’s receipt from all participating Developers of the 
required study agreement, technical data, and deposit detailed above.120  However, the NYISO 
will not present an Expedited Deliverability Study report to the Operating Committee for 
approval during the decision and settlement window of a Class Year Study.  Nor will the NYISO 
proceed with the report to the Operating Committee until ten days following the completion of 
the Class Year Study decision and settlement period.121  The NYISO will not complete an 
Expedited Deliverability Study in this window of time in order to avoid potential changes in the 
base case based on decisions in the Class Year and in the Buyer-Side Mitigation determinations.

Within five Business Days of the Operating Committee’s approval of an Expedited 
Deliverability Study (i.e., the “Expedited Deliverability Study Initial Decision Period”), each 
Developer in the study must provide notice to the NYISO via email stating whether or not it 
accepts the Deliverable MW reported to it by the NYISO in the study report (i.e., an “Expedited 
Deliverability Study Acceptance Notice” or an “Expedited Deliverability Study Non-Acceptance 
Notice,” as applicable).122  A Developer’s failure to notify the NYISO within this period will be 
deemed as non-acceptance of the Deliverable MW.123  As soon as practicable following the end 
of the decision period, the NYISO will report to all applicable Developers the decisions 
submitted by Developers.124  If one or more of the Developers did not accept its Deliverability 
MW (i.e., an “Expedited Deliverability Study Non-Acceptance Event”), the NYISO will within 
ten Business Days remove those Developers from the current Expedited Deliverability Study, 
update the study results to reflect the impact of the withdrawn projects, and issue the updated 
report.125  The Developers that accepted their Deliverable MW in the initial decision period will 
be deemed to have accepted their respective Deliverability MW in the revised report, as there 
would be no change to deliverability costs.

118 Proposed OATT Section 25.7.7.2.

119 Proposed OATT Section 25.7.7.2.

120 Proposed OATT Sections 25.5.9.2.1, 25.5.9.3.  The NYISO will notify Developers if it will not be able to complete the study within the initial schedule and provide an estimated completion date and an explanation of the reasons for why additional time is required.  Proposed OATT Section 25.5.9.2.3.

121 Proposed OATT Section 25.5.9.2.3.

122 Proposed OATT Section 25.5.9.2.4. 
123 Proposed OATT Section 25.5.9.2.4. 
124 Proposed OATT Section 25.5.9.2.4. 
125 Proposed OATT Section 25.5.9.2.4.

Honorable Kimberly D. Bose December 19, 2019

Page 26

iv.  Expedited Deliverability Study Base Case and Study Performance 
	Requirements

The base case for the Expedited Deliverability Study will use the same base case

inclusion rules as the Class Year Deliverability Study.126  However, the base case for the

Expedited Deliverability Study will include CRIS requests for projects in an ongoing Class Year. The deliverability base cases will be trued-up before the commencement of the next Expedited Deliverability Study or next Class Year Study, whichever occurs earlier.  In addition, the base case for the Expedited Deliverability Study will be revised and the deliverability re-evaluated for potential impacts to projects if (i) the pending Class Year completes the decision and settlement process during the performance of the Expedited Deliverability Study, (ii) a Class Year project rejects its deliverable MWs or SDUs, and (iii) the NYISO determines that this may impact the deliverability of a project in the Expedited Deliverability Study.127

The NYISO will also use the same deliverability test methodology for the Class Year 
Study and Expedited Deliverability Study for Highways, Byways, and Other Interfaces, with 
limited exceptions described below.128  As part of these revisions, the NYISO clarifies that the 
definition of NYCA deliverability applies equally in the Class Year Study and in the Expedited 
Deliverability Study.129  In addition, the NYISO proposes to establish separate tariff sections 
detailing the performance of the deliverability test methodology for Highways and Byways in the 
Class Year Study (in Section 25.7.8.2.1) and the Expedited Deliverability Study (in Section

25.7.8.2.2).  The methodology is nearly identical, except for how CRIS is modeled in each study 
due to the different time frames for the studies.130  The NYISO also proposes to establish 
separate tariff sections detailing the performance of the deliverability test methodology for Other 
Interfaces in the Class Year Study (in Section 25.7.9.1) and the Expedited Deliverability Study 
(in Section 25.7.9.2).  The methodology is nearly identical, except that the Class Year Study 
accounts for SDUs, which are not evaluated as part of the Expedited Deliverability Study.

v.  Interaction Between Expedited Deliverability Study and Class Year Study

A Developer’s project may not be simultaneously evaluated in both the Class Year Study 
and an Expedited Deliverability Study and may not exit one study to enter the other until the 
developer’s participation in the initial study has been completed.131  Following the completion of 
one of the studies, a Developer that participated in that study can enter its project into the other

126 For purposes of developing the Annual Transmission Baseline Assessment and Annual Transmission Reliability Assessment for a given Expedited Deliverability Study, the NYISO will use the same Existing System Representation requirements for a Class Year Study.  Proposed revisions to OATT Section 25.5.5.

127 Proposed OATT Section 25.5.9.2.3.

128 Proposed revisions to OATT Sections 25.7.8−25.7.9. 129 Proposed revisions to OATT Section 25.7.8.1.

130 Proposed revisions to OATT Section 25.7.8.2.1.3 (previously Section 25.7.8.2.3); proposed OATT Section 25.7.8.2.2.3.

131 Proposed OATT Section 25.7.1.  For purposes of applying the limitation on participation in

simultaneous studies, a project will not be considered to be participating in a Class Year Study if it withdraws prior 
to the completion of Annual Transmission Baseline Assessment study cases pursuant to Section 30.8.1.2 of the 
OATT.

Honorable Kimberly D. Bose December 19, 2019

Page 27

study.  For example, a Developer whose project was found in an Expedited Deliverability Study to be not deliverable or to be only partially deliverable, but that wants to obtain its full requested CRIS level could then (i) enter into the next Open Class Year for the evaluation and 
identification of any required SDUs, or (ii) enter into a subsequent Expedited Deliverability Study requesting the same or a different CRIS amount (e.g., if the Developer anticipates that subsequent system changes would now make it deliverable).132  As described above, the next Expedited Deliverability Study will in most cases begin approximately thirty calendar days after the completion of the prior Expedited Deliverability Study.133

The NYISO also proposes to modify the requirements concerning the NYISO

Deliverability Interconnection Standard to clarify existing rules and to incorporate the Expedited Deliverability Study within the existing Class Year Study framework.  Such revisions clarify that facilities with CRIS that request an increase to its CRIS must meet the NYISO Deliverability Interconnection Standard to obtain additional CRIS, as well as clarify options for those projects to seek such additional CRIS.134  In addition, the NYISO proposes to clarify the tariff language describing the CRIS modeled in the Class Year Study to address CRIS that has been obtained in a Class Year Study or an Expedited Deliverability Study.135

vi.  Transition Rules

A Developer’s project currently participating only for CRIS purposes in Class Year 2019 will not be permitted to withdraw from Class Year 2019 and enter the first Expedited 
Deliverability Study once these proposed revisions are effective.  By the time the first Expedited Deliverability Study starts, the NYISO anticipates having completed the preliminary 
deliverability analysis for Class Year 2019 and having identified Additional SDU Studies.  In 
addition, the Expedited Deliverability Study will model all pending Class Year 2019 CRIS 
requests in the base case, so evaluating the project in the Expedited Deliverability Study will 
likely only make the project less deliverable.

D. 	Conforming Revisions to BSM Rules to Reflect Revisions in the

Interconnection Processes Including the Introduction of Additional SDU Studies and Expedited Deliverability Studies

The BSM Rules are closely aligned with the NYISO’s interconnection processes for new 
and existing resources seeking to bring new supply into the NYISO’s Installed Capacity 
market.136  This filing therefore necessarily includes proposed revisions to Section 23.4.5.7 of 
the Services Tariff, which are discussed individually in this section.  The NYISO is also adding 
(or in some cases relocating) defined terms that describe how the BSM Rules will be applied

132 Proposed OATT Section 25.7.1.

133 Proposed OATT Section 25.5.9.2.1.

134 Proposed revisions to OATT Section 25.3.1.

135 Proposed revisions to OATT Section 25.7.8.1.3.

136  See New York Indep. Sys. Operator, Inc., Letter Order, Docket No. ER18-80-000 (December 7, 2017) (accepting NYISO’s proposed “comprehensive queue improvements” including the Class Year bifurcation 
provisions and related adjustments to the BSM Rules).

Honorable Kimberly D. Bose December 19, 2019

Page 28

throughout the revised interconnection process as proposed revisions to Section 23.2.1 of the

Services Tariff.  Collectively, these proposed tariff amendments update existing provisions, and when necessary add new language, to accurately and completely describe how the BSM Rules will be applied to Examined Facilities.

The NYISO is not proposing to change how it will conduct determinations made under 
the BSM Rules (“BSM Determinations”) for Examined Facilities that are evaluated along with a 
Class Year Study.  The NYISO is removing and replacing various tariff references that would be 
rendered obsolete by other parts of this filing.  The NYISO is also adding defined terms to reflect 
the proposed new features of the interconnection process that are being proposed as well as 
making some ministerial changes with the existing language to make them clearer and better 
organized.  The proposed tariff revisions also address the ordering of BSM Determinations for 
projects that are being evaluated as part of a Class Year Study, Additional SDU Study or 
Expedited Deliverability Study in relation to each other.  The revisions clearly specify which 
rules will apply to facilities that are being evaluated as part of each type of study.  At the same 
time, the revisions are consistent with the current rules by providing for exemption and Offer 
Floor determinations to be made at the end of a project’s interconnection process, regardless of 
the type of study that it participates in.

The proposed revisions will further ensure that the BSM Rules continue to be transparent 
and provide clarity to developers and market participants.  Proposed clarifications will ensure 
that the Offer Floor Determinations for Examined Facilities in either a Class Year Study, 
Additional SDU Study, or Expedited Deliverability Study will be coordinated such that the 
projects participating in any such studies are appropriately considered in subsequent BSM 
Forecasts and Offer Floor determinations for Examined Facilities in subsequent studies.  This 
coordination is also needed to apply the pending proposed renewable exemption megawatt 
threshold to projects that are evaluated in a Class Year Study, Additional SDU Study, or 
Expedited Deliverability Study.

In short, the proposed revisions to the BSM Rules are necessary to conform to the

proposed changes to the interconnection processes, and should be accepted as just, reasonable, and not unduly discriminatory.

i.  Conforming Revisions to BSM Tariff Provisions to Reflect the Revised Class 
	Year Study Process and the Creation of the Additional SDU and Expedited 
	Deliverability Studies

Numerous revisions to the BSM Rules are required to appropriately account for, and

conform to, the changes being proposed in the interconnection processes.  For instance, since the 
Class Year Study bifurcation rules are being eliminated and replaced with two new categories of 
deliverability studies—i.e., the Additional SDU Study and the Expedited Deliverability Study, 
references in the BSM Rules to bifurcation processes must be addressed.  These include the 
removal of language in Section 23.4.5.7 that addresses the bifurcation rules originally approved

Honorable Kimberly D. Bose December 19, 2019

Page 29

by the Commission in December 2017.137  Proposed deletions that remove references to the 
Bifurcation of a Class Year Study occur in Sections 23.4.5.7.2, 23.4.5.7.3.2, 23.4.5.7.3.3,138

23.4.5.7.3.5, 23.4.5.7.13.1.1, 23.4.5.7.13.1.1(b), 23.4.5.7.13.4.2, 23.4.5.7.14.3.2, and

23.4.5.7.14.4.1 of the Services Tariff.  These changes update the BSM Rules to make it clear that BSM Determination will no longer be aligned with the completion of the two possible 
components of a bifurcated Class Year Study (i.e., “CY X-1” and “CY X-2”).

The proposed changes to the interconnection process in this filing necessitate that the

BSM Rules will apply to three possible interconnection studies that developers will be required 
to go through in order to obtain CRIS and become Installed Capacity Suppliers—a Class Year 
Deliverability Study, an Additional SDU Study, or an Expedited Deliverability Study.139  The 
proposed revisions therefore add references to Additional SDU Studies and Expedited 
Deliverability Studies.  New defined terms would be added to  Section 23.2.1 of the Services 
Tariff, which cross-reference the relevant definitions in Section 25 of the OATT (OATT, 
Attachment S).  Appropriate references to Additional SDU Studies and Expedited Deliverability 
Studies would also be added throughout Attachment H where it originally only referenced the 
“Class Year” or “Class Year Study.”  These additions occur in the definition of “Examined 
Facilities,” which is being moved from Section 23.4.5.7.3 into the Section 23.2.1 Definitions, as 
well as Sections 23.4.5.7.2, 23.4.5.7.2.1, 23.4.5.7.3.2, 23.4.5.7.3.3, 23.4.5.7.3.4, 23.4.5.7.3.5,

23.4.5.7.3.8, 23.4.5.7.6, 23.4.5.7.9., 23.4.5.7.13, 23.4.5.7.14, and 23.4.5.7.15.  Because the

proposal for Additional SDU Studies will only involve projects that were originally part of a

Class Year Study, the proposed revisions to the BSM Rules do not always list “Class Year Study, 
Additional SDU Study and Expedited Deliverability Study.”  In some limited instances the 
proposed amendments only require the additional reference to the Expedited Deliverability 
Study.  For example, Examined Facilities participating in an Additional SDU Study actually 
enter that study via a Class Year Study, therefore, tariff revisions that reference the entry into a 
study need only refer to a Class Year Study or Expedited Deliverability Study, as is the case in 
Section 23.4.5.7.9.3.2.  In other circumstances, however, adding the reference to Expedited 
Deliverability Studies is not applicable, but a reference to the Additional SDU Studies is 
required.  For example, only Class Year Studies and Additional SDU Studies can have multiple 
decision rounds after the initial decision period.  Examined Facilities in an Expedited 
Deliverability Study only have one decision round.  Therefore, the revisions in Section

23.4.5.7.3.3 only require the NYISO to provide BSM determinations prior to or

contemporaneous with “each Subsequent Decision Period for the Class Year Study and Additional SDU Study.”

137 See id.

138 The deletion of the bifurcation language allows existing Sections 23.4.5.7.3.3.1 through 23.4.5.7.3.3.5 of the Services Tariff to be consolidated into a single Section 23.4.5.7.3.3

139 The BSM Rules may also potentially apply to certain resources smaller than 2 MW that are not required 
to go through the Class Year process in order to receive CRIS MW.  See Responses to April 1, 2019 Letter and 
Notification of Implementation Issues that Necessitate Additional Limited Tariff Revisions, Docket No. ER19-467-
001 at pp 27−28 (explaining that “Resources could be subject to the BSM Rules and not be subject to the Class Year 
deliverability analysis” and that resources smaller than 2 MW would not be subject to a deliverability evaluation).

Honorable Kimberly D. Bose December 19, 2019

Page 30

ii.  Conforming Revisions to the BSM Rules Regarding the Timing of BSM

Determinations and How Examined Facilities will Impact the BSM Forecast Assumptions

The proposal to modify the interconnection processes to potentially allow for the

separation of certain Examined Facilities from other projects in the Class Year Study to be

evaluated with an Additional SDU Studies is similar to a bifurcation process, but requires several 
enhancements to the BSM Rules to reflect how BSM Determinations will be conducted and 
when they will be provided to developers.  The BSM Rules will need to allow for flexibility with 
regard to the timing of BSM Determinations for Examined Facilities that are subject to 
Additional SDU Studies that remain separated from the Class Year Study with which they were 
originally grouped.  They must allow for determinations to be provided with the subsequent 
Class Year Study following the Class Year Study that these Examined Facilities were originally 
a part of.  They must also establish when determinations would be made for Examined Facilities 
that remain separated from a Class Year Study.  Similarly, the creation of the Expedited 
Deliverability Study that can be conducted multiple times per year while a Class Year Study 
and/or an Additional SDU Study is ongoing requires the BSM Rules to account for how the 
NYISO will order the entry of these Projects into the BSM Forecast Assumptions.

In order to be clear about when the NYISO will develop its forecast assumptions for each 
of these three studies, the NYISO has modified and moved language that describes the 
“Mitigation Study Period” and the Starting Capability Period from Section 23.4.5.7.2 of the 
Services Tariff into the definitions found in Section 23.2.1.  Because the year of the Class Year 
Study determines the Starting Capability Period, which is the Summer Capability Period that 
“commences three years from the start of the year of the Class Year Study,” it also determines 
the Mitigation Study Period.  These terms continue to have the same meaning and application for 
a Class Year Study.  Additional clarification is required to describe the Starting Capability 
Period for Additional SDU Studies and Expedited Deliverability Studies because these studies 
could possibly start during one Class Year Study and be completed after the subsequent Class 
Year Study has begun.  Therefore, the proposed definition of Starting Capability Period provides 
that it is the same period used for the ongoing Class Year Study at the time the Additional SDU 
Study or the Expedited Deliverability Study process arrives at the Decision Period.140

The proposed revisions to the definition of Starting Capability Period also require that if the Additional SDU Study or the Expedited Deliverability Study arrives at its respective decision period while there is no Class Year Study underway, the Starting Capability Period would be the same period used for the “most recently completed Class Year Study.”

These enhancements to Section 23.4.5.7.3.2 of the Services Tariff also provide clarity 
with regard to the BSM Determinations for projects that are undergoing a Class Year Study, 
Additional SDU Study or Expedited Deliverability Study.  The general rule that has applied to 
Class Year Projects continues to apply, regardless of whether the Examined Facilities are being 
evaluated as part of a Class Year Study, Additional SDU Study or Expedited Deliverability

140 The revisions to the interconnection process will not allow for a new Class Year Study to start during the decision period for an Additional SDU Study or an Expedited Deliverability Study.

Honorable Kimberly D. Bose December 19, 2019

Page 31

Study.  As it does currently, the NYISO “will clear projects from lowest to highest, using for 
each Examined Facility the lower of (i) the first year value of its Unit Net CONE or (ii) 75 
percent of the Mitigation Net CONE.”  This provision, while remaining substantively 
unchanged, would be extended to apply to when the NYISO is evaluating more than one 
Examined Facility concurrently within either an Additional SDU Study or Expedited 
Deliverability Study.

The provision is also enhanced to reflect how Examined Facilities that have been through a Class Year Study, Additional SDU Study, or Expedited Deliverability Study will be included in the evaluation of Examined Facilities that utilize the same Mitigation Study Period, but have a 
later decision period.  The proposed revisions to this section make it clear that an Examined 
Facility that has accepted its determination from a previous study will be included in the BSM 
Forecast for any subsequent study that utilizes the same Mitigation Study Period.  The revisions to this section also make it clear when projects in an Additional SDU Study will have a separate decisional process from a Class Year Study.

In addition to deleting obsolete bifurcation language, the proposed revisions to Section

23.4.5.7.3.3 of the Services Tariff include clarifications regarding when the NYISO will provide 
its BSM Determinations to each project.  The revised language now allows the NYISO to 
provide this information to the project developer “prior to or contemporaneous with the 
commencement of the Initial Decision Period” for each study.  This timing enhancement is also 
applicable to the iterative decision periods that may occur for the Class Year Study and 
Additional SDU Study, where the NYISO is required to provide Revised Project Cost 
Allocations and BSM Determinations until all projects left in the study accept their respective 
cost allocation.  It is important to note that for an Expedited Deliverability Study there is no 
opportunity for the project to reject its allocation of interconnection costs, but a project has one 
opportunity to drop out of an Expedited Deliverability Study after it has received its initial BSM 
Determination.  There will be no change to deliverability costs and therefore project costs and 
the revised BSM determinations will be the same or more favorable for the projects that remain 
in the Expedited Deliverability Study.  Consequently, Developers that accept their initial BSM 
Determinations in an Expedited Deliverability Study will be deemed to accept their CRIS and the 
NYISO will provide revised and final BSM determinations to the remaining developers within

10 Business Days after the Initial Decision Period.  These revised BSM determinations will be final for all Examined Facilities that did not drop out of the study during this single decision process that applies to Expedited Deliverability Studies.

iii.  Accounting for the Renewable Exemption 1,000 Megawatt Limit According to 
	Mitigation Study Period

The NYISO’s pending compliance filing in Docket No. ER16-1404-000141 proposed to 
establish an exemption from the BSM Rules for up to 1,000 MW of intermittent renewable 
resources per Class Year.  However, if the revisions to the interconnection process proposed in

141 See New York Indep. Sys. Operator, Inc., Motion Requesting Commission Action on Compliance Filing, notice of Implementation Plans, and Conditional Request for Tariff Waivers of the New York Independent System Operator, Inc., Docket No. ER16-1404 (July 19, 2019) (describing the pending proposed Renewable Exemption and the NYISO’s implementation plans).

Honorable Kimberly D. Bose December 19, 2019

Page 32

this filing are accepted, the NYISO would no longer be making BSM Determinations solely on a 
single Class Year Study basis.  Accordingly, the NYISO has proposed revisions to Sections

23.4.5.7.13.1.1(b) and 23.4.5.7.13.2 that would govern the application of the 1,000 MW

Renewable Exemption to projects evaluated for BSM using the same Mitigation Study Period. As a result, the proposed revisions would apply the 1,000 MW Renewable Exemption limit to the Examined Facilities evaluated using the same Mitigation Study Period instead of the 
Examined Facilities in a given Class Year Study.

Substantively the mechanisms for applying the proposed 1,000 MW Renewable

Exemption remains unchanged, except the exemption threshold now applies to the multiple

studies that utilize the same Mitigation Study Period rather than to a singular or bifurcated Class Year Study.

Given the possibility that there will be multiple groups of Examined Facilities undergoing BSM evaluations utilizing the same Mitigation Study Period, this proposal includes a “first 
studied, first served” approach to allocating the available megawatts of the Renewable 
Exemption.  The exemptions would be awarded on a one for one basis for each megawatt of 
CRIS awarded to the Examined Facility that is a Renewable Exemption Applicant.  Each 
megawatt of CRIS that is awarded with a Renewable Exemption in a completed study reduces the Renewable Exemption megawatts that are available for the projects that are subsequently 
evaluated using the same Mitigation Study Period.

If the total amount of CRIS requested by Renewable Exemption Applicants in a Class

Year Study, Additional SDU Study or Expedited Deliverability Study exceeds the balance of the 
Renewable Exemption MW available for that Mitigation Study Period, the projects are awarded 
a prorated Renewable Exemption.  The prorated award would be calculated by multiplying the 
available Renewable Exemption MW remaining by each projects CRIS request divided by the 
sum total of the amount of CRIS requested by all the Renewable Exemption Applicants that have 
accepted their project cost allocation in the Class Year Study, Additional SDU Study or

Expedited Deliverability Study.

iv.  Necessary Data Requirements and Exemption Limitations for Expedited 
	Deliverability Studies Determinations

Due to the significantly shorter duration of Expedited Deliverability Studies, the NYISO 
has proposed some procedural deadlines under the BSM Rules that will make it easier for the 
NYISO to make timely and orderly BSM Determinations for Examined Facilities participating in 
the Expedited Deliverability Studies.  The NYISO has added a Section 23.4.5.7.3.6 to 
Attachment H of the Services Tariff, which adds a data submittal requirement for projects 
seeking to enter an Expedited Deliverability Study.  Project cost data requirements that are 
necessary for the NYISO to make a BSM Determination for each project must be deemed 
complete by the NYISO prior to the start of the Expedited Deliverability Study for the project to 
become a participant of that study.  If the project has not received a completeness determination 
from the NYISO at the time the Expedited Deliverability Study starts, the project will have the 
opportunity to enter a subsequent Expedited Deliverability Study or Class Year Study in 
accordance with the proposed revisions to Attachment S.  This new requirement is necessary to

Honorable Kimberly D. Bose December 19, 2019

Page 33

ensure the NYISO has complete and sufficient information to conduct the required BSM Determinations within the compressed timeline associated with the proposed Expedited Deliverability Studies.

Similarly, to allow Expedited Deliverability Studies move forward in the three to four 
month time frame, certain exemptions will not be available in an Expedited Deliverability 
Studies.  The project can enter and Expedited Deliverability Study and may be deemed exempt 
from an Offer Floor, but it will not be able to receive a Self Supply exemption or a Renewable 
Exemption, unless it uses technology already identified in the Services Tariff as an Exempt 
Renewable Technology.  The proposed revisions to Sections 23.4.5.7.6 and 23.4.5.7.14.1.1 of the 
Services Tariff explicitly prohibit a project requesting a Self Supply Exemption from 
participating in an Expedited Deliverability Study.  These projects, however, can continue to 
request a Self Supply Exemption as part of a Class Year Study or Additional SDU Study.  In 
addition, Section 23.4.5.7.13.1.1 (a)(ii) has been revised to allow projects in an Expedited 
Deliverability Study to request a Renewable Exemption only if it is “powered solely by a 
technology that is identified in the Tariff at the time of the start . . . of  Expedited Deliverability 
Study to be an Exempt Renewable Technology as defined in 23.4.5.7.13.1.1(a)(i)(A) above.” 
Again, these limitations are required to facilitate NYISO completion of its BSM Determinations 
within the three to four month time frames that are expected to be needed  to complete the 
Expedited Deliverability Study.  These exemptions, however, continue to remain fully available 
to projects that are part of a Class Year or Additional SDU Study.

The proposed revisions to BSM Rules also explicitly exclude UDR projects from entering 
an Expedited Deliverability Study.  UDRs must be both new and incremental transmission 
facilities and present a complex analysis to evaluate the Unit Net CONE for the Installed 
Capacity that they may bring into the Locality where they sink.  Because UDRs are required to 
be both new and incremental transmission this practically limits them from participating in an 
Expedited Deliverability Study.  Similarly, large interconnection projects are not allowed to enter 
these studies unless they already have obtained ERIS and are requesting CRIS only.  In addition, 
the NYISO does not believe that it will be practical to make a BSM Determination for a UDR 
project in the three or four month period that Expedited Deliverability Studies are expected to 
take given the unique features of the analysis that must be conducted for such projects.

v.  Ministerial Changes to Enhance Readability of BSM Rules

The NYISO also proposes to make several non-substantive ministerial and clarifying 
changes to the BSM Rules.  The NYISO has made several clean-up changes in Section 23.2.1 
and has moved into this section the definition of Examined Facilities.  The NYISO has also 
added several pertinent defined terms that are defined within the OATT into this definition 
section, so the reader can find the full definition of that term.  For example, the revised section 
will now include the definition of the three studies Class Year Study, Additional SDU Study and 
the Expedited Deliverability Study as well as the definition of the Final Decision Round.  In 
Sections 23.4.5.7.2.1 and  23.4.5.7.3.5, the NYISO is replacing less clear language that refers to 
an Expected CRIS Transferee with the term Expected CRIS Transferee.  Similarly, the NYISO is 
proposing clarifying revisions in Sections 23.4.5.7.2.4 and 23.4.5.7.3.5 to clarify that an NCZ 
Examined Project will be treated similarly to an Examined Facility in a Class Year Study or

Honorable Kimberly D. Bose December 19, 2019

Page 34

Additional SDU Study.  There are also several ministerial revisions proposed to correct the references to sections in the tariff and capitalized defined terms, such as “Developer.”

vi.  The NYISO’s Treatment of Proposed Language Currently Pending Before the 
	Commission

The NYISO’s longstanding practice when proposing revisions to its tariffs is to include all previously filed language that is accepted by the Commission or that is pending before the Commission with a specific effective date that precedes the NYISO requested effective date for the instant filing.  Attachments VI and VII to this filing, containing revisions to Attachment H of the Services Tariff, comport with this practice.

The NYISO is also attaching, for informational purposes only, clean and blacklined

versions of the instant tariff revisions, which include all pending language, in Attachment H, that 
the NYISO has filed with the Commission.  Attachments VIII and IX to this filing reflect a 
comprehensive version of Attachment H that was used in the development of this proposal to 
broadly inform the stakeholders on how the instant filing requires modification to the previously 
proposed rules.  These include the NYISO’s ESR Compliance Filing142 and its Section 205 filing 
for Distributed Energy Resources.143  Attachments VIII and IX to this filing also include pending 
language for which the NYISO may have requested a more immediate effective date than the 
tariff language found in Attachments VI and VII, but the effective date cannot be attached to a 
specific calendar date.  For example, there is language regarding bifurcation of the Class Year 
that is found throughout Attachments VIII and IX, but does not show up in Attachments VI and 
VII because when the language was filed, the NYISO requested an effective date for revised 
language that was contingent on the latter of the Commission’s acceptance of the bifurcated 
Class Year proposal or the NYISO’s Renewable Exemption compliance filing.144  The tariff 
language in Attachments VIII and IX also informs the Commission and stakeholders on how this 
proposal will interact with the pending tariff language that the NYISO has filed with a more 
immediate effective date, such as its reinstatement of Category III within the Examined Facility 
definition, which was proposed in the NYISO’s ESR Compliance Filing.145

142 New York Indep. Sys. Operator, Inc., Compliance Filing and Request for Extension of Time of Effective Date, Docket No. ER19-467-000 (December 3, 2018) (“ESR Compliance Filing”). 
	143 New York Indep. Sys. Operator, Inc., Proposed Tariff Revisions Regarding Establishment of 
Participation Model for Aggregations of Resources, Including Distributed Energy Resources and Proposed Effective Dates, Docket No. ER19-2276-000 (June 27, 2019) (“DER Filing”).

144 New York Indep. Sys. Operator, Inc., Interconnection Process Improvements, Docket No. ER18-80-000, 
at p 47 (October 16, 2017) (requesting a flexible effective date for its proposed revisions referencing bifurcation of 
the Class Year within the pending Renewable and Self Supply exemptions revisions; namely, that the language 
“become effective two weeks after the occurrence of the later of the following: (1) December 16, 2017, the 
requested effective date for all other Class Year bifurcation tariff revisions proposed in this filing (which are 
included in Attachments XVII and XVIII); and (2) the date that the Commission accepts Sections 23.4.5.7.13 and

23.4.5.7.14, as proposed in Docket No. ER16-1404.”).

145 See ESR Compliance Filing at pp 64−67 (requesting an effective date for the reinstatement of Category III language that would be one day after the Commission issues an order accepting the language, unless the timing of the order were such that immediate effectiveness of this language would disrupt the NYISO’s administration of the Class Year process or the BSM Rules).

Honorable Kimberly D. Bose December 19, 2019

Page 35

vii. Stakeholder Reservation of Rights Regarding Contested Pending Tariff 
	Language

As discussed above, the proposed tariff revisions in this filing were made to a “base”

version of the tariff that includes previously proposed, but still pending, tariff language.  Some of 
that tariff language was protested by certain stakeholders when it was initially filed with the 
Commission.  The relevant language appears in the version of Sections 23.2.1 and 23.4.5.7.13 of 
the Services Tariff that are included in Attachments III and IV of this filing.146  Various 
stakeholders may continue to object to the acceptance of that pending language in its current 
form.

There is no reason why disputes over a pending compliance revision should prevent the adoption of undisputed new enhancements that are unrelated except for the fact that the same 
underlying tariff provision is implicated.  During the stakeholder process that culminated in this filing, the NYISO clearly stated that it would not construe stakeholder support for these 
necessary enhancements to the BSM Rules as a change to positions stakeholders may have taken on pending revisions or as a waiver of arguments previously made to the Commission.  The 
NYISO also indicated that it would inform the Commission that stakeholders that voted to 
support this filing did so with the understanding that they were not changing or waiving past 
positions or arguments regarding pending tariff revisions.

E.	CRIS Expiration Rules

Attachment S to the OATT establishes the manner by which a Developer can obtain

CRIS and rules governing the expiration of such CRIS.147  As part of the stakeholder process and 
the NYISO’s continued effort to enhance its processes, the NYISO identified certain matters 
concerning the maintenance and expiration of CRIS in its existing tariffs that required 
clarification.

i.  Retention of CRIS by Facilities Not Subject to the NYISO’s FERC-
	Jurisdictional Interconnection Process.

Under the NYISO’s existing rules, a Large Facility or Small Generating Facility obtains 
CRIS through Attachment S but withdraws or is withdrawn from the Interconnection Queue 
before becoming operational will not retain its CRIS.  A Large Facility or Small Generating 
Facility that is subject to the NYISO’s FERC-jurisdictional interconnection process generally has 
a period of four years to enter into commercial operation, after which, if it has not done so, it will 
be withdrawn from the NYISO’s Interconnection Queue and will lose any CRIS associated with

146 The relevant language can be found in Sections 23.2.1, 23.4.5.7.13.1 and 23.4.5.7.13.4.2 of the Services 
Tariff.  Section 23.2.1 includes a pending revision to the definition of “Examined Facility” that would restore 
“Category III” Examined Facilities to the BSM Rules.  That pending revision was first proposed in the NYISO’s 
December 3, 2018 compliance filing in Docket No. ER19-467 and has been discussed extensively in that 
proceeding.  Sections 23.4.5.7.13.1 and 23.4.5.7.13.4.2 of the Services Tariff include revisions that involve the 
1,000 MW limit original proposed for the Renewable Exemptions in the NYISO’s April 13, 2016 compliance filing 
in Docket No. ER16-1404.

147 OATT Section 25.9.3.1.

Honorable Kimberly D. Bose December 19, 2019

Page 36

the project.148  However, the existing tariff is silent on the length of time that a proposed project that only participates in the NYISO’s FERC-jurisdiction interconnection process to obtain CRIS can hold CRIS without going into service.149

Accordingly, the NYISO proposes to revise the requirements for the retention of CRIS 
for facilities not subject to the NYISO’s FERC-jurisdictional interconnection processes. 
Specifically, for such facilities that obtain CRIS through Attachment S, the NYISO proposes to 
terminate the CRIS unless the facility goes into operation (i.e., synchronizes to the system) 
within four years of obtaining CRIS.150  This four-year period is consistent with the time period 
that facilities being studied under the LFIP and SGIP have to enter into commercial operation or 
be subject to being withdrawn from the NYISO’s Interconnection Queue and losing their CRIS. 
The proposed revisions are intended to provide clear rules that strike a balance between 
providing a project a reasonable period of time to go into operation while not allowing a project 
to hold on to CRIS indefinitely without going into service.  In addition, to ensure that facilities 
that have obtained their CRIS before these new rules obtain the full benefit of this four year 
period, the NYISO proposes a transition rule.  Specifically, if a facility has already obtained its 
CRIS on or before the effective date of this tariff change, the NYISO will only terminate its 
CRIS if the facility does not synchronize within four years of the effective date of the tariff 
revisions.

ii.  Expiration of CRIS for Facilities That Have Not Participated in an Installed 
	Capacity Auction or Registered as an Installed Capacity Resource

A Large Facility or Small Generating Facility that has gone into service and has CRIS 
will retain such CRIS as long as the facility is not CRIS-inactive for more than three continuous years.151  A facility generally becomes “CRIS-inactive” on the last day of the month for which it ceases to offer capacity into the NYISO’s capacity auction or ceases to be a registered Capacity Resource for a Load Serving Entity (“LSE”) through a bilateral transaction or self-supply 
arrangement.152  The consequence of the current formulation of the rule is that until a facility 
either offers capacity or registers as a Capacity Resource, it cannot become CRIS-inactive, and the three-year CRIS expiration clock will not start.  As a result, the facility would be able to 
retain CRIS indefinitely, as the facility could never be deemed to be CRIS-inactive, regardless of the fact that the facility was not making use of the CRIS.

148 Subject to Section 30.4.4.5.2 of the OATT, Large Facilities have four years to go into commercial

operation following the acceptance of their cost allocation and posting Security in accordance with Attachment S. 
See OATT Section 30.4.4.5.1.1.  Similarly, a Small Generator has four years to go into commercial operation from 
the tendering of a Small Generator Interconnection Agreement (“SGIA”).  See OATT Section 30.4.4.5.3.1.

149 A facility that has CRIS but is not subject to the NYISO’s FERC-jurisdictional interconnection process 
would be those projects that interconnect to New York State Transmission System or Distribution System pursuant 
to a non-FERC-jurisdictional interconnection process, such as the New York State Standardized Interconnection 
Requirements or a Transmission Owner interconnection process, and seek to obtain CRIS through Attachment S.

150 OATT Section 25.9.3.4.

151 OATT Section 25.9.3.1.  Once a facility is CRIS-inactive for three continuous years, the facility’s CRIS will terminate unless otherwise provided for in Section 25.9.3.1 of the OATT.

152 OATT Section 25.9.3.1.1.

Honorable Kimberly D. Bose December 19, 2019

Page 37

The NYISO proposes to revise and clarify the existing CRIS expiration rules to tighten 
the rules governing the retention of CRIS to prevent facilities from holding CRIS without (i) 
participating in the Installed Capacity market or (ii) otherwise certifying as an Installed Capacity 
Supplier or exporting capacity to an External Control Area for an extended period of time. 
Under this revised approach, the date on which the project goes into operation triggers the 
potential for a facility to be considered CRIS-inactive, which will then start the three-year period 
that a facility may be CRIS-inactive before its CRIS is terminated.153  For purposes of this 
proposal, the date of operation will be the date on which the project completes its initial 
synchronization with the system.  The initial synchronization date is the date that a facility with 
CRIS can start to participate in the NYISO-administered Installed Capacity markets and serves 
as an appropriate start date to commence the three-year period.  Accordingly, all resources with 
CRIS will be obligated to inform the NYISO of their initial synchronization.154  Thereafter, 
facilities with CRIS that have synchronized shall be CRIS-inactive beginning on the last day of 
the month for which it (i) failed to offer capacity in the NYISO’s capacity auction and/or (ii) 
failed to certify capacity as an Installed Capacity Supplier through a Bilateral Transaction or to 
export capacity to an External Control Area.  This will then commence the three-year period.155

This proposed revision will apply equally to load modifiers that have CRIS but never participate in the Installed Capacity market, including resources with CRIS that are acting as a load modifier outside of the NYISO-administered markets through a contract with an LSE.156 Load modifiers will be treated as CRIS-inactive following their initial synchronization until they participate in the Installed Capacity market or certify capacity as an Installed Capacity Suppliers through a Bilateral Transaction.  However, facilities with CRIS that export capacity to an 
External Control Area will not be considered to be CRIS-inactive by the mere fact that they are not participating in the NYISO Installed Capacity market.

These proposed tariff revisions may affect existing facilities with CRIS that are not

presently classified as CRIS-inactive under the existing rules.  The NYISO, therefore, proposes that if an existing facility synchronized before the last day of the month containing the effective date of these revisions and such facility was not previously CRIS-inactive under the current 
rules, such facility will be not be considered to be CRIS-inactive under the proposed rules until the last day of the month containing the effective date.157  The facility will only be considered as CRIS-inactive under the proposed rules based on activity on or after that date.

153 Proposed OATT Sections 25.9.3.1.1, 25.9.3.1.2.

154 For facilities being studied under the LFIP and SGIP, the NYISO proposes to include this requirement in their Standard Large Generator Interconnection Agreement (“LGIA”) and SGIA by providing a pro forma letter requiring the Developer to advise the NYISO when the facility completes its initial synchronization.  This revision to the LGIA and SGIA is further discussed in Part IV.K.ii.

155 Proposed OATT Section 25.9.3.1.1.

156 Proposed OATT Section 25.9.3.1.1.

157 Proposed OATT Section 25.9.3.1.1.1.  For example, if the Commission accepts the proposed revisions in Section IV.E with an effective date in February 2020, existing load modifiers that fail to offer into the NYISO capacity market for March 2020 would first be CRIS-inactive in April 2020 and, if remained CRIS-inactive for three continuous years, would lose its CRIS.

Honorable Kimberly D. Bose December 19, 2019

Page 38

iii.  Additional Revisions

The NYISO also proposes to clarify the existing requirements for handling CRIS for

proposed facilities that withdraw from the NYISO Interconnection Queue prior to going

operational in Section 25.9.3.1 of the NYISO OATT.  The proposed revisions detail the

NYISO’s current rule that precludes a facility from retaining its CRIS status under Attachment S if the facility withdraws or is withdrawn from the NYISO Interconnection Queue prior to going into operation.158

F. 	Eliminate Duplication in SRIS and Class Year Studies

The NYISO proposes to revise the scope of the analysis performed in the SRIS and Class Year Study stages of the interconnection process to eliminate duplicative or unnecessary 
analysis.  The proposed revisions have the potential to shorten the time required to perform the SRIS and the Class Year Study.

The SRIS currently consists of a short circuit analysis, a stability analysis, and a power 
flow analysis, which analysis is specifically detailed in the study scope for each SRIS.159  Based 
on the NYISO’s experience in administering the SRIS and applying the applicable reliability 
criteria, the NYISO determined that certain types of analysis currently performed in the SRIS 
can be more narrowly applied or eliminated in most cases or are more efficiently addressed in the 
Class Year Study.  This revision will shorten the length of many SRISs without the risk of 
overlooking potential reliability violations.  The NYISO, therefore, proposes to revise the SRIS 
requirements to provide that the study will instead consist of short circuit analysis, local steady 
state analysis, and local stability analysis.160  Among other things, the revised scope of the SRIS 
will eliminate the need to perform thermal transfer, voltage transfer, and stability transfer 
analysis for internal interfaces unless there is a reasonable potential that SUFs are required.  In 
addition, when N-1-1 analysis is necessary, the NYISO will perform a limited, local N-1-1 
analysis, in place of a wide-area N-1-1 analysis, which is currently the default.  If, however, the 
NYISO determines that additional analysis could reasonably be expected to identify reliability 
violations requiring SUFs, the NYISO may perform additional analysis at the SRIS stage.161  The 
NYISO will advise the Developer if such additional analyses are required as a part of the scoping 
meeting for its project and detail the additional analyses in the SRIS study scope, which must be 
approved by the Operating Committee.

For purposes of the Class Year Study, the NYISO will then focus on incremental system-
wide and/or projects’ interaction analysis.  The NYISO will continue to perform thermal, 
voltage, and stability analysis.162  However, to the extent local thermal, voltage, and stability 
analysis was performed as part of the SRIS, the NYISO will rely on such analysis in the Class

158 Proposed OATT Sections 25.9.3.1, 25.9.3.1.1.

159 OATT Section 30.7.3.

160 Proposed OATT Section 30.7.3.1.  Note that the tariff language was relocated from Section 30.7.3 and

revised.

161 Proposed OATT Section 30.7.3.1. 
162 OATT Section 25.6.1.1.1.1.4.

Honorable Kimberly D. Bose December 19, 2019

Page 39

Year Study, including the identification of SUFs required to mitigate adverse impacts under the 
NYISO Minimum Interconnection Standard.163  The NYISO will then refine the cost and timing 
to construct any SUFs identified in the SRIS.164  In addition, the NYISO will no longer 
reproduce resource adequacy analysis, but will instead use the most recent reliability analysis of 
the existing system already performed in the NYISO’s reliability planning process.165  The 
NYISO will begin to implement the changes to the Class Year Study analysis for Class Year 
2019.

G.	Require Class Year Study Agreements, Deposits, and Project Data Earlier in

Class Year Process

The NYISO proposes to revise the timing in the Class Year process for a Developer to 
elect to enter a Class Year Study and to submit a completed Class Year Study Agreement, along 
with the required project data and deposit.  The proposed process changes will expedite the 
commencement of the Class Year Study and shorten the duration of the Class Year Study 
process by advancing certain eligibility and enrollment requirements prior to the Class Year Start 
Date.

i.  Background

The Class Year Study commences on the Class Year Start Date, which is the first

Business Day after thirty calendar days following the completion of the prior Class Year

Study.166  As soon as practicable after the Class Year Start Date is established, the NYISO

tenders a Class Year Study Agreement to each Developer that satisfies the requirements to be an Eligible Class Year Developer.167

To become a Class Year Project, the Developer of an Eligible Class Year Project must 
currently elect to enter into the applicable Class Year by providing notice to the NYISO five 
Business Days after the Class Year Start Date.168  In addition, the Developer of an Eligible Class 
Year Project must have a completed SRIS or System Impact Study approved by the Operating 
Committee for its project and have satisfied a regulatory milestone or provided the required 
deposit in lieu of satisfying the milestone.169  The Developer of an Eligible Class Year Project

163 Proposed revisions to OATT Section 25.6.1.1.1.1.4.

164 Proposed revisions to OATT Section 25.6.1.1.1.1.4. 165 Proposed revisions to OATT Section 25.6.1.1.1.1.5. 166 OATT Section 25.5.9.

167 OATT Section 30.8.1.  The NYISO may also tender a Class Year Study Agreement at an earlier point to 
a Developer that is an Eligible Class Year Project, upon request.  Id.  An Eligible Class Year Project is a Developer 
“that (i) satisfies the criteria for inclusion in the next Class Year Interconnection Facilities Study, as those criteria 
are specified in Sections 25.5.9 and 25.6.2.3.1 of this Attachment S, Section 32.1.1.7 of Attachment Z to the OATT 
and/or Section 32.3.5.3.2 of Attachment Z to the OATT; or (ii) that seeks evaluation in a Class Year Study to obtain 
or increase CRIS as permitted by this Attachment S and satisfies the criteria for inclusion in the next Class Year

Interconnection Facilities Study specified in Section 25.5.9 of this Attachment S.”

168 OATT Section 25.5.9.1.

169 OATT Sections 25.5.9, 26.2.3.1.  Small Generating Facilities must satisfy separate criteria for entering 
into a Class Year, which requirements are set forth in OATT Sections 25.5.9, 32.1.1.7, and 32.3.5.3.2.  The NYISO 
proposes to also revise OATT Section 32.1.1.7 to make it explicit that a Small Generating Facility seeking more

Honorable Kimberly D. Bose December 19, 2019

Page 40

must also execute the Class Year Study Agreement and deliver it to the NYISO within thirty

calendar days of receiving the agreement.170  Along with the executed Class Year Study

Agreement, the Developer must submit, among other things, the required technical data, the

required study deposit, and an additional deposit if the project has not satisfied an applicable

regulatory milestone.171  Within ten Business Days of the NYISO’s confirming receipt of

executed Class Year Study Agreement, required technical data, and required deposits, the

NYISO and Connecting Transmission Owner will execute the agreement.172  The changes

between the current Class Year enrollment process and the proposed revisions are reflected in the figure provided as Attachment III.

The NYISO’s proposed revisions to the eligibility and enrollment requirements will 
refine and clarify the procedures for Developers seeking to enter a Class Year Study and 
eliminate potentially significant delays at the start of the Class Year process.  Efficiency at the 
start of the Class Year will become more and more important with the increasing size of the 
Class Year.

ii.  Revisions to Expedite Enrollment Process

The NYISO proposes to make a number of revisions to streamline and expedite this

enrollment process.  The Class Year Study will continue to commence on the Class Year Start

Date, which remains the first Business Day after thirty calendar days following the completion of the prior Class Year Study.173  However, as detailed below, the NYISO will now provide prior notice of the upcoming Class Year Start Date and require that the Developer of Eligible Class Year Projects satisfy certain eligibility requirements prior to, rather than after, the Class Year Start Date.  After it confirms that the Developer has satisfied the eligibility requirements, the NYISO will tender the Class Year Study Agreement to the Developer.  The Developer will then have ten Business Days, rather than thirty calendar days, to complete the Class Year Study 
Agreement and to provide the required deposits and project data.

The NYISO reduced the amount of time for a Developer to enroll in the Class Year Study 
in response to feedback from Developers and stakeholders that the thirty-day response period for 
Developers was needlessly long.  Developers seeking to enter a Class Year have sufficient 
knowledge through the NYISO’s committees and working groups concerning when the next 
Class Year is going to begin.  The enrollment requirements that must be completed after the 
tender of the Class Year Study Agreement are known and can be prepared in advance, as the pro 
forma Class Year Study Agreement is available in the NYISO OATT and contains all of the data 
fields that the NYISO requires.  There are few, if any, unknowns that would require action by the 
Developer following the tendering of the Class Year Study Agreement.  Moreover, now that the 
NYISO will be providing formal, advanced notice of the next Class Year Study Date, the

than 2 MW of CRIS must satisfy the requirements of Section 30.8.1, as applicable.  Proposed revision to OATT Section 32.1.1.7.

170 OATT Section 30.8.1. 
171 OATT Section 30.8.1. 
172 OATT Section 30.8.1. 
173 OATT Section 25.5.9.

Honorable Kimberly D. Bose December 19, 2019

Page 41

Developer will, in practice, have roughly the same amount of time as before to satisfy the enrollment requirements.

Finally, the proposed revisions will specify the consequences to Developers that

subsequently retract their election to enter the Class Year Study.  The changes to the Class Year enrollment requirements will not apply to Class Year 2019, which has already proceeded beyond the enrollment stage.  They will, however, apply to the Class Year subsequent to Class Year 2019.  A detailed description of the specific tariff amendments necessary to streamline and 
expedite the Class Year Study enrollment process is set forth below.

iii.  Proposed Tariff Modifications

First, the NYISO proposes to require prior to the Class Year Start Date that the Developer provide its notice of intent to enter the study, to detail the manner in which it will address the 
regulatory milestone requirement, and to demonstrate that it has satisfied certain other existing Class Year requirements.174

The NYISO will provide notice of the Class Year Start Date.175  Within five Business 
Days of the posting of this notice, the Developer of an Eligible Class Year Project must provide 
notice to the NYISO electing to enter the Class Year and addressing the regulatory milestone 
requirement at this time by either: (i) demonstrating that the project satisfies an applicable 
reliability milestone or (ii) notifying the NYISO that, within 10 Business Days of the NYISO’s 
tendering the Class Year Study Agreement, the Developer will submit the required deposit in 
lieu of the applicable reliability milestone or a qualifying contract (which is described in Part 
IV.H below).176  In addition, on or before the Class Year Start Date, the Developer must: (i) 
demonstrate that it satisfies the other existing tariff criteria for inclusion in the next Class Year 
(e.g., having its SRIS approved by the Operating Committee), and (ii) if the Developer is only 
request CRIS, already have completed either a Class Year Study for ERIS, a System Impact 
Study in the SGIP, or a comparable utility interconnection study if the project is not subject to 
the NYISO’s interconnection procedures.177

Second, the NYISO will then tender a Class Year Study Agreement to a Developer that has satisfied the above eligibility requirements.178

Third, the Developer must complete, but is not required to have executed, the Class Year 
Study Agreement and deliver it to the NYISO within ten Business Days after Developer’s receipt

174 Proposed revisions to OATT Sections 25.5.9.1, 30.8.1.

175 Proposed revisions to OATT Section 25.5.9.1.  The NYISO will both post notice and send notice to entities registered for the distribution list for the Operating Committee.  Id.

176 Proposed revisions to OATT Sections 25.5.9.1, 30.8.1. 177 Proposed revisions to OATT Section 25.5.9.1.

178 Proposed revisions to OATT Sections 25.5.9.1, 30.8.1.  The NYISO may also tender a Class Year Study 
Agreement at an earlier point to a Developer that is an Eligible Class Year Project, upon request.  OATT Section

30.8.1.  When a Developer requests tender of a Class Year Study Agreement before the NYISO issues notice of a

Class Year Start Date, the Developer must either demonstrate that the project satisfies the applicable regulatory

milestone or provide notice that it will submit the regulatory milestone deposit or submit a qualifying contract before the NYISO will tender the Class Year Study Agreement.  Id.

Honorable Kimberly D. Bose December 19, 2019

Page 42

of the Class Year Study Agreement.179  Along with the completed Class Year Study Agreement, 
the Developer must submit, among other things, the required technical data,180 the required study 
deposit, and either a deposit or demonstration of a qualifying contract if it has not satisfied an 
applicable regulatory milestone (as described in Part IV.H below).181  This proposal will shift the 
point in time when the parties will execute the Class Year Study Agreement, and reduce 
administrative redundancy by eliminating the execution of multiple versions of the Class Year 
Study Agreement if the information or technical data is insufficient.  The NYISO is not 
proposing to modify any of the other information that must be submitted with the completed 
Class Year Study Agreement.182

Fourth, the NYISO proposes to establish time frames and requirements for the NYISO to review, and the Developer to correct, deficiencies in the technical data provided by the 
Developer.  If the NYISO determines that the technical data provided by the Developer is 
deficient, it will notify the Developer of the reasons for the deficiency.183  The Developer must then provide the additional information required to cure the deficiency within ten Business Days of receipt of this notice.184  The Developer’s failure to cure the deficiency will result in the 
withdrawal of the project from the Interconnection Queue.185

Fifth, the NYISO, Connecting Transmission Owner, and Developer will execute the

Class Year Study Agreement within ten calendar days of the NYISO confirming receipt of the Class Year Study Agreement, the required technical data, and required deposits from the 
Developer.186

A Developer that satisfies the above requirements will become a Class Year Project.187  If 
a Developer elects to enter a Class Year Study, but retracts its election prior to the NYISO’s 
tender of the Class Year Study Agreement for the Developer to complete, the project will not

179 Proposed revisions to OATT Section 30.8.1.  The OATT currently requires a Developer to execute an 
Class Year Study Agreement prior to submitting it to the NYISO.  The NYISO has revised this requirement, so that 
the Developer is only required at this point to complete the required fields in the pro forma agreement and deliver it 
to the NYISO.  After the NYISO confirms the receipt of the agreement (including confirmation of the information 
contained in the agreement), the technical data, the study deposit, and demonstration of a regulatory milestone or 
qualifying contract or two-part deposit in lieu of satisfying the regulatory milestone requirement, the Developer,

NYISO, and Connecting Transmission Owner will subsequently have ten calendar days to execute the agreement. 
See proposed revisions to OATT Sections 25.8.1, 30.4.4.6, 30.8.1, 30.8.2.1.  The NYISO is proposing a similar 
change to the requirements for the facility study agreement in the SGIP.  See proposed revisions to OATT Sections

32.3.5.2, 32.3.5.8.

180 This data includes date required by the Connecting Transmission Owner, to the extent that such data is requested by the NYISO when it provides notice of the Class Year Start Date or tenders the Class Year Study 
Agreement.  Proposed revisions to OATT Section 30.8.1.

181 Proposed revisions to OATT Section 30.8.1.

182 This includes the Developer’s election of which interconnection service will be evaluated in the Class Year Study and, for Large Facilities that are not yet in service, an updated, proposed In-Service Date, Initial 
Synchronization Date, and Commercial Operation Date.  OATT Section 30.8.1.

183 Proposed revisions to OATT Section 30.8.1.

184 Proposed revisions to OATT Section 30.8.1. 
185 Proposed revisions to OATT Section 30.8.1. 
186 Proposed revisions to OATT Section 30.8.1. 
187 Proposed revisions to OATT Section 25.5.9.1.

Honorable Kimberly D. Bose December 19, 2019

Page 43

become a member of the Class Year Study.188  If, however, the Developer retracts its election 
after the NYISO’s tender of the Class Year Study Agreement (whether prior to or after the 
deadline for executing the Class Year Study Agreement), the Developer’s project will not 
become a member of a Class Year Study, but such retraction will count as one of the two Class 
Year Studies that a project is permitted to enter.189  The proposed revisions would also no longer 
require withdrawal from the NYISO’s Interconnection Queue for failing to execute a Class Year 
Study Agreement after requesting tender, unless the project exceeded the number of Class Year 
Studies that it is permitted to enter under Section 25.6.2.3.4 of Attachment S.

H. 	Revise and Clarify Regulatory Milestones Requirements

To participate in a Class Year Study, a Developer must currently, at the time it submits its 
executed Class Year Study Agreement, either demonstrate that its project has satisfied one of the 
regulatory milestones prescribed in Attachment S of the OATT or provide a two-part deposit 
consisting of $100,000, plus $3,000/MW for the nameplate capability of the facility.190  As 
described in Part IV.G above, the NYISO proposes to revise the enrollment requirements for the 
Class Year to require that, at the same time that it provides notice to the NYISO of its election to 
enter a Class Year, the Developer also demonstrate that its project satisfies a regulatory 
milestone or notify the NYISO that it will satisfy a permitted alternative in lieu of a regulatory 
milestone.191

As detailed below, the NYISO proposes certain revisions to the regulatory milestone

requirements: (i) to clarify the application of the regulatory milestones for certain project types (e.g., offshore wind projects), (ii) to permit a project that has not yet satisfied a regulatory 
milestone to rely on certain financial agreements instead of a deposit to satisfy the regulatory milestone requirement for purposes of entering the Class Year, and (iii) to provide for the return of a deposit in lieu of a regulatory milestone at the completion of Class Year Study, regardless of whether the Developer accepts or rejects its cost allocation.

The proposed revisions will provide additional clarity concerning the regulatory

milestone requirements.  In addition, the proposed revisions establish additional flexibility to

enable projects to enter a Class Year prior to the satisfaction of a regulatory milestone.  Finally, 
the proposed revisions clarify the treatment of deposits provided in lieu of satisfying a regulatory 
milestone and ensure consistent treatment within the OATT regarding the refund of deposits.

i.  Clarifications of Application of Regulatory Milestones for Certain Project 
	Types

A Developer must obtain or achieve at least one of the regulatory determinations or

actions for a Large Facility listed in Section 25.6.2.3.1.1 of Attachment S.  The NYISO reviewed 
with its stakeholders the application of the existing regulatory milestones to different project

188 Proposed revisions to OATT Section 25.5.9.1.

189 Proposed revisions to OATT Sections 25.5.9.1, 30.8.1. 190 OATT Section 30.8.1.

191 Proposed revisions to OATT Section 25.5.9.1.

Honorable Kimberly D. Bose December 19, 2019

Page 44

types.  Based on this review, the NYISO developed with stakeholder input certain new

regulatory milestones and clarifications to other existing milestones.  The NYISO proposes to include these revised milestones in Section 25.6.2.3.1.1 of the OATT.  The revisions ensure that appropriate milestones exist for the different project types that participate in the NYISO’s 
interconnection processes.

First, the NYISO proposes to insert a new regulatory milestone applicable to offshore wind facilities to be located on the outer continental shelf.192  Specifically, the Developer of a Large Generating Facility that is an offshore wind facility on the outer continental shelf must demonstrate that it has a construction and operations plan deemed sufficient by the Bureau of Ocean Energy Management (“BOEM”) for which the BOEM has issued a Notice of Intent to prepare a Draft Environmental Impact Statement for the Large Facility in accordance with the U.S. Environmental Protection Agency pursuant to the National Environmental Policy Act of 1969 (“NEPA”) and its implementing regulations.193

Second, the NYISO proposes to clarify the application of the regulatory milestone for 
obtaining a negative declaration issued pursuant to the New York State Environmental Quality 
Review Act (“SEQRA”) in the case of an uncoordinated SEQRA review—that is, in cases in 
which no lead agency is designated.194  As amended, the provision will clarify that a negative 
declaration issued by any entity in accordance with SEQRA will satisfy the regulatory milestone 
requirement.195

Third, the NYISO also proposes to clarify the milestone for a determination pursuant to Article VII of the New York Public Service Law regarding the siting of major utility 
transmission facilities.  As amended, the milestone provides that a determination that a project’s Article VII application complies with Section 122 of the Public Service Law may apply to either a Class Year Transmission Project or a transmission portion of a Large Facility.196

Finally, the NYISO proposes to insert a new regulatory milestone that is applicable to

Large Facilities with Attachment Facilities, System Upgrade Facilities, or System Deliverability Upgrades that require an Article VII application.197  The new milestone provides for a 
determination pursuant to Article VII that the Article VII application complies with Section 122 of the Public Service Law.

192 The milestone is limited to offshore wind facilities on the outer continental shelf because wind facilities greater than 25 MW within New York State’s jurisdictional waters would be subject to a determination pursuant to Article 10 of the New York Public Service Law for which there is a separate regulatory milestone.  See OATT 
Section 25.6.2.3.1.1.7.

193 Proposed OATT Section 25.6.2.3.1.1.8. 194 OATT Section 25.6.2.3.1.1.2.

195 Proposed revisions to OATT Section 25.6.2.3.1.1.2. 196 Proposed revisions to OATT Section 25.6.2.3.1.1.4. 197 Proposed OATT Section 25.6.2.3.1.1.9.

Honorable Kimberly D. Bose December 19, 2019

Page 45

ii. 	Alternate Approach for Addressing Regulatory Milestone

A Developer that cannot timely satisfy its applicable regulatory milestone may currently 
make use of an alternative approach to enter a Class Year Study.  Currently, the Developer may 
provide a deposit in lieu of the milestone in the amount of $100,000, plus $3,000 per MW, for 
purposes of entering a Class Year Study.198  If a Developer uses an alternative approach, the 
Developer will still be required to satisfy a regulatory milestone within six months of the 
NYISO’s tendering to the Developer a Standard Large Generator Interconnection Agreement 
(“LGIA”) for the project.199

The NYISO proposes to establish another alternative that a Developer can provide in lieu 
of satisfying the regulatory milestone or providing the deposit for purposes of entering a Class 
Year Study.  Specifically, the NYISO propose to permit a Developer to demonstrate that it 
satisfies one of the following milestones: (i) a New York State Energy Research and 
Development Authority (“NYSERDA”) Renewable Energy Certificate (REC) contract; (ii) a 
NYSERDA “Market Bridge Incentive” contract; or (iii) a power purchase agreement.200  As with 
the deposit, these alternatives provide evidence that a Developer’s project is progressing and is 
more likely to move forward with its project.  The proposed revisions will provide Developers 
with additional flexibility to proceed with their projects in the Class Year and minimize costs to 
Developers, while ensuring the NYISO that Developers are making reasonable progress in 
advancing their projects.

Notwithstanding a Developer’s use of a qualifying financial agreement for purposes of 
entering a Class Year, the Developer will still be ultimately responsible for satisfying a 
regulatory milestone.201  The financial agreements do not constitute a milestone in project 
development akin to the permitting milestones currently used as regulatory milestones.

If a Developer in the current Class Year 2019 has used a deposit as an alternative to 
satisfy the regulatory milestone requirements, it may obtain a refund from the NYISO for this 
deposit if it satisfies one of the alternative financial agreement milestones by March 1, 2020.202

iii.	Study Deposit

Currently, the $3,000 per MW portion of the deposit that a Developer may submit in lieu of a regulatory milestone is fully refundable and will be returned by the NYISO upon the earlier of the Developer’s satisfaction of the regulatory milestone or its withdrawal from the

198 OATT Sections 25.5.9.1, 25.6.2.3.1.  The NYISO proposes to clarify that the MW amount will be

determined based on the project’s “requested ERIS” amount, rather than its “nameplate capacity.”  This change

addresses the circumstances in which a generator’s nameplate capacity differs from the amount of ERIS it is seeking in the interconnection process, as in the case of uprates or generators with output limiting equipment. 
	199 OATT Sections 25.6.2.3.2, 25.6.2.3.3, 30.11.1.  The NYISO proposes to clarify this timing requirement in Section 25.6.2.3.3 of the OATT.

200 Proposed revisions to OATT Section 25.6.2.3.1. 
201 OATT Sections 25.6.2.3.2, 25.6.2.3.3, 30.11.1. 
202 Proposed revisions to OATT Section 25.6.2.3.1.

Honorable Kimberly D. Bose December 19, 2019

Page 46

Interconnection Queue.203  The NYISO proposes to revise this requirement to address other

circumstances in which the Developer will exit the Class Year, after which the NYISO will not 
need to retain the deposit.  Specifically, the NYISO proposes that it will return the deposit at the earlier of the Developer’s: (i) satisfaction of the regulatory milestone; (ii) withdrawal from the 
Interconnection Queue; (iii) withdrawal from the Class Year Study to the extent permitted by 
Attachments S and X; (iv) rejection of its Project Cost Allocation for System Upgrade Facilities in a Class Year Study; or (v) acceptance of its Project Cost Allocation and posting of Security for SUFs in a Class Year Study.204 Finally, the NYISO clarifies that upon a Large Facility’s 
withdrawal from the NYISO’s Interconnection Queue, the $3,000/MW deposit will be 
refundable with interest actually earned.205

I.	Revise Treatment of Deposits

The NYISO’s interconnection procedures provide for the NYISO to pay interest when

refunding a deposit due to a project’s withdrawal from the Interconnection Queue.206  Currently, 
the NYISO is required to pay interest on the refunded deposit at an interest rate consistent with 
Section 35.19a of the Commission’s Regulations (hereinafter the “FERC interest rate”).207

The NYISO proposes to revise this requirement to change the interest rate owed on

amounts refunded to a Developer from the FERC interest rate to “any interest actually earned on 
such deposits.”208  The NYISO proposes these revisions because it is unable to earn interest at 
the FERC interest rate.  As a not-for-profit organization that derives its operating revenues from 
its Market Participants, the NYISO lacks the resources to cover the difference between the FERC 
interest rate and the rate that is actually earned on the deposits.  The Commission has approved 
similar interest rate requirements for refunded security deposits elsewhere in the NYISO

tariffs.209  The Commission has also approved similar interest rate requirements for refunded security deposits in other ISOs/RTOs.210

203 OATT Section 25.6.2.3.1.

204 Proposed revisions to OATT Section 25.6.2.3.1. 205 Proposed revisions to OATT Section 25.6.2.3.1. 206 OATT Section 30.3.6.

207 OATT Section 30.3.6.

208 Proposed revisions to OATT Section 30.3.6.  Consistent with its approach for other deposits provided under the OATT, the NYISO will hold the deposit in an interest-bearing account with the deposited amount being associated with the Developer.

209 OATT Sections 31.2.6.2, 31.4.4.4; see also New York Indep. Sys. Operator, Inc., 166 FERC ¶ 61,099 
(2019) (accepting the revisions to the interest rate to interest actually earned in transmission planning process 
requirements).

210 See, e.g., Southwest Power Pool, Inc., 149 FERC ¶ 61,048, at PP 203, 205 (2014); California Indep. Sys. Operator, 149 FERC ¶ 61,178 at P 11 (2014); Midcontinent Indep. Sys. Operator, Inc., 153 FERC ¶ 61,168, at P 83 (2015) (accepting the revision to the interest rate to be the “interest actually earned on such deposits” as proposed in MISO’s September 16, 2015 filing in Docket No. ER15-2657-000).

Honorable Kimberly D. Bose December 19, 2019

Page 47

J. 	Expand Definition of Class Year Transmission Project

A “Class Year Transmission Project” is a transmission facility that is studied under the

LFIP in Attachment X of the OATT and subject to the Class Year Study process in Attachment S of the OATT.211  Attachments X and S establish the requirements by which the Developer of a 
generation or transmission facility may request that the NYISO evaluate the facility for ERIS 
under the NYISO Minimum Interconnection Standard to enable the facility to provide Energy 
and Ancillary Services and for CRIS under the NYISO Deliverability Interconnection Standard 
to enable the facility to participate in the NYISO-administered capacity markets.  A Class Year 
Transmission Project is excluded from the definition of a “Transmission Project” for purposes of the separate Transmission Interconnection Procedures (“TIP”) in Attachment P of the OATT.212 The TIP requirements concern the reliable interconnection of a transmission facility to the New 
York State Transmission System under the NYISO Transmission Interconnection Standard, but 
do not evaluate the facility for ERIS or CRIS.213

The NYISO has historically reviewed controllable transmission lines requesting ERIS or 
CRIS under its LFIP and Class Year Study process.  Under the current definition of a Class Year 
Transmission Project, however, the Developer must be eligible to request and must request CRIS 
for its proposed transmission facility to be considered a Class Year Transmission Project and be 
studied under the LFIP in Attachment X, rather than the TIP under Attachment P.214  The current 
definition of Class Year Transmission Project does not account for the scenario in which the

Developer of a merchant controllable transmission line wants to be evaluated for only ERIS, and not for CRIS.  Under the current definition of Class Year Transmission Project, such a 
transmission facility would be labelled as a Transmission Project and subject to the TIP 
requirements, rather than being evaluated for ERIS under the LFIP.

The NYISO, therefore, proposes to revise this definition of Class Year Transmission 
Project to provide that a Developer of a proposed controllable transmission line that requests 
only ERIS will also be a Class Year Transmission Project that will be studied under the LFIP. 
The NYISO defines a controllable transmission facility as “a transmission facility over which 
power flow can be directly controlled by power flow devices directly connected to the Class 
Year Transmission Project without having to re-dispatch generation.”215  Controllable

transmission projects that are able to request ERIS are more suitable for evaluation in the LFIP 
than the TIP.  Because these lines are controllable, they can be dispatched up and down to 
address system conditions and are, therefore, more akin to generation from an electrical 
standpoint than to uncontrollable AC transmission.  Accordingly, such transmission facilities are 
better evaluated alongside generation in the LFIP, including in the Class Year Study.

211 See OATT Section 30.2.1.

212 OATT Section 22.3.1.3.

213 See OATT Sections 22.3.1.3.

214 OATT Sections 25.1, 30.1 (definitions of Class Year Transmission Project).

215 Proposed revisions to OATT Sections 25.1, 30.1 (definitions of Class Year Transmission Project).  The NYISO proposes to make conforming changes to OATT Section 25.3.1 to incorporate the revised definition of Class Year Transmission Project.

Honorable Kimberly D. Bose December 19, 2019

Page 48

K. 	Minor Clarifications and Ministerial Errors

i.  EPC Agreement Requirements for SUFs and SDUs on Affected Systems

The NYISO’s interconnection studies may identify the need for SUFs or SDUs on

Affected Systems that are required for the Developer’s interconnection of its project, but are not 
addressed in the pro forma interconnection agreement among the NYISO, Connecting 
Transmission Owner, and Developer.  The NYISO’s practice has been to enter into and file with 
the Commission engineering, procurement, and construction agreements (“EPC Agreements”) 
among the NYISO, the Affected System Operator, and the Developer or Developers that have 
accepted their Project Cost Allocation for, and have funded or committed to fund, SUFs and/or 
SDUs on Affected Systems.  This approach is consistent with the existing requirements in 
Section 30.12.1 of Attachment X that if an SUF or SDU involves an Affected Transmission 
Owner, the Developer is required to execute and fulfill agreement(s) with the NYISO and the 
Connecting Transmission Owner and any Affected Transmission Owner to cover the 
engineering, procurement, and construction of such upgrades.216  As the NYISO does not have a 
pro forma EPC Agreement, it works with the Developer and Affected System Operator to 
develop an EPC Agreement based on the LGIA, as modified to address only the engineering, 
procurement, and construction elements.  Each agreement has then been filed with and accepted 
by the Commission.217

The NYISO proposes to clarify this process in Attachments X and S of its OATT.218

Specifically, if a Developer (or multiple Developers) accepts its Project Cost Allocation for, and 
funds or commits to funds, SUFs and/or SDUs on an Affected System, the Developer(s) and 
Affected System Operator (or Affected Transmission Owner) will cooperate with the NYISO in 
developing an agreement to provide for the engineering, procuring, and construction of the SUFs 
and/or SDUs.219  The NYISO also proposes to clarify that the EPC Agreement will be based on 
the LGIA, as modified to address only the engineering, procurement, and construction of the 
SUFs and SDUs.  Finally, the NYISO proposes to require that the parties to the agreement use 
Reasonable Efforts to complete and execute the agreement, or to submit it unexecuted with the 
Commission, within six months of the NYISO’s tender of the agreement.220

216 Similarly, Section 25.7.11.1.4.2.6 of Attachment S to the OATT requires that an entity that has sought 
External CRIS rights that accepts its SDU Project Cost Allocation and funds or commits to fund an SDU Upgrade 
must also execute and fulfill agreement(s) with the NYISO and the Connecting Transmission Owner and any 
Affected Transmission Owner to cover the engineering, procurement, and construction of the SDUs. 
	217 See, e.g., New York Indep. Sys. Operator, Inc., et al., Letter Order, Docket No. ER19-2543-000 (October 3, 2019) (accepting agreement for engineering, procurement, and construction of SDUs on Affected Systems); New York Indep. Sys. Operator, Inc., et al., Letter Order, Docket No. ER15-2083-000 (August 19, 2015) (accepting 
agreement for engineering, procurement, and construction of SUFs on Affected System). 
	218 Proposed OATT Section 25.7.12.13; proposed revisions to OATT Section 30.3.5. 
	219 Section 25.7.12.13 also clarifies that if an SDU is identified on the Connecting Transmission Owner’s  system, the engineering, procurement, and construction of the SDU will be addressed in the interconnection 
agreement among the NYISO, Developer, and Connecting Transmission Owner.

220 Proposed OATT Section 25.7.12.13; proposed revisions to OATT Section 30.3.5.

Honorable Kimberly D. Bose December 19, 2019

Page 49

ii.  Modifications to Pro Forma LGIA and Pro Forma SGIA

The NYISO proposes to make limited substantive modifications and minor corrections to its LGIA located in Appendix 3 in Section 30.14 of Attachment X of the OATT and its Standard Small Generator Interconnection Agreement (“SGIA”) located in Appendix 7 in Section 32.5 of Attachment Z of the OATT.

First, the NYISO proposes to revise both the LGIA and SGIA to require the Developer to 
provide the NYISO and Connecting Transmission Owner with a notice form indicating its 
project’s satisfaction of the key milestones of its Initial Synchronization Date and its 
Commercial Operation Date.  The LGIA currently includes as Appendix E a form letter that the 
Developer must provide to the NYISO and Connecting Transmission Owner confirming that the 
Developer has commenced Commercial Operation of its Large Facility.  The NYISO proposes to 
insert a similar form letter in the SGIA for a Small Generating Facility’s commencement of its 
Commercial Operation Date, along with inserting similar form letters in the LGIA and SGIA for 
Developer’s initial synchronization of its facility.221  Such form letters are not administratively 
burdensome and enable the NYISO to more easily track the status of projects under 
development, including providing specific information for testing and scheduling purposes. 
Moreover, consistent with the proposed revisions to the CRIS expiration rules in Part IV.E, the 
form letter for the initial synchronization of new facilities will be used to identify the beginning 
of the three-year period that a facility may be CRIS-inactive until such facility loses its CRIS. 
The NYISO made conforming changes to the definition of “Commercial Operation Date” and 
“Initial Synchronization Date” in the LGIA to address the use of these forms.222 In addition, the 
NYISO inserted definitions of the following terms in the SGIP and SGIA concerning key project 
milestones to conform with the defined terms used in the LGIA and the use of the notice forms: 
Commercial Operation, Commercial Operation Date, Initial Synchronization Date, In-Service 
Date, and Trial Operation.223

Second, Sections 4.2 and 5.2 of the SGIA currently only permit a Connecting

Transmission Owner and Developer to agree for the Developer to construct the required

Distribution Upgrades, System Upgrade Facilities, and System Deliverability Upgrade Facilities associated with its project if the upgrades are located on land owned by the Developer.  The 
NYISO proposes to modify these provisions to permit the Developer to construct these upgrades, with the Connecting Transmission Owner’s agreement, even if such upgrades are not located on land owned by the Developer.  The proposed revision will provide the Connecting Transmission Owner and Developer with additional flexibility concerning the construction of required 
upgrades.  The revisions will also not harm the Connecting Transmission Owner, which must 
agree for the Developer to construct such upgrades.

Third, the NYISO proposes to clarify the meaning of the term “Loss” as that term is used in the Indemnity provisions in Article 18 of the LGIA.  Currently, Article 18.2 details the

221 Proposed Appendix E-1 of the LGIA (and heading revision from Appendix E to Appendix E-2 to existing form); proposed Attachments 8 and 9 of the SGIA.

222 Proposed revisions to Article 1 of the LGIA.

223 Proposed revisions to OATT Section 32.5 Appendix 1 and Attachment 1 of the SGIA.

Honorable Kimberly D. Bose December 19, 2019

Page 50

categories of loss that are subject to the indemnity requirements (i.e., “damages, losses, claims, 
including claims and actions related to injury to or death of any person or damage to property, 
the alleged violation of any Environmental Law, or the release or threatened release of any 
Hazardous Substance, demand suits, recoveries, costs and expenses, court costs, attorney fees, 
and all other obligations by or to third parties”).  However, these categories are not currently 
collectively defined as “Loss.”  Rather, there is separate definition of Loss in the definitions 
section of the LGIP and LGIA that does not fully capture the loss categories detailed in Article

18.1.  The NYISO, therefore, proposes to define “Loss” in Article 18.1 as any and all of the

categories of Loss detailed in that provision, and to delete the definition of Loss from the

definition sections of the LGIP and LGIA.  This revision will eliminate uncertainty and internal inconsistencies concerning the definition of Loss.

Fourth, the NYISO proposes to modify the LGIA to correct certain inadvertent changes 
to the LGIA that were included as part of the modifications that the NYISO submitted in Docket 
No. ER18-80-000 on October 16, 2017, which modifications were accepted by the Commission 
on December 7, 2017.  The Commission has accepted these corrections as non-conforming 
revisions to recently filed interconnection agreements.224  The corrections are as follows:

•   Correction in the definition of “Standard Large Generator Interconnection Agreement” to 
	the tariff reference from Appendix 6 to Appendix 3 of Attachment X of the NYISO 
	OATT;

•   Correction of the cross-reference in Article 2.1 from Article 3.1, which no longer exists, 
	to Article 3;

•   Correction to the first reference to “Indemnified Party” in Article 18.1.2 of the LGIA, 
	which had been inadvertently changed to “Indemnifying Party;”

•   Correction of two cross-references in Section 18.3.12; and

•   Correction of a cross-reference in Article 22.4.

Finally, the NYISO proposes to make the following additional minor conforming revisions and clean-up changes to the LGIA and SGIA.

•   Including “Class Year Study Agreement” as an alternative term for the “Interconnection 
	Facilities Study Agreement” in the definition section of the LGIA;

•   Correcting the reference to “Developer” rather than “Interconnection Customer” in the 
	definition of “NYISO Deliverability Interconnection Standard” in the definition section 
	of the LGIA;

•   Correcting the word “his” to “its” referring to a Developer’s share of upgrade costs in 
	Article 5.5.2 of the LGIA;

•   Inserting the reference to “Class Year Study” in place of “Class Year Interconnection 
	Facilities Study” in Article 5.15 of the LGIA;

•   Correcting pluralization in Articles 18.3.4 and 22.8 of the LGIA;

224 See, e.g., New York Indep. Sys. Operator, Inc. and Consolidated Edison Co. of New York, Inc., Letter Order, Docket No. ER18-1161-000 (May 17, 2018).

Honorable Kimberly D. Bose December 19, 2019

Page 51

•   Adding placeholders for the name of the signors of the LGIA in the signature blocks of 
	the LGIA;

•   Correcting the word “by” to “be” in Article 1.8.1 of the SGIA;

•   Correcting capitalization of defined term, “Force Majeure Event” in Article 7.5.2 of the 
	SGIA;

•   Correcting cross-reference to Articles in Article 12.11.1 of the SGIA;

•   Correcting spelling of “courier” in Article 13.1 of the SGIA;

•   Updating email contact information for the NYISO in Articles 13.3 and 13.4 of the 
	SGIA;

•   Adding placeholders for the name of the signors of the SGIA in the signature blocks of 
	the SGIA;

•   Correcting capitalization of defined term, “Good Utility Practice” in the definition of 
	“System Upgrade Facilities” in Attachment 1 of the SGIA; and

•   Corrected spacing throughout LGIA and SGIA.

iii.  Miscellaneous

The NYISO’s proposed revisions to the OATT also include a number of minor revisions intended to clarify and clean up existing language.  The NYISO proposes to make the following revisions in a number of places in the tariff language.

•   The NYISO corrected spacing and inserted (or deleted inadvertent) periods and commas;

•   The NYISO updated the headings and section numbering to address new, revised, and 
	deleted tariff provisions;

•   The NYISO used the new shortened form of “Class Year Study” in place of “Class Year 
	Interconnection Facilities Study” and “Class Year Study Agreement” in place of “Class 
	Year Interconnection Facilities Study Agreement” in certain places of the tariff;

•   The NYISO clarified that certain actions performed by the stakeholder Operating

Committee could be performed by an Operating Committee subcommittee (e.g., Section

25.7.7.1);

•   The NYISO replaced “NYISO” with “ISO” for internal consistency;

•   The NYISO used the defined acronyms CRIS and ERIS to replace the full terms; and

•   The NYISO made the following additional clarifications and clean-ups that are 
	referenced and explained in the following table:

Tariff Section

OATT Section 25.1.2 (definition of “Affected Transmission Owner”)

OATT Section 25.1.2 (definition of “Class Year”)

Description and Rationale of Proposed Modification

Removed inadvertent period in definition of “Affected Transmission Owner.”

Removed “or” as definition refers to all projects in a Class Year Interconnection Facilities Study.

Honorable Kimberly D. Bose December 19, 2019

Page 52

Tariff Section

OATT Section 25.1.2 (definition of “Class Year Interconnection Facilities Study”)

OATT Section 25.1.2 (definition of “Class Year Interconnection Facilities Study

Agreement”)

OATT Section 25.1.2 (definition of “Energy Resource Interconnection Service”)

OATT Section 25.1.2 (definition of “Security”)

OATT Section 25.2.1

OATT Section 25.3.1

OATT Section 25.3.1.2

OATT Section 25.3.1.2 
OATT Section 25.3.1.3

OATT Section 25.5.5.1

OATT Section 25.5.5.1 (previously Section

25.5.5.2)

OATT Sections 25.5.6 and 25.5.7

OATT Section 25.5.9 (revised to Section

25.5.9.1)

Description and Rationale of Proposed Modification

Inserted “Class Year Study” as a shortened defined term for “Class Year Interconnection Facilities Study”.

Inserted “Class Year Study Agreement” as a shortened defined term for “Class Year

Interconnection Facilities Study Agreement.” Corrected parenthesis in defined term.

Inserted the word “this” before Attachment S to clarify applicable provision.

Revised to clarify the Large Facilities and 
Small Generating Facilities that are subject to 
being evaluated under the NYISO Minimum 
Interconnection Standard in a Class Year 
Study.

Revised to clarify that facilities that are 
subject to being evaluated under the NYISO Deliverability Interconnection Standard. 
Revised to clarify that Developers electing CRIS are also eligible to receive “External-to-
ROS Deliverability Rights.”

Replaced “capacity” with defined term “Installed Capacity.”

Deleted no longer required provision 
concerning the transition for Class Year 2007 
to begin evaluating projects under the NYISO 
Deliverability Interconnection Standard. 
Deleted no longer required provision 
concerning the requirements for the Existing 
System Representation used solely for Class 
Year 2017.

Inserted the word “this” in several locations to clarify applicable provision and corrected

cross reference.

Clarified Developer’s responsibility for all of the costs of Attachment Facilities and

Distribution Upgrades required for the interconnection of its facility.

Removed language indicating that the 
application of certain provisions would only 
apply to Class Years subsequent to Class 
Year 2012 and 2017, as the provisions are 
now the applicable provisions.  In addition,

Honorable Kimberly D. Bose December 19, 2019

Page 53

Tariff Section	Description and Rationale of Proposed

Modification

the NYISO added that it would also provide the Class Year Schedule information to its distribution list for the Transmission Planning Advisory subcommittee.

OATT Section 25.6.2.3.2	Corrected internal cross reference.

OATT Section 25.6.2.3.4.2	Clarified the reference to the Class Year entry

requirements that a Developer must satisfy if required to enter a Class Year to avoid having its project withdrawn.

OATT Section 25.6.2.3.4.3	Clarified the reference to the Class Year entry

requirements that a Developer must satisfy if required to enter a Class Year to avoid having its project withdrawn.

OATT Section 25.7.3	Removed no longer required language

concerning deliverability test for Class Year prior to Class Year 2012 and corrected 
misspelling of “Deliverability.”

OATT Section 25.7.10	Corrected misspellings of “Deliverability”

and “Unforced.”

OATT Section 25.7.11.1.4.2.6	Inserted the word “this” to clarify applicable

provision.

OATT Section 25.7.12.5.1	Revised “of the OATT” to “to the OATT.”

OATT Section 25.8.2	Revised “and requesting” to “that request.”

OATT Section 25.8.2	Removed language indicating that the

application of certain provisions would only apply to Class Years subsequent to Class Year 2012, as the provisions are now the applicable provisions.

OATT Section 25.8.2	Replaced “the Class Year Project’s

Deliverable MW” with “the Developer’s

Deliverable MW.”

OATT Section 25.8.2.1	Clarified that the Developer must signify its

willingness to pay for its share of SUFs and

SDUs “that it accepted.”

OATT Section 25.8.2.3	Replaced “issue” with “provide.”

OATT Section 25.8.3	Replaced “Class year Projects” with

“Developers.”

OATT Section 25.8.3	Capitalized defined term “Non-Acceptance

Notices.”

OATT Section 25.8.3	Replaced “Class Year projects” with

“Developers in the Class Year Study”.

OATT Section 25.8.3	Deleted “report” as the NYISO does not issue

a “Deliverability MW report,” rather the

Honorable Kimberly D. Bose December 19, 2019

Page 54

Tariff Section

OATT Section 25.8.4

OATT Section 25.8.5 
OATT Section 25.8.6.4

OATT Section 25.8.7.3.2

OATT Section 25.8.7.3.2

OATT Section 25.8.7.4.3

OATT Section 25.10.1.2 
OATT Section 25.10.1.3 
OATT Section 25.10.2.5

OATT Section 25.11, Appendix 1 
OATT Section 25.11, Appendix 1

OATT Section 30.1 (definition of “Class Year Interconnection Facilities Study”)

OATT Section 30.1 (definition of “Class Year 
Interconnection Facilities Study Agreement”)

OATT Section 30.1 (definition of “NYISO Minimum Interconnection Standard”)

OATT Section 30.1 (definition of “Standard 
Large Facility Interconnection Procedures”) 
OATT Section 30.1 (definition of “Standard 
Large Generator Interconnection Agreement”)

Description and Rationale of Proposed Modification

revised Deliverability MW are issued in the revised Class Year Deliverability Study

described in the start of the relevant sentence. Clarified by removing “all Developer have dropped out of the Class Year” as it is already addressed by the preceding language.

Deleted “still” as a ministerial cleanup to remove excess wording.

Replaced “Class Year Project” with “project,” as the project may include projects in the

Class Year Study or Additional SDU Study. Includes reference to “Additional SDU

Study” with Class Year Deliverability Study for studies that determine Headroom for

SDUs.

Replaces “Class Year project” with 
“Developer” to clarify that the Developer’s 
project may have participated in either the 
Class Year Study or an Additional SDU 
Study.

Replaces “each Class Year of Developers” with “each Developer” to account for both Developers in the Class Year Study or an Additional SDU Study.

Corrected internal cross-reference. 
Corrected internal cross-reference.

Revised “of the OATT” to “to the OATT.” 
Revised “Appendix One” to “Appendix 1” 
Revised Class Year placeholder from “200X”

to “20XX” as future Class Years will be in the teens or subsequent years.

Inserted “Class Year Study” as a shortened defined term for “Class Year Interconnection Facilities Study”.

Inserted “Class Year Study Agreement” as a shortened defined term for “Class Year

Interconnection Facilities Study Agreement.” Clarified that the LFIP are in “this”

Attachment X, rather than Attachment Z. Inserted “this” to clarify the application of requirements in Attachment X.

Inserted “this” to clarify the application of the requirements in Attachment X.

Honorable Kimberly D. Bose December 19, 2019

Page 55

Tariff Section

OATT Section 30.2.3

OATT Section 30.3.3.1

OATT Section 30.3.2.2

OATT Section 30.3.2.2

OATT Section 30.3.2.7 
OATT Section 30.4.4.1

OATT Section 30.8.1 
OATT Section 30.8.1.1

OATT Section 30.8.1.2

OATT Section 30.8.2

OATT Section 30.14, Appendix 1

OATT Section 30.14, Appendix 1

Description and Rationale of Proposed Modification

Clarified that the relevant power flow base information will be provided to Developers considering “or requesting” CRIS.

Clarified that a deposit provided in lieu of 
Site Control for Large Facilities shall be 
refunded if the Developer can demonstrate

Site Control within the ten Business Day cure period; otherwise, the deposit is non-

refundable.

Revised to provide that an existing Large 
Generating Facility requesting only CRIS 
must request CRIS in either a Class Year

Study “or an Expedited Deliverability Study.” Revised that the NYISO will assist any

Developer “requesting,” rather than “considering,” CRIS to assess potential system deliverability issues.

Replaced “of the ISO OATT” with “to the ISO OATT.”

Deleted “Agreement” when reference to “Interconnection System Reliability Impact Study” was referring to study, not study

agreement.

Corrected use of defined term for “Class Year Start Date.”

Removed “to be” as the NYISO will invoice Developers for the work already conducted in the prior month.

Removed language indicating that the 
application of certain provisions would only apply to Class Years subsequent to Class Year 2017, as the provisions are now the applicable provisions.

Inserted “Class Year Study” to specify the schedule being referred to.

Added a placeholder in #6 of the 
Interconnection Request for Developer to 
indicate its MW of requested CRIS; in 
addition, removed “this” from before 
Attachment X as the document is the 
Interconnection Request, not Attachment X. Under “Additional Information Requested for BTM:NG Resources,” replaced

Honorable Kimberly D. Bose December 19, 2019

Page 56

Tariff Section

OATT Section 30.14 Appendix 2

OATT Section 30.14, Attachment B to Appendix 2

OATT Section 32.1.2.2.3 
OATT Section 32.3.4.4

OATT Section 32.4.11.1

OATT Section 32.5, Appendix 1

OATT Section 32.5, Appendix 1 (definition of “Capacity Resource Interconnection

Service”)

OATT Section 32.5, Appendix 2

OATT Section 32.5, Attachment A to Appendix 2

OATT Section 32.5, Attachment A to Appendix 6

Description and Rationale of Proposed Modification

“Interconnection Customer” with

“Developer,” as “Developer” is the term used in the LFIP.

Revised the Class Year Study Agreement to amend: (i) the placeholders for the recitals to include the full defined term of “Capacity Resource Interconnection Service,” and (ii) the Term and Termination provision to

provide for the possibility of an Additional 
SDU Study and to correct a cross-reference. 
Revised Data Form for Class Year Study

Agreement to request Auxiliary Load MVAR as needed data for studies; to replace

“Interconnection Customer” with

“Developer;” to amend the data requested for Behind-the-Meter Net Generation Resources; to include whether the new or existing load is in the Transmission Owner’s service territory; and to make other ministerial revisions.

Deleted inadvertent language “(e.g…” 
Deleted “with the executed system impact study” as the NYISO in its 2017 
interconnection process reform filing 
removed system impact study agreements under the SGIP.

Deleted “capacity” as duplicative from term “Capacity Resource Interconnection Service capacity value.”

Replaced “Article” with “Section.” 
Inserted acronym CRIS as an alternative defined term.

Inserted additional space in Small Generator Interconnection Request for Developer to provide Project Description.

Corrected “ir” to “or” in recitals.

Inserted additional spacing in data form for Facilities Studies Agreement for Developer to provide required information.

Honorable Kimberly D. Bose December 19, 2019

Page 57

V.	PROPOSED EFFECTIVE DATE

The NYISO respectfully requests that the Commission accept the proposed tariff

revisions to become effective the day immediately following the end of the statutory sixty-day notice period under Section 205 of the Federal Power Act (i.e., on February 18, 2020).

VI.    REQUISITE STAKEHOLDER APPROVAL

The tariff revisions proposed in this filing were discussed with stakeholders at multiple 
meetings of the Transmission Planning Advisory Subcommittee, the Installed Capacity Working 
Group, the Market Issues Working Group, and the Electric System Planning Working Group. 
The revisions were approved at the Business Issues Committee meeting on November 6, 2019, 
the Operating Committee meeting on November 8, 2019, and at the Management Committee 
meeting on November 20, 2019.  On December 5, 2019, the NYISO Board of Directors 
approved the proposed tariff revisions for filing with the Commission pursuant to Section 205 of 
the Federal Power Act.

VII.   SERVICE

The NYISO will send an electronic link to this filing to the official representative of each 
of its customers, to each participant on its stakeholder committees, to the New York Public 
Service Commission, and to the New Jersey Board of Public Utilities.  In addition, a complete 
copy of the Public documents included with this filing will be posted on the NYISO’s website at 
www.nyiso.com.

VIII.  CONCLUSION

Wherefore, for the foregoing reasons, the New York Independent System Operator, Inc., 
respectfully requests that the Commission accept the proposed tariff changes identified in this 
filing.

Respectfully submitted,

/s/ Brian R. Hodgdon

Brian R. Hodgdon David Allen

Counsel for the

New York Independent System Operator, Inc.

cc:	Anna Cochrane	David Morenoff

James Danly	Daniel Nowak

Jignasa Gadani	Larry Parkinson

Jette Gebhart	Douglas Roe

Kurt Longo	Frank Swigonski

John C. Miller	Gary Will