10 Krey Boulevard     Rensselaer, NY  12144

August 16, 2010

Ms. Kimberly D. Bose Secretary

Federal Energy Regulatory Commission 888 First Street, N.E.

Washington D.C. 20426

Re:    New York Independent System Operator, Inc., Compliance Implementation Plan, 
	Docket No. ER07-521-___

Dear Ms. Bose:

In compliance with Paragraph 18 and Ordering Paragraph B of the Commission’s

July 15, 2010 order (“July 2010 Order”)1 in the above-captioned proceeding, the New York

Independent System Operator, Inc. (“NYISO”) respectfully submits this detailed implementation plan including a timetable for offering Load Serving Entities (“LSEs”) fixed price Transmission Congestion Contracts (“TCCs”) between any point of injection and the LSE’s load zone (“nonhistoric fixed price TCCs”).

As is discussed in greater detail below, the NYISO intends to file proposed tariff

revisions early in 2012 describing the requirements for purchasing and holding non-historic fixed 
price TCCs in conjunction with tariff revisions necessary to implement a new  “Multi-Duration 
Centralized TCC Auction.”  As the Commission recognized, the NYISO intends to offer non-
historic fixed price TCCs as part of its Autumn 2012 Multi-Duration Centralized TCC Auction 
process.  Once these non-historic fixed price TCCs are offered, the NYISO would be in full 
compliance with the Commission’s long term firm transmission rights policies as set forth in 
Order Nos. 681 and 681-A.2

The NYISO’s implementation plan, described in detail herein, concentrates on the

software revisions necessary to move the current single duration TCC auction format to one that 
allows auction participants to bid to purchase and offer to sell a variety of TCC durations during 
a single auction round.3  Tariff revisions to describe both the procedural changes in the Multi-

1  New York Independent System Operator, Inc., 132 FERC ¶ 61,030 (2010).

2  Long-Term Firm Transmission Rights in Organized Electricity Markets, Order No.

681, FERC Stats. & Regs. ¶ 31,226 (July 20, 2006), reh’g denied, Order No. 681-A, 117 FERC ¶ 61,201 (November 16, 2006).

3 As part of this project, the NYISO, with its stakeholders’ support, is also expanding the 
opportunities in the monthly Reconfiguration Auction to allow Market Participants to submit

- 1 -

Honorable Kimberly D. Bose August 16, 2010

Page 2

Duration Centralized TCC Auction and the process for purchasing, and the responsibilities of 
holding, non-historic fixed price TCCs will also be pursued during this implementation period.

I.	Communications

Communications and correspondence regarding this filing should be directed to:

Robert E. Fernandez, General Counsel

Elaine D. Robinson, Director of Regulatory Affairs 
*Mollie Lampi, Assistant General Counsel 
New York Independent System Operator, Inc.

10 Krey Boulevard

Rensselaer, NY 12144 
Tel:  (518) 356-6000 
Fax: (518) 356-4702 
rfernandez@nyiso.com 
erobinson@nyiso.com 
mlampi@nyiso.com

*Persons designated to receive service

II.	Detailed Implementation Schedule

August, 2010	Concept Design Approval

Working with stakeholders since 2009 the NYISO has finalized the 
concept design for a Multi-Duration Centralized TCC Auction.  At 
their August Business Issues Committee (“BIC”) meeting, 
stakeholders approved the broad design.  The BIC approval noted 
that the availability of non-historic fixed price TCCs would be 
coordinated with the first Multi-Duration Centralized TCC Auction.

4

bids to buy and offers to sell TCCs for any month(s) in the capability period.  Software changes to implement this functionality are subsumed in the software revisions discussed herein.

4 See BIC presentation at

http://www.nyiso.com/public/webdocs/committees/bic/meeting_materials/2010-08-
04/Agenda_11_TCC_EFP1_MD_Mkt_Design_Revised.pdf

Honorable Kimberly D. Bose August 16, 2010

Page 3

Fourth Quarter,	Detailed Market Design

2010	The NYISO will continue to work with stakeholders on the details

of the Multi-Duration Centralized TCC Auction functionality.  In addition, the NYISO will start working with stakeholders to 
develop the appropriate credit policies necessary to support all changes being made to the TCC auction process.

Fourth Quarter,	Software Specifications

2010	The NYISO’s auction software is constructed both in house and by

Nexant, a software vendor.  Software for the TCC Automated

Market System (“TCC AMS”) is developed in-house and consists, 
primarily, of the web-based interface used by TCC auction 
participants to submit their bids and offers and receive information 
from the NYISO on their TCC auction activity.  In addition to the 
modifications to the  TCC AMS, software changes to accommodate 
the new TCC auction format are necessary in the Credit 
Management System and in related data and storage systems (“in-
house, auction-related software”). The TCC auction solution engine 
is provided by Nexant.

Beginning in the fourth quarter of 2010,  the NYISO will complete 
a functional requirement specification document (“FRS”) 
describing the changes needed in the TCC AMS to, among other 
things, move from bid and offer screens that allow TCCs to be 
purchased and sold only in single-duration rounds to functionality 
that will allow TCCs to be purchased and sold in multiple duration 
rounds.  The FRS will specify software applications and responses 
plus provide a detailed list of business and user needs that the 
Multi-Duration Centralized TCC Auction design will be required to 
support.

In addition, discussions will continue with Nexant concerning 
modifications required to the TCC auction solution engine 
including modifications of its software to align with the changes being made in the TCC AMS.  Any software development required in the Nexant software will be conducted in parallel with the 
NYISO’s TCC AMS development.

December 1, 2010 	Status Report to FERC

This first status report will describe the tasks that have been 
completed in the implementation of the multi-duration TCC 
auction.

Honorable Kimberly D. Bose August 16, 2010

Page 4

First Quarter, 2011 	Software Requirements, or “Use Case” Development, Begins

The NYISO will develop “Use Cases” which describe a goal-

oriented set of interactions between the users and the system

including the detailed functionality required for the in-house,

auction-related  software based on the output from detailed market 
design discussions with stakeholders.  Working from these Use 
Cases, software developers will write the software design 
specifications (“SDS”) necessary to re-design the in-house, auction-
related software.

Second Quarter,	Software Design Specifications

2011	The Use Case development that started in the first quarter is

expected to complete in the second quarter. Software developers

will then begin work on the SDS.  While the tariff revision process, 
that will begin in this quarter (see below) and conclude in the first 
quarter of 2012, may lead to changes in functional requirements and 
design specifications throughout that period of time, the principal 
elements of the SDSs are planned to be complete by the end of this 
quarter.

Additionally, the NYISO is targeting this quarter to complete

development of the new credit policy started in fourth quarter 2010.

Second Quarter,	Stakeholder Tariff Revision Process Begins

2011	Extensive tariff revisions will be necessary to support the Multi-

Duration Centralized TCC Auction and non-historic fixed price 
TCCs purchase opportunity.  The stakeholder tariff development 
and approval process will begin in parallel with the development of 
the SDSes, with NYISO-prepared draft tariff sheets and culminate 
in final votes by the Management Committee and Board of 
Directors.  The process is expected to take between eight and nine 
months at which time the revisions will be ready for filing with the 
Commission.

Tariff revisions to implement related credit policy changes will be 
pursued in tandem with the Multi-Duration Centralized TCC 
Auction and non-historic fixed price TCCs tariff revisions.

Honorable Kimberly D. Bose August 16, 2010

Page 5

December 1, 2011 	Status Report to FERC

The second status report will update the uncompleted tasks

described in the first status report, describe the tasks begun since 
the first status report was filed, and report on the remaining tasks 
necessary to meet the NYISO’s implementation schedule.

First Quarter, 2012 	Tariff Filing

The NYISO will file tariff revisions implementing the Multi-

Duration Centralized TCC Auction and the non-historic fixed price TCCs program.  These revisions will be filed at least 120 days 
before planned implementation to allow time for LSEs interested in purchasing non-historic fixed price TCCs to understand the process and obligations of their purchase opportunity.

First Quarter, 2012 	Testing

Before declaring that the software development is complete, the

NYISO conducts extensive software testing. Quality assurance and user acceptance testing of the revised in-house, auction-related and Nexant software will start in this quarter.

Second Quarter,	Manual  Revisions

2012	In this quarter, the NYISO will develop revisions to the TCC

Manual to describe the multi-duration TCC auction process and the 
process for purchasing non-historic fixed price TCCs.  These will 
also be provided to Market Participants for review and approval. 
The NYISO will also be updating its TCC Auction User Guide.

Second Quarter,	Market Trials

2012	During the second quarter, the NYISO will also facilitate market

trials which offer stakeholders an opportunity to become familiar 
with the new TCC auction functionality.  Stakeholders that utilize 
the TCC AMS will be asked to participate in these market trials by 
submitting multi-duration bids and offers.  The NYISO will 
conduct the practice auction as if it were a real auction.  No 
financial consequences flow from this practice auction round and 
no TCCs are awarded.

Honorable Kimberly D. Bose August 16, 2010

Page 6

Second Quarter,	Testing

2012	Testing of all in-house, auction-related software revisions

completes in this quarter once market trials, quality assurance and

user acceptance testing are finished.

Third Quarter,	Multi-duration auction with opportunity to purchase non-

2012	historic fixed prices TCCs is conducted

The Autumn Multi-Duration Centralized TCC Auction process will 
commence in this quarter.  LSEs interested in purchasing non-
historic fixed price TCCs will receive information on eligibility 
requirements and on the process they will need to follow to 
purchase their fixed price TCCs.  The NYISO plans to post an 
auction timeline developed with stakeholder input several weeks in 
advance of the first auction and opportunity to purchase non-
historic fixed price TCCs.

III.	Conclusion

For the foregoing reasons, the New York Independent System Operator, Inc., respectfully requests that the Commission accept its compliance implementation plan as fully complying with Paragraph 18 and Ordering Paragraph B of the July 2010 Order.

Respectfully submitted,

/s/  Mollie Lampi

Mollie Lampi

Assistant General Counsel

New York Independent System Operator, Inc.

10 Krey Blvd.

Rensselaer, New York 12144 (518) 356 7530

mlampi@nyiso.com

CERTIFICATE OF SERVICE

I hereby certify that I have this day served the foregoing document upon each person

designated on the official service list compiled by the Secretary in this proceeding in accordance 
with the requirements of Rule 2010 of the Rules of Practice and Procedure, 18 C.F.R. § 385.2010 
(2010).

Dated at Washington, DC this 16th day of August, 2010.

By:  /s/  Catherine A. Karimi

Catherine A. Karimi

Sr. Professional Assistant 
Hunton & Williams LLP 
1900 K Street, NW

Washington, DC  20006-1109 (202) 955-1500