SERVICE AGREEMENT NO. 2521

SERVICE AGREEMENT NO. 2521

INTERCONNECTION AGREEMENT
 AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.
 AND

CONSOLIDATED EDISON COMPANY OF NEW YORK, INC.

Dated as of March 26, 2020

(East River 2 Uprate Project)

SERVICE AGREEMENT NO. 2521

TABLE OF CONTENTS

Page Number

ARTICLE 1. DEFINITIONS 1

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION 9

2.1 Effective Date 9

2.2 Term of Agreement 9

2.3 Termination 9

2.4 Termination Costs 10

2.5 Disconnection 10

2.6 Survival 10

ARTICLE 3. REGULATORY FILINGS 10

ARTICLE 4. SCOPE OF INTERCONNECTION SERVICE 10

4.1 Provision of Service 10

4.2 No Transmission Delivery Service 11

4.3 No Other Services 11

ARTICLE 5. INTERCONNECTION FACILITIES ENGINEERING, PROCUREMENT,

AND CONSTRUCTION 11

5.1 Milestones 11

5.2 Power System Stabilizers 12

5.3 Limited Operation 12

5.4 Permits 12

5.5 Suspension 12

5.6 Tax Status; Non-Jurisdictional Entities 13

5.7 Modification 13

ARTICLE 6. TESTING AND INSPECTION 14

6.1 Pre-Commercial Operation Date Testing and Modifications 14

6.2 Post-Commercial Operation Date Testing and Modifications 14

6.3 Right to Observe Testing 14

6.4 Right to Inspect 14

ARTICLE 7. METERING 15

7.1 General 15

7.2 Standards 15

7.3 Testing of Metering Equipment 15

7.4 Metering Data 16

ARTICLE 8. COMMUNICATIONS 16

8.1 Con Edison Obligations 16

8.2 Remote Terminal Unit 16

ARTICLE 9. OPERATIONS 16

9.1 General 16

9.2 Operational Obligations 17

9.3 Con Edison Obligations 17

9.4 Start-Up and Synchronization 17

9.5 Real and Reactive Power Control and Primary Frequency Response 17

9.6 Outages and Interruptions 19

i

SERVICE AGREEMENT NO. 2521

9.7 Use of Attachment Facilities by Third Parties 22

9.8 Disturbance Analysis Data Exchange 22

9.9 Phasor Measurement Units 22

ARTICLE 10. MAINTENANCE 23

10.1 Con Edison Obligations 23

10.2 Coordination 23

10.3 Secondary Systems 23

10.4 Operating and Maintenance Expenses 23

ARTICLE 11. PERFORMANCE OBLIGATION 24

11.1 Attachment Facilities 24

11.2 System Upgrade Facilities and System Deliverability Upgrades 24

11.3 Special Provisions for Affected Systems 24

11.4 Con Edison Compensation for Emergency Services 24

ARTICLE 12. EMERGENCIES 24

12.1 Obligations 24

12.2 Notice 24

12.3 NYISO and Con Edison Authority 25

12.4 Large Generating Facility 26

12.5 Limited Liability 26

ARTICLE 13. REGULATORY REQUIREMENTS AND GOVERNING LAW 26

13.1 Regulatory Requirements 26

13.2 Governing Law 26

ARTICLE 14. NOTICES 26

14.1 General 26

14.2 Alternative Forms of Notice 27

14.3 Operations and Maintenance Notice 27

ARTICLE 15. FORCE MAJEURE 27

ARTICLE 16. DEFAULT 27

16.1 General 27

16.2 Right to Terminate 28

ARTICLE 17. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE 28

17.1 Indemnity 28

17.2 No Consequential Damages 29

17.3 Insurance 30

ARTICLE 18. ASSIGNMENT 30

ARTICLE 19. SEVERABILITY 30

ARTICLE 20. COMPARABILITY 30

ARTICLE 21. CONFIDENTIALITY 31

21.1 Confidentiality 31

21.2 Term 31

21.3 Confidential Information 31

21.4 Scope 31

21.5 Release of Confidential Information 32

21.6 Rights 32

21.7 No Warranties 32

21.8 Standard of Care 32

ii

SERVICE AGREEMENT NO. 2521

21.9 Order of Disclosure 32

21.10 Termination of Agreement 33

21.11 Remedies 33

21.12 Disclosure to FERC, its Staff, or a State 33

21.13 Required Notices Upon Requests or Demands for Confidential Information . 34

ARTICLE 22. INFORMATION REQUIREMENT 34

22.1 Information Acquisition 34

22.2 Information Submission by Con Edison 34

22.3 Updated Information Submission by Con Edison 34

22.4 Information Supplementation 35

ARTICLE 23. INFORMATION ACCESS AND AUDIT RIGHTS 35

23.1 Information Access 35

23.2 Reporting of Non-Force Majeure Events 36

23.3 Audit Rights 36

23.4 Audit Rights Periods 36

ARTICLE 24. SUBCONTRACTORS 36

24.1 General 36

24.2 Responsibility of Principal 37

24.3 No Limitation by Insurance 37

ARTICLE 25. DISPUTES 37

25.1 Submission 37

25.2 External Arbitration Procedures 37

25.3 Arbitration Decisions 38

25.4 Costs 38

25.5 Termination 38

ARTICLE 26. REPRESENTATIONS, WARRANTIES AND COVENANTS 38

26.1 General 38

ARTICLE 27. MISCELLANEOUS 39

27.1 Binding Effect 39

27.2 Conflicts 39

27.3 Rules of Interpretation 39

27.4 Compliance 40

27.5 Joint and Several Obligations 40

27.6 Entire Agreement 40

27.7 No Third Party Beneficiaries 40

27.8 Waiver 41

27.9 Headings 41

27.10 Multiple Counterparts 41

27.11 Amendment 41

27.12 Modification by the Parties 41

27.13 Reservation of Rights 41

27.14 No Partnership 42

27.15 Other Transmission Rights 42

iii

SERVICE AGREEMENT NO. 2521

Appendices

iv

SERVICE AGREEMENT NO. 2521

STANDARD LARGE GENERATOR INTERCONNECTION AGREEMENT

THIS STANDARD LARGE GENERATOR INTERCONNECTION AGREEMENT

(“Agreement”) is made and entered into this 26th day of March 2020, by and among the New

York Independent System Operator, Inc., a not-for-profit corporation organized and existing

under the laws of the State of New York (“NYISO”), and Consolidated Edison Company of New York, Inc. a transportation corporation organized and existing under the laws of the State of New York (“Con Edison”). The NYISO or Con Edison each may be referred to as a “Party” or
together referred to as the “Parties.”

RECITALS

WHEREAS, NYISO operates the New York State Transmission System and Con Edison owns certain facilities included in the New York State Transmission System;

WHEREAS, Con Edison owns, controls, and operates the Generating Facility identified as a Large Generating Facility in Appendix C to this Agreement;

WHEREAS, the Generating Facility is presently participating in the NYISO-administered wholesale markets and provides steam services to Con Edison; and

WHEREAS, NYISO and Con Edison have agreed to enter into this Agreement in connection with the material increase to the nameplate capacity of the Large Generating Facility, which is interconnected with the New York State Transmission System;

NOW, THEREFORE, in consideration of and subject to the mutual covenants contained herein, it is agreed:

ARTICLE 1. DEFINITIONS

Whenever used in this Agreement with initial capitalization, the following terms shall have the

meanings specified in this Article 1. Terms used in this Agreement with initial capitalization that are not defined in this Article 1 shall have the meanings specified in Section 1 of the ISO OATT, Section 30.1 of Attachment X of the ISO OATT, Section 25.1.2 of Attachment S of the ISO
OATT, the body of the LFIP or the body of this Agreement.

Affected System shall mean an electric system other than the transmission system owned,
controlled or operated by Con Edison that may be affected by the proposed interconnection.

Affected System Operator shall mean the entity that operates an Affected System.

Affected Transmission Owner shall mean the New York public utility or authority (or its

designated agent) other than Con Edison that (i) owns facilities used for the transmission of

Energy in interstate commerce and provides Transmission Service under the Tariff, and (ii)

owns, leases or otherwise possesses an interest in a portion of the New York State Transmission
System where System Deliverability Upgrades, System Upgrade Facilities, or Network Upgrade

1

SERVICE AGREEMENT NO. 2521

Facilities are or will be installed pursuant to Attachment P, Attachment X, Attachment Z, or Attachment S to the ISO OATT.

Affiliate shall mean, with respect to a person or entity, any individual, corporation, partnership, firm, joint venture, association, joint-stock company, trust or unincorporated organization,
directly or indirectly controlling, controlled by, or under common control with, such person or entity. The term “control” shall mean the possession, directly or indirectly, of the power to direct the management or policies of a person or an entity. A voting interest of ten percent or more shall create a rebuttable presumption of control.

Ancillary Services shall mean those services that are necessary to support the transmission of Capacity and Energy from resources to Loads while maintaining reliable operation of the New York State Transmission System in accordance with Good Utility Practice.

Applicable Laws and Regulations shall mean all duly promulgated applicable federal, state and local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or administrative orders, permits and other duly authorized actions of any Governmental Authority, including but not limited to Environmental Law.

Applicable Reliability Councils shall mean the NERC, the NPCC and the NYSRC.

Applicable Reliability Standards shall mean the requirements and guidelines of the Applicable Reliability Councils, and the Transmission District to which Con Edison’s Large Generating
Facility is directly interconnected, as those requirements and guidelines are amended and
modified and in effect from time to time; provided that neither Party shall waive its right to
challenge the applicability or validity of any requirement or guideline as applied to it in the
context of this Agreement.

Attachment Facilities shall mean all facilities and equipment between the Large Generating

Facility and the Point of Interconnection, including any modification, additions or upgrades that are necessary to physically and electrically interconnect the Large Generating Facility to the New York State Transmission System. Attachment Facilities are sole use facilities and shall not include Stand Alone System Upgrade Facilities, Distribution Upgrades, System Upgrade
Facilities or System Deliverability Upgrades.

Base Case shall mean the base case power flow, short circuit, and stability data bases used for the Interconnection Studies by NYISO or Con Edison; described in Section 30.2.3 of the
Standard Large Facility Interconnection Procedures.

Breach shall mean the failure of a Party to perform or observe any material term or condition of this Agreement.

Breaching Party shall mean a Party that is in Breach of this Agreement.

Business Day shall mean Monday through Friday, excluding federal holidays.

2

SERVICE AGREEMENT NO. 2521

Byway shall mean all transmission facilities comprising the New York State Transmission

System that are neither Highways nor Other Interfaces. All transmission facilities in Zone J and Zone K are Byways.

Calendar Day shall mean any day including Saturday, Sunday or a federal holiday.

Capacity Region shall mean one of four subsets of the Installed Capacity statewide markets
comprised of (1) Rest of State (i.e., Load Zones A through F); (2) Lower Hudson Valley (i.e.,
Load Zones G, H and I); (3) New York City (i.e., Load Zone J); and (4) Long Island (i.e., Load
Zone K) , except for Class Year Interconnection Facility Studies conducted prior to Class Year
2012, for which “Capacity Region” shall be defined as set forth in Section 25.7.3 of Attachment
S to the ISO OATT.

Capacity Resource Interconnection Service (“CRIS”) shall mean the service provided by

NYISO to Con Edison that satisfies the NYISO Deliverability Interconnection Standard or that is
otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT; such
service being one of the eligibility requirements for participation as a NYISO Installed Capacity
Supplier.

Class Year Deliverability Study shall mean an assessment, conducted by the NYISO staff in
cooperation with Market Participants, to determine whether System Deliverability Upgrades are
required for Class Year CRIS Projects under the NYISO Deliverability Interconnection Standard.

Commercial Operation shall mean the status of a Large Generating Facility that has
commenced generating electricity for sale, excluding electricity generated during Trial
Operation.

Commercial Operation Date of a unit shall mean the date on which the Large Generating

Facility commences Commercial Operation as agreed to by the Parties, notice of which must be provided to the NYISO in the form of Appendix E-2 to this Agreement.

Confidential Information shall mean any information that is defined as confidential by Article 21 of this Agreement.

Control Area shall mean an electric power system or combination of electric power systems to
which a common automatic generation control scheme is applied in order to: (1) match, at all
times, the power output of the Generators within the electric power system(s) and capacity and
energy purchased from entities outside the electric power system(s), with the Load within the
electric power system(s); (2) maintain scheduled interchange with other Control Areas, within
the limits of Good Utility Practice; (3) maintain the frequency of the electric power system(s)
within reasonable limits in accordance with Good Utility Practice; and (4) provide sufficient

generating capacity to maintain Operating Reserves in accordance with Good Utility Practice. A Control Area must be certified by the NPCC.

Default shall mean the failure of a Party in Breach of this Agreement to cure such Breach in accordance with Article 16 of this Agreement.

3

SERVICE AGREEMENT NO. 2521

Distribution System shall mean Con Edison’s facilities and equipment used to distribute

electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s Large Facility
Interconnection Procedures in Attachment X to the ISO OATT or Small Generator
Interconnection Procedures in Attachment Z to the ISO OATT under FERC Order Nos. 2003
and/or 2006. The term Distribution System shall not include LIPA’s distribution facilities.

Distribution Upgrades shall mean the additions, modifications, and upgrades to Con Edison’s
Distribution System at or beyond the Point of Interconnection to facilitate interconnection of a
Large Facility or Small Generating Facility and render the transmission service necessary to
affect Con Edison’s wholesale sale of electricity in interstate commerce. Distribution Upgrades
do not include Attachment Facilities, System Upgrade Facilities, or System Deliverability
Upgrades. Distribution Upgrades are sole use facilities and shall not include Stand Alone
System Upgrade Facilities, System Upgrade Facilities, or System Deliverability Upgrades.

Effective Date shall mean the date on which this Agreement becomes effective upon execution by the Parties, subject to acceptance by the Commission, or if filed unexecuted, upon the date specified by the Commission.

Emergency State shall mean the condition or state that the New York State Power System is in when an abnormal condition occurs that requires automatic or immediate manual action to
prevent or limit loss of the New York State Transmission System or Generators that could
adversely affect the reliability of the New York State Power System.

Energy Resource Interconnection Service (“ERIS”) shall mean the service provided by
NYISO to interconnect Con Edison’s Large Generating Facility to the New York State
Transmission System or to the Distribution System in accordance with the NYISO Minimum
Interconnection Standard, to enable the New York State Transmission System to receive Energy
and Ancillary Services from the Large Generating Facility, pursuant to the terms of the ISO
OATT.

Environmental Law shall mean Applicable Laws and Regulations relating to pollution or protection of the environment or natural resources.

Federal Power Act shall mean the Federal Power Act, as amended, 16 U.S.C. §§ 791a et seq. (“FPA”).

FERC shall mean the Federal Energy Regulatory Commission (“Commission”) or its successor.

Force Majeure shall mean any act of God, labor disturbance, act of the public enemy, war,
insurrection, riot, fire, storm or flood, explosion, breakage or accident to machinery or
equipment, any order, regulation or restriction imposed by governmental, military or lawfully
established civilian authorities, or any other cause beyond a Party’s control. A Force Majeure
event does not include acts of negligence or intentional wrongdoing by the Party claiming Force
Majeure.

4

SERVICE AGREEMENT NO. 2521

Generating Facility shall mean Con Edison’s device for the production of electricity identified
in the Interconnection Request, but shall not include the Attachment Facilities or Distribution
Upgrades.

Generating Facility Capacity shall mean the net seasonal capacity of the Generating Facility and the aggregate net seasonal capacity of the Generating Facility where it includes multiple energy production devices.

Good Utility Practice shall mean any of the practices, methods and acts engaged in or approved
by a significant portion of the electric industry during the relevant time period, or any of the
practices, methods and acts which, in the exercise of reasonable judgment in light of the facts
known at the time the decision was made, could have been expected to accomplish the desired
result at a reasonable cost consistent with good business practices, reliability, safety and
expedition. Good Utility Practice is not intended to be limited to the optimum practice, method,
or act to the exclusion of all others, but rather to delineate acceptable practices, methods, or acts
generally accepted in the region.

Governmental Authority shall mean any federal, state, local or other governmental regulatory or administrative agency, court, commission, department, board, or other governmental
subdivision, legislature, rulemaking board, tribunal, or other governmental authority having jurisdiction over any of the Parties, their respective facilities, or the respective services they provide, and exercising or entitled to exercise any administrative, executive, police, or taxing authority or power; provided, however, that such term does not include Con Edison, NYISO, Affected Transmission Owner, or any Affiliate thereof.

Hazardous Substances shall mean any chemicals, materials or substances defined as or

included in the definition of “hazardous substances,” “hazardous wastes,” “hazardous materials,” “hazardous constituents,” “restricted hazardous materials,” “extremely hazardous substances,” “toxic substances,” “radioactive substances,” “contaminants,” “pollutants,” “toxic pollutants” or words of similar meaning and regulatory effect under any applicable Environmental Law, or any other chemical, material or substance, exposure to which is prohibited, limited or regulated by any applicable Environmental Law.

Highway shall mean 115 kV and higher transmission facilities that comprise the following

NYCA interfaces: Dysinger East, West Central, Volney East, Moses South, Central East/Total
East, and UPNY-ConEd, and their immediately connected, in series, bulk power system facilities
in New York State. Each interface shall be evaluated to determine additional “in series”
facilities, defined as any transmission facility higher than 115 kV that (a) is located in an
upstream or downstream zone adjacent to the interface and (b) has a power transfer distribution
factor (DFAX) equal to or greater than five percent when the aggregate of generation in zones or
systems adjacent to the upstream zone or zones that define the interface is shifted to the
aggregate of generation in zones or systems adjacent to the downstream zone or zones that define
the interface. In determining “in series” facilities for Dysinger East and West Central interfaces,
the 115 kV and 230 kV tie lines between NYCA and PJM located in LBMP Zones A and B shall
not participate in the transfer. Highway transmission facilities are listed in ISO Procedures.

5

SERVICE AGREEMENT NO. 2521

Initial Synchronization Date shall mean the date upon which the Large Generating Facility is initially synchronized and upon which Trial Operation begins, notice of which must be provided to the NYISO in the form of Appendix E-1.

In-Service Date shall mean the date upon which Con Edison reasonably expects it will be ready to begin use of the Attachment Facilities to obtain back feed power.

Interconnection Facilities Study shall mean a study conducted by NYISO or a third party

consultant for Con Edison to determine a list of facilities (including the Attachment Facilities, Distribution Upgrades, System Upgrade Facilities and System Deliverability Upgrades as identified in the Interconnection System Reliability Impact Study), the cost of those facilities, and the time required to interconnect the Large Generating Facility with the New York State Transmission System or with the Distribution System. The scope of the study is defined in Section 30.8 of the Standard Large Facility Interconnection Procedures.

Interconnection Facilities Study Agreement (“Class Year Study Agreement”) shall mean the form of agreement contained in Appendix 2 of the Standard Large Facility Interconnection Procedures for conducting the Interconnection Facilities Study.

Interconnection Request shall mean Con Edison’s request, in the form of Appendix 1 to the
Standard Large Facility Interconnection Procedures, in accordance with the Tariff, to
interconnect a new Large Generating Facility to the New York State Transmission System or to
the Distribution System, or to materially increase the capacity of, or make a material
modification to the operating characteristics of, an existing Large Generating Facility that is
interconnected with the New York State Transmission System or with the Distribution System.

Interconnection Study shall mean any of the following studies: the Optional Interconnection Feasibility Study, the Interconnection System Reliability Impact Study, and the Interconnection Facilities Study described in the Standard Large Facility Interconnection Procedures.

Interconnection System Reliability Impact Study (“SRIS”) shall mean an engineering study,
conducted in accordance with Section 30.7 of the Standard Large Facility Interconnection
Procedures, that evaluates the impact of the proposed Large Generating Facility on the safety and
reliability of the New York State Transmission System and, if applicable, an Affected System, to
determine what Attachment Facilities, Distribution Upgrades and System Upgrade Facilities are
needed for the proposed Large Generating Facility of Con Edison to connect reliably to the New
York State Transmission System or to the Distribution System in a manner that meets the
NYISO Minimum Interconnection Standard in Attachment X to the ISO OATT.

IRS shall mean the Internal Revenue Service.

Large Generating Facility shall mean a Generating Facility having a Generating Facility Capacity of more than 20 MW.

Material Modification shall mean those modifications that have a material impact on the cost or timing of any Interconnection Request with a later queue priority date.

6

SERVICE AGREEMENT NO. 2521

Metering Equipment shall mean all metering equipment installed or to be installed at the Large Generating Facility pursuant to this Agreement at the metering points, including but not limited to instrument transformers, MWh-meters, data acquisition equipment, transducers, remote
terminal unit, communications equipment, phone lines, and fiber optics.

NERC shall mean the North American Electric Reliability Council or its successor organization.

New York State Transmission System shall mean the entire New York State electric

transmission system, which includes (i) the Transmission Facilities Under ISO Operational Control; (ii) the Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities within the New York Control Area.

Notice of Dispute shall mean a written notice of a dispute or claim that arises out of or in connection with this Agreement or its performance.

NPCC shall mean the Northeast Power Coordinating Council or its successor organization.

NYISO Deliverability Interconnection Standard - The standard that must be met, unless

otherwise provided for by Attachment S to the ISO OATT, by (i) any generation facility larger

than 2MW in order for that facility to obtain CRIS; (ii) any Class Year Transmission Project; (iii) any entity requesting External CRIS Rights, and (iv) any entity requesting a CRIS transfer
pursuant to Section 25.9.5 of Attachment S to the ISO OATT. To meet the NYISO
Deliverability Interconnection Standard, the Developer must, in accordance with the rules in
Attachment S to the ISO OATT, fund or commit to fund any System Deliverability Upgrades identified for its project in the Class Year Deliverability Study.

NYISO Minimum Interconnection Standard - The reliability standard that must be met by
any generation facility or Class Year Transmission Project that is subject to NYISO’s Large
Facility Interconnection Procedures in Attachment X to the ISO OATT or the NYISO’s Small
Generator Interconnection Procedures in Attachment Z, that is proposing to connect to the New
York State Transmission System or Distribution System, to obtain ERIS. The Minimum
Interconnection Standard is designed to ensure reliable access by the proposed project to the
New York State Transmission System or to the Distribution System. The Minimum
Interconnection Standard does not impose any deliverability test or deliverability requirement on
the proposed interconnection.

NYSRC shall mean the New York State Reliability Council or its successor organization.

Other Interfaces shall mean the following interfaces into Capacity Regions: Lower Hudson

Valley [i.e., Rest of State (Load Zones A-F) to Lower Hudson Valley (Load Zones G, H and I)]; New York City [i.e., Lower Hudson Valley (Load Zones G, H and I) to New York City (Load Zone J)]; and Long Island [i.e., Lower Hudson Valley (Load Zones G, H and I) to Long Island (Load Zone K)], and the following Interfaces between the NYCA and adjacent Control Areas: PJM to NYISO, ISO-NE to NYISO, Hydro-Quebec to NYISO, and Norwalk Harbor
(Connecticut) to Northport (Long Island) Cable.

Party or Parties shall mean NYISO or Con Edison, or both.

7

SERVICE AGREEMENT NO. 2521

Point of Interconnection shall mean the point, as set forth in Appendix A to this Agreement, where the Attachment Facilities connect to the New York State Transmission System or to the Distribution System.

Reasonable Efforts shall mean, with respect to an action required to be attempted or taken by a
Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and
are otherwise substantially equivalent to those a Party would use to protect its own interests.

Retired: A Generator that has permanently ceased operating on or after May 1, 2015 either: i) pursuant to applicable notice; or ii) as a result of the expiration of its Mothball Outage or its ICAP Ineligible Forced Outage.

Services Tariff shall mean the NYISO Market Administration and Control Area Tariff, as filed
with the Commission, and as amended or supplemented from time to time, or any successor tariff
thereto.

Stand Alone System Upgrade Facilities shall mean System Upgrade Facilities that Con Edison
may construct without affecting day-to-day operations of the New York State Transmission
System during their construction. NYISO and Con Edison must agree as to what constitutes
Stand Alone System Upgrade Facilities and identify them in Appendix A to this Agreement.

Standard Large Facility Interconnection Procedures (“Large Facility Interconnection Procedures” or “LFIP”) shall mean the interconnection procedures applicable to an
Interconnection Request pertaining to a Large Generating Facility that are included in
Attachment X of the ISO OATT.

Standard Large Generator Interconnection Agreement (“LGIA”) shall mean this

Agreement, which is the form of interconnection agreement applicable to an Interconnection

Request pertaining to a Large Generating Facility, that is included in Appendix 3 to Attachment X of the ISO OATT.

System Deliverability Upgrades shall mean the least costly configuration of commercially available components of electrical equipment that can be used, consistent with Good Utility Practice and Applicable Reliability Requirements, to make the modifications or additions to Byways and Highways and Other Interfaces on the existing New York State Transmission
System and Distribution System that are required for the proposed project to connect reliably to the system in a manner that meets the NYISO Deliverability Interconnection Standard at the requested level of Capacity Resource Interconnection Service.

System Protection Facilities shall mean the equipment, including necessary protection signal
communications equipment, required to (1) protect the New York State Transmission System
from faults or other electrical disturbances occurring at the Large Generating Facility and (2)
protect the Large Generating Facility from faults or other electrical system disturbances
occurring on the New York State Transmission System or on other delivery systems or other
generating systems to which the New York State Transmission System is directly connected.

8

SERVICE AGREEMENT NO. 2521

System Upgrade Facilities shall mean the least costly configuration of commercially available
components of electrical equipment that can be used, consistent with Good Utility Practice and
Applicable Reliability Requirements, to make the modifications to the existing transmission
system that are required to maintain system reliability due to: (i) changes in the system,
including such changes as load growth and changes in load pattern, to be addressed in the form
of generic generation or transmission projects; and (ii) proposed interconnections. In the case of
proposed interconnection projects, System Upgrade Facilities are the modifications or additions
to the existing New York State Transmission System that are required for the proposed project to
connect reliably to the system in a manner that meets the NYISO Minimum Interconnection
Standard.

Tariff shall mean the NYISO Open Access Transmission Tariff (“OATT”), as filed with the
Commission, and as amended or supplemented from time to time, or any successor tariff.

Trial Operation shall mean the period during which Con Edison is engaged in on-site test

operations and commissioning of the Large Generating Facility prior to Commercial Operation.

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION

2.1 Effective Date.

This Agreement shall become effective upon execution by the Parties, subject to

acceptance by FERC, or if filed unexecuted, upon the date specified by FERC. The NYISO and
Con Edison shall promptly file this Agreement with FERC upon execution in accordance with
Article 3.

2.2 Term of Agreement.

Subject to the provisions of Article 2.3, this Agreement shall remain in effect for a period of twenty (20) years from the Effective Date and shall be automatically renewed for each
successive one-year period thereafter.

2.3 Termination.

Written Notice.

This Agreement may be terminated by Con Edison after giving the NYISO ninety (90) Calendar Days advance written notice, or by the NYISO and Con Edison notifying FERC after the Large Generating Facility is Retired.

Default.

Either Party may terminate this Agreement in accordance with Article 16.

9

SERVICE AGREEMENT NO. 2521

Compliance.

Notwithstanding Articles 2.3.1 and 2.3.2, no termination of this Agreement shall become effective until the Parties have complied with all Applicable Laws and Regulations applicable to such termination, including the filing with FERC of a notice of termination of this Agreement, which notice has been accepted for filing by FERC.

2.4 Termination Costs.

If a Party elects to terminate this Agreement pursuant to Article 2.3.1 above, the

terminating Party shall pay all costs incurred or charges assessed by the other Party, as of the

date of the other Party’s receipt of such notice of termination, that are the responsibility of the

terminating Party under this Agreement. In the event of termination by a Party, both Parties shall use commercially Reasonable Efforts to mitigate the costs, damages and charges arising as a
consequence of termination.

2.5 Disconnection.

Upon termination of this Agreement, Con Edison will take all appropriate steps to

disconnect the Large Generating Facility from the New York State Transmission System. All costs required to effectuate such disconnection shall be borne by Con Edison.

2.6 Survival.

This Agreement shall continue in effect after termination to the extent necessary to

permit the determination and enforcement of liability and indemnification obligations arising from acts or events that occurred while this Agreement was in effect.

ARTICLE 3. REGULATORY FILINGS

NYISO and Con Edison shall file this Agreement (and any amendment hereto) with the appropriate Governmental Authority, if required. Any information related to studies for
interconnection asserted by Con Edison to contain Confidential Information shall be treated in accordance with Article 21 of this Agreement and Attachment F to the ISO OATT.

ARTICLE 4. SCOPE OF INTERCONNECTION SERVICE

4.1 Provision of Service.

NYISO will provide Con Edison with interconnection service of the following type for the term of this Agreement.

Product.

NYISO will provide Energy Resource Interconnection Service and Capacity Resource Interconnection Service to Con Edison at the Point of Interconnection.

10

SERVICE AGREEMENT NO. 2521

Con Edison is responsible for ensuring that its actual Large Generating Facility output matches the scheduled delivery from the Large Generating Facility to the New York State Transmission System, consistent with the scheduling requirements of the NYISO’s FERC-
approved market structure, including ramping into and out of such scheduled delivery, as
measured at the Point of Interconnection, consistent with the scheduling requirements of the ISO OATT and any applicable FERC-approved market structure.

4.2 No Transmission Delivery Service.

The execution of this Agreement does not constitute a request for, nor agreement to

provide, any Transmission Service under the ISO OATT, and does not convey any right to

deliver electricity to any specific customer or Point of Delivery. If Con Edison wishes to obtain Transmission Service on the New York State Transmission System, then Con Edison must
request such Transmission Service in accordance with the provisions of the ISO OATT.

4.3 No Other Services.

The execution of this Agreement does not constitute a request for, nor agreement to provide Energy, any Ancillary Services or Installed Capacity under the NYISO Market
Administration and Control Area Services Tariff (“Services Tariff”). If Con Edison wishes to supply Energy, Installed Capacity or Ancillary Services, then Con Edison will make application to do so in accordance with the NYISO Services Tariff.

ARTICLE 5. INTERCONNECTION FACILITIES ENGINEERING,
 PROCUREMENT, AND CONSTRUCTION

5.1 Milestones.

Con Edison shall select the In-Service Date, Initial Synchronization Date, and

Commercial Operation Date; and the dates for completion of the Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades as set forth in Appendix A hereto, and such dates shall be set forth in Appendix B hereto.

Interconnection Facilities.

Con Edison shall design, procure, and construct the Attachment Facilities, System

Upgrade Facilities, and System Deliverability Upgrades set forth in Appendix A hereto using
Good Utility Practice, and in compliance with Applicable Laws and Regulations and with
Applicable Reliability Standards. Con Edison shall design, procure, and construct the
Attachment Facilities, System Upgrade Facilities, and System Deliverability Upgrades, using
Reasonable Efforts to complete the Attachment Facilities and System Upgrade Facilities and
System Deliverability Upgrades by the dates set forth in Appendix B hereto. Con Edison shall
not be required to undertake any action which is inconsistent with its standard safety practices,
its material and equipment specifications, its design criteria and construction procedures, its
labor agreements, and Applicable Laws and Regulations. Con Edison shall keep NYISO advised
periodically as to the progress of its efforts. In the event Con Edison reasonably expects that it
will not be able to complete the Attachment Facilities and System Upgrade Facilities and System

11

SERVICE AGREEMENT NO. 2521

Deliverability Upgrades by the specified dates, Con Edison shall promptly provide written notice
to NYISO, and shall undertake Reasonable Efforts to meet the earliest dates thereafter. In no
event shall the NYISO have any liability whatsoever to Con Edison for the design, procurement
or construction of the Attachment Facilities, System Upgrade Facilities or System Deliverability
Upgrades. Con Edison shall not transfer operational control of any Attachment Facilities and
Stand Alone System Upgrade Facilities to the NYISO upon completion of such facilities.

5.2 Power System Stabilizers.

Con Edison shall procure, install, maintain and operate Power System Stabilizers in
accordance with the requirements identified in the Interconnection Studies conducted for Con
Edison’s Large Generating Facility. NYISO reserves the right to reasonably establish minimum
acceptable settings for any installed Power System Stabilizers, subject to the design and
operating limitations of the Large Generating Facility. If the Large Generating Facility’s Power
System Stabilizers are removed from service or not capable of automatic operation, Con Edison
shall immediately notify NYISO. The requirements of this paragraph shall not apply to wind
generators.

5.3 Limited Operation.

If any of the Attachment Facilities or System Upgrade Facilities or System Deliverability
Upgrades are not reasonably expected to be completed prior to the Commercial Operation Date
of Con Edison’s Large Generating Facility, NYISO shall, upon the request and at the expense of
Con Edison, in conjunction with Con Edison, perform operating studies on a timely basis to
determine the extent to which Con Edison’s Large Generating Facility may operate prior to the
completion of the Attachment Facilities or System Upgrade Facilities or System Deliverability
Upgrades consistent with Applicable Laws and Regulations, Applicable Reliability Standards,
Good Utility Practice, and this Agreement. NYISO shall permit Con Edison to operate the
Large Generating Facility and the Attachment Facilities in accordance with the results of such
studies.

5.4 Permits.

NYISO and Con Edison shall cooperate with each other in good faith in obtaining all permits, licenses and authorizations that are necessary to accomplish the interconnection in compliance with Applicable Laws and Regulations.

5.5 Suspension.

Con Edison reserves the right, upon written notice to NYISO, to suspend at any time all work by Con Edison associated with the construction and installation of the Attachment
Facilities and/or System Upgrade Facilities and/or System Deliverability Upgrades required for only Con Edison under this Agreement with the condition that the New York State Transmission System shall be left in a safe and reliable condition in accordance with Good Utility Practice and the safety and reliability criteria of Con Edison and NYISO.

12

SERVICE AGREEMENT NO. 2521

In the event Con Edison suspends work required under this Agreement pursuant to this Article 5.5, and has not recommenced the work required under this Agreement on or before the expiration of three (3) years following commencement of such suspension, this Agreement shall be deemed terminated. The three-year period shall begin on the date the suspension, or the date of the written notice to the NYISO, if no effective date is specified.

5.6 Tax Status; Non-Jurisdictional Entities.

Tax Status.

Each Party shall cooperate with the other Party to maintain the other Party’s tax status. Nothing in this Agreement is intended to adversely affect the tax status of either Party, or the
status of either Party with respect to the issuance of bonds including, but not limited to, Local Furnishing Bonds. Notwithstanding any other provisions of this Agreement, LIPA, NYPA and Consolidated Edison Company of New York, Inc. shall not be required to comply with any
provisions of this Agreement that would result in the loss of tax-exempt status of any of their
Tax-Exempt Bonds or impair their ability to issue future tax-exempt obligations. For purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long Island Power
Authority, NYPA and Consolidated Edison Company of New York, Inc., the interest on which is not included in gross income under the Internal Revenue Code.

Non-Jurisdictional Entities.

LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA, from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general ratemaking authority.

5.7 Modification.

General.

Con Edison may undertake modifications to its facilities covered by this Agreement. If Con Edison plans to undertake a modification, Con Edison shall provide to NYISO sufficient
information regarding such modification so that NYISO may evaluate the potential impact of
such modification prior to commencement of the work. Such information shall be deemed to be Confidential Information hereunder and shall include information concerning the timing of such modifications and whether such modifications are expected to interrupt the flow of electricity
from the Large Generating Facility. Con Edison shall provide the relevant drawings, plans, and specifications to NYISO at least ninety (90) Calendar Days in advance of the commencement of the work or such shorter period upon which the Parties may agree, which agreement shall not
unreasonably be withheld, conditioned or delayed.

In the case of Large Generating Facility modifications that do not require Con Edison to
submit an Interconnection Request, the NYISO shall provide, within sixty (60) Calendar Days
(or such other time as the Parties may agree), an estimate of any additional modifications to the
New York State Transmission System, the Attachment Facilities or System Upgrade Facilities or
System Deliverability Upgrades necessitated by such Con Edison modification and a good faith

13

SERVICE AGREEMENT NO. 2521

estimate of the costs thereof. Con Edison shall be responsible for the cost of any such additional modifications, including the cost of studying the impact of the Con Edison modification.

Standards.

Any additions, modifications, or replacements made to Con Edison’s facilities shall be

designed, constructed and operated in accordance with this Agreement, NYISO requirements and Good Utility Practice.

ARTICLE 6. TESTING AND INSPECTION

6.1 Pre-Commercial Operation Date Testing and Modifications.

Prior to the Commercial Operation Date, Con Edison shall test the Attachment Facilities
and System Upgrade Facilities and System Deliverability Upgrades and the Large Generating
Facility to ensure their safe and reliable operation. Similar testing may be required after initial
operation. Con Edison shall make any modifications to its facilities that are found to be
necessary as a result of such testing. Con Edison shall bear the cost of all such testing and
modifications. Con Edison shall generate test energy at the Large Generating Facility only if it
has arranged for the injection of such test energy in accordance with NYISO procedures.

6.2 Post-Commercial Operation Date Testing and Modifications.

Con Edison shall at its own expense perform routine inspection and testing of its

facilities and equipment in accordance with Good Utility Practice and Applicable Reliability

Standards as may be necessary to ensure the continued interconnection of the Large Generating Facility with the New York State Transmission System in a safe and reliable manner.

6.3 Right to Observe Testing.

Con Edison shall notify the NYISO, in advance of its performance of tests of its

Attachment Facilities. The NYISO, shall have the right, at its own expense, to observe such
testing.

6.4 Right to Inspect.

The NYISO shall have the right, but shall have no obligation to: (i) observe Con Edison’s
tests and/or inspection of any of its System Protection Facilities and other protective equipment,
including Power System Stabilizers; (ii) review the settings of Con Edison’s System Protection
Facilities and other protective equipment; and (iii) review Con Edison’s maintenance records
relative to the Attachment Facilities, the System Protection Facilities and other protective
equipment. NYISO may exercise these rights from time to time as it deems necessary upon
reasonable notice to Con Edison. The exercise or non-exercise by NYISO of any such rights
shall not be construed as an endorsement or confirmation of any element or condition of the
Attachment Facilities or the System Protection Facilities or other protective equipment or the
operation thereof, or as a warranty as to the fitness, safety, desirability, or reliability of same.
Any information that NYISO obtains through the exercise of any of its rights under this Article

14

SERVICE AGREEMENT NO. 2521

6.4 shall be treated in accordance with Article 21 of this Agreement and Attachment F to the ISO
OATT.

ARTICLE 7. METERING

7.1 General.

Con Edison shall comply with applicable requirements of NYISO and the New York

Public Service Commission when exercising its rights and fulfilling its responsibilities under this
Article 7. Unless otherwise agreed to by the NYISO approved meter service provider, Con
Edison shall install Metering Equipment at the Point of Interconnection prior to any operation of
the Large Generating Facility and shall own, operate, test and maintain such Metering
Equipment. Net power flows including MW and MVAR, MWHR and loss profile data to and
from the Large Generating Facility shall be measured at the Point of Interconnection. Con
Edison shall provide metering quantities, in analog and/or digital form, as required, to NYISO
upon request. Where the Point of Interconnection for the Large Generating Facility is other than
the generator terminal, Con Edison shall also provide gross MW and MVAR quantities at the
generator terminal. Con Edison shall bear all reasonable documented costs associated with the
purchase, installation, operation, testing and maintenance of the Metering Equipment.

7.2 Standards.

Con Edison shall install, calibrate, and test revenue quality Metering Equipment

including potential transformers and current transformers in accordance with applicable ANSI and PSC standards as detailed in the NYISO Control Center Communications Manual and in the NYISO Revenue Metering Requirements Manual.

7.3 Testing of Metering Equipment.

Con Edison shall inspect and test all of its Metering Equipment upon installation and at
least once every two (2) years thereafter. If requested to do so by NYISO, Con Edison shall, at
its expense, inspect or test Metering Equipment more frequently than every two (2) years. Con
Edison shall give reasonable notice of the time when any inspection or test shall take place, and
Con Edison and NYISO may have representatives present at the test or inspection. If at any time
Metering Equipment is found to be inaccurate or defective, it shall be adjusted, repaired or

replaced at Con Edison’s expense, in order to provide accurate metering. If Metering Equipment
fails to register, or if the measurement made by Metering Equipment during a test varies by more
than two percent from the measurement made by the standard meter used in the test, Con Edison
shall adjust the measurements by correcting all measurements for the period during which
Metering Equipment was in error. If the period cannot be reasonably ascertained, the adjustment
shall be for the period immediately preceding the test of the Metering Equipment equal to one-
half the time from the date of the last previous test of the Metering Equipment. The NYISO
shall reserve the right to review all associated metering equipment installation on Con Edison’s
property at any time.

15

SERVICE AGREEMENT NO. 2521

7.4 Metering Data.

At Con Edison’s expense, the metered data shall be telemetered to one or more locations designated by the Parties. Such telemetered data shall be used, under normal operating
conditions, as the official measurement of the amount of energy delivered from the Large
Generating Facility to the Point of Interconnection.

ARTICLE 8. COMMUNICATIONS

8.1 Con Edison Obligations.

In accordance with applicable NYISO requirements, Con Edison shall maintain

satisfactory operating communications with the NYISO. Con Edison shall provide standard

voice line, dedicated voice line and facsimile communications at the Large Generating Facility
control room or central dispatch facility through use of either the public telephone system, or a
voice communications system that does not rely on the public telephone system. Con Edison
shall also provide the dedicated data circuit(s) necessary to provide Con Edison data to NYISO
as set forth in Appendix D hereto. The data circuit(s) shall extend from the Large Generating
Facility to the location(s) specified by Con Edison and NYISO. Any required maintenance of
such communications equipment shall be performed by Con Edison. Operational

communications shall be activated and maintained under, but not be limited to, the following events: system paralleling or separation, scheduled and unscheduled shutdowns, equipment clearances, and hourly and daily load data.

8.2 Remote Terminal Unit.

Prior to the Initial Synchronization Date of the Large Generating Facility, a Remote Terminal Unit, or equivalent data collection and transfer equipment acceptable to the Parties, shall be installed by Con Edison to gather accumulated and instantaneous data to be telemetered to the location(s) designated by NYISO through use of a dedicated point-to-point data circuit(s) as indicated in Article 8.1. The communication protocol for the data circuit(s) shall be specified by NYISO. Instantaneous bi-directional analog real power and reactive power flow information must be telemetered directly to the location(s) specified by NYISO.

Each Party will promptly advise the other Party if it detects or otherwise learns of any

metering, telemetry or communications equipment errors or malfunctions that require the

attention and/or correction by Con Edison. Con Edison shall correct such error or malfunction as soon as reasonably feasible.

ARTICLE 9. OPERATIONS

9.1 General.

Each Party shall comply with Applicable Laws and Regulations and Applicable

Reliability Standards. Each Party shall provide to the other Party all information that may

reasonably be required by the other Party to comply with Applicable Laws and Regulations and Applicable Reliability Standards.

16

SERVICE AGREEMENT NO. 2521

9.2 Operational Obligations.

Con Edison and NYISO shall cause the New York State Transmission System and the
Attachment Facilities to be operated, maintained and controlled in a safe and reliable manner in
accordance with this Agreement and the NYISO Tariffs. NYISO and Con Edison may provide
operating instructions to Con Edison consistent with this Agreement, NYISO procedures and
Con Edison’s operating protocols and procedures as they may change from time to time. NYISO
will consider changes to their respective operating protocols and procedures proposed by Con
Edison.

9.3 Con Edison Obligations.

Con Edison shall at its own expense operate, maintain and control the Large Generating
Facility and the Attachment Facilities in a safe and reliable manner and in accordance with this
Agreement. Con Edison shall operate the Large Generating Facility and the Attachment
Facilities in accordance with NYISO and Con Edison requirements, as such requirements are set
forth or referenced in Appendix C hereto. Appendix C will be modified to reflect changes to the
requirements as they may change from time to time. Either Party may request that the other
Party provide copies of the requirements set forth or referenced in Appendix C hereto.

9.4 Start-Up and Synchronization.

Con Edison is responsible for the proper synchronization of the Large Generating Facility

to the New York State Transmission System in accordance with NYISO and Con Edison

procedures and requirements.

9.5 Real and Reactive Power Control and Primary Frequency Response.

Power Factor Design Criteria.

9.5.1.1 Synchronous Generation. Con Edison shall maintain effective composite power delivery of the Large Generating Facility at the Point of Interconnection within the existing reactive power capability range, in accordance with Good Utility Practice.

Con Edison shall design and maintain the plant auxiliary systems to operate safely throughout the entire real and reactive power design range.

9.5.1.2 Non-Synchronous Generation. Con Edison shall design the Large Generating
Facility to maintain composite power delivery at continuous rated power output at the high-side
of the generator substation at a power factor within the range of 0.95 leading to 0.95 lagging,
unless the NYISO or Con Edison has established a different power factor range that applies to all
non-synchronous generators in the Control Area or Con Edison’s Transmission District (as
applicable) on a comparable basis, in accordance with Good Utility Practice. This power factor
range standard shall be dynamic and can be met using, for example, power electronics designed
to supply this level of reactive capability (taking into account any limitations due to voltage
level, real power output, etc.) or fixed and switched capacitors, or a combination of the two.

17

SERVICE AGREEMENT NO. 2521

This requirement shall only apply to newly interconnection non-synchronous generators that have not yet executed a Facilities Study Agreement as of September 21, 2016.

Con Edison shall design and maintain the plant auxiliary systems to operate safely throughout the entire real and reactive power design range.

Voltage Schedules.

Once Con Edison has synchronized the Large Generating Facility with the New York
State Transmission System, NYISO shall require Con Edison to operate the Large Generating
Facility to produce or absorb reactive power within the capability of the Large Generating
Facility. NYISO’s voltage schedules shall treat all sources of reactive power in the New York
Control Area in an equitable and not unduly discriminatory manner. NYISO shall exercise
Reasonable Efforts to provide Con Edison with such schedules in accordance with NYISO
procedures, and may make changes to such schedules as necessary to maintain the reliability of
the New York State Transmission System. Con Edison shall operate the Large Generating
Facility to maintain the specified output voltage or power factor at the Point of Interconnection
within the capability of the Large Generating Facility as directed by Con Edison’s system
operator or the NYISO. If Con Edison is unable to maintain the specified voltage or power
factor, it shall promptly notify NYISO.

Payment for Reactive Power.

NYISO shall pay Con Edison for reactive power or voltage support service that Con Edison provides from the Large Generating Facility in accordance with the provisions of Rate Schedule 2 of the NYISO Services Tariff.

Governors and Regulators.

Whenever the Large Generating Facility is operated in parallel with the New York State
Transmission System, the turbine speed governors and automatic voltage regulators shall be in
automatic operation at all times. If the Large Generating Facility’s speed governors or automatic
voltage regulators are not capable of such automatic operation, Con Edison shall immediately
notify NYISO, or its designated representative, and ensure that such Large Generating Facility’s
real and reactive power are within the design capability of the Large Generating Facility’s

generating unit(s) and steady state stability limits and NYISO system operating (thermal, voltage and transient stability) limits. Con Edison shall not cause its Large Generating Facility to
disconnect automatically or instantaneously from the New York State Transmission System or trip any generating unit comprising the Large Generating Facility for an under or over frequency condition unless the abnormal frequency condition persists for a time period beyond the limits set forth in ANSI/IEEE Standard C37.106, or such other standard as applied to other generators in the New York Control Area on a comparable basis.

18

SERVICE AGREEMENT NO. 2521

9.6 Outages and Interruptions.

Outages.

9.6.1.1 Outage Authority and Coordination.

Con Edison may, in accordance with NYISO procedures and Good Utility Practice,

remove from service any of its Attachment Facilities or System Upgrade Facilities and System
Deliverability Upgrades as necessary to perform maintenance or testing or to install or replace
equipment. In all circumstances, Con Edison shall use Reasonable Efforts to minimize the effect of such removal.

9.6.1.2 Outage Schedules.

Con Edison shall post scheduled outages of its transmission facilities on the NYISO

OASIS. Con Edison shall submit its planned maintenance schedules for the Large Generating
Facility to NYISO for a minimum of a rolling thirty-six month period. Con Edison shall update
its planned maintenance schedules as necessary. NYISO may direct Con Edison to reschedule
its maintenance as necessary to maintain the reliability of the New York State Transmission
System. Compensation to Con Edison for any additional direct costs that Con Edison incurs as a
result of rescheduling maintenance, including any additional overtime, breaking of maintenance
contracts or other costs above and beyond the cost Con Edison would have incurred absent the
request to reschedule maintenance, shall be in accordance with the ISO OATT. Con Edison will
not be eligible to receive compensation, if during the twelve (12) months prior to the date of the
scheduled maintenance, Con Edison had modified its schedule of maintenance activities other
than at the direction of the NYISO.

9.6.1.3 Outage Restoration.

Con Edison shall provide NYISO, to the extent such information is known, information on the nature of any Emergency State, an estimated time of restoration, and any corrective actions required. Initial verbal notice shall be followed up as soon as practicable with written notice explaining the nature of the outage.

Interruption of Service. If required by Good Utility Practice or Applicable

Reliability Standards to do so, the NYISO may require Con Edison to interrupt or reduce

production of electricity if such production of electricity could adversely affect the ability of

NYISO and Con Edison to perform such activities as are necessary to safely and reliably operate and maintain the New York State Transmission System. The following provisions shall apply to any interruption or reduction permitted under this Article 9.6.2:

9.6.2.1 The interruption or reduction shall continue only for so long as reasonably necessary under Good Utility Practice;

9.6.2.2 Any such interruption or reduction shall be made on an equitable, nondiscriminatory basis with respect to all generating facilities directly connected to the New York State Transmission System;

19

SERVICE AGREEMENT NO. 2521

9.6.2.3 When the interruption or reduction must be made under circumstances

which do not allow for advance notice, NYISO shall notify Con Edison by telephone as soon as
practicable of the reasons for the curtailment, interruption, or reduction, and, if known, its
expected duration. Telephone notification shall be followed by written notification as soon as
practicable;

9.6.2.4 Except during the existence of an Emergency State, when the interruption
or reduction can be scheduled without advance notice, NYISO shall notify Con Edison in
advance regarding the timing of such scheduling and further notify Con Edison of the expected
duration. NYISO shall coordinate with Con Edison using Good Utility Practice to schedule the
interruption or reduction during periods of least impact to Con Edison and the New York State
Transmission System;

9.6.2.5 The Parties shall cooperate and coordinate with each other to the extent necessary in order to restore the Large Generating Facility, Attachment Facilities, and the New York State Transmission System to their normal operating state, consistent with system
conditions and Good Utility Practice.

Under-Frequency and Over Frequency Conditions.

The New York State Transmission System is designed to automatically activate a load-
shed program as required by the NPCC in the event of an under-frequency system disturbance.
Con Edison shall implement under-frequency and over-frequency relay set points for the Large
Generating Facility as required by the NPCC to ensure “ride through” capability of the New
York State Transmission System. Large Generating Facility response to frequency deviations of
predetermined magnitudes, both under-frequency and over-frequency deviations, shall be studied
and coordinated with the NYISO and Con Edison in accordance with Good Utility Practice. The
term “ride through” as used herein shall mean the ability of a Generating Facility to stay
connected to and synchronized with the New York State Transmission System during system
disturbances within a range of under-frequency and over-frequency conditions, in accordance
with Good Utility Practice and with NPCC Regional Reliability Reference Directory # 12, or its
successor.

System Protection and Other Control Requirements.

9.6.4.1 System Protection Facilities. Con Edison shall, at its expense, install,

operate and maintain any System Protection Facilities that may be required as a part of the Large Generating Facility or the Attachment Facilities or the New York State Transmission System as a result of the interconnection of the Large Generating Facility.

9.6.4.2 The protection facilities of Con Edison shall be coordinated with other systems in accordance with Good Utility Practice and Applicable Reliability Standards.

9.6.4.3 Con Edison shall be responsible for protection of its respective facilities consistent with Good Utility Practice and Applicable Reliability Standards.

20

SERVICE AGREEMENT NO. 2521

9.6.4.4 Con Edison’s protective relay design shall incorporate the necessary test switches to perform the tests required in Article 6 of this Agreement. The required test switches will be placed such that they allow operation of lockout relays while preventing breaker failure schemes from operating and causing unnecessary breaker operations and/or the tripping of the Large Generating Facility.

9.6.4.5 Con Edison will test, operate and maintain System Protection Facilities in accordance with Good Utility Practice, NERC and NPCC criteria.

9.6.4.6 Prior to the In-Service Date, and again prior to the Commercial Operation Date, Con Edison shall perform, or its agents shall perform, a complete calibration test and
functional trip test of the System Protection Facilities. At intervals suggested by Good Utility Practice and following any apparent malfunction of the System Protection Facilities, Con Edison shall perform both calibration and functional trip tests of its System Protection Facilities. These tests do not require the tripping of any in-service generation unit. These tests do, however,
require that all protective relays and lockout contacts be activated.

Requirements for Protection.

In compliance with NPCC requirements and Good Utility Practice, Con Edison shall
provide, install, own, and maintain relays, circuit breakers and all other devices necessary to
remove any fault contribution of the Large Generating Facility to any short circuit occurring on
the New York State Transmission System not otherwise isolated by Con Edison’s equipment,
such that the removal of the fault contribution shall be coordinated with the protective
requirements of the New York State Transmission System. Such protective equipment shall
include, without limitation, a disconnecting device or switch with load-interrupting capability
located between the Large Generating Facility and the New York State Transmission System at a
site selected by Con Edison. Con Edison shall be responsible for protection of the Large
Generating Facility and Con Edison’s other equipment from such conditions as negative
sequence currents, over- or under-frequency, sudden load rejection, over- or under-voltage, and
generator loss-of-field. Con Edison shall be solely responsible to disconnect the Large
Generating Facility and Con Edison’s other equipment if conditions on the New York State
Transmission System could adversely affect the Large Generating Facility.

Power Quality.

The facilities of Con Edison shall neither cause excessive voltage flicker nor introduce excessive distortion to the sinusoidal voltage or current waves as defined by ANSI Standard C84.1-1989, in accordance with IEEE Standard 519, or any applicable superseding electric industry standard. In the event of a conflict between ANSI Standard C84.1-1989, or any
applicable superseding electric industry standard, ANSI Standard C84.1-1989, or the applicable superseding electric industry standard, shall control.

21

SERVICE AGREEMENT NO. 2521

9.7 Use of Attachment Facilities by Third Parties.

Purpose of Attachment Facilities.

Except as may be required by Applicable Laws and Regulations, or as otherwise agreed to among the Parties, the Attachment Facilities shall be constructed for the sole purpose of interconnecting the Large Generating Facility to the New York State Transmission System and shall be used for no other purpose.

Third Party Users.

If required by Applicable Laws and Regulations or if the Parties mutually agree, such
agreement not to be unreasonably withheld, to allow one or more third parties to use the
Attachment Facilities, or any part thereof, Con Edison will be entitled to compensation for the
capital expenses it incurred in connection with the Attachment Facilities based upon the pro rata
use of the Attachment Facilities by Con Edison and all third party users, in accordance with
Applicable Laws and Regulations or upon some other mutually-agreed upon methodology. In
addition, cost responsibility for ongoing costs, including operation and maintenance costs
associated with the Attachment Facilities, will be allocated between Con Edison and any third
party users based upon the pro rata use of the Attachment Facilities by Con Edison and all third
party users, in accordance with Applicable Laws and Regulations or upon some other mutually
agreed upon methodology. If the issue of such compensation or allocation cannot be resolved
through such negotiations, it shall be submitted to FERC for resolution.

9.8 Disturbance Analysis Data Exchange.

The Parties will cooperate with one another in the analysis of disturbances to either the
Large Generating Facility or the New York State Transmission System by gathering and
providing access to any information relating to any disturbance, including information from
disturbance recording equipment, protective relay targets, breaker operations and sequence of
events records, and any disturbance information required by Good Utility Practice.

9.9 Phasor Measurement Units

Con Edison shall install and maintain, at its expense, phasor measurement units

(“PMUs”) if it meets the following criteria: (1) completed a Class Year after Class Year 2017; and (2) proposes a new Large Facility that either (a) has a maximum net output equal to or greater than 100 MW or (b) requires, as Attachment Facilities or System Upgrade Facilities, a new substation of 230kV or above.

PMUs shall be installed on the Large Facility on the low side of the generator step-up

transformer, unless it is a non-synchronous generation facility, in which case the PMUs shall be
installed on the Con Edison side of the Point of Interconnection. The PMUs must be capable of
performing phasor measurements at a minimum of 60 samples per second which are
synchronized via a high-accuracy satellite clock. To the extent Con Edison installs similar
quality equipment, such as relays or digital fault recorders, that can collect data at least at the

22

SERVICE AGREEMENT NO. 2521

same rate as PMUs and which data is synchronized via a high-accuracy satellite clock, such equipment would satisfy this requirement.

Con Edison shall be required to install and maintain, at its expense, PMU equipment

which includes the communication circuit capable of carrying the PMU data to a local data

concentrator, and then transporting the information continuously to the NYISO; as well as store
the PMU data locally for thirty days. Con Edison shall provide to the NYISO all necessary and
requested information through Con Edison’s and the NYISO’s synchrophasor system, including
the following: (a) gross MW and MVAR measured at the Large Generating Facility side of the
generator step-up transformer (or, for a non-synchronous generation facility, to be measured at
the Large Generating Facility side of the Point of Interconnection); (b) generator terminal

voltage and current magnitudes and angles; (c) generator terminal frequency and frequency rate of change; and (d) generator field voltage and current, where available; and (e) breaker status, if available. Con Edison will provide for the ongoing support and maintenance of the network communications linking the data concentrator to the NYISO, consistent with ISO Procedures detailing the obligations related to SCADA data.

ARTICLE 10. MAINTENANCE

10.1 Con Edison Obligations.

Con Edison shall maintain its transmission facilities, Large Generating Facility and
Attachment Facilities in a safe and reliable manner and in accordance with this Agreement.

10.2 Coordination.

Con Edison shall keep NYISO fully informed of the preventive and corrective

maintenance that is planned, and shall schedule all such maintenance in accordance with NYISO procedures.

10.3 Secondary Systems.

Con Edison shall be responsible for the inspection, maintenance, and testing of control or power circuits that operate below 600 volts, AC or DC, including, but not limited to, any
hardware, control or protective devices, cables, conductors, electric raceways, secondary
equipment panels, transducers, batteries, chargers, and voltage and current transformers. Con
Edison shall provide advance notice to NYISO, before undertaking any work on such circuits, especially on electrical circuits involving circuit breaker trip and close contacts, current
transformers, or potential transformers.

10.4 Operating and Maintenance Expenses.

Subject to the provisions herein addressing the use of facilities by others, and except for
operations and maintenance expenses associated with modifications made for providing
interconnection or transmission service to a third party and such third party pays for such
expenses, Con Edison shall be responsible for all expenses including overheads, associated with

23

SERVICE AGREEMENT NO. 2521

owning, operating, maintaining, repairing, and replacing the Large Generating Facility, the
Attachment Facilities, the System Upgrade Facilities, and System Deliverability Upgrades.

ARTICLE 11. PERFORMANCE OBLIGATION

11.1 Attachment Facilities.

Con Edison shall design, procure, construct, install, own and/or control the Attachment Facilities described in Appendix A hereto, at its sole expense.

11.2 System Upgrade Facilities and System Deliverability Upgrades.

Con Edison shall design, procure, construct, install, and own the System Upgrade

Facilities and System Deliverability Upgrades described in Appendix A hereto. The

responsibility of Con Edison for costs related to System Upgrade Facilities and System

Deliverability Upgrades shall be determined in accordance with the provisions of Attachment S to the ISO OATT.

11.3 Special Provisions for Affected Systems.

For the re-payment of amounts advanced to Affected System Operator for System

Upgrade Facilities or System Deliverability Upgrades, Con Edison and Affected System

Operator shall enter into an agreement that provides for such re-payment, but only if

responsibility for the cost of such System Upgrade Facilities or System Deliverability Upgrades is not to be allocated in accordance with Attachment S to the ISO OATT. The agreement shall specify the terms governing payments to be made by Con Edison to the Affected System
Operator as well as the re-payment by the Affected System Operator.

11.4 Con Edison Compensation for Emergency Services.

If, during an Emergency State, Con Edison provides services at the request or direction of the NYISO or Con Edison’s Control Center, Con Edison will be compensated for such services in accordance with the NYISO Services Tariff.

ARTICLE 12. EMERGENCIES

12.1 Obligations.

Each Party shall comply with the Emergency State procedures of NYISO, the applicable Reliability Councils, Applicable Laws and Regulations, and any emergency procedures agreed to by the NYISO Operating Committee.

12.2 Notice.

NYISO shall notify Con Edison promptly when it becomes aware of an Emergency State
that affects the Attachment Facilities or the New York State Transmission System that may
reasonably be expected to affect Con Edison’s operation of the Large Generating Facility. Con
Edison shall notify NYISO promptly when it becomes aware of an Emergency State that affects

24

SERVICE AGREEMENT NO. 2521

the Large Generating Facility or the Attachment Facilities that may reasonably be expected to affect the New York State Transmission System. To the extent information is known, the
notification shall describe the Emergency State, the extent of the damage or deficiency, the expected effect on the operation of Con Edison’s facilities and operations, its anticipated
duration and the corrective action taken and/or to be taken. The initial notice shall be followed as soon as practicable with written notice.

12.3 NYISO and Con Edison Authority.

General.

NYISO or Con Edison may take whatever actions with regard to the New York State

Transmission System or the Attachment Facilities it deems necessary during an Emergency State in order to (i) preserve public health and safety, (ii) preserve the reliability of the New York State Transmission System or the Attachment Facilities, (iii) limit or prevent damage, and (iv)
expedite restoration of service.

NYISO and Con Edison shall use Reasonable Efforts to minimize the effect of such

actions or inactions on the Large Generating Facility. NYISO or Con Edison may, on the basis
of technical considerations, require the Large Generating Facility to mitigate an Emergency State
by taking actions necessary and limited in scope to remedy the Emergency State, including, but
not limited to, directing Con Edison to shut-down, start-up, increase or decrease the real or
reactive power output of the Large Generating Facility; implementing a reduction or
disconnection pursuant to Article 12.3.2; directing Con Edison to assist with blackstart (if
available) or restoration efforts; or altering the outage schedules of the Large Generating Facility
and the Attachment Facilities. Con Edison shall comply with all of the NYISO’s operating
instructions concerning Large Generating Facility real power and reactive power output within
the manufacturer’s design limitations of the Large Generating Facility’s equipment that is in
service and physically available for operation at the time, in compliance with Applicable Laws
and Regulations.

Reduction and Disconnection.

NYISO or Con Edison may reduce Capacity Resource Interconnection Service and
Energy Resource Interconnection Service or disconnect the Large Generating Facility or the
Attachment Facilities, when such reduction or disconnection is necessary under Good Utility
Practice due to an Emergency State. These rights are separate and distinct from any right of
Curtailment of NYISO pursuant to the ISO OATT. When NYISO can schedule the reduction or
disconnection in advance, NYISO shall notify Con Edison of the reasons, timing and expected
duration of the reduction or disconnection. NYISO shall coordinate with Con Edison using
Good Utility Practice to schedule the reduction or disconnection during periods of least impact to
Con Edison and the New York State Transmission System. Any reduction or disconnection shall
continue only for so long as reasonably necessary under Good Utility Practice. The Parties shall
cooperate with each other to restore the Large Generating Facility, the Attachment Facilities, and
the New York State Transmission System to their normal operating state as soon as practicable
consistent with Good Utility Practice.

25

SERVICE AGREEMENT NO. 2521

12.4 Large Generating Facility.

Consistent with Good Utility Practice and this Agreement, Con Edison may take

whatever actions or inactions with regard to the Large Generating Facility during an Emergency
State in order to (i) preserve public health and safety, (ii) preserve the reliability of the Large
Generating Facility, (iii) limit or prevent damage, and (iv) expedite restoration of service. Con
Edison shall use Reasonable Efforts to minimize the effect of such actions or inactions on the
New York State Transmission System. NYISO shall use Reasonable Efforts to assist Con
Edison in such actions.

12.5 Limited Liability.

Except as otherwise provided in Article 11.4 of this Agreement, neither Party shall be
liable to the other Party for any action it takes in responding to an Emergency State so long as
such action is made in good faith and is consistent with Good Utility Practice and the NYISO
Tariffs.

ARTICLE 13. REGULATORY REQUIREMENTS AND GOVERNING LAW

13.1 Regulatory Requirements.

Each Party’s obligations under this Agreement shall be subject to its receipt of any

required approval or certificate from one or more Governmental Authorities in the form and

substance satisfactory to the applying Party, or the Party making any required filings with, or

providing notice to, such Governmental Authorities, and the expiration of any time period

associated therewith. Each Party shall in good faith seek and use its Reasonable Efforts to obtain such other approvals. Nothing in this Agreement shall require Con Edison to take any action that could result in its inability to obtain, or its loss of, status or exemption under the Federal Power Act or the Public Utility Holding Company Act of 2005 or the Public Utility Regulatory Policies Act of 1978, as amended.

13.2 Governing Law.

The validity, interpretation and performance of this Agreement and each of its

provisions shall be governed by the laws of the state of New York, without regard to its conflicts of law principles.

This Agreement is subject to all Applicable Laws and Regulations.

Each Party expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, rules, or regulations of a Governmental Authority.

ARTICLE 14. NOTICES

14.1 General.

Unless otherwise provided in this Agreement, any notice, demand or request required or
permitted to be given by a Party to the other Party and any instrument required or permitted to be

26

SERVICE AGREEMENT NO. 2521

tendered or delivered by a Party in writing to the other Party shall be effective when delivered
and may be so given, tendered or delivered, by recognized national courier, or by depositing the same with the United States Postal Service with postage prepaid, for delivery by certified or
registered mail, addressed to the Party, or personally delivered to the Party, at the address set out in Appendix F hereto.

A Party may change the notice information in this Agreement by giving five (5) Business Days written notice prior to the effective date of the change.

14.2 Alternative Forms of Notice.

Any notice or request required or permitted to be given by a Party to the other Party and not required by this Agreement to be given in writing may be so given by telephone, facsimile or email to the telephone numbers and email addresses set out in Appendix F hereto.

14.3 Operations and Maintenance Notice.

Con Edison shall notify the NYISO in writing of the identity of the person(s) that it

designates as the point(s) of contact with respect to the implementation of Articles 9 and 10 of this Agreement.

ARTICLE 15. FORCE MAJEURE

15.1 Economic hardship is not considered a Force Majeure event.

15.2 A Party shall not be responsible or liable, or deemed, in Default with respect to

any obligation hereunder, (including obligations under Article 4 of this Agreement), other than
the obligation to pay money when due, to the extent the Party is prevented from fulfilling such
obligation by Force Majeure. A Party unable to fulfill any obligation hereunder (other than an
obligation to pay money when due) by reason of Force Majeure shall give notice and the full
particulars of such Force Majeure to the other Party in writing or by telephone as soon as
reasonably possible after the occurrence of the cause relied upon. Telephone notices given
pursuant to this Article shall be confirmed in writing as soon as reasonably possible and shall
specifically state full particulars of the Force Majeure, the time and date when the Force Majeure
occurred and when the Force Majeure is reasonably expected to cease. The Party affected shall
exercise due diligence to remove such disability with reasonable dispatch, but shall not be
required to accede or agree to any provision not satisfactory to it in order to settle and terminate a
strike or other labor disturbance.

ARTICLE 16. DEFAULT

16.1 General.

No Breach shall exist where such failure to discharge an obligation (other than the

payment of money) is the result of Force Majeure as defined in this Agreement or the result of an
act or omission of the other Party. Upon a Breach, the non-Breaching Party shall give written
notice of such to the Breaching Party. The Breaching Party shall have thirty (30) Calendar Days

27

SERVICE AGREEMENT NO. 2521

from receipt of the Breach notice within which to cure such Breach; provided however, if such
Breach is not capable of cure within thirty (30) Calendar Days, the Breaching Party shall
commence such cure within thirty (30) Calendar Days after notice and continuously and
diligently complete such cure within ninety (90) Calendar Days from receipt of the Breach
notice; and, if cured within such time, the Breach specified in such notice shall cease to exist.

16.2 Right to Terminate.

If a Breach is not cured as provided in this Article 16, or if a Breach is not capable of

being cured within the period provided for herein, the non-Breaching Party shall thereafter have the right to declare a Default and terminate this Agreement by written notice at any time until cure occurs, and be relieved of any further obligation hereunder and, whether or not that Party terminates this Agreement, to recover from the defaulting Party all amounts due hereunder, plus all other damages and remedies to which it is entitled at law or in equity. The provisions of this Article 16 will survive termination of this Agreement.

ARTICLE 17. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE

17.1 Indemnity.

Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and save

harmless, as applicable, the other Party (the “Indemnified Party”) from, any and all damages,

losses, claims, including claims and actions relating to injury to or death of any person or

damage to property, the alleged violation of any Environmental Law, or the release or threatened
release of any Hazardous Substance, demand, suits, recoveries, costs and expenses, court costs,
attorney fees, and all other obligations by or to third parties (any and all of these a “Loss”),
arising out of or resulting from (i) the Indemnified Party’s performance of its obligations under
this Agreement on behalf of the Indemnifying Party, except in cases where the Indemnifying
Party can demonstrate that the Loss of the Indemnified Party was caused by the gross negligence
or intentional wrongdoing of the Indemnified Party or (ii) the violation by the Indemnifying
Party of any Environmental Law or the release by the Indemnifying Party of any Hazardous
Substance.

Indemnified Party.

If a Party is entitled to indemnification under this Article 17 as a result of a claim by a third party, and the Indemnifying Party fails, after notice and reasonable opportunity to proceed under Article 17.1.3, to assume the defense of such claim, such Indemnified Party may at the expense of the Indemnifying Party contest, settle or consent to the entry of any judgment with respect to, or pay in full, such claim.

Indemnifying Party.

If an Indemnifying Party is obligated to indemnify and hold any Indemnified Party

harmless under this Article 17, the amount owing to the Indemnified Party shall be the amount of such Indemnified Party’s actual Loss, net of any insurance or other recovery.

28

SERVICE AGREEMENT NO. 2521

Indemnity Procedures.

Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or investigation as to which
the indemnity provided for in Article 17.1 may apply, the Indemnified Party shall notify the
Indemnifying Party of such fact. Any failure of or delay in such notification shall not affect a
Party’s indemnification obligation unless such failure or delay is materially prejudicial to the
Indemnifying Party.

Except as stated below, the Indemnifying Party shall have the right to assume the defense
thereof with counsel designated by such Indemnifying Party and reasonably satisfactory to the
Indemnified Party. If the defendants in any such action include the Indemnified Party and the
Indemnifying Party and if the Indemnified Party reasonably concludes that there may be legal
defenses available to it which are different from or additional to those available to the
Indemnifying Party, the Indemnified Party shall have the right to select separate counsel to assert
such legal defenses and to otherwise participate in the defense of such action on its own behalf.
In such instances, the Indemnifying Party shall only be required to pay the fees and expenses of
one additional attorney to represent an Indemnified Party having such differing or additional
legal defenses.

The Indemnified Party shall be entitled, at its expense, to participate in any such action,
suit or proceeding, the defense of which has been assumed by the Indemnifying Party.
Notwithstanding the foregoing, the Indemnifying Party (i) shall not be entitled to assume and
control the defense of any such action, suit or proceedings if and to the extent that, in the opinion
of the Indemnified Party and its counsel, such action, suit or proceeding involves the potential
imposition of criminal liability on the Indemnified Party, or there exists a conflict or adversity of
interest between the Indemnified Party and the Indemnifying Party, in such event the
Indemnifying Party shall pay the reasonable expenses of the Indemnified Party, and (ii) shall not
settle or consent to the entry of any judgment in any action, suit or proceeding without the
consent of the Indemnified Party, which shall not be unreasonably withheld, conditioned or
delayed.

17.2 No Consequential Damages.

Other than the liquidated damages heretofore described and the indemnity obligations set
forth in Article 17.1, in no event shall either Party be liable under any provision of this
Agreement for any losses, damages, costs or expenses for any special, indirect, incidental,
consequential, or punitive damages, including but not limited to loss of profit or revenue, loss of
the use of equipment, cost of capital, cost of temporary equipment or services, whether based in
whole or in part in contract, in tort, including negligence, strict liability, or any other theory of
liability; provided, however, that damages for which a Party may be liable to the other Party
under separate agreement will not be considered to be special, indirect, incidental, or
consequential damages hereunder.

29

SERVICE AGREEMENT NO. 2521

17.3 Insurance.

Con Edison shall, at its own expense, maintain in force throughout the period of this
Agreement insurance coverages for the Large Generating Facility in types and amounts
consistent with its existing commercial practice for the generating facilities that it owns and
operates and Good Utility Practice. Such insurance does not limit or qualify the liabilities and
obligations assumed by Con Edison under this Agreement. Con Edison may self-insure this
insurance obligation.

ARTICLE 18. ASSIGNMENT

This Agreement may be assigned by a Party only with the written consent of the other

Party; provided that a Party may assign this Agreement without the consent of the other Partys to
any Affiliate of the assigning Party with an equal or greater credit rating and with the legal
authority and operational ability to satisfy the obligations of the assigning Party under this
Agreement; provided further that a Party may assign this Agreement without the consent of the
other Party in connection with the sale, merger, restructuring, or transfer of a substantial portion
or all of its assets, including the Attachment Facilities it owns, so long as the assignee in such a
transaction directly assumes in writing all rights, duties and obligations arising under this
Agreement; and provided further that Con Edison shall have the right to assign this Agreement,
without the consent of the NYISO for collateral security purposes to aid in providing financing
for the Large Generating Facility, provided that Con Edison will promptly notify the NYISO of
any such assignment. Any financing arrangement entered into by Con Edison pursuant to this
Article will provide that prior to or upon the exercise of the secured party’s, trustee’s or
mortgagee’s assignment rights pursuant to said arrangement, the secured creditor, the trustee or
mortgagee will notify the NYISO of the date and particulars of any such exercise of assignment
right(s) and will provide the NYISO with proof that it meets the requirements of Article 17.3.
Any attempted assignment that violates this Article is void and ineffective. Any assignment
under this Agreement shall not relieve a Party of its obligations, nor shall a Party’s obligations be
enlarged, in whole or in part, by reason thereof. Where required, consent to assignment will not
be unreasonably withheld, conditioned or delayed.

ARTICLE 19. SEVERABILITY

If any provision in this Agreement is finally determined to be invalid, void or

unenforceable by any court or other Governmental Authority having jurisdiction, such

determination shall not invalidate, void or make unenforceable any other provision, agreement or covenant of this Agreement.

ARTICLE 20. COMPARABILITY

The Parties will comply with all applicable comparability and code of conduct laws, rules and regulations, as amended from time to time.

30

SERVICE AGREEMENT NO. 2521

ARTICLE 21. CONFIDENTIALITY

21.1 Confidentiality.

Certain information exchanged by the Parties during the term of this Agreement shall
constitute confidential information (“Confidential Information”) and shall be subject to this
Article 21.

If requested by a Party receiving information, the Party supplying the information shall provide in writing, the basis for asserting that the information referred to in this Article warrants confidential treatment, and the requesting Party may disclose such writing to the appropriate Governmental Authority. Each Party shall be responsible for the costs associated with affording confidential treatment to its information.

21.2 Term.

During the term of this Agreement, and for a period of three (3) years after the expiration or termination of this Agreement, except as otherwise provided in this Article 21, each Party shall hold in confidence and shall not disclose to any person Confidential Information.

21.3 Confidential Information.

The following shall constitute Confidential Information: (1) any non-public information that is treated as confidential by the disclosing Party and which the disclosing Party identifies as Confidential Information in writing at the time, or promptly after the time, of disclosure; or (2) information designated as Confidential Information by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

21.4 Scope.

Confidential Information shall not include information that the receiving Party can

demonstrate: (1) is generally available to the public other than as a result of a disclosure by the
receiving Party; (2) was in the lawful possession of the receiving Party on a non-confidential
basis before receiving it from the disclosing Party; (3) was supplied to the receiving Party
without restriction by a third party, who, to the knowledge of the receiving Party after due
inquiry, was under no obligation to the disclosing Party to keep such information confidential;

(4) was independently developed by the receiving Party without reference to Confidential

Information of the disclosing Party; (5) is, or becomes, publicly known, through no wrongful act
or omission of the receiving Party or Breach of this Agreement; or (6) is required, in accordance
with Article 21.9 of this Agreement, Order of Disclosure, to be disclosed by any Governmental
Authority or is otherwise required to be disclosed by law or subpoena, or is necessary in any
legal proceeding establishing rights and obligations under this Agreement. Information
designated as Confidential Information will no longer be deemed confidential if the Party that
designated the information as confidential notifies the other Party that it no longer is
confidential.

31

SERVICE AGREEMENT NO. 2521

21.5 Release of Confidential Information.

No Party shall release or disclose Confidential Information to any other person, except to
its Affiliates (limited by FERC Standards of Conduct requirements), subcontractors, employees,
consultants, or to parties who may be considering providing financing to or equity participation
with Con Edison, or to potential purchasers or assignees of a Con Edison, on a need-to-know
basis in connection with this Agreement, unless such person has first been advised of the
confidentiality provisions of this Article 21 and has agreed to comply with such provisions.
Notwithstanding the foregoing, a Party providing Confidential Information to any person shall
remain primarily responsible for any release of Confidential Information in contravention of this
Article 21.

21.6 Rights.

Each Party retains all rights, title, and interest in the Confidential Information that each

Party discloses to the other Party. The disclosure by each Party to the other Party of Confidential Information shall not be deemed a waiver by any Party or any other person or entity of the right to protect the Confidential Information from public disclosure.

21.7 No Warranties.

By providing Confidential Information, no Party makes any warranties or representations
as to its accuracy or completeness. In addition, by supplying Confidential Information, no Party
obligates itself to provide any particular information or Confidential Information to the other
Party nor to enter into any further agreements or proceed with any other relationship or joint
venture.

21.8 Standard of Care.

Each Party shall use at least the same standard of care to protect Confidential Information it receives as it uses to protect its own Confidential Information from unauthorized disclosure, publication or dissemination. Each Party may use Confidential Information solely to fulfill its obligations to the other Party under this Agreement or its regulatory requirements, including the ISO OATT and NYISO Services Tariff. The NYISO shall, in all cases, treat the information it receives in accordance with the requirements of Attachment F to the ISO OATT.

21.9 Order of Disclosure.

If a court or a Government Authority or entity with the right, power, and apparent

authority to do so requests or requires either Party, by subpoena, oral deposition, interrogatories,
requests for production of documents, administrative order, or otherwise, to disclose Confidential
Information, that Party shall provide the other Party with prompt notice of such request(s) or
requirement(s) so that the other Party may seek an appropriate protective order or waive
compliance with the terms of this Agreement. Notwithstanding the absence of a protective order
or waiver, the Party may disclose such Confidential Information which, in the opinion of its
counsel, the Party is legally compelled to disclose. Each Party will use Reasonable Efforts to

32

SERVICE AGREEMENT NO. 2521

obtain reliable assurance that confidential treatment will be accorded any Confidential Information so furnished.

21.10 Termination of Agreement.

Upon termination of this Agreement for any reason, each Party shall, within ten (10)
Calendar Days of receipt of a written request from the other Party, use Reasonable Efforts to
destroy, erase, or delete (with such destruction, erasure, and deletion certified in writing to the
other Party) or return to the other Party, without retaining copies thereof, any and all written or
electronic Confidential Information received from the other Party pursuant to this Agreement.

21.11 Remedies.

The Parties agree that monetary damages would be inadequate to compensate a Party for
another Party’s Breach of its obligations under this Article 21. Each Party accordingly agrees
that the other Party shall be entitled to equitable relief, by way of injunction or otherwise, if the
first Party Breaches or threatens to Breach its obligations under this Article 21, which equitable
relief shall be granted without bond or proof of damages, and the receiving Party shall not plead
in defense that there would be an adequate remedy at law. Such remedy shall not be deemed an
exclusive remedy for the Breach of this Article 21, but shall be in addition to all other remedies
available at law or in equity. The Parties further acknowledge and agree that the covenants

contained herein are necessary for the protection of legitimate business interests and are

reasonable in scope. No Party, however, shall be liable for indirect, incidental, or consequential
or punitive damages of any nature or kind resulting from or arising in connection with this
Article 21.

21.12 Disclosure to FERC, its Staff, or a State.

Notwithstanding anything in this Article 21 to the contrary, and pursuant to 18 C.F.R.
section 1b.20, if FERC or its staff, during the course of an investigation or otherwise, requests
information from one of the other Party that is otherwise required to be maintained in confidence
pursuant to this Agreement or the ISO OATT, the Party shall provide the requested information
to FERC or its staff, within the time provided for in the request for information. In providing the
information to FERC or its staff, the Party must, consistent with 18 C.F.R. section 388.112,
request that the information be treated as confidential and non-public by FERC and its staff and
that the information be withheld from public disclosure. Parties are prohibited from notifying
the other Party to this Agreement prior to the release of the Confidential Information to the
Commission or its staff. The Party shall notify the other Party to the Agreement when it is
notified by FERC or its staff that a request to release Confidential Information has been received
by FERC, at which time the Parties may respond before such information would be made public,
pursuant to 18 C.F.R. section 388.112. Requests from a state regulatory body conducting a
confidential investigation shall be treated in a similar manner if consistent with the applicable
state rules and regulations. A Party shall not be liable for any losses, consequential or otherwise,
resulting from that Party divulging Confidential Information pursuant to a FERC or state
regulatory body request under this paragraph.

33

SERVICE AGREEMENT NO. 2521

21.13 Required Notices Upon Requests or Demands for Confidential Information

Except as otherwise expressly provided herein, neither Party shall disclose Confidential
Information to any person not employed or retained by the Party possessing the Confidential
Information, except to the extent disclosure is (i) required by law; (ii) reasonably deemed by the
disclosing Party to be required to be disclosed in connection with a dispute between or among
the Parties, or the defense of litigation or dispute; (iii) otherwise permitted by consent of the
other Party, such consent not to be unreasonably withheld; or (iv) necessary to fulfill its
obligations under this Agreement, the ISO OATT or the NYISO Services Tariff. Prior to any
disclosures of a Party’s Confidential Information under this subparagraph, or if any third party or
Governmental Authority makes any request or demand for any of the information described in
this subparagraph, the disclosing Party agrees to promptly notify the other Party in writing and
agrees to assert confidentiality and cooperate with the other Party in seeking to protect the
Confidential Information from public disclosure by confidentiality agreement, protective order or
other reasonable measures.

ARTICLE 22. INFORMATION REQUIREMENT

22.1 Information Acquisition.

Con Edison shall submit specific information regarding the electrical characteristics of its
respective facilities to NYISO, as described below and in accordance with Applicable Reliability
Standards.

22.2 Information Submission by Con Edison.

The initial information submission by Con Edison shall occur no later than one hundred
eighty (180) Calendar Days prior to Trial Operation and shall include New York State
Transmission System information regarding selection of equipment necessary to meet any
system protection and stability requirements. On a monthly basis Con Edison shall provide
NYISO a status report on the construction and installation of the Attachment Facilities, System
Upgrade Facilities and System Deliverability Upgrades, including, but not limited to, the
following information: (1) progress to date; (2) a description of the activities since the last
report; (3) a description of the action items for the next period; and (4) the delivery status of
equipment ordered.

22.3 Updated Information Submission by Con Edison.

No later than one hundred eighty (180) Calendar Days prior to the Trial Operation, Con
Edison shall also submit a completed copy of the Large Generating Facility data requirements
contained in Appendix 1 to the Standard Large Facility Interconnection Procedures. It shall also
include any additional information provided for the Interconnection Facilities Study.
Information in this submission shall be the most current Large Generating Facility design or
expected performance data. Information submitted for stability models shall be compatible with
NYISO standard models. If there is no compatible model, Con Edison will work with a
consultant mutually agreed to by the Parties to develop and supply a standard model and
associated information.

34

SERVICE AGREEMENT NO. 2521

If Con Edison’s data is different from what was originally provided to NYISO pursuant
to an Interconnection Study Agreement and this difference may be reasonably expected to affect
the other Con Edison facilities or the New York State Transmission System, but does not require
the submission of a new Interconnection Request, then NYISO will conduct appropriate studies
to determine the impact on the New York State Transmission System based on the actual data
submitted pursuant to this Article 22.3. Such studies will provide an estimate of any additional
modifications to the New York State Transmission System, the Attachment Facilities, System
Upgrade Facilities or System Deliverability Upgrades based on the actual data and a good faith
estimate of the costs thereof. Con Edison shall not begin Trial Operation until such studies are
completed. Con Edison shall be responsible for the cost of any modifications required by the

actual data, including the cost of any required studies.

22.4 Information Supplementation.

Prior to the Commercial Operation Date, Con Edison shall supplement its information submissions described above in this Article 22 with any and all “as-built” Large Generating Facility information or “as-tested” performance information that differs from the initial
submissions or, alternatively, written confirmation that no such differences exist. Con Edison shall conduct tests on the Large Generating Facility as required by Good Utility Practice such as an open circuit “step voltage” test on the Large Generating Facility to verify proper operation of the Large Generating Facility’s automatic voltage regulator.

Unless otherwise agreed, the test conditions shall include: (1) Large Generating Facility
at synchronous speed; (2) automatic voltage regulator on and in voltage control mode; and (3) a
five percent change in Large Generating Facility terminal voltage initiated by a change in the
voltage regulators reference voltage. Con Edison shall provide validated test recordings showing
the responses of Large Generating Facility terminal and field voltages. In the event that direct
recordings of these voltages is impractical, recordings of other voltages or currents that mirror
the response of the Large Generating Facility’s terminal or field voltage are acceptable if
information necessary to translate these alternate quantities to actual Large Generating Facility
terminal or field voltages is provided. Large Generating Facility testing shall be conducted and
results provided to the NYISO for each individual generating unit in a station.

Subsequent to the Commercial Operation Date, Con Edison shall provide NYISO any
information changes due to equipment replacement, repair, or adjustment, including any
information changes due to equipment replacement, repair or adjustment in the directly
connected substation or any adjacent substation. Con Edison shall provide such information no
later than thirty (30) Calendar Days after the date of the equipment replacement, repair or
adjustment.

ARTICLE 23. INFORMATION ACCESS AND AUDIT RIGHTS

23.1 Information Access.

Each Party (“Disclosing Party”) shall make available to the other Party (“Requesting

Party”) information that is in the possession of the Disclosing Party and is necessary in order for

35

SERVICE AGREEMENT NO. 2521

the Requesting Party to: (i) verify the costs incurred by the Disclosing Party for which the

Requesting Party is responsible under this Agreement; and (ii) carry out its obligations and

responsibilities under this Agreement. The Parties shall not use such information for purposes other than those set forth in this Article 23.1 of this Agreement and to enforce their rights under this Agreement.

23.2 Reporting of Non-Force Majeure Events.

Each Party (the “Notifying Party”) shall notify the other Party when the Notifying Party becomes aware of its inability to comply with the provisions of this Agreement for a reason other than a Force Majeure event. The Parties agree to cooperate with each other and provide
necessary information regarding such inability to comply, including the date, duration, reason for the inability to comply, and corrective actions taken or planned to be taken with respect to such inability to comply. Notwithstanding the foregoing, notification, cooperation or information
provided under this Article shall not entitle the Party receiving such notification to allege a cause for anticipatory breach of this Agreement.

23.3 Audit Rights.

Subject to the requirements of confidentiality under Article 21 of this Agreement, each
Party shall have the right, during normal business hours, and upon prior reasonable notice to the other Party, to audit at its own expense the other Party’s accounts and records pertaining to the
other Party’s performance or satisfaction of its obligations under this Agreement. Such audit
rights shall include audits of the other Party’s costs and each Party’s actions in an Emergency
State. Any audit authorized by this Article shall be performed at the offices where such accounts and records are maintained and shall be limited to those portions of such accounts and records
that relate to the Party’s performance and satisfaction of obligations under this Agreement. Each Party shall keep such accounts and records for a period equivalent to the audit rights periods
described in Article 23.4 of this Agreement.

23.4 Audit Rights Periods.

Records related to a Party’s performance or satisfaction of its obligations under this

Agreement shall be subject to audit for twenty-four months after the event for which the audit is
sought.

ARTICLE 24. SUBCONTRACTORS

24.1 General.

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided, however, that each Party shall require its subcontractors to comply with all applicable terms and conditions of this Agreement in providing such services and each Party shall remain primarily liable to the other Party for the performance of such subcontractor.

36

SERVICE AGREEMENT NO. 2521

24.2 Responsibility of Principal.

The creation of any subcontract relationship shall not relieve the hiring Party of any of its obligations under this Agreement. The hiring Party shall be fully responsible to the other Party
for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been made; provided, however, that in no event shall the NYISO or Con Edison be liable for the
actions or inactions of Con Edison or its subcontractors with respect to obligations of the Con
Edison under Article 5 of this Agreement. Any applicable obligation imposed by this Agreement upon the hiring Party shall be equally binding upon, and shall be construed as having application to, any subcontractor of such Party.

24.3 No Limitation by Insurance.

The obligations under this Article 24 will not be limited in any way by any limitation of subcontractor’s insurance.

ARTICLE 25. DISPUTES

25.1 Submission.

In the event any Party has a dispute, or asserts a claim, that arises out of or in connection
with this Agreement or its performance (a “Dispute”), such Party shall provide the other Party
with written notice of the Dispute (“Notice of Dispute”). Such Dispute shall be referred to a
designated senior representative of each Party for resolution on an informal basis as promptly as
practicable after receipt of the Notice of Dispute by the other Party. In the event the designated
representatives are unable to resolve the Dispute through unassisted or assisted negotiations
within thirty (30) Calendar Days of the other Party’s receipt of the Notice of Dispute, such
Dispute may, upon mutual agreement of the Parties, be submitted to arbitration and resolved in
accordance with the arbitration procedures set forth below. In the event the Parties do not agree
to submit such Dispute to arbitration, each Party may exercise whatever rights and remedies it
may have in equity or at law consistent with the terms of this Agreement.

25.2 External Arbitration Procedures.

Any arbitration initiated under this Agreement shall be conducted before a single neutral
arbitrator appointed by the Parties. If the Parties fail to agree upon a single arbitrator within ten

(10) Calendar Days of the submission of the Dispute to arbitration, each Party shall choose one
arbitrator who shall sit on a three-member arbitration panel. The two arbitrators chosen by the
Parties shall then jointly choose the third arbitrator for the three-member arbitration panel;
provided, however, that, if they are unable to agree upon the third arbitrator, the arbitrators shall
request the appointment of the third arbitrator by the American Arbitration Association. The
arbitrator(s) shall be knowledgeable in electric utility matters, including electric transmission and
bulk power issues, and shall not have any current or past substantial business or financial
relationships with either party to the arbitration (except prior arbitration). The arbitrator(s) shall
provide each of the Parties an opportunity to be heard and, except as otherwise provided herein,
shall conduct the arbitration in accordance with the Commercial Arbitration Rules of the
American Arbitration Association (“Arbitration Rules”) and any applicable FERC regulations or

37

SERVICE AGREEMENT NO. 2521

RTO rules; provided, however, in the event of a conflict between the Arbitration Rules and the terms of this Article 25, the terms of this Article 25 shall prevail.

25.3 Arbitration Decisions.

Unless otherwise agreed by the Parties, the arbitrator(s) shall render a decision within

ninety (90) Calendar Days of appointment and shall notify the Parties in writing of such decision
and the reasons therefor. The arbitrator(s) shall be authorized only to interpret and apply the
provisions of this Agreement and shall have no power to modify or change any provision of this
Agreement in any manner. The decision of the arbitrator(s) shall be final and binding upon the
Parties, and judgment on the award may be entered in any court having jurisdiction. The
decision of the arbitrator(s) may be appealed solely on the grounds that the conduct of the
arbitrator(s), or the decision itself, violated the standards set forth in the Federal Arbitration Act
or the Administrative Dispute Resolution Act. The final decision of the arbitrator must also be
filed with FERC if it affects jurisdictional rates, terms and conditions of service, Attachment
Facilities, System Upgrade Facilities, or System Deliverability Upgrades.

25.4 Costs.

Each Party shall be responsible for its own costs incurred during the arbitration process
and for the following costs, if applicable: (1) one-half the cost of the three arbitrators chosen to
sit on the three-member panel; or (2) one-half the cost of the single arbitrator jointly chosen by
the Parties.

25.5 Termination.

Notwithstanding the provisions of this Article 25, any Party may terminate this

Agreement in accordance with its provisions or pursuant to an action at law or equity. The issue of whether such a termination is proper shall not be considered a Dispute hereunder.

ARTICLE 26. REPRESENTATIONS, WARRANTIES AND COVENANTS

26.1 General.

Each Party makes the following representations, warranties and covenants:

Good Standing.

Such Party is duly organized, validly existing and in good standing under the laws of the state in which it is organized, formed, or incorporated, as applicable; that it is qualified to do business in the state or states in which the Large Generating Facility, Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades owned by such Party, as
applicable, are located; and that it has the corporate power and authority to own its properties, to carry on its business as now being conducted and to enter into this Agreement and carry out the transactions contemplated hereby and perform and carry out all covenants and obligations on its part to be performed under and pursuant to this Agreement.

38

SERVICE AGREEMENT NO. 2521

Authority.

Such Party has the right, power and authority to enter into this Agreement, to become a
Party hereto and to perform its obligations hereunder. This Agreement is a legal, valid and
binding obligation of such Party, enforceable against such Party in accordance with its terms,
except as the enforceability thereof may be limited by applicable bankruptcy, insolvency,
reorganization or other similar laws affecting creditors’ rights generally and by general equitable
principles (regardless of whether enforceability is sought in a proceeding in equity or at law).

No Conflict.

The execution, delivery and performance of this Agreement does not violate or conflict with the organizational or formation documents, or bylaws or operating agreement, of such Party, or any judgment, license, permit, order, material agreement or instrument applicable to or binding upon such Party or any of its assets.

Consent and Approval.

Such Party has sought or obtained, or, in accordance with this Agreement will seek or obtain, each consent, approval, authorization, order, or acceptance by any Governmental
Authority in connection with the execution, delivery and performance of this Agreement, and it will provide to any Governmental Authority notice of any actions under this Agreement that are required by Applicable Laws and Regulations.

ARTICLE 27. MISCELLANEOUS

27.1 Binding Effect.

This Agreement and the rights and obligations hereof, shall be binding upon and shall inure to the benefit of the successors and permitted assigns of the Parties hereto.

27.2 Conflicts.

If there is a discrepancy or conflict between or among the terms and conditions of this
cover agreement and the Appendices hereto, the terms and conditions of this cover agreement
shall be given precedence over the Appendices, except as otherwise expressly agreed to in
writing by the Parties. As permitted by the foregoing, the Parties expressly agree that the terms
and conditions of the Appendices shall take precedence over the provisions of this cover
agreement in case of a discrepancy or conflict between or among the terms or conditions of
same.

27.3 Rules of Interpretation.

This Agreement, unless a clear contrary intention appears, shall be construed and

interpreted as follows: (1) the singular number includes the plural number and vice versa; (2)

reference to any person includes such person’s successors and assigns but, in the case of a Party,
only if such successors and assigns are permitted by this Agreement, and reference to a person in

39

SERVICE AGREEMENT NO. 2521

a particular capacity excludes such person in any other capacity or individually; (3) reference to
any agreement (including this Agreement), document, instrument or tariff means such
agreement, document, instrument, or tariff as amended or modified and in effect from time to
time in accordance with the terms thereof and, if applicable, the terms hereof; (4) reference to
any Applicable Laws and Regulations means such Applicable Laws and Regulations as
amended, modified, codified, or reenacted, in whole or in part, and in effect from time to time,
including, if applicable, rules and regulations promulgated thereunder; (5) unless expressly stated
otherwise, reference to any Article, Section or Appendix means such Article of this Agreement
or such Appendix to this Agreement, or such Section to the Standard Large Facility
Interconnection Procedures or such Appendix to the Standard Large Facility Interconnection
Procedures, as the case may be; (6) “hereunder”, “hereof’, “herein”, “hereto” and words of
similar import shall be deemed references to this Agreement as a whole and not to any particular
Article or other provision hereof or thereof; (7) “including” (and with correlative meaning
“include”) means including without limiting the generality of any description preceding such
term; and (8) relative to the determination of any period of time, “from” means “from and
including”, “to” means “to but excluding” and “through” means “through and including”.

27.4 Compliance.

Each Party shall perform its obligations under this Agreement in accordance with

Applicable Laws and Regulations, Applicable Reliability Standards, the ISO OATT and Good Utility Practice. To the extent a Party is required or prevented or limited in taking any action by such regulations and standards, such Party shall not be deemed to be in Breach of this Agreement for its compliance therewith. When either Party becomes aware of such a situation, it shall
notify the other Party promptly so that the Parties can discuss the amendment to this Agreement that is appropriate under the circumstances.

27.5 Joint and Several Obligations.

Except as otherwise stated herein, the obligations of NYISO and Con Edison are several, and are neither joint nor joint and several.

27.6 Entire Agreement.

This Agreement, including all Appendices and Schedules attached hereto, constitutes the
entire agreement between the Parties with reference to the subject matter hereof, and supersedes
all prior and contemporaneous understandings or agreements, oral or written, between the Parties
with respect to the subject matter of this Agreement. There are no other agreements,
representations, warranties, or covenants which constitute any part of the consideration for, or
any condition to, either Party’s compliance with its obligations under this Agreement.

27.7 No Third Party Beneficiaries.

This Agreement is not intended to and does not create rights, remedies, or benefits of any character whatsoever in favor of any persons, corporations, associations, or entities other than the Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their successors in interest and permitted their assigns.

40

SERVICE AGREEMENT NO. 2521

27.8 Waiver.

The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver of any

obligation, right, or duty of, or imposed upon, such Party. Any waiver at any time by either
Party of its rights with respect to this Agreement shall not be deemed a continuing waiver or a
waiver with respect to any other failure to comply with any other obligation, right, duty of this
Agreement. Termination or Default of this Agreement for any reason by Con Edison shall not
constitute a waiver of Con Edison’s legal rights to obtain Capacity Resource Interconnection
Service and Energy Resource Interconnection Service from the NYISO in accordance with the
provisions of the ISO OATT. Any waiver of this Agreement shall, if requested, be provided in
writing.

27.9 Headings.

The descriptive headings of the various Articles of this Agreement have been inserted for convenience of reference only and are of no significance in the interpretation or construction of this Agreement.

27.10 Multiple Counterparts.

This Agreement may be executed in two or more counterparts, each of which is deemed an original but all constitute one and the same instrument.

27.11 Amendment.

The Parties may by mutual agreement amend this Agreement, by a written instrument duly executed by both of the Parties.

27.12 Modification by the Parties.

The Parties may by mutual agreement amend the Appendices to this Agreement, by a

written instrument duly executed by both of the Parties. Such an amendment shall become

effective and a part of this Agreement upon satisfaction of all Applicable Laws and Regulations.

27.13 Reservation of Rights.

NYISO and Con Edison shall have the right to make unilateral filings with FERC to

modify this Agreement with respect to any rates, terms and conditions, charges, classifications of
service, rule or regulation under section 205 or any other applicable provision of the Federal
Power Act and FERC’s rules and regulations thereunder; provided that each Party shall have the
right to protest any such filing by the other Party and to participate fully in any proceeding
before FERC in which such modifications may be considered. Nothing in this Agreement shall
limit the rights of the Parties or of FERC under sections 205 or 206 of the Federal Power Act and
FERC’s rules and regulations thereunder, except to the extent that the Parties otherwise mutually
agree as provided herein.

41

SERVICE AGREEMENT NO. 2521

27.14 No Partnership.

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership between the Parties or to impose any partnership obligation or partnership liability upon any Party. Neither Party shall have any right, power or authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, the other Party.

27.15 Other Transmission Rights.

Notwithstanding any other provision of this Agreement, nothing herein shall be construed
as relinquishing or foreclosing any rights, including but not limited to firm transmission rights,
capacity rights, or transmission congestion rights that Con Edison shall be entitled to, now or in
the future under any other agreement or tariff as a result of, or otherwise associated with, the
transmission capacity, if any, created by the System Upgrade Facilities and System
Deliverability Upgrades.

42

SERVICE AGREEMENT NO. 2521

IN WITNESS WHEREOF, the Parties have executed this LGIA in duplicate originals, each of which shall constitute and be an original effective Agreement between the Parties.

New York Independent System Operator, Inc.

By:

Name:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title:

Date:

Consolidated Edison Company of New York, Inc.

By:

Name:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title:

Date:

43

SERVICE AGREEMENT NO. 2521

APPENDICES

Appendix A

Attachment Facilities and System Upgrade Facilities

Appendix B

Milestones

Appendix C

Interconnection Details

Appendix D

Security Arrangements Details

Appendix E-1

Initial Synchronization Date

Appendix E-2

Commercial Operation Date

Appendix F

Addresses for Delivery of Notices

SERVICE AGREEMENT NO. 2521

APPENDIX A

ATTACHMENT FACILITIES AND SYSTEM UPGRADE FACILITIES

1. Attachment Facilities:

(a) Existing Attachment Facilities:

The Attachment Facilities (“AFs”) include all of the facilities between the Large

Generating Facility and the Point of Interconnection (“POI”). As depicted in Figure A-1 to this Appendix A, the AFs consist of the following major electrical and physical equipment:

• a generator step up (“GSU”) GT-2, which is a three phase delta/wye grounded
 18kV/69kV transformer with a rating of 132/176/230 MVA; and

• a circuit breaker GGT-2.

(b) New Attachment Facilities:

None.

2. System Upgrade Facilities

(a) Existing System Upgrade Facilities

None.

(b) New System Upgrade Facilities

None.

3. System Deliverability Upgrades:

None.

4. Estimated Costs

N/A.

A-1

SERVICE AGREEMENT NO. 2521

Figure A-1

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

A-2

SERVICE AGREEMENT NO. 2521

APPENDIX B

MILESTONES

None. As detailed in Appendix C, Con Edison’s modification to its existing Large

Generating Facility was completed in the Fall of 2014. The modified Large Generating Facility is in-service.

B-1

SERVICE AGREEMENT NO. 2521

APPENDIX C

INTERCONNECTION DETAILS

1. Description of Large Generating Facility, including Point of Interconnection

Con Edison owns an existing 172MW natural gas fired combustion turbine electricity

generation facility known as East River 2 (“Existing Facility”), which Large Generating Facility
is part of the East River Generating Station located in the city of New York, New York. Con
Edison installed GE Advanced Gas-Path (“AGP”) hardware and controls on the Existing
Facility. The modification included the removal of the existing combustion and gas-path
hardware, replacing them with AGP specific hardware, installing flow sensors on the gas control
valves, and performing controls modification. The modification was completed in the fall of
2014. This modification increased the output of the Existing Facility by approximately 12 MW
to a total of 184 MW (“New Facility”). The New Facility is temperature sensitive and has a
maximum summer capability and a maximum winter capability, as specified below, and as
depicted in the temperature output curve set forth below in Figure C-1.

Psummer\_max\_gross @ T (0F) = \_\_160.1\_\_\_ MW @ \_91\_ 0F Paux\_load = \_4.9\_MW

Psummer\_max\_net @ T (0F) = Psummer\_max\_gross - Paux\_load = 155.2

Pwinter\_max\_gross @ T (0F) = \_201.6\_\_\_\_ MW @ \_21\_ 0F Paux\_load = \_5.8\_MW

Pwinter\_max\_net @ T (0F) = Pwinter\_max\_gross - Paux\_load = 195.8

Figure C-1

East River CTG-2

220

215
210
205
200
195
190
185
180
175
170
165
160
155
150
145
140

10 20 30 40 50 60 70 80 90

Temperature Deg. F

C-1

Net Megawattts

SERVICE AGREEMENT NO. 2521

The Point of Interconnection (“POI”) for the Large Generating Facility is the 69kV bus section 5-1 between circuit breakers BT 51-52, 51, F21, BT 5-9, and GGT-2, located at Con Edison’s East 13th Street Station. The Point of Interconnection is identified on the one-line diagram in Figure A-1 in Appendix A.

2. Operating Requirements

a. Con Edison must comply with all applicable NYISO tariffs and procedures, as
 amended from time to time.

b. Con Edison must comply with its operating instructions and requirements, to the
 extent not inconsistent with the terms of this Agreement, the NYISO OATT, or
 applicable NYISO procedures.

3. Steam Operations

In addition to providing electric energy, the Large Generating Facility also provides steam services that is utilized by Con Edison as a steam utility in New York City. When the Large Generating Facility is providing steam, certain operational requirement noted above need to be revised to accommodate the dual nature of the generating facility.

The requirement to procure, install, maintain, and operate Power System Stabilizes
contained in Article 5.1 of this Agreement must also be consistent with the requirements to
provide steam services to Con Edison. In addition, the power factor requirements in Article

9.5.1 of this Agreement and the voltage schedule requirements in Article 9.5.2 of this Agreement to produce and absorb reactive power shall be consistent with the requirements of the Con
Edison steam system. The Con Edison generating facilities, including the New Facility, that provide steam to the Con Edison steam system are exempt from over and under generation to the extent provided in Sections 4.5, 5.12.1.11.2, and 15.3A.2.2 of the NYISO’s Services Tariff and Section 16.3.4.2.1.2 of the NYISO’s OATT.

The outage restoration requirements contains in Article 9.6 of this Agreement and the
Emergency State procedures referenced in Article 12 of this Agreement may be impacted by an
emergency on the Con Edison steam system. In addition, an outage restoration requirement or
state emergency on the electric system can also impact the Con Edison steam system.

C-2

SERVICE AGREEMENT NO. 2521

APPENDIX D

SECURITY ARRANGEMENTS DETAILS

Infrastructure security of New York State Transmission System equipment and

operations and control hardware and software is essential to ensure day-to-day New York State Transmission System reliability and operational security. The Commission will expect the
NYISO, all Transmission Owners, Con Edison, and all other Market Participants to comply with the recommendations offered by the President’s Critical Infrastructure Protection Board and, eventually, best practice recommendations from the electric reliability authority. All public utilities will be expected to meet basic standards for system infrastructure and operational
security, including physical, operational, and cyber-security practices.

D-1

SERVICE AGREEMENT NO. 2521

APPENDIX E-1

INITIAL SYCHRONIZATION DATE

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Re: Large Generating Facility

Dear :

On [Date] Con Edison initially synchronized the Large Generating Facility [specify units, if
applicable]. This letter confirms Con Edison’s Initial Synchronization Date was [specify].

Thank you.

[Signature]

[Con Edison Representative]

E-1

SERVICE AGREEMENT NO. 2521

APPENDIX E-2

COMMERCIAL OPERATION DATE

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Re: \_\_\_\_\_\_\_\_\_\_\_\_\_ Large Generating Facility

Dear \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_:

On [Date] Con Edison has completed Trial Operation of Unit No. \_\_\_. This letter confirms that Con Edison commenced Commercial Operation of Unit No. \_\_\_ at the Large Generating
Facility, effective as of [Date plus one day].

Thank you.

[Signature]

[Con Edison Representative]

E-2

SERVICE AGREEMENT NO. 2521

APPENDIX F

ADDRESSES FOR DELIVERY OF NOTICES

Notices:

NYISO:

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144
Phone: (518) 356-6000
Fax: (518) 356-6118

Con Edison:

Consolidated Edison Company of New York, Inc.

4 Irving Place, Room 13 NW

New York, NY 10003

Attn: Vice President, System and Transmission Operations Phone: (212) 460-1210

Fax: (212) 353-8831

Alternative Forms of Delivery of Notices (telephone, facsimile or email):

NYISO:

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144
Phone: (518) 356-6000
Fax: (518) 356-6118

Con Edison:

Consolidated Edison Company of New York, Inc.

4 Irving Place, Room 13 NW

New York, NY 10003

Attn: Vice President, System and Transmission Operations Phone: (212) 460-1210

Fax: (212) 353-8831

F-1