## Sheet1
Attachment B
NMPC - Smart Path Connect Project
Estimated Cost of Removal - As of March 2023
| # | Segment | Work Performed | CAPEX | OPEX | COR | Funding # | Payments | CAPEX | OPEX | COR
| 1. | Geotech Contract | T-Line Installation and Removal (100%) | 100% | 0% | 0% | C088956 | 11156394 | 11156394 | 0 | 0
| 2. | Contract Execution | T-Line Engin/Materials/Construction (88.6%) | 100% | 0% | 0% | C088956 | 19338154 | 19338154 | 0 | 0
| 3. | Contract Execution | Substation Engineering (11.4%) | 100% | 0% | 0% | C089486 | 2500000 | 2500000 | 0 | 0
| 4. | EM&CP + Article VII Support | T-Line Scope Support (75%) | 100% | 0% | 0% | C088956 | 697016.25 | 697016.25 | 0 | 0
| 5. | EM&CP + Article VII Support | Substation Scope Support (25%) | 100% | 0% | 0% | C089486 | 232338.75 | 232338.75 | 0 | 0
| 6. | Segment 1-8 | T-Line Installation and Removal | 90% | 1% | 9% | C088956 | 361370000 | 325233000 | 3613700 | 32523300
| 7. | Segment 9 | Austin Road Substation Excluding Control House | 100% | 0% | 0% | C089486 | 30400000 | 30400000 | 0 | 0
| 8. | Segment 9 | Austin Road Substation Control House Only | 100% | 0% | 0% | C089487 | 2000000 | 2000000 | 0 | 0
| 9. | Segment 10 | Edic Substation - Installation & Removal | 90% | 0% | 10% | C089488 |  | 0 | 0 | 0
| 10. | Segment 11 | Chases Lake Substation - Installation & Removal | 10% | 0% | 90% | C089489 |  | 0 | 0 | 0
| 11. | Segment 12 | Porter Substation - Installation & Removal | 10% | 0% | 90% | C089490 |  | 0 | 0 | 0
| = | Total B&M EPC Contract |  | 91.55% | 0.8449% | 7.604% |  | 427693903 | 391556903 | 3613700 | 32523300
| 12. | Non-B&M CAPEX | Purchase Land for Austin Rd. Substation | 100% | 0% | 0% | C082830 | 200000 | 200000 | 0 | 0
| 13. | Non-B&M CAPEX | T-Line Activities (90%) | 100% | 0% | 0% | C088956 | 49946487.3 | 49946487.3 | 0 | 0
| 14. | Non-B&M CAPEX | Substation Activities (10%) | 100% | 0% | 0% | C089486 | 3959609.7 | 3959609.7 | 0 | 0
| = | Total B&M and Non-B&M |  | 92.5% | 0.75% | 6.75% |  | 481800000 | 445663000 | 3613700 | 32523300
| 15. | AFUDC | T-Line Activities (90%) | 100% | 0% | 0% | C088956 | 35550000 | 35550000 | 0 | 0
| 16. | AFUDC | Substation Activities (10%) | 100% | 0% | 0% | C089486 | 3950000 | 3950000 | 0 | 0
| = | TOTAL SPEND WITH AFUDC |  | 93.07% | 0.6932% | 6.239% |  | 521300000 | 485163000 | 3613700 | 32523300