SERVICE AGREEMENT NO. 2833

SERVICE AGREEMENT NO. 2833

STANDARD SMALL GENERATOR

INTERCONNECTION AGREEMENT 
	AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC., 
	ORANGE AND ROCKLAND UTILITIES, INC.,

AND

LITTLE POND SOLAR, LLC 
Dated as of January 31, 2024

(Little Pond Solar Project)

SERVICE AGREEMENT NO. 2833

TABLE OF CONTENTS

Article 1	Scope and Limitations of Agreement	2

1.1	Applicability		2

1.2	Purpose		2

1.3	Scope of Interconnection Service		2

1.4	Limitations		2

1.5	Responsibilities of the Parties		2

1.6	Parallel Operation Obligations		4

1.7	Metering		4

1.8	Reactive Power and Primary Frequency Response		4

1.9	Capitalized Terms		8

Article 2	Inspection, Testing, Authorization, and Right of Access	9

2.1	Equipment Testing and Inspection		9

2.2	Authorization Required Prior to Parallel Operation		9

2.3	Right of Access		10

Article 3	Effective Date, Term, Termination, and Disconnection	11

3.1	Effective Date		11

3.2	Term of Agreement		11

3.3	Termination		11

3.4	Temporary Disconnection		12

Article 4	Cost Responsibility for Interconnection Facilities and Distribution

Upgrades	14

4.1	Interconnection Facilities		14

4.2	Distribution Upgrades		14

Article 5	Cost Responsibility for System Upgrade Facilities and System

Deliverability Upgrades	15

5.1	Applicability		15

5.2	System Upgrades		15

5.3	Special Provisions for Affected Systems		15

Article 6	Billing, Payment, Milestones, and Financial Security	16

6.1	Billing and Payment Procedures and Final Accounting		16

6.2	Milestones		16

6.3	Financial Security Arrangements		17

Article 7	Assignment, Liability, Indemnity, Force Majeure, Consequential

Damages, and Default	18

7.1	Assignment		18

7.2	Limitation of Liability		18

7.3	Indemnity		18

7.4	Consequential Damages		19

7.5	Force Majeure		20

i

SERVICE AGREEMENT NO. 2833

7.6	Breach and Default		20

Article 8	Insurance	22

Article 9	Confidentiality	23

Article 10	Disputes	25

Article 11	Taxes	26

Article 12	Miscellaneous	27

12.1	Governing Law, Regulatory Authority, and Rules		27

12.2	Amendment		27

12.3	No Third-Party Beneficiaries		27

12.4	Waiver		27

12.5	Entire Agreement		27

12.6	Multiple Counterparts		28

12.7	No Partnership		28

12.8	Severability		28

12.9	Security Arrangements		28

12.10	Environmental Releases		28

12.11	Subcontractors		28

12.12	Reservation of Rights		29

Article 13	Notices	30

13.1	General		30

13.2	Billing and Payment		30

13.3	Alternative Forms of Notice		31

13.4	Designated Operating Representative		32

13.5	Changes to the Notice Information		32

Article 14	Signatures	33

Attachment 1 Glossary of Terms

Attachment 2  Detailed Scope of Work, Including Description and Costs of the Small Generating Facility, Interconnection Facilities, and Metering Equipment

Attachment 3  One-line Diagram Depicting the Small Generating Facility, Interconnection Facilities, Metering Equipment, and Upgrades

Attachment 4  Milestones

Attachment 5  Additional Operating Requirements for the New York State Transmission System, the Distribution System and Affected Systems Needed to Support the Interconnection 
Customer’s Needs

Attachment 6  Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of Upgrade Costs

Attachment 7  Insurance Coverage

ii

SERVICE AGREEMENT NO. 2833

Attachment 8  Initial Synchronization Date 
Attachment 9  Commercial Operation Date

Attachment 10 Terms and Conditions of Orange & Rockland, Inc. Construction Projects

iii

SERVICE AGREEMENT NO. 2833

This Standard Small Generator Interconnection Agreement (“Agreement” or “SGIA”) is made 
and entered into this 31st day of January, 2024, by and among the New York Independent 
System Operator, Inc., a not-for-profit corporation organized and existing under the laws of the 
State of New York (“NYISO”) and Orange and Rockland Utilities, Inc., a transportation 
corporation organized and existing under the laws of the State of New York (“Connecting 
Transmission Owner”), and Little Pond Solar, LLC, a limited liability company organized and 
existing under the laws of the State of Delaware (“Interconnection Customer”) each hereinafter 
sometimes referred to individually as “Party” or referred to collectively as the “Parties.”

In consideration of the mutual covenants set forth herein, the Parties agree as follows:

1

SERVICE AGREEMENT NO. 2833

Article 1	Scope and Limitations of Agreement

1.1	Applicability

This Agreement shall be used for all Interconnection Requests submitted under the Small Generator Interconnection Procedures (SGIP) except for those submitted under the 10 kW 
Inverter Process contained in SGIP Attachment 5.

1.2	Purpose

This Agreement governs the terms and conditions under which the Interconnection

Customer’s Small Generating Facility will interconnect with, and operate in parallel with, the New York State Transmission System or the Distribution System.

1.3	Scope of Interconnection Service

1.3.1   The NYISO will provide Energy Resource Interconnection Service and Capacity 
	Resource Interconnection Service to Interconnection Customer at the Point of 
	Interconnection.

1.3.2   This Agreement does not constitute an agreement to purchase or deliver the

Interconnection Customer’s power.  The purchase or delivery of power and other 
services that the Interconnection Customer may require will be covered under 
separate agreements, if any, or applicable provisions of NYISO’s or Connecting 
Transmission Owner’s tariffs.  The Interconnection Customer will be responsible 
for separately making all necessary arrangements (including scheduling) for 
delivery of electricity in accordance with the applicable provisions of the ISO 
OATT and Connecting Transmission Owner’s tariff.  The execution of this 
Agreement does not constitute a request for, nor agreement to, provide Energy, 
any Ancillary Services or Installed Capacity under the NYISO Services Tariff or 
any Connecting Transmission Owner’s tariff.  If Interconnection Customer wishes 
to supply or purchase Energy, Installed Capacity or Ancillary Services, then 
Interconnection Customer will make application to do so in accordance with the 
NYISO Services Tariff or Connecting Transmission Owner’s tariff.

1.4	Limitations

Nothing in this Agreement is intended to affect any other agreement by and among the

NYISO, Connecting Transmission Owner and the Interconnection Customer, except as otherwise expressly provided herein.

1.5	Responsibilities of the Parties

1.5.1   The Parties shall perform all obligations of this Agreement in accordance with all 
	Applicable Laws and Regulations, Operating Requirements, and Good Utility 
	Practice.

2

SERVICE AGREEMENT NO. 2833

1.5.2 	The Interconnection Customer shall construct, interconnect, operate and maintain

its Small Generating Facility and construct, operate, and maintain its

Interconnection Facilities in accordance with the applicable manufacturer’s

recommended maintenance schedule, and in accordance with this Agreement, and with Good Utility Practice.

1.5.3 	The Connecting Transmission Owner shall construct, operate, and maintain its

Interconnection Facilities and Upgrades covered by this Agreement in accordance with this Agreement, and with Good Utility Practice.

1.5.4 	The Interconnection Customer agrees to construct its facilities or systems in

accordance with applicable specifications that meet or exceed those provided by 
the National Electrical Safety Code, the American National Standards Institute, 
IEEE, Underwriter’s Laboratory, and Operating Requirements in effect at the time 
of construction and other applicable national and state codes and standards. The 
Interconnection Customer agrees to design, install, maintain, and operate its Small 
Generating Facility so as to reasonably minimize the likelihood of a disturbance 
adversely affecting or impairing the system or equipment of the Connecting

Transmission Owner or Affected Systems.

1.5.5 	The Connecting Transmission Owner and Interconnection Customer shall operate,

maintain, repair, and inspect, and shall be fully responsible for the facilities that it 
now or subsequently may own unless otherwise specified in the Attachments to 
this Agreement.  Each of those Parties shall be responsible for the safe 
installation, maintenance, repair and condition of their respective lines and 
appurtenances on their respective sides of the point of change of ownership.  The 
Connecting Transmission Owner and the Interconnection Customer, as 
appropriate, shall provide Interconnection Facilities that adequately protect the 
Connecting Transmission Owner’s electric system, personnel, and other persons 
from damage and injury.  The allocation of responsibility for the design, 
installation, operation, maintenance and ownership of Interconnection Facilities 
shall be delineated in the Attachments to this Agreement.

1.5.6 	The NYISO shall coordinate with all Affected Systems to support the

interconnection.  The Connecting Transmission Owner shall cooperate with the NYISO in these efforts.

1.5.7 	The Interconnection Customer shall ensure “frequency ride through” capability

and “voltage ride through” capability of its Small Generating Facility. The

Interconnection Customer shall enable these capabilities such that its Small

Generating Facility shall not disconnect automatically or instantaneously from the 
system or equipment of the Connecting Transmission Owner and any Affected 
Systems for a defined under-frequency or over-frequency condition, or an under-
voltage or over-voltage condition, as tested pursuant to section 2.1 of this 
agreement. The defined conditions shall be in accordance with Good Utility 
Practice and consistent with any standards and guidelines that are applied to other 
generating facilities in the Balancing Authority Area on a comparable basis. The

3

SERVICE AGREEMENT NO. 2833

Small Generating Facility’s protective equipment settings shall comply with the 
Transmission Owner’s automatic load-shed program.  The Transmission Owner 
shall review the protective equipment settings to confirm compliance with the 
automatic load-shed program.  The term “ride through” as used herein shall mean 
the ability of a Small Generating Facility to stay connected to and synchronized 
with the system or equipment of the Transmission Owner and any Affected 
Systems during system disturbances within a range of conditions, in accordance 
with Good Utility Practice and consistent with any standards and guidelines that 
are applied to other generating facilities in the Balancing Authority on a 
comparable basis. The term “frequency ride through” as used herein shall mean 
the ability of a Small Generating Facility to stay connected to and synchronized 
with the system or equipment of the Transmission Owner and any Affected 
Systems during system disturbances within a range of under-frequency and over-
frequency conditions, in accordance with Good Utility Practice and consistent 
with any standards and guidelines that are applied to other generating facilities in 
the Balancing Authority Area on a comparable basis. The term “voltage ride 
through” as used herein shall mean the ability of a Small Generating Facility to 
stay connected to and synchronized with the system or equipment of the 
Transmission Owner and any Affected Systems during system disturbances 
within a range of under-voltage and over-voltage conditions, in accordance with 
Good Utility Practice and consistent with any standards and guidelines that are 
applied to other generating facilities in the Balancing Authority Area on a 
comparable basis.

1.6	Parallel Operation Obligations

Once the Small Generating Facility has been authorized to commence parallel operation, the Interconnection Customer shall abide by all rules and procedures pertaining to the parallel operation of the Small Generating Facility in the applicable control area, including, but not 
limited to: (1) the rules and procedures concerning the operation of generation set forth in the NYISO tariffs or ISO Procedures or the Connecting Transmission Owner’s tariff; (2) any 
requirements consistent with Good Utility Practice or that are necessary to ensure the safe and reliable operation of the Transmission System or Distribution System; and (3) the Operating Requirements set forth in Attachment 5 of this Agreement.

1.7	Metering

The Interconnection Customer shall be responsible for the Connecting Transmission 
Owner’s reasonable and necessary cost for the purchase, installation, operation, maintenance, 
testing, repair, and replacement of metering and data acquisition equipment specified in 
Attachments 2 and 3 of this Agreement.  The Interconnection Customer’s metering (and data 
acquisition, as required) equipment shall conform to applicable industry rules and Operating 
Requirements.

1.8 	Reactive Power and Primary Frequency Response

1.8.1   Power Factor Design Criteria

4

SERVICE AGREEMENT NO. 2833

1.8.1.1  Synchronous Generation.  The Interconnection Customer shall design its 
Small Generating Facility to maintain a composite power delivery at continuous 
rated power output at the Point of Interconnection at a power factor within the 
range of 0.95 leading to 0.95 lagging, unless the NYISO or the Transmission 
Owner in whose Transmission District the Small Generating Facility 
interconnects has established different requirements that apply to all similarly 
situated generators in the New York Control Area or Transmission District (as 
applicable) on a comparable basis, in accordance with Good Utility Practice.

1.8.1.2  Non-Synchronous Generation.  The Interconnection Customer shall

design its Small Generating Facility to maintain a composite power delivery at 
continuous rated power output at the high-side of the generator substation at a 
power factor within the range of 0.95 leading to 0.95 lagging, unless the NYISO 
or the Transmission Owner in whose Transmission District the Small Generating 
Facility interconnects has established a different power factor range that applies to 
all similarly situated non-synchronous generators in the control area or 
Transmission District (as applicable) on a comparable basis, in accordance with 
Good Utility Practice.  This power factor range standard shall be dynamic and can 
be met using, for example, power electronics designed to supply this level of 
reactive capability (taking into account any limitations due to voltage level, real 
power output, etc.) or fixed and switched capacitors, or a combination of the two. 
This requirement shall only apply to newly interconnecting non-synchronous 
generators that have not yet executed a Facilities Study Agreement as of 
September 21, 2016.

1.8.2 	The NYISO is required to pay the Interconnection Customer for reactive power,

or voltage support service, that the Interconnection Customer provides from the Small Generating Facility in accordance with Rate Schedule 2 of the NYISO Services Tariff.

1.8.3 	Primary Frequency Response.  Interconnection Customer shall ensure the primary

frequency response capability of its Small Generating Facility by installing,

maintaining, and operating a functioning governor or equivalent controls.  The 
term “functioning governor or equivalent controls” as used herein shall mean the 
required hardware and/or software that provides frequency responsive real power 
control with the ability to sense changes in system frequency and autonomously 
adjust the Small Generating Facility’s real power output in accordance with the 
droop and deadband parameters and in the direction needed to correct frequency 
deviations.  Interconnection Customer is required to install a governor or

equivalent controls with the capability of operating: (1) with a maximum 5

percent droop and ±0.036 Hz deadband; or (2) in accordance with the relevant 
droop, deadband, and timely and sustained response settings from an approved 
Applicable Reliability Standard providing for equivalent or more stringent 
parameters.  The droop characteristic shall be: (1) based on the nameplate 
capacity of the Small Generating Facility, and shall be linear in the range of 
frequencies between 59 to 61 Hz that are outside of the deadband parameter; or

(2) based on an approved Applicable Reliability Standard providing for an

5

SERVICE AGREEMENT NO. 2833

equivalent or more stringent parameter.  The deadband parameter shall be: the 
range of frequencies above and below nominal (60 Hz) in which the governor or 
equivalent controls is not expected to adjust the Small Generating Facility’s real 
power output in response to frequency deviations.  The deadband shall be 
implemented: (1) without a step to the droop curve, that is, once the frequency 
deviation exceeds the deadband parameter, the expected change in the Small 
Generating Facility’s real power output in response to frequency deviations shall 
start from zero and then increase (for under-frequency deviations) or decrease (for 
over-frequency deviations) linearly in proportion to the magnitude of the 
frequency deviation; or (2) in accordance with an approved Applicable Reliability 
Standard providing for an equivalent or more stringent parameter. 
Interconnection Customer shall notify NYISO that the primary frequency 
response capability of the Small Generating Facility has been tested and 
confirmed during commissioning.  Once Interconnection Customer has 
synchronized the Small Generating Facility with the New York State 
Transmission System, Interconnection Customer shall operate the Small 
Generating Facility consistent with the provisions specified in Articles 1.8.3.1 and

1.8.3.2 of this Agreement.  The primary frequency response requirements

contained herein shall apply to both synchronous and non-synchronous Small Generating Facilities.

1.8.3.1 Governor or Equivalent Controls. Whenever the Small Generating Facility 
is operated in parallel with the New York State Transmission System, 
Interconnection Customer shall operate the Small Generating Facility with its 
governor or equivalent controls in service and responsive to frequency. 
Interconnection Customer shall: (1) in coordination with NYISO, set the 
deadband parameter to: (1) a maximum of ±0.036 Hz and set the droop parameter 
to a maximum of 5 percent; or (2) implement the relevant droop and deadband 
settings from an approved Applicable Reliability Standard that provides for 
equivalent or more stringent parameters.  Interconnection Customer shall be 
required to provide the status and settings of the governor and equivalent controls 
to NYISO and/or the Connecting Transmission Owner upon request.  If 
Interconnection Customer needs to operate the Small Generating Facility with its 
governor or equivalent controls not in service, Interconnection Customer shall 
immediately notify NYISO and the Connecting Transmission Owner, and provide 
both with the following information: (1) the operating status of the governor or 
equivalent controls (i.e., whether it is currently out of service or when it will be 
taken out of service); (2) the reasons for removing the governor or equivalent 
controls from service; and (3) a reasonable estimate of when the governor or 
equivalent controls will be returned to service.  Interconnection Customer shall 
make Reasonable Efforts to return its governor or equivalent controls into service 
as soon as practicable.  Interconnection Customer shall make Reasonable Efforts 
to keep outages of the Small Generating Facility’s governor or equivalent controls 
to a minimum whenever the Small Generating Facility is operated in parallel with 
the New York State Transmission System.

6

SERVICE AGREEMENT NO. 2833

1.8.3.2 Timely and Sustained Response.  Interconnection Customer shall ensure 
that the Small Generating Facility’s real power response to sustained frequency 
deviations outside of the deadband setting is automatically provided and shall 
begin immediately after frequency deviates outside of the deadband, and to the 
extent the Small Generating Facility has operating capability in the direction 
needed to correct the frequency deviation.  Interconnection Customer shall not 
block or otherwise inhibit the ability of the governor or equivalent controls to 
respond and shall ensure that the response is not inhibited, except under certain 
operational constraints including, but not limited to, ambient temperature

limitations, physical energy limitations, outages of mechanical equipment, or regulatory requirements.  The Small Generating Facility shall sustain the real power response at least until system frequency returns to a value within the deadband setting of the governor or equivalent controls.  An Applicable 
Reliability Standard with equivalent or more stringent requirements shall 
supersede the above requirements.

1.8.3.3 Exemptions.  Small Generating Facilities that are regulated by the United 
States Nuclear Regulatory Commission shall be exempt from Articles 1.8.3,

1.8.3.1, and 1.8.3.2 of this Agreement.   Small Generating Facilities that are

behind the meter generation that is sized-to-load (i.e., the thermal load and the

generation are near-balanced in real-time operation and the generation is primarily 
controlled to maintain the unique thermal, chemical, or mechanical output 
necessary for the operating requirements of its host facility) shall be required to 
install primary frequency response capability requirements in accordance with the 
droop and deadband capability requirements specified in Article 1.8.3, but shall 
be otherwise exempt from the operating requirements in Articles 1.8.3, 1.8.3.1,

1.8.3.2, and 1.8.3.4 of this Agreement.

1.8.3.4 Electric Storage Resources.  Interconnection Customer interconnecting an 
electric storage resource shall establish an operating range in Attachment 5 of its 
SGIA that specifies a minimum state of charge and a maximum state of charge 
between which the electric storage resource will be required to provide primary 
frequency response consistent with the conditions set forth in Articles 1.8.3,

1.8.3.1, 1.8.3.2, and 1.8.3.3 of this Agreement.  Attachment 5 shall specify

whether the operating range is static or dynamic, and shall consider (1) the

expected magnitude of frequency deviations in the interconnection; (2) the

expected duration that system frequency will remain outside of the deadband

parameter in the interconnection; (3) the expected incidence of frequency

deviations outside of the deadband parameter in the interconnection; (4) the

physical capabilities of the electric storage resource; (5) operational limitations of the electric storage resources due to manufacturer specification; and (6) any other relevant factors agreed to by the NYISO, Connecting Transmission Owner, and Interconnection Customer.  If the operating range is dynamic, then Attachment 5 must establish how frequently the operating range will be reevaluated and the factors that may be considered during its reevaluation.

7

SERVICE AGREEMENT NO. 2833

Interconnection Customer’s electric storage resource is required to provide timely 
and sustained primary frequency response consistent with Article 1.8.3.2 of this 
Agreement when it is online and dispatched to inject electricity to the New York 
State Transmission System and/or receive electricity from the New York State 
Transmission System.  This excludes circumstances when the electric storage 
resource is not dispatched to inject electricity to the New York State Transmission 
System and/or dispatched to receive electricity from the New York State 
Transmission System.  If Interconnection Customer’s electric storage resource is 
charging at the time of a frequency deviation outside of its deadband parameter, it 
is to increase (for over-frequency deviations) or decrease (for under-frequency 
deviations) the rate at which it is charging in accordance with its droop parameter. 
Interconnection Customer’s electric storage resource is not required to change 
from charging to discharging, or vice versa, unless the response necessitated by 
the droop and deadband settings requires it to do so and it is technically capable 
of making such a transition.

1.9	Capitalized Terms

Capitalized terms used herein shall have the meanings specified in the Glossary of Terms in Attachment 1 or the body of this Agreement.  Capitalized terms used herein that are not so defined shall have the meanings specified in Appendix 1 of Attachment Z, Section 25.1.2 of Attachment S, or Section 30.1 of Attachment X of the ISO OATT.

8

SERVICE AGREEMENT NO. 2833

Article 2	Inspection, Testing, Authorization, and Right of Access

2.1	Equipment Testing and Inspection

2.1.1	The Interconnection Customer shall test and inspect its Small Generating Facility

and Interconnection Facilities prior to interconnection.  The Interconnection 
Customer shall notify the NYISO and the Connecting Transmission Owner of 
such activities no fewer than five Business Days (or as may be agreed to by the 
Parties) prior to such testing and inspection.  Testing and inspection shall occur on 
a Business Day.  The Connecting Transmission Owner may, at its own expense, 
send qualified personnel to the Small Generating Facility site to inspect the 
interconnection and observe the testing.  The Interconnection Customer shall 
provide the NYISO and Connecting Transmission Owner a written test report 
when such testing and inspection is completed.  The Small Generating Facility 
may not commence parallel operations if the NYISO, in consultation with the 
Connecting Transmission Owner, finds that the Small Generating Facility has not 
been installed as agreed upon or may not be operated in a safe and reliable 
manner.

2.1.2 	The NYISO and Connecting Transmission Owner shall each provide the

Interconnection Customer written acknowledgment that it has received the

Interconnection Customer’s written test report.  Such written acknowledgment 
shall not be deemed to be or construed as any representation, assurance, 
guarantee, or warranty by the NYISO or Connecting Transmission Owner of the 
safety, durability, suitability, or reliability of the Small Generating Facility or any 
associated control, protective, and safety devices owned or controlled by the 
Interconnection Customer or the quality of power produced by the Small 
Generating Facility.

2.2 	Authorization Required Prior to Parallel Operation

2.2.1   The NYISO, in consultation with the Connecting Transmission Owner, shall use 
	Reasonable Efforts to list applicable parallel Operating Requirements in 
	Attachment 5 of this Agreement. Additionally, the NYISO, in consultation with 
	the Connecting Transmission Owner, shall notify the Interconnection Customer of 
	any changes to these requirements as soon as they are known.  The NYISO and 
	Connecting Transmission Owner shall make Reasonable Efforts to cooperate with 
	the Interconnection Customer in meeting requirements necessary for the 
	Interconnection Customer to commence parallel operations by the in-service date.

2.2.2   The Interconnection Customer shall not operate its Small Generating Facility in 
	parallel with the New York State Transmission System or the Distribution System 
	without prior written authorization of the NYISO.  The NYISO, in consultation 
	with the Connecting Transmission Owner, will provide such authorization once 
	the NYISO receives notification that the Interconnection Customer has complied 
	with all applicable parallel Operating Requirements.  Such authorization shall not 
	be unreasonably withheld, conditioned, or delayed.

9

SERVICE AGREEMENT NO. 2833

2.3	Right of Access

2.3.1   Upon reasonable notice, the NYISO and/or Connecting Transmission Owner may 
	send a qualified person to the premises of the Interconnection Customer at or 
	immediately before the time the Small Generating Facility first produces energy 
	to inspect the interconnection, and observe the commissioning of the Small 
	Generating Facility (including any required testing), startup, and operation for a 
	period of up to three Business Days after initial start-up of the unit.  In addition, 
	the Interconnection Customer shall notify the NYISO and Connecting 
	Transmission Owner at least five Business Days prior to conducting any on-site 
	verification testing of the Small Generating Facility.

2.3.2   Following the initial inspection process described above, at reasonable hours, and 
	upon reasonable notice, or at any time without notice in the event of an 
	emergency or hazardous condition, the NYISO and Connecting Transmission 
	Owner each shall have access to the Interconnection Customer’s premises for any 
	reasonable purpose in connection with the performance of the obligations 
	imposed on them by this Agreement or if necessary to meet their legal obligation 
	to provide service to their customers.

2.3.3   Each Party shall be responsible for its own costs associated with following this 
	article.

10

SERVICE AGREEMENT NO. 2833

Article 3	Effective Date, Term, Termination, and Disconnection

3.1	Effective Date

This Agreement shall become effective upon execution by the Parties subject to

acceptance by FERC (if applicable), or if filed unexecuted, upon the date specified by the FERC. 
The NYISO and Connecting Transmission Owner shall promptly file, or cause to be filed, this 
Agreement with FERC upon execution, if required.  If the Agreement is disputed and the 
Interconnection Customer requests that it be filed with FERC in an unexecuted form, the NYISO 
shall file, or cause to be filed, this Agreement and the NYISO shall identify the disputed 
language.

3.2	Term of Agreement

This Agreement shall become effective on the Effective Date and shall remain in effect 
for a period of ten years from the Effective Date and shall be automatically renewed for each 
successive one-year period thereafter, unless terminated earlier in accordance with article 3.3 of 
this Agreement.

3.3	Termination

No termination shall become effective until the Parties have complied with all Applicable 
Laws and Regulations applicable to such termination, including the filing with FERC of a notice 
of termination of this Agreement (if required), which notice has been accepted for filing by 
FERC.

3.3.1	The Interconnection Customer may terminate this Agreement at any time by

giving the NYISO and Connecting Transmission Owner 20 Business Days written

notice.  The NYISO may terminate this Agreement after the Small Generating

Facility is Retired.

3.3.2	Any Party may terminate this Agreement after Default pursuant to article 7.6.

3.3.3	Upon termination of this Agreement, the Small Generating Facility will be

disconnected from the New York State Transmission System or the Distribution System, as applicable.  All costs required to effectuate such disconnection shall be borne by the terminating Party, unless such termination resulted from the nonterminating Party’s Default of this SGIA or such non-terminating Party otherwise is responsible for these costs under this SGIA.

3.3.4 	The termination of this Agreement shall not relieve any Party of its liabilities and

obligations, owed or continuing at the time of the termination.  The

Interconnection Customer shall pay all amounts in excess of any deposit or other 
security without interest within 30 calendar days after receipt of the invoice for 
such amounts.  If the deposit or other security exceeds the invoice, the Connecting 
Transmission Owner shall refund such excess within 30 calendar days of the 
invoice without interest.  If the Interconnection Customer disputes an amount to 
be paid the Interconnection Customer shall pay the disputed amount to the

11

SERVICE AGREEMENT NO. 2833

Connecting Transmission Owner or into an interest bearing escrow account,

pending resolution of the dispute in accordance with Article 10 of this Agreement. To the extent the dispute is resolved in the Interconnection Customer’s favor, that portion of the disputed amount will be returned to the Interconnection Customer with interest at rates applicable to refunds under the Commission’s regulations. 
To the extent the dispute is resolved in the Connecting Transmission Owner’s 
favor, that portion of any escrowed funds and interest will be released to the 
Connecting Transmission Owner.

3.3.5   The limitations of liability, indemnification and confidentiality provisions of this 
	Agreement shall survive termination or expiration of this Agreement.

3.4	Temporary Disconnection

Temporary disconnection shall continue only for so long as reasonably necessary under Good Utility Practice.

3.4.1   Emergency Conditions

“Emergency Condition” shall mean a condition or situation: (1) that in the judgment of 
the Party making the claim is imminently likely to endanger life or property; or (2) that, in the 
case of the NYISO or Connecting Transmission Owner, is imminently likely (as determined in a 
non-discriminatory manner) to cause a material adverse effect on the security of, or damage to 
the New York State Transmission System or Distribution System, the Connecting Transmission 
Owner’s Interconnection Facilities or the electric systems of others to which the New York State 
Transmission System or Distribution System is directly connected; or (3) that, in the case of the 
Interconnection Customer, is imminently likely (as determined in a non-discriminatory manner) 
to cause a material adverse effect on the security of, or damage to, the Small Generating Facility 
or the Interconnection Customer’s Interconnection Facilities.  Under Emergency Conditions, the 
NYISO or Connecting Transmission Owner may immediately suspend interconnection service 
and temporarily disconnect the Small Generating Facility.  The NYISO or Connecting

Transmission Owner shall notify the Interconnection Customer promptly when it becomes aware of an Emergency Condition that may reasonably be expected to affect the Interconnection 
Customer’s operation of the Small Generating Facility.  The Interconnection Customer shall notify the NYISO and Connecting Transmission Owner promptly when it becomes aware of an Emergency Condition that may reasonably be expected to affect the New York State 
Transmission System or Distribution System or any Affected Systems.  To the extent 
information is known, the notification shall describe the Emergency Condition, the extent of the damage or deficiency, the expected effect on the operation of each Party’s facilities and 
operations, its anticipated duration, and the necessary corrective action.

3.4.2   Routine Maintenance, Construction, and Repair

The NYISO or Connecting Transmission Owner may interrupt interconnection service or curtail the output of the Small Generating Facility and temporarily disconnect the Small 
Generating Facility from the New York State Transmission System or Distribution System when necessary for routine maintenance, construction, and repairs on the New York State

12

SERVICE AGREEMENT NO. 2833

Transmission System or Distribution System.  The NYISO or the Connecting Transmission

Owner shall provide the Interconnection Customer with five Business Days notice prior to such 
interruption.  The NYISO and Connecting Transmission Owner shall use Reasonable Efforts to 
coordinate such reduction or temporary disconnection with the Interconnection Customer.

3.4.3   Forced Outages

During any forced outage, the NYISO or Connecting Transmission Owner may suspend interconnection service to the Interconnection Customer to effect immediate repairs on the New York State Transmission System or the Distribution System.  The NYISO shall use Reasonable Efforts to provide the Interconnection Customer with prior notice.  If prior notice is not given, the NYISO shall, upon request, provide the Interconnection Customer written documentation after the fact explaining the circumstances of the disconnection.

3.4.4   Adverse Operating Effects

The NYISO or Connecting Transmission Owner shall notify the Interconnection

Customer as soon as practicable if, based on Good Utility Practice, operation of the Small

Generating Facility may cause disruption or deterioration of service to other customers served from the same electric system, or if operating the Small Generating Facility could cause damage to the New York State Transmission System, the Distribution System or Affected Systems, or if disconnection is otherwise required under Applicable Reliability Standards or the ISO OATT. Supporting documentation used to reach the decision to disconnect shall be provided to the 
Interconnection Customer upon request.  If, after notice, the Interconnection Customer fails to remedy the adverse operating effect within a reasonable time, the NYISO or Connecting 
Transmission Owner may disconnect the Small Generating Facility.  The NYISO or Connecting Transmission Owner shall provide the Interconnection Customer with five Business Day notice of such disconnection, unless the provisions of article 3.4.1 apply.

3.4.5   Modification of the Small Generating Facility

The Interconnection Customer must receive written authorization from the NYISO and

Connecting Transmission Owner before making any change to the Small Generating Facility that 
may have a material impact on the safety or reliability of the New York State Transmission 
System or the Distribution System.  Such authorization shall not be unreasonably withheld. 
Modifications shall be done in accordance with Good Utility Practice.  If the Interconnection 
Customer makes such modification without the prior written authorization of the NYISO and 
Connecting Transmission Owner, the Connecting Transmission Owner shall have the right to 
temporarily disconnect the Small Generating Facility.  If disconnected, the Small Generating 
Facility will not be reconnected until the unauthorized modifications are authorized or removed.

3.4.6   Reconnection

The Parties shall cooperate with each other to restore the Small Generating Facility,

Interconnection Facilities, and the New York State Transmission System and Distribution

System to their normal operating state as soon as reasonably practicable following a temporary disconnection.

13

SERVICE AGREEMENT NO. 2833

Article 4	Cost Responsibility for Interconnection Facilities and Distribution Upgrades

4.1	Interconnection Facilities

4.1.1   The Interconnection Customer shall pay for the cost of the Interconnection

Facilities itemized in Attachment 2 of this Agreement.  The NYISO, in

consultation with the Connecting Transmission Owner, shall provide a best

estimate cost, including overheads, for the purchase and construction of its

Interconnection Facilities and provide a detailed itemization of such costs.  Costs 
associated with Interconnection Facilities may be shared with other entities that 
may benefit from such facilities by agreement of the Interconnection Customer, 
such other entities, the NYISO, and the Connecting Transmission Owner.

4.1.2   The Interconnection Customer shall be responsible for its share of all reasonable 
	expenses, including overheads, associated with (1) owning, operating, 
	maintaining, repairing, and replacing its own Interconnection Facilities, and

(2) operating, maintaining, repairing, and replacing the Connecting Transmission 
Owner’s Interconnection Facilities, as set forth in Attachment 2 to this 
Agreement.

4.2	Distribution Upgrades

The Connecting Transmission Owner shall design, procure, construct, install, and own

the Distribution Upgrades described in Attachment 6 of this Agreement.  If the Connecting

Transmission Owner and the Interconnection Customer agree, the Interconnection Customer may construct Distribution Upgrades.  The actual cost of the Distribution Upgrades, including 
overheads, shall be directly assigned to the Interconnection Customer.  The Interconnection 
Customer shall be responsible for its share of all reasonable expenses, including overheads, 
associated with owning, operating, maintaining, repairing, and replacing the Distribution 
Upgrades, as set forth in Attachment 6 to this Agreement.

14

SERVICE AGREEMENT NO. 2833

Article 5	Cost Responsibility for System Upgrade Facilities and System Deliverability

Upgrades

5.1	Applicability

No portion of this article 5 shall apply unless the interconnection of the Small Generating Facility requires System Upgrade Facilities or System Deliverability Upgrades.

5.2	System Upgrades

The Connecting Transmission Owner shall procure, construct, install, and own the

System Upgrade Facilities and System Deliverability Upgrades described in Attachment 6 of this Agreement.  To the extent that design work is necessary in addition to that already accomplished in the Class Year Interconnection Facilities Study for the Interconnection Customer, the 
Connecting Transmission Owner shall perform or cause to be performed such work.  If all the 
Parties agree, the Interconnection Customer may construct System Upgrade Facilities and 
System Deliverability Upgrades.

5.2.1   As described in Section 32.3.5.3 of the SGIP in Attachment Z of the ISO OATT, 
	the responsibility of the Interconnection Customer for the cost of the System 
	Upgrade Facilities and System Deliverability Upgrades described in Attachment 6 
	of this Agreement shall be determined in accordance with Attachment S of the 
	ISO OATT, as required by Section 32.3.5.3.2 of Attachment Z.  The 
	Interconnection Customer shall be responsible for all System Upgrade Facility 
	costs as required by Section 32.3.5.3.2 of Attachment Z or its share of any System 
	Upgrade Facilities and System Deliverability Upgrades costs resulting from the 
	final Attachment S process, as applicable, and Attachment 6 to this Agreement 
	shall be revised accordingly.

5.2.2   Pending the outcome of the Attachment S cost allocation process, if applicable, 
	the Interconnection Customer may elect to proceed with the interconnection of its 
	Small Generating Facility in accordance with Section 32.3.5.3 of the SGIP.

5.3 	Special Provisions for Affected Systems

For the repayment of amounts advanced to the Affected System Operator for System Upgrade Facilities or System Deliverability Upgrades, the Interconnection Customer and Affected System Operator shall enter into an agreement that provides for such repayment, but only if responsibility for the cost of such System Upgrade Facilities is not to be allocated in accordance with Attachment S of the ISO OATT.  The agreement shall specify the terms governing payments to be made by the Interconnection Customer to the Affected System Operator as well as the repayment by the Affected System Operator.

15

SERVICE AGREEMENT NO. 2833

Article 6	Billing, Payment, Milestones, and Financial Security

6.1	Billing and Payment Procedures and Final Accounting

6.1.1	The Connecting Transmission Owner shall bill the Interconnection Customer for

the design, engineering, construction, and procurement costs of Interconnection

Facilities and Upgrades contemplated by this Agreement on a monthly basis, or as otherwise agreed by those Parties.  The Interconnection Customer shall pay all invoice amounts within 30 calendar days after receipt of the invoice.

6.1.2 	Within three months of completing the construction and installation of the

Connecting Transmission Owner’s Interconnection Facilities and/or Upgrades 
described in the Attachments to this Agreement, the Connecting Transmission 
Owner shall provide the Interconnection Customer with a final accounting report 
of any difference between (1) the Interconnection Customer’s cost responsibility 
for the actual cost of such facilities or Upgrades, and (2) the Interconnection 
Customer’s previous aggregate payments to the Connecting Transmission Owner 
for such facilities or Upgrades.  If the Interconnection Customer’s cost 
responsibility exceeds its previous aggregate payments, the Connecting 
Transmission Owner shall invoice the Interconnection Customer for the amount 
due and the Interconnection Customer shall make payment to the Connecting 
Transmission Owner within 30 calendar days.  If the Interconnection Customer’s 
previous aggregate payments exceed its cost responsibility under this Agreement, 
the Connecting Transmission Owner shall refund to the Interconnection Customer 
an amount equal to the difference within 30 calendar days of the final accounting 
report.

6.1.3 	If the Interconnection Customer disputes an amount to be paid, the

Interconnection Customer shall pay the disputed amount to the Connecting

Transmission Owner or into an interest bearing escrow account, pending

resolution of the dispute in accordance with Article 10 of this Agreement.  To the extent the dispute is resolved in the Interconnection Customer’s favor, that portion of the disputed amount will be credited or returned to the Interconnection 
Customer with interest at rates applicable to refunds under the Commission’s 
regulations.  To the extent the dispute is resolved in the Connecting Transmission Owner’s favor, that portion of any escrowed funds and interest will be released to the Connecting Transmission Owner.

6.2	Milestones

Subject to the provisions of the SGIP, the Parties shall agree on milestones for which

each Party is responsible and list them in Attachment 4 of this Agreement.  A Party’s obligations 
under this provision may be extended by agreement.  If a Party anticipates that it will be unable 
to meet a milestone for any reason other than a Force Majeure event, it shall immediately notify 
the other Parties of the reason(s) for not meeting the milestone and: (1) propose the earliest 
reasonable alternate date by which it can attain this and future milestones, and (2) requesting 
appropriate amendments to Attachment 4.  The Party affected by the failure to meet a milestone

16

SERVICE AGREEMENT NO. 2833

shall not unreasonably withhold agreement to such an amendment unless: (1) it will suffer

significant uncompensated economic or operational harm from the delay, (2) attainment of the same milestone has previously been delayed, or (3) it has reason to believe that the delay in 
meeting the milestone is intentional or unwarranted notwithstanding the circumstances explained by the Party proposing the amendment.

6.3	Financial Security Arrangements

At least 20 Business Days prior to the commencement of the design, procurement,

installation, or construction of a discrete portion of the Connecting Transmission Owner’s

Interconnection Facilities and Upgrades, the Interconnection Customer shall provide the

Connecting Transmission Owner, at the Interconnection Customer’s option, a guarantee, a surety 
bond, letter of credit or other form of security that is reasonably acceptable to the Connecting 
Transmission Owner and is consistent with the Uniform Commercial Code of the jurisdiction 
where the Point of Interconnection is located.  Such security for payment shall be in an amount 
sufficient to cover the costs for constructing, designing, procuring, and installing the applicable 
portion of the Connecting Transmission Owner’s Interconnection Facilities and Upgrades and 
shall be reduced on a dollar-for-dollar basis for payments made to the Connecting Transmission 
Owner under this Agreement during its term.  The Connecting Transmission Owner may draw 
on any such security to the extent that the Interconnection Customer fails to make any payments 
due under this Agreement.  In addition:

6.3.1   The guarantee must be made by an entity that meets the creditworthiness

requirements of the Connecting Transmission Owner, and contain terms and conditions that guarantee payment of any amount that may be due from the Interconnection Customer, up to an agreed-to maximum amount.

6.3.2   The letter of credit or surety bond must be issued by a financial institution or 
	insurer reasonably acceptable to the Connecting Transmission Owner and must 
	specify a reasonable expiration date.

6.3.3   Notwithstanding the above, Security posted for System Upgrade Facilities for a 
	Small Generating Facility required to enter the Class Year process, or cash or 
	Security provided for System Deliverability Upgrades, shall meet the 
	requirements for Security contained in Attachment S to the ISO OATT.

17

SERVICE AGREEMENT NO. 2833

Article 7	Assignment, Liability, Indemnity, Force Majeure, Consequential Damages,

and Default

7.1	Assignment

This Agreement, and each and every term and condition hereof, shall be binding upon and inure to the benefit of the Parties hereto and their respective successors and assigns.  This Agreement may be assigned by any Party upon 15 Business Days prior written notice and opportunity to object by the other Parties; provided that:

7.1.1   A Party may assign this Agreement without the consent of the other Parties to any 
	affiliate of the assigning Party with an equal or greater credit rating and with the 
	legal authority and operational ability to satisfy the obligations of the assigning 
	Party under this Agreement, provided that the Interconnection Customer promptly 
	notifies the NYISO and the Connecting Transmission Owner of any such 
	assignment.  A Party may assign this Agreement without the consent of the other 
	Parties in connection with the sale, merger, restructuring, or transfer of a 
	substantial portion of all of its assets, including the Interconnection Facilities it 
	owns, so long as the assignee in such a transaction directly assumes all rights, 
	duties and obligation arising under this Agreement.

7.1.2   The Interconnection Customer shall have the right to assign this Agreement,

without the consent of the NYISO or Connecting Transmission Owner, for

collateral security purposes to aid in providing financing for the Small Generating 
Facility.

7.1.3   Any attempted assignment that violates this article is void and ineffective.

Assignment shall not relieve a Party of its obligations, nor shall a Party’s

obligations be enlarged, in whole or in part, by reason thereof.  An assignee is responsible for meeting the same financial, credit, and insurance obligations as the Interconnection Customer.  Where required, consent to assignment will not be unreasonably withheld, conditioned or delayed.

7.2	Limitation of Liability

Each Party’s liability to the other Parties for any loss, cost, claim, injury, liability, or

expense, including reasonable attorney’s fees, relating to or arising from any act or omission in its performance of this Agreement, shall be limited to the amount of direct damage actually incurred.  In no event shall any Party be liable to the other Parties for any indirect, special, consequential, or punitive damages.

7.3	Indemnity

7.3.1   This provision protects each Party from liability incurred to third parties as a

result of carrying out the provisions of this Agreement.  Liability under this

provision is exempt from the general limitations on liability found in article 7.2.

18

SERVICE AGREEMENT NO. 2833

7.3.2 	Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and

hold harmless the other Parties (each an “ Indemnified Party”) from, any and all 
damages, losses, claims, including claims and actions relating to injury to or death of any person or damage to property, the alleged violation of any Environmental 
Law, or the release or threatened release of any Hazardous Substance, demand, 
suits, recoveries, costs and expenses, court costs, attorney fees, and all other 
obligations by or to third parties (any and all of these a “Loss”), arising out of or 
resulting from: (i) the Indemnified Party’s performance under this Agreement on behalf of the Indemnifying Party, except in cases where the Indemnifying Party 
can demonstrate that the Loss of the Indemnified Party was caused by the gross 
negligence or intentional wrongdoing by the Indemnified Party, or (ii) the 
violation by the Indemnifying Party of any Environmental Law or the release by 
the Indemnifying Party of a Hazardous Substance.

7.3.3 	If a Party is entitled to indemnification under this article as a result of a claim by a

third party, and the Indemnifying Party fails, after notice and reasonable

opportunity to proceed under this article, to assume the defense of such claim, 
such Indemnified Party may at the expense of the Indemnifying Party contest, 
settle or consent to the entry of any judgment with respect to, or pay in full, such 
claim.

7.3.4 	If an Indemnifying Party is obligated to indemnify and hold any Indemnified

Party harmless under this article, the amount owing to the Indemnified Party shall be the amount of such Indemnified Party’s actual loss, net of any insurance or 
other recovery.

7.3.5 	Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or

investigation as to which the indemnity provided for in this article may apply, the 
Indemnified Party shall notify the Indemnifying Party of such fact.  Any failure of 
or delay in such notification shall not affect a Party’s indemnification obligation 
unless such failure or delay is materially prejudicial to the Indemnifying Party.

7.4	Consequential Damages

Other than as expressly provided for in this Agreement, no Party shall be liable under any provision of this Agreement for any losses, damages, costs or expenses for any special, indirect, incidental, consequential, or punitive damages, including but not limited to loss of profit or 
revenue, loss of the use of equipment, cost of capital, cost of temporary equipment or services, 
whether based in whole or in part in contract, in tort, including negligence, strict liability, or any other theory of liability; provided, however, that damages for which a Party may be liable to 
another Party under another agreement will not be considered to be special, indirect, incidental, 
or consequential damages hereunder.

19

SERVICE AGREEMENT NO. 2833

7.5	Force Majeure

7.5.1	As used in this article, a “Force Majeure Event” shall mean “any act of God, labor

disturbance, act of the public enemy, war, insurrection, riot, fire, storm or flood, 
explosion, breakage or accident to machinery or equipment, any order, regulation 
or restriction imposed by governmental, military or lawfully established civilian 
authorities, or any other cause beyond a Party’s control.  A Force Majeure Event 
does not include an act of negligence or intentional wrongdoing.”  For the 
purposes of this article, this definition of Force Majeure shall supersede the 
definitions of Force Majeure set out in Section 32.10.1 of the ISO OATT.

7.5.2 	If a Force Majeure Event prevents a Party from fulfilling any obligations under

this Agreement, the Party affected by the Force Majeure Event (“Affected Party”) 
shall promptly notify the other Parties, either in writing or via the telephone, of 
the existence of the Force Majeure Event.  The notification must specify in 
reasonable detail the circumstances of the Force Majeure Event, its expected 
duration, and the steps that the Affected Party is taking to mitigate the effects of 
the event on its performance.  The Affected Party shall keep the other Parties 
informed on a continuing basis of developments relating to the Force Majeure 
Event until the event ends.  The Affected Party will be entitled to suspend or 
modify its performance of obligations under this Agreement (other than the 
obligation to make payments) only to the extent that the effect of the Force 
Majeure Event cannot be mitigated by the use of Reasonable Efforts.  The 
Affected Party will use Reasonable Efforts to resume its performance as soon as 
possible.

7.6	Breach and Default

7.6.1   No Breach of this Agreement shall exist where such failure to discharge an

obligation (other than the payment of money) is the result of a Force Majeure

Event or the result of an act or omission of the other Parties.  Upon a Breach, the 
non-breaching Party shall give written notice of such Breach to the Breaching 
Party.  Except as provided in article 7.6.2, the Breaching Party shall have 60 
calendar days from receipt of the Breach notice within which to cure such Breach; 
provided however, if such Breach is not capable of cure within 60 calendar days, 
the Breaching Party shall commence such cure within 20 calendar days after 
notice and continuously and diligently complete such cure within six months from 
receipt of the Breach notice; and, if cured within such time, the Breach specified 
in such notice shall cease to exist.

7.6.2   If a Breach is not cured as provided in this article, or if a Breach is not capable of 
	being cured within the period provided for herein, a Default shall exist and the 
	non-defaulting Parties acting together shall thereafter have the right to terminate 
	this Agreement, in accordance with article 3.3 hereof, by written notice to the 
	defaulting Party at any time until cure occurs, and be relieved of any further 
	obligation hereunder and, whether or not those Parties terminate this Agreement, 
	to recover from the defaulting Party all amounts due hereunder, plus all other

20

SERVICE AGREEMENT NO. 2833

damages and remedies to which they are entitled at law or in equity.  The 
provisions of this article shall survive termination of this Agreement.

7.6.3   In cases where the Interconnection Customer has elected to proceed under

Section 32.3.5.3 of the SGIP, if the Interconnection Request is withdrawn or

deemed withdrawn pursuant to the SGIP during the term of this Agreement, this Agreement shall terminate.

21

SERVICE AGREEMENT NO. 2833

Article 8	Insurance

8.1	The Interconnection Customer shall, at its own expense, maintain in force general

liability insurance without any exclusion for liabilities related to the interconnection

undertaken pursuant to this Agreement.  The amount of such insurance shall be sufficient 
to insure against all reasonably foreseeable direct liabilities given the size and nature of 
the generating equipment being interconnected, the interconnection itself, and the 
characteristics of the system to which the interconnection is made.  Such insurance 
coverage is specified in Attachment 7 to this Agreement.  The Interconnection Customer 
shall obtain additional insurance only if necessary as a function of owning and operating 
a generating facility.  Such insurance shall be obtained from an insurance provider 
authorized to do business in New York State where the interconnection is located. 
Certification that such insurance is in effect shall be provided upon request of the 
Connecting Transmission Owner, except that the Interconnection Customer shall show 
proof of insurance to the Connecting Transmission Owner no later than ten Business 
Days prior to the anticipated commercial operation date.  An Interconnection Customer 
of sufficient creditworthiness may propose to self-insure for such liabilities, and such a 
proposal shall not be unreasonably rejected.

8.2 	The NYISO and Connecting Transmission Owner agree to maintain general liability

insurance or self-insurance consistent with the existing commercial practice.  Such

insurance or self-insurance shall not exclude the liabilities undertaken pursuant to this Agreement.

8.3 	The Parties further agree to notify one another whenever an accident or incident occurs

resulting in any injuries or damages that are included within the scope of coverage of such insurance, whether or not such coverage is sought.

22

SERVICE AGREEMENT NO. 2833

Article 9	Confidentiality

9.1	Confidential Information shall mean any confidential and/or proprietary information

provided by one Party to the other Party that is clearly marked or otherwise designated 
“Confidential.”  For purposes of this Agreement all design, operating specifications, and 
metering data provided by the Interconnection Customer shall be deemed Confidential 
Information regardless of whether it is clearly marked or otherwise designated as such. 
Confidential Information shall include, without limitation, information designated as 
such by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

9.2 	Confidential Information does not include information previously in the public domain,

required to be publicly submitted or divulged by Governmental Authorities (after notice 
to the other Party and after exhausting any opportunity to oppose such publication or 
release), or necessary to be divulged in an action to enforce this Agreement.  Each Party 
receiving Confidential Information shall hold such information in confidence and shall 
not disclose it to any third party nor to the public without the prior written authorization 
from the Party providing that information, except to fulfill obligations under this

Agreement, or to fulfill legal or regulatory requirements.

9.2.1 	Each Party shall employ at least the same standard of care to protect Confidential

Information obtained from the other Parties as it employs to protect its own Confidential Information.

9.2.2 	Each Party is entitled to equitable relief, by injunction or otherwise, to enforce its

rights under this provision to prevent the release of Confidential Information

without bond or proof of damages, and may seek other remedies available at law or in equity for breach of this provision.

9.3 	Notwithstanding anything in this article to the contrary, and pursuant to 18 CFR §

lb.20, if FERC, during the course of an investigation or otherwise, requests

information from one of the Parties that is otherwise required to be maintained in 
confidence pursuant to this Agreement, the Party shall provide the requested 
information to FERC, within the time provided for in the request for information. 
In providing the information to FERC, the Party may, consistent with 18 CFR § 
388.112, request that the information be treated as confidential and non-public by 
FERC and that the information be withheld from public disclosure.  Each Party is 
prohibited from notifying the other Parties to this Agreement prior to the release 
of the Confidential Information to FERC.  The Party shall notify the other Parties 
to this Agreement when it is notified by FERC that a request to release 
Confidential Information has been received by FERC, at which time either of the 
Parties may respond before such information would be made public, pursuant to

18 CFR § 388.112.  Requests from a state regulatory body conducting a

confidential investigation shall be treated in a similar manner if consistent with the applicable state rules and regulations.

9.4 	Consistent with the provisions of this article 9, the Parties to this Agreement will

cooperate in good faith to provide each other, Affected Systems, Affected System

23

SERVICE AGREEMENT NO. 2833

Operators, and state and federal regulators the information necessary to carry out the terms of the SGIP and this Agreement.

24

SERVICE AGREEMENT NO. 2833

Article 10	Disputes

10.1	The NYISO, Connecting Transmission Owner and Interconnection Customer agree to

attempt to resolve all disputes arising out of the interconnection process according to the provisions of this article.

10.2 	In the event of a dispute, the Parties will first attempt to promptly resolve it on an

informal basis.  The NYISO will be available to the Interconnection Customer and

Connecting Transmission Owner to help resolve any dispute that arises with respect to

performance under this Agreement.  If the Parties cannot promptly resolve the dispute on an informal basis, then any Party shall provide the other Parties with a written Notice of Dispute.  Such notice shall describe in detail the nature of the dispute.

10.3 	If the dispute has not been resolved within two Business Days after receipt of the notice,

any Party may contact FERC’s Dispute Resolution Service (“DRS”) for assistance in resolving the dispute.

10.4 	The DRS will assist the Parties in either resolving their dispute or in selecting an

appropriate dispute resolution venue (e.g., mediation, settlement judge, early neutral

evaluation, or technical expert) to assist the Parties in resolving their dispute.  The result of this dispute resolution process will be binding only if the Parties agree in advance. DRS can be reached at 1-877-337-2237 or via the internet at

http://www.ferc.gov/legal/adr.asp.

10.5 	Each Party agrees to conduct all negotiations in good faith and will be responsible for

one-third of any costs paid to neutral third-parties.

10.6 	If any Party elects to seek assistance from the DRS, or if the attempted dispute resolution

fails, then any Party may exercise whatever rights and remedies it may have in equity or law consistent with the terms of this Agreement.

25

SERVICE AGREEMENT NO. 2833

Article 11	Taxes

11.1	The Parties agree to follow all applicable tax laws and regulations, consistent with FERC

policy and Internal Revenue Service requirements.

11.2 	Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.

Nothing in this Agreement is intended to adversely affect the tax status of any Party

including the status of NYISO, or the status of any Connecting Transmission Owner with 
respect to the issuance of bonds including, but not limited to, Local Furnishing Bonds. 
Notwithstanding any other provisions of this Agreement, LIPA, NYPA and Consolidated 
Edison Company of New York, Inc. shall not be required to comply with any provisions 
of this Agreement that would result in the loss of tax-exempt status of any of their Tax-
Exempt Bonds or impair their ability to issue future tax-exempt obligations.  For

purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long 
Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc., 
the interest on which is not included in gross income under the Internal Revenue Code.

11.3 	LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA,

from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general ratemaking authority.

11.4 	Any payments due to the Connecting Transmission Owner under this Agreement shall be

adjusted to include any tax liability incurred by the Connecting Transmission Owner with respect to the interconnection request which is the subject of this Agreement.  Such 
adjustments shall be made in accordance with the provisions of Article 5.17 of the LGIA in Attachment X of the ISO OATT.  Except where otherwise noted, all costs, deposits, financial obligations and the like specified in this Agreement shall be assumed not to 
reflect the impact of applicable taxes.

26

SERVICE AGREEMENT NO. 2833

Article 12	Miscellaneous

12.1	Governing Law, Regulatory Authority, and Rules

The validity, interpretation and enforcement of this Agreement and each of its provisions shall be governed by the laws of the state of New York, without regard to its conflicts of law principles.  This Agreement is subject to all Applicable Laws and Regulations.  Each Party 
expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, or regulations of a Governmental Authority.

12.2	Amendment

The Parties may amend this Agreement by a written instrument duly executed by the Parties, or under article 12.12 of this Agreement.

12.3 	No Third-Party Beneficiaries

This Agreement is not intended to and does not create rights, remedies, or benefits of any character whatsoever in favor of any persons, corporations, associations, or entities other than the Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their successors in interest and where permitted, their assigns.  Notwithstanding the foregoing, any 
subcontractor of the Connecting Transmission Owner or NYISO assisting either of those Parties with the Interconnection Request covered by this Agreement shall be entitled to the benefits of indemnification provided for under Article 7.3 of this Agreement and the limitation of liability 
provided for in Article 7.2 of this Agreement.

12.4	Waiver

12.4.1 The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver of any obligation, right, or duty of, or imposed upon, such Party.

12.4.2 Any waiver at any time by a Party of its rights with respect to this Agreement 
	shall not be deemed a continuing waiver or a waiver with respect to any other 
	failure to comply with any other obligation, right, duty of this Agreement. 
	Termination or default of this Agreement for any reason by Interconnection 
	Customer shall not constitute a waiver of the Interconnection Customer’s legal 
	rights to obtain an interconnection from the NYISO.  Any waiver of this 
	Agreement shall, if requested, be provided in writing.

12.5	Entire Agreement

This Agreement, including all Attachments, constitutes the entire agreement between the 
Parties with reference to the subject matter hereof, and supersedes all prior and contemporaneous 
understandings or agreements, oral or written, between the Parties with respect to the subject 
matter of this Agreement.  There are no other agreements, representations, warranties, or 
covenants which constitute any part of the consideration for, or any condition to, any Party’s 
compliance with its obligations under this Agreement, except as noted in Attachment 5.

27

SERVICE AGREEMENT NO. 2833

12.6 	Multiple Counterparts

This Agreement may be executed in two or more counterparts, each of which is deemed an original but all constitute one and the same instrument.

12.7	No Partnership

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership between the Parties or to impose any partnership

obligation or partnership liability upon any Party.  No Party shall have any right, power or

authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, another Party.

12.8	Severability

If any provision or portion of this Agreement shall for any reason be held or adjudged to be invalid or illegal or unenforceable by any court of competent jurisdiction or other 
Governmental Authority, (1) such portion or provision shall be deemed separate and 
independent, (2) the Parties shall negotiate in good faith to restore insofar as practicable the 
benefits to each Party that were affected by such ruling, and (3) the remainder of this Agreement shall remain in full force and effect.

12.9 	Security Arrangements

Infrastructure security of electric system equipment and operations and control hardware and software is essential to ensure day-to-day reliability and operational security.  FERC expects the NYISO, the Connecting Transmission Owner, Market Participants, and Interconnection 
Customers interconnected to electric systems to comply with the recommendations offered by 
the President’s Critical Infrastructure Protection Board and, eventually, best practice 
recommendations from the electric reliability authority.  All public utilities are expected to meet basic standards for system infrastructure and operational security, including physical, 
operational, and cyber-security practices.

12.10  Environmental Releases

Each Party shall notify the other Parties, first orally and then in writing, of the release of 
any hazardous substances, any asbestos or lead abatement activities, or any type of remediation 
activities related to the Small Generating Facility or the Interconnection Facilities, each of which 
may reasonably be expected to affect the other Parties.  The notifying Party shall: (1) provide the 
notice as soon as practicable, provided such Party makes a good faith effort to provide the notice 
no later than 24 hours after such Party becomes aware of the occurrence, and (2) promptly

furnish to the other Parties copies of any publicly available reports filed with any governmental authorities addressing such events.

12.11  Subcontractors

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,

28

SERVICE AGREEMENT NO. 2833

however, that each Party shall require its subcontractors to comply with all applicable terms and conditions of this Agreement in providing such services and each Party shall remain primarily liable to the other Parties for the performance of such subcontractor.

12.11.1 	The creation of any subcontract relationship shall not relieve the hiring

Party of any of its obligations under this Agreement.  The hiring Party

shall be fully responsible to the other Parties to the extent provided for in 
Articles 7.2 and 7.3 above for the acts or omissions of any subcontractor 
the hiring Party hires as if no subcontract had been made; provided, 
however, that in no event shall the NYISO or Connecting Transmission 
Owner be liable for the actions or inactions of the Interconnection 
Customer or its subcontractors with respect to obligations of the 
Interconnection Customer under this Agreement.  Any applicable 
obligation imposed by this Agreement upon the hiring Party shall be 
equally binding upon, and shall be construed as having application to, any 
subcontractor of such Party.

12.11.2	The obligations under this article will not be limited in any way by any

limitation of subcontractor’s insurance.

12.12  Reservation of Rights

Nothing in this Agreement shall alter the right of the NYISO or Connecting Transmission 
Owner to make unilateral filings with FERC to modify this Agreement with respect to any rates, 
terms and conditions, charges, classifications of service, rule or regulation under Section 205 or 
any other applicable provision of the Federal Power Act and FERC’s rules and regulations 
thereunder which rights are expressly reserved herein, and the existing rights of the 
Interconnection Customer to make a unilateral filing with FERC to modify this Agreement under 
any applicable provision of the Federal Power Act and FERC’s rules and regulations are also 
expressly reserved herein; provided that each Party shall have the right to protest any such filing 
by another Party and to participate fully in any proceeding before FERC in which such 
modifications may be considered.  Nothing in this Agreement shall limit the rights of the Parties 
or of FERC under Sections 205 or 206 of the Federal Power Act and FERC’s rules and 
regulations, except to the extent that the Parties otherwise agree as provided herein.

29

SERVICE AGREEMENT NO. 2833

Article 13	Notices

13.1	General

Unless otherwise provided in this Agreement, any written notice, demand, or request required or authorized in connection with this Agreement  shall be deemed properly given if delivered in person, delivered by recognized national courier service, or sent by first class mail, postage prepaid, to the person specified below:

If to the Interconnection Customer:

Interconnection Customer: Little Pond Solar, LLC Attention: Asset Management Department 
Address: 3402 Pico Blvd.

City: Santa Monica    State: CA	Zip: 90405

Phone: 310-581-6299

If to the Connecting Transmission Owner:

Connecting Transmission Owner: Orange and Rockland Utilities, Inc. Attention: Vice President, Operations

Address: 390 West Route 59

City: Spring Valley    State: NY	Zip: 10977

Phone:  (845) 577-3161

If to the NYISO:

Before Commercial Operation of the Small Generating Facility

New York Independent System Operator, Inc.

Attention:  Vice President, System and Resource Planning Address:  10 Krey Boulevard

City:    Rensselaer	State:  NY	Zip: 12144

Phone:  (518) 356-6000

After Commercial Operation:

New York Independent System Operator, Inc. Attention: Vice President, Operations 
Address:  10 Krey Boulevard

City:    Rensselaer	State:  NY	Zip: 12144

Phone:  (518) 356-6000

13.2	Billing and Payment

Billings and payments shall be sent to the addresses set out below: Interconnection Customer: Little Pond Solar, LLC

30

SERVICE AGREEMENT NO. 2833

Attention: Cypress Creek Renewables, LLC Address: 3402 Pico Blvd.

City: Santa Monica    State: CA	Zip: 90405

Connecting Transmission Owner: Orange and Rockland Utilities, Inc.

Attention: Vice President, Operations

Address: 390 West Route 59

City: Spring Valley    State: NY	Zip: 10977

13.3 	Alternative Forms of Notice

Any notice or request required or permitted to be given by either Party to the other and not required by this Agreement to be given in writing may be so given by telephone or e-mail to the telephone numbers and e-mail addresses set out below:

If to the Interconnection Customer:

Interconnection Customer: Little Pond Solar, LLC Attention: Asset Management Department 
Address: 3402 Pico Blvd.

City: Santa Monica    State: CA	Zip: 90405

Phone: 310-581-6299

E-mail:  assetmanagement@ccrenew.com

If to the Connecting Transmission Owner:

Connecting Transmission Orange and Rockland Utilities, Inc.

Attention:	Vice President, Operations

Address:	390 West Route 59

City: Spring Valley    State: NY	Zip: 10977

Phone:  (845) 577-3161 
E-mail:  choew@oru.com

If to the NYISO:

New York Independent System Operator, Inc. Attention:  Vice President, Operations 
Address:  10 Krey Boulevard

City:    Rensselaer	State:  NY	Zip: 12144

Phone:  (518) 356-6000

E-mail:  interconnectionsupport@nyiso.com

31

SERVICE AGREEMENT NO. 2833

13.4 	Designated Operating Representative

The Parties may also designate operating representatives to conduct the communications 
which may be necessary or convenient for the administration of this Agreement.  This person 
will also serve as the point of contact with respect to operations and maintenance of the Party’s 
facilities.

Interconnection Customer’s Operating Representative:

Interconnection Customer: Little Pond Solar, LLC Attention: Asset Management Department 
Address: 3402 Pico Blvd.

City: Santa Monica   State: CA	Zip: 90405

Phone: 310-581-6299

E-mail:  assetmanagement@ccrenew.com

Connecting Transmission Owner’s Operating Representative:

Connecting Transmission Owner: Orange and Rockland Utilities, Inc. Attention: Vice President, Operations

Address: 390 West Route 59

City: Spring Valley   State: NY	Zip: 10977

Phone:  (845) 577-3161 
E-mail:  choew@oru.com

NYISO’s Operating Representative:

New York Independent System Operator, Inc. Attention:  Vice President, Operations 
Address:  10 Krey Boulevard

City:    Rensselaer	State:  NY	Zip: 12144

Phone:  (518) 356-6000

E-mail:  interconnectionsupport@nyiso.com

13.5 	Changes to the Notice Information

Either Party may change this information by giving five Business Days written notice prior to the effective date of the change.

32

SERVICE AGREEMENT NO. 2833

Article 14	Signatures

IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their respective duly authorized representatives.

For the New York Independent System Operator, Inc. 
By:

Name: _________________________ 
Title: __________________________ 
Date: __________________________

For Orange and Rockland Utilities, Inc. 
By:

Name: Won Choe__________

Title: Vice President_______________ Date: __________________________ For Little Pond Solar, LLC

By: Citrine Solar LLC, its sole member 
By:

Name: Matthew Murphy____________ 
Title: Chief Operations Officer_______ 
Date: ___________________________

33

SERVICE AGREEMENT NO. 2833

Attachment 1

Glossary of Terms

Affected System - An electric system other than the transmission system owned, controlled or operated by the Connecting Transmission Owner that may be affected by the proposed 
interconnection.

Affected System Operator - Affected System Operator shall mean the operator of any Affected 
System.

Affected Transmission Owner -The New York public utility or authority (or its designated

agent) other than the Connecting Transmission Owner that: (i) owns facilities used for the

transmission of Energy in interstate commerce and provides Transmission Service under the

Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State Transmission System where System Deliverability Upgrades or System Upgrade Facilities are installed pursuant to Attachment Z and Attachment S to the ISO OATT.

Applicable Laws and Regulations - All duly promulgated applicable federal, state and local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or 
administrative orders, permits and other duly authorized actions of any Governmental Authority, including but not limited to Environmental Law.

Applicable Reliability Standards - The criteria, requirements and guidelines of the North

American Electric Reliability Council, the Northeast Power Coordinating Council, the New York 
State Reliability Council and related and successor organizations, or the Transmission District to 
which the Interconnection Customer’s Small Generating Facility is directly interconnected, as 
those criteria, requirements and guidelines are amended and modified and in effect from time to 
time; provided that no Party shall waive its right to challenge the applicability of or validity of 
any criterion, requirement or guideline as applied to it in the context of Attachment Z to the ISO 
OATT and this Agreement.  For the purposes of this Agreement, this definition of Applicable

Reliability Standards shall supersede the definition of Applicable Reliability Standards set out in Attachment X to the ISO OATT.

Base Case - The base case power flow, short circuit, and stability data bases used for the 
Interconnection Studies by NYISO, Connecting Transmission Owner or Interconnection 
Customer; described in Section 32.2.3 of the Large Facility Interconnection Procedures.

Breach - The failure of a Party to perform or observe any material term or condition of this Agreement.

Business Day - Monday through Friday, excluding federal holidays.

Capacity Resource Interconnection Service -The service provided by NYISO to

Interconnection Customers that satisfy the NYISO Deliverability Interconnection Standard or 
that are otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT;

1-1

SERVICE AGREEMENT NO. 2833

such service being one of the eligibility requirements for participation as a NYISO Installed Capacity Supplier.

Commercial Operation shall mean the status of the Small Generating Facility that has

commenced generating electricity for sale, excluding electricity generated during Trial

Operation, notice of which must be provided to the NYISO in the form of Attachment 9 to this Agreement.

Commercial Operation Date of a unit shall mean the date on which the Large Generating

Facility commences Commercial Operation as agreed to by the Parties, notice of which must be provided to the NYISO in the form of Attachment 9 to this Agreement.

Connecting Transmission Owner - The New York public utility or authority (or its designated 
agent) that: (i) owns facilities used for the transmission of Energy in interstate commerce and 
provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an 
interest in the portion of the New York State Transmission System or Distribution System at the 
Point of Interconnection, and (iii) is a Party to the Standard Small Generator Interconnection 
Agreement.

Default - The failure of a Party in Breach of this Agreement to cure such Breach under the Small Generator Interconnection Agreement.

Distribution System - The Transmission Owner’s facilities and equipment used to distribute 
electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s Large Facility Interconnection Procedures in Attachment X to the ISO OATT or Small Generator 
Interconnection Procedures in Attachment Z to the ISO OATT under FERC Order Nos. 2003 
and/or 2006.  For the purpose of this Agreement, the term Distribution System shall not include LIPA’s distribution facilities.

Distribution Upgrades - The additions, modifications, and upgrades to the Connecting

Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate interconnection of the Small Generating Facility and render the transmission service necessary to effect the Interconnection Customer’s wholesale sale of electricity in interstate commerce. 
Distribution Upgrades do not include Interconnection Facilities or System Upgrade Facilities or System Deliverability Upgrades.

Energy Resource Interconnection Service - The service provided by NYISO to interconnect 
the Interconnection Customer’s Small Generating Facility to the New York State Transmission 
System or Distribution System in accordance with the NYISO Minimum Interconnection 
Standard, to enable the New York State Transmission System to receive Energy and Ancillary 
Services from the Small Generating Facility, pursuant to the terms of the ISO OATT.

Force Majeure - Any act of God, labor disturbance, act of the public enemy, war, insurrection, 
riot, fire, storm or flood, explosion, breakage or accident to machinery or equipment, any order, 
regulation or restriction imposed by governmental, military or lawfully established civilian 
authorities, or any other cause beyond a Party’s control.  A Force Majeure event does not include 
an act of negligence or intentional wrongdoing.  For the purposes of this Agreement, this

1-2

SERVICE AGREEMENT NO. 2833

definition of Force Majeure shall supersede the definitions of Force Majeure set out in Section

32.2.11 of the NYISO Open Access Transmission Tariff.

Good Utility Practice - Any of the practices, methods and acts engaged in or approved by a

significant portion of the electric industry during the relevant time period, or any of the practices, 
methods and acts which, in the exercise of reasonable judgment in light of the facts known at the 
time the decision was made, could have been expected to accomplish the desired result at a 
reasonable cost consistent with good business practices, reliability, safety and expedition.  Good 
Utility Practice is not intended to be limited to the optimum practice, method, or act to the 
exclusion of all others, but rather to be acceptable practices, methods, or acts generally accepted 
in the region.

Governmental Authority - Any federal, state, local or other governmental regulatory or

administrative agency, court, commission, department, board, or other governmental subdivision, legislature, rulemaking board, tribunal, or other governmental authority having jurisdiction over the Parties, their respective facilities, or the respective services they provide, and exercising or entitled to exercise any administrative, executive, police, or taxing authority or power; provided, however, that such term does not include the Interconnection Customer, NYISO, Affected 
Transmission Owner, Connecting Transmission Owner or any Affiliate thereof.

Initial Synchronization Date shall mean the date upon which the Small Generating Facility is initially synchronized and upon which Trial Operation begins, notice of which must be provided to the NYISO in the form of Attachment 8.

In-Service Date shall mean the date upon which the Developer reasonably expects it will be

ready to begin use of the Connecting Transmission Owner’s Interconnection Facilities to obtain back feed power.

Interconnection Customer - Any entity, including the Transmission Owner or any of the

affiliates or subsidiaries, that proposes to interconnect its Small Generating Facility with the New York State Transmission System or the Distribution System.

Interconnection Facilities - The Connecting Transmission Owner’s Interconnection Facilities and the Interconnection Customer’s Interconnection Facilities.  Collectively, Interconnection Facilities include all facilities and equipment between the Small Generating Facility and the 
Point of Interconnection, including any modification, additions or upgrades that are necessary to physically and electrically interconnect the Small Generating Facility to the New York State 
Transmission System or the Distribution System.  Interconnection Facilities are sole use facilities and shall not include Distribution Upgrades or System Upgrade Facilities.

Interconnection Request - The Interconnection Customer’s request, in accordance with the

Tariff, to interconnect a new Small Generating Facility, or to materially increase the capacity of, 
or make a material modification to the operating characteristics of, an existing Small Generating 
Facility that is interconnected with the New York State Transmission System or the Distribution 
System.  For the purposes of this Agreement, this definition of Interconnection Request shall 
supersede the definition of Interconnection Request set out in Attachment X to the ISO OATT.

1-3

SERVICE AGREEMENT NO. 2833

Interconnection Study - Any study required to be performed under Sections 32.2 or 32.3 of the 
SGIP.

Material Modification - A modification that has a material impact on the cost or timing of any Interconnection Request with a later queue priority date.

New York State Transmission System - The entire New York State electric transmission

system, which includes: (i) the Transmission Facilities under ISO Operational Control; (ii) the

Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities within the New York Control Area.

NYISO Deliverability Interconnection Standard - The standard that must be met, unless

otherwise provided for by Attachment S to the ISO OATT, by (i) any generation facility larger 
than 2MW in order for that facility to obtain CRIS; (ii) any Class Year Transmission Project 
proposing to interconnect to the New York State Transmission System and receive Unforced 
Capacity Delivery Rights; (iii) any entity requesting External CRIS Rights, and (iv) any entity 
requesting a CRIS transfer pursuant to Section 25.9.5 of Attachment S to the ISO OATT.  To 
meet the NYISO Deliverability Interconnection Standard, the Interconnection Customer must, in 
accordance with the rules in Attachment S to the ISO OATT, fund or commit to fund any System 
Deliverability Upgrades identified for its project in the Class Year Deliverability Study.

NYISO Minimum Interconnection Standard - The reliability standard that must be met by 
any generation facility or Class Year Transmission Project that is subject to NYISO’s Large 
Facility Interconnection Procedures in Attachment X to the ISO OATT or the NYISO’s Small 
Generator Interconnection Procedures in this Attachment Z, that is proposing to connect to the 
New York State Transmission System or Distribution System, to obtain ERIS.  The Minimum 
Interconnection Standard is designed to ensure reliable access by the proposed project to the 
New York State Transmission System or to the Distribution System.  The Minimum

Interconnection Standard does not impose any deliverability test or deliverability requirement on the proposed interconnection.

Operating Requirements - Any operating and technical requirements that may be applicable 
due to Regional Transmission Organization, Independent System Operator, control area, or the 
Connecting Transmission Owner’s requirements, including those set forth in the Small Generator 
Interconnection Agreement.  Operating Requirements shall include Applicable Reliability 
Standards.

Party or Parties - The NYISO, Connecting Transmission Owner, Interconnection Customer or any combination of the above.

Point of Interconnection - The point where the Interconnection Facilities connect with the New York State Transmission System or the Distribution System.

Reasonable Efforts - With respect to an action required to be attempted or taken by a Party 
under this Agreement, efforts that are timely and consistent with Good Utility Practice and are 
otherwise substantially equivalent to those a Party would use to protect its own interests.

1-4

SERVICE AGREEMENT NO. 2833

Small Generating Facility - The Interconnection Customer’s facility, no larger than 20 MW for 
the production and/or storage for later injection of electricity identified in the Interconnection 
Request if proposing to interconnect to the New York State Transmission System or Distribution 
System, but shall not include (i) facilities proposing to simply receive power from the New York 
State Transmission System or the Distribution System; (ii) facilities proposing to interconnect to the 
New York State Transmission System or the Distribution System made solely for the purpose of 
generation with no wholesale sale for resale nor to net metering; (iii) facilities proposing to the New 
York State Transmission System or the Distribution System made solely for the purpose of net 
metering; (iv) facilities proposing to interconnect to LIPA’s distribution facilities; and (v) the 
Interconnection Customer’s Interconnection Facilities. A facility will be treated as a single Small 
Generating Facility if all units within the facility are behind a single facility meter, even if such units 
are different technology types.

System Deliverability Upgrades - The least costly configuration of commercially available components of electrical equipment that can be used, consistent with Good Utility Practice and Applicable Reliability Requirements, to make the modifications or additions to the existing New York State Transmission System that are required for the proposed project to connect reliably to the system in a manner that meets the NYISO Deliverability Interconnection Standard for 
Capacity Resource Interconnection Service.

System Upgrade Facilities - The least costly configuration of commercially available

components of electrical equipment that can be used, consistent with Good Utility Practice and 
Applicable Reliability Requirements to make the modifications to the existing transmission 
system that are required to maintain system reliability due to:  (i) changes in the system, 
including such changes as load growth and changes in load pattern, to be addressed in the form 
of generic generation or transmission projects; and (ii) proposed interconnections.  In the case of 
proposed interconnection projects, System Upgrade Facilities are the modification or additions to 
the existing New York State Transmission System that are required for the proposed project to 
connect reliably to the system in a manner that meets the NYISO Minimum Interconnection 
Standard.

Tariff - The NYISO’s Open Access Transmission Tariff, as filed with the FERC, and as amended or supplemented from time to time, or any successor tariff.

Trial Operation shall mean the period during which Interconnection Customer is engaged in on-
site test operations and commissioning of the Small Generating Facility prior to Commercial 
Operation.

Upgrades - The required additions and modifications to the Connecting Transmission Owner’s portion of the New York State Transmission System or the Distribution System at or beyond the Point of Interconnection.  Upgrades may be System Upgrade Facilities or System Deliverability Upgrades Distribution Upgrades.  Upgrades do not include Interconnection Facilities.

1-5

SERVICE AGREEMENT NO. 2833

Attachment 2

Detailed Scope of Work, Including Description and Costs of the Small Generating Facility, 
	Interconnection Facilities, and Metering Equipment

Equipment, including the Small Generating Facility, Interconnection Facilities, and

metering equipment shall be itemized and identified as being owned by the Interconnection

Customer, or the Connecting Transmission Owner.  The NYISO, in consultation with the

Connecting Transmission Owner, will provide a best estimate itemized cost, including

overheads, of its Interconnection Facilities and metering equipment, and a best estimate itemized cost of the annual operation and maintenance expenses associated with its Interconnection 
Facilities and metering equipment.

A.	PROJECT DESCRIPTION

The Interconnection Customer is constructing a 20 MW photovoltaic facility (“Small

Generating Facility”) in Sparrow Bush, New York. The Small Generating Facility will consist of a collector system comprising:

•   Seven (7) photovoltaic (“PV”) arrays;

•   Seven (7) Power Electronics FS3190MU inverters, each with integrated 34.5 kV step-up 
	transformers; and

•   Seven (7) MV switchgear with MV breaker and electronic trip.

The Point of Interconnection (“POI”) for the Small Generating Facility is at the generator tie line’s termination at the 69 kV insulators on the termination structure of the new three (3) breaker line tap station (“Little Pond Station”).

The Point of Change of Ownership (“PCO”) is the generator tie line’s termination at the

69 kV insulators on the new Little Pond Station’s termination structure.  The POI and PCO are detailed on Figure 1 in Attachment 3.

B. 	INTERCONNECTION CUSTOMER’S INTERCONNECTION FACILITIES

As depicted on the one line diagram in Attachment 3, the Interconnection Customer’s 
Interconnection Facilities (“ICIF”) include all of the facilities between the Interconnection 
Customer’s side of the PCO and the Small Generating Facility.  The ICIF consist of a collector 
station (the “Little Pond Solar Collector Substation”) and the generator lead line. Each of the 
Power Electronics FS3190MU inverters contains an integrated transformer that steps up power to

34.5 kV.  At the Little Pond Solar Collector Substation, the power will be stepped up again to 69 kV for interconnection to the Little Pond Station via an overhead 69 kV transmission line.  The Small Generating Facility will be located southwest of the Little Pond Station.

The ICIF consist of the following:

•   Little Pond Solar Collector Substation

2-1

SERVICE AGREEMENT NO. 2833

o   One (1) 69 kV, 2000 A, 40 kA circuit breaker;

o   Three (3) single phase, 72 kV voltage transformers;

o   One (1) 69 kV, three phase, 1200 A line disconnect switch;

o   Three (3) 72 kV surge arresters;

o   Six (6) 27 kV surge arresters;

o   One (1) generator step-up (“GSU”) transformer, 34.5/19.9kV - 69 kV, 15/20/25 
	MVA grounded Y - delta - grounded Y;

o   One (1) 38 kV, three phase, 1200 A disconnect switch;

o   Two (2) 38 kV, 1200 A, 31.5 kA circuit breakers;

o   Four (4) 38 kV, three phase, 600A disconnect switches; and

o   One (1) 3 MVAR cap bank with cap switcher.

•	Generator Lead Line

o   The generator lead line is a new 0.1 mile 69 kV overhead line from the Little

Pond Solar Collector Substation to the Little Pond Station. This line is included as 
part of the ICIF all the way up to the PCO inside the Little Pond Station. This line 
will be part of the new tap station bus differential protection wrapping to the 
Interconnection Customer high voltage circuit breaker. Current transformers 
(“CTs”) and other protection and controls will be routed between stations.

C.	CONNECTING TRANSMISSION OWNER’S INTERCONNECTION

FACILITIES

As the PCO and the POI are co-located, there are no Connecting Transmission Owner’s 
Interconnection Facilities for this interconnection, and the Interconnection Customer and 
Connecting Transmission Owner have agreed that there will be no charges for operation and 
maintenance of Connecting Transmission Owner’s Interconnection Facilities under this 
Agreement.

D.	SCOPE OF WORK AND RESPONSIBILITIES

The Interconnection Customer shall be responsible for the construction of the

Interconnection Customer’s Interconnection Facilities.

E.	ESTIMATED COSTS OF CONNECTING TRANSMISSION OWNER’S

INTERCONNECTION FACILITIES

None.

F.	O&M EXPENSES FOR CONNECTING TRANSMISSION OWNER’S

INTERCONNECTION FACILITIES

None.

2-2

SERVICE AGREEMENT NO. 2833

Attachment 3

One-line Diagram Depicting the Small Generating Facility, Interconnection Facilities, Metering Equipment, and Upgrades

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

3-1

SERVICE AGREEMENT NO. 2833

Attachment 4

Milestones

1.  Milestones

The following milestones shall apply to the engineering, procurement, and construction 
activities related to the interconnection of the Small Generating Facility.  With the exception of 
the In-Service Dates and Commercial Operation Date, the timeframes projected for the 
milestones are non-binding estimates. The In-Service Dates and Commercial Operation Date can 
only be extended in accordance with the requirements set forth in the NYISO OATT.  The actual 
dates for completion of the milestones are highly dependent upon system reliability, lead times 
for the procurement of equipment and material, release of engineering packages by the 
Interconnection Customer and approval of the “issued for construction” packages by Connecting 
Transmission Owner, the availability of labor, approved outage scheduling, receipt of regulatory 
approvals, and the results of equipment testing.  The below proposed dates with the Connecting 
Transmission Owner as the responsible party are achievable provided that (i) this Agreement is 
signed by all parties in January 2024 and (ii) the Interconnection Customer confirms that the 
means of communication between the protective devices at the  Little Pond Station and the 
remote ends, Shoemaker Station, Mongaup Station, and Cuddebackville Station, shall be 
established before construction of the Other SUFs concludes.

In-Service Date:	January 2025

Critical milestones and responsibility as agreed to by the Parties:

MILESTONE

1.	Engineering start (SUF)

2.	Procurement start (SUF)

3.	Engineering start (Other SUF)

4.	Procurement start (Other SUF)

5.	Construction start (SUF)

6.	Engineering end (SUF)

7.	Construction start (Other SUF)

8.	Procurement end (Other SUF)

9.	Engineering end (Other SUF)

10.	Procurement end (SUF)

11.	Construction end (SUF)

12.	Construction end (Other SUF)

DATE	RESPONSIBLE

PARTY

Completed	Interconnection Customer

Completed	Interconnection Customer

March 2024	Connecting Transmission

Owner

April 2024	Connecting Transmission

Owner

August 2024	Interconnection Customer

August 2024	Interconnection Customer

October 2024	Connecting Transmission

Owner

November 2024	Connecting Transmission

Owner

December 2024	Connecting Transmission

Owner

December 2024	Interconnection Customer

January 2025	Interconnection Customer

January 2025	Connecting Transmission

Owner

4-1

SERVICE AGREEMENT NO. 2833

13.	Complete walk down and punchlist

14.	Utility acceptance of SUFs

15.	Initial Synchronization Date

16.	SUFs complete

17.	Other SUFs complete

18.	In-Service Date

19.	Transfer Little Pond Station title

20.	Commercial Operation Date

January 2025	Connecting Transmission

Owner

January 2025	Connecting Transmission

Owner

January 2025	Interconnection Customer

January 2025	Interconnection Customer

January 2025	Connecting Transmission

Owner

January 2025	Interconnection Customer

January 2025	Interconnection Customer 
January 2025 	Interconnection Customer

2.  Security to be Posted

At least twenty (20) Business Days prior to Interconnection Customer’s issuance of

written authorization to proceed with engineering and procurement contemplated by Milestone 3 
in the table contained in Section 1 of this Attachment 4, Interconnection Customer shall provide 
to Connecting Transmission Owner security in the form of a letter of credit in accordance with 
Section 6.3 of this Agreement and a signed security agreement, by and between the 
Interconnection Customer and the Connecting Transmission Owner, in a form that is acceptable 
to the Connecting Transmission Owner in its sole discretion to the extent not inconsistent with 
this Agreement or the NYISO OATT, securing the performance of the Interconnection 
Customer’s obligations under this Agreement with respect to the Other System Upgrade 
Facilities at remote ends Shoemaker Station, Mongaup Station, and Cuddebackville Station, in 
the amount of $1,018,060 for the estimated cost of such Other System Upgrade Facilities 
described in Attachment 6 of this Agreement.

4-2

SERVICE AGREEMENT NO. 2833

Attachment 5

Additional Operating Requirements for the New York State Transmission System, the Distribution System and Affected Systems Needed to Support the Interconnection 
	Customer’s Needs

1.  Additional Operating Requirements

The NYISO, in consultation with the Connecting Transmission Owner, shall also provide requirements that must be met by the Interconnection Customer prior to initiating parallel 
operation with the New York State Transmission System or the Distribution System.

The Interconnection Customer must comply with all applicable NYISO tariffs and procedures, as amended from time to time.

The Interconnection Customer must comply with relevant provisions of the Connecting 
Transmission Owner’s Electric System Bulletin (O&R - ENGR - 006: Facility Connection 
Requirements for New Generation, Merchant Transmission And End-User Facilities (Revision 1

- December 1, 2015), including appendices, as amended from time to time, Switching Operating Instruction Manuals, and Transmission Operations Manual (Manual 02), to the extent not 
inconsistent with the terms of this Agreement or applicable NYISO tariffs and procedures, as amended from time to time.

The Interconnection Customer shall provide real-time verbal notifications to the Connecting Transmission Owner’s O&R Energy Control Center prior to connecting or disconnecting any of its inverters.

2.  Additional Agreements

The security agreement described in Attachment 4 and all of the agreements described in 
this Attachment are referred to collectively as the “Additional Agreements”.  It is the belief and 
intention of the Interconnection Customer and the Connecting Transmission Owner that nothing 
in the Additional Agreements conflicts in any material way with this Agreement.  If the 
Connecting Transmission Owner or Interconnection Customer becomes aware of a conflict, such 
party shall notify the other party promptly so that the Connecting Transmission Owner and 
Interconnection Customer can mutually agree upon an amendment, if needed, of such Additional 
Agreement.  The NYISO is not a party to, has no responsibility under, and shall have no liability 
in connection with the Additional Agreements.  All Additional Agreements must be in form and 
substance acceptable to the Connecting Transmission Owner in its sole discretion.

a. 	Transfer of Title to Equipment: Upon completion of construction and testing of

(i) the Little Pond Station, (ii) the SASUF’s described in Section B of Attachment 
6, and (iii) the SUFs described in Section C(i) of Attachment 6 (the equipment 
described in the foregoing subsections (i), (ii) and (iii) are collectively, the “CTO 
Equipment”) by the Interconnection Customer and acceptance of the CTO 
Equipment by the Connecting Transmission Owner,  Interconnection Customer 
will transfer title to the CTO Equipment (not including any underlying real estate) 
to the Connecting Transmission Owner, free and clear of any liens and

5-1

SERVICE AGREEMENT NO. 2833

encumbrances, except those mutually agreed to by the Interconnection Customer 
and the Connecting Transmission Owner pursuant to an Additional Agreement.

b. 	Conveyance of Easement for the Little Pond Station:  Upon completion of

construction and testing of the CTO Equipment by the Interconnection Customer 
and acceptance of the CTO Equipment by the Connecting Transmission Owner, 
Interconnection Customer shall cause the applicable fee owner to grant the 
Connecting Transmission Owner a perpetual and exclusive easement (the “Little 
Pond Station Easement”), at the sole cost and expense of Interconnection 
Customer, that is acceptable to the Connecting Transmission Owner, that will 
give the Connecting Transmission Owner rights to access, locate, operate, 
maintain, inspect, repair, alter, upgrade, install, construct, and replace the CTO 
Equipment and electric transmission and distributing lines, cables and wires, 
telecommunications lines, cables and wires, conduit, gas mains, transformers, 
switches, and all other related facilities, equipment, and appurtenances thereto 
within the designated area described on Attachment 5-1 (the “Little Pond Station 
Parcel”), provided that the Little Pond Station Parcel is acceptable to the 
Connecting Transmission Owner in the sole discretion of the Connecting 
Transmission Owner, including, without limitation, that the Little Pond Station 
Parcel is free and clear of any liens and encumbrances, except those mutually 
agreed to by the Interconnection Customer and Connecting Transmission Owner. 
The Little Pond Station Easement shall include, without limitation, (i) the 
perpetual right of ingress and egress in, upon, along, over, through and across 
adjoining property for the Connecting Transmission Owner to have free and 
complete access to the Little Pond Station and such other related facilities at all 
times from a public road; (ii) that not more than twelve (12) months after the 
Commercial Operation Date of the Small Generating Facility, such access shall be 
provided on a road paved in accordance with the Connecting Transmission Owner 
specifications at the sole cost and expense of Interconnection Customer; (iii) that 
until such paving of such access road, the Connecting Transmission Owner shall 
have no liability to the Interconnection Customer for damage to any roads used 
for access resulting from reasonable snow removal operations; and (iv) that the 
applicable fee owner shall continue to be responsible for the payment of real 
estate taxes attributable to the Little Pond Station Parcel.  The Little Pond Station 
Easement shall be executed simultaneously with the transfer of the CTO 
Equipment to the Connecting Transmission Owner.  Any due diligence performed 
by the Connecting Transmission Owner with respect to the Little Pond Station 
Parcel shall be at the sole cost and expense of the Interconnection Customer.  In 
the event that the applicable fee owner does not execute the Little Pond Station 
Easement as contemplated in this subsection (b) for any reason, (A) such failure 
shall constitute a Breach of this Agreement that is subject to the Breach and 
Default requirements in Article 7.6 of this Agreement, and (B) the 
Interconnection Customer shall reimburse the Connecting Transmission Owner 
for all costs and expenses incurred in connection with inspections and due 
diligence relating to the CTO Equipment and Little Pond Station Parcel.

5-2

SERVICE AGREEMENT NO. 2833

c. 	Conveyance of Easement on Adjoining Land.  Prior to and as a condition of the

Connecting Transmission Owner’s acceptance of the CTO Equipment, and

execution of the Little Pond Station Easement, the Interconnection Customer shall 
cause (i) the conveyance of an easement by the third party owner of the land 
adjoining the Little Pond Station Parcel (owned in fee by The Hartwood Club, 
Inc. as of the date of this Agreement) (the “Hartwood Land”) to the Connecting 
Transmission Owner that permits access, location, operation, maintenance, 
inspection, repair, alteration, upgrading, installation, construction and replacement 
of electric transmission and distributing lines, cables and wires, 
telecommunications lines, cables and wires, conduit, gas mains, transformers, 
switches, and all other related facilities, equipment and appurtenances thereto 
(collectively, the “Connection Facilities”) within an area approved by the 
Connecting Transmission Owner, and (ii) the issuance of a no-objection letter (the 
“No-Objection Letter”) relating to the Connection Facilities addressed to the 
Connecting Transmission Owner from the owner of the pipeline under the 
Hartwood Land (the “Pipeline Owner”), which shall be an Additional Agreement. 
Upon completion of construction of the Connection Facilities, as may be 
requested by the Connecting Transmission Owner, any access road and related 
facilities installed on the Hartwood Land in connection with the installation of the 
Connection Facilities shall be left in place.  Interconnection Customer shall 
comply with the requirements set forth in the No-Objection Letter prior to the 
transfer of the transfer of the CTO Equipment to the Connecting Transmission 
Owner.   Any compliance required to satisfy the Pipeline Owner’s requirements 
within the eighteen (18) month period following the transfer of the CTO 
Equipment to the Connecting Transmission Owner relating to (A) unacceptable 
levels of AC or DC stray current and (B)  working with the Pipeline Owner to 
perform cooperative interference testing of the corrosion protection systems and 
the mitigation of any interference, shall be in either case performed by the 
Interconnection Customer at the sole cost and expense of the Interconnection 
Customer.

d. 	Liability for Little Pond Station Parcel and Adjoining Land.  Among other

things, the Interconnection Customer assumes liability for and shall at all times 
indemnify, defend, and save harmless, as applicable, the Connecting 
Transmission Owner, to the extent not in conflict with Article 7.3 of this 
Agreement, from, any and all damages, losses, claims, demands, suits, recoveries, 
costs and expenses, court costs, attorney fees, liabilities and all obligations by or 
to third parties (including without limitation any Governmental Authority), arising 
out of or resulting from any (i) actual or alleged violation of any Environmental 
Law, or (ii) release, threatened release or presence of any Hazardous Substances, 
in each case of (i) and (ii), existing on, under, or in connection with the Little 
Pond Station Parcel and the Little Pond Station and the Hartwood Land on or 
before the date on which the CTO Equipment is accepted by and transferred to the 
Connecting Transmission Owner.

The Interconnection Customer shall comply with the Terms attached hereto as

Attachment 10, to the extent not inconsistent with the terms of this Agreement or

5-3

SERVICE AGREEMENT NO. 2833

applicable NYISO tariffs and procedures, as amended from time to time, in

connection with the installation of the CTO Equipment within the Connecting 
Transmission Owner’s existing right of way located on the Hartwood Land.

e.  Construction of Permanent Air Bridge if Required.  Interconnection Customer 
	shall have the Pipeline Owner or operator of the TCE pipeline confirm in writing 
	the conditions upon which such Pipeline Owner or operator would require the 
	construction of an air bridge over such pipeline.  If any of the vehicles or equipment 
	that the Connecting Transmission Owner plans to use to travel over such pipeline 
	as disclosed in writing to Interconnection Customer, which vehicles shall not 
	exceed 60,000 pounds in total vehicle weight, would require the construction of an 
	air bridge, Interconnection Customer shall construct and convey to Connecting 
	Transmission Owner a permanent air bridge across the right of way of the TCE 
	pipeline lien free that satisfies the Pipeline Owner or operator requirements 
	simultaneously  with the conveyance of the Little Pond Easement to the Connecting 
	Transmission Owner.

5-4

SERVICE AGREEMENT NO. 2833

Attachment 5-1

Little Pond Station Parcel

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

5-5

SERVICE AGREEMENT NO. 2833

Attachment 6

Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of 
	Upgrade Costs

The NYISO, in consultation with the Connecting Transmission Owner, shall describe Upgrades and provide an itemized best estimate of the cost, including overheads, of the 
Upgrades and annual operation and maintenance expenses associated with such Upgrades.  The Connecting Transmission Owner shall functionalize Upgrade costs and annual expenses as either transmission or distribution related.

The cost estimate for System Upgrade Facilities and System Deliverability Upgrades

shall be taken from the ISO OATT Attachment S cost allocation process or applicable

Interconnection Study, as required by Section 32.3.5.3.2 of Attachment Z.  The cost estimate for Distribution Upgrades shall include the costs of Distribution Upgrades that are reasonably 
allocable to the Interconnection Customer at the time the estimate is made, and the costs of any Distribution Upgrades not yet constructed that were assumed in the Interconnection Studies for the Interconnection Customer but are, at the time of the estimate, an obligation of an entity other than the Interconnection Customer.

The cost estimates for Distribution Upgrades, System Upgrade Facilities, and System Deliverability Upgrades are estimates.  The Interconnection Customer is ultimately responsible for the actual cost of the Distribution Upgrades,  System Upgrade Facilities, and System 
Deliverability Upgrades needed for its Small Generating Facility, as that is determined under Attachments S, X, and Z of the ISO OATT.

A.	DISTRIBUTION UPGRADES

None.

B. 	SYSTEM UPGRADE FACILITIES (“SUF”) - STAND ALONE SUFs

The Small Generating Facility will interconnect to Connecting Transmission Owner’s

transmission facilities that are part of the New York State Transmission System via the new three

(3) breaker line tap Little Pond Station.

As depicted on the one line-diagram in Attachment 3, the PCO and the POI are co-

located at the generator tie line termination at the 69 kV insulators on the Little Pond Station’s termination structure.

The Stand Alone System Upgrade Facilities (“SASUF”) shall consist of the following:

•   relays as follows:

o   SEL-411 for primary current differential, backup distance, overcurrent and

breaker failure (“BF”) protection, with associated direct transfer trip (“DTT”) and BF lockout relays;

o   GE D60 for back up line distance, overcurrent protection and breaker failure 
	protection, with associated DTT and BF lockout relay;

6-1

SERVICE AGREEMENT NO. 2833

o   SEL-487B for primary bus differential protection, with associated bus lockout 
	relay; and

o   GE B30 for back up bus differential protection, with associated bus lockout relay.

•	Conduit and cable system;

•	Power, protection, control and communication cables;

•	Three (3) 69 kV, 2000 A, sulfur hexafluoride (“SF6”), three-phase dead tank circuit

breakers, with 2000:5 multi-ratio (“MR”) bushing current transformers (“CTs”);

•	Three (3) 69 kV, 2000 A, three-phase, group operated, horizontal disconnect switches;

•	Three (3) 69 kV, 2000 A, three-phase, group operated, vertical disconnect switches;

•	Nine (9) single-phase, 57 kV duty cycle surge arresters;

•	Five (5), single-phase, 69 kV potential transformer (“PT”) units;

•	Three (3) single-phase, 69 kV station service PTs, 25 kVA;

•	80kW Diesel Generator

•	Connecting Transmission Owner, NYISO and NY PSC approved revenue grade meter

and remote terminal unit (“RTU”);

•	Three (3) 69 kV revenue metering PTs and CTs;

•	Prefabricated Connecting Transmission Owner Standard Control Enclosure:

o   Bus differential panels (SEL-487B & GE B30);

o   Line/breaker protection panels (SEL-411 (2) & GE D60 (2));

o   Revenue metering panel;

o   Connecting Transmission Owner, NYISO and NY PSC approved revenue grade 
	meter;

o   Communication cabinet;

o   Security cabinet;

o   Human machine interface (“HMI”);

o   AC panel;

o   DC panel;

o   Battery system;

o   RTU (SEL-3530 RTAC);

o   Annunciator;

o   HVAC;

•	Bus support insulators and dead end insulators;

•	All high voltage conductor and taps;

•	All connectors;

•	Perimeter and structure LED lighting;

•	Fencing:

o   Perimeter;

o   Two (2) vehicle access gates;

o   One (1) man gate;

•	Access road (estimated 1½ mile);

•	Paved driveway in station;

•	Station Structures: Two (2) bay 69 kV line galvanized steel transmission line terminal

take off structures (H-frame) on concrete foundations with transmission line attachment 
equipment designed in accordance with O&R Structural Loading Criteria, Rev 9.  Phase 
spacing shall meet or exceed existing phase spacing for design voltage, generator tie line 
dead end, disconnect switches, station service potential transformer (“SSPT”), bus PTs,

6-2

SERVICE AGREEMENT NO. 2833

CT/PT metering units, lighting poles, lighting and dynasphere attachments, and bus support structures;

•   Foundations: Two bay line termination, generator tie line dead end, disconnect switches, 
	SSPT, bus PTs, CT/PT metering unites, lighting poles, diesel generator, control house 
	enclosure, dynasphere and bus support foundations; and

•   Storm water and drainage facilities.

SUF grounding shall be in accordance with IEEE Std. 80 and Connecting Transmission Owner standards. A grounding study shall be conducted to ensure the grounding requirements of Connecting Transmission Owner are met.  A lightning study shall be conducted to confirm that the SUFs are protected per Connecting Transmission Owner standards.

C.	SYSTEM UPGRADE FACILITIES (“SUF”) - OTHER SUFs

i.	SUFs at Little Pond Station

The Little Pond Station will split the existing 69 kV Mongaup - Cuddebackville Line 131 
transmission line at Structure “A”.  Structure “A” is an existing double circuit lattice structure for 
Line 131 and Line 12 that will be replaced by three (3) new dead end monopole structures; two

(2) monopoles to intercept the existing Line 131 into the Little Pond Station , and the third to support Line 12. The split of Line 131 will result in two new lines, Line 132 Mongaup - Little Pond Station and Line 131 Little Pond Station - Cuddebackville.  The other SUFs (“Other SUFs”) for the new Little Pond Station shall consist of the following:

•   Three (3) 69 kV, single circuit, dead end, vertical galvanized steel monopole transmission 
	structures on concrete foundations, with transmission line attachment equipment;

o   The three (3) steel poles shall be designed in accordance with O&R Structural 
	Loading Criteria, Rev 9.  Phase spacing shall meet or exceed existing phase 
	spacing.  Phase conductors and shield wires utilized for design shall be three (3) 
	795 aluminum-conductor steel-reinforced (“ACSR”) 45/7 tern at 6,000 lbs 
	National Electric Safety Code (“NESC”) heavy tension, two (2) 7#7 alumoweld 
	shield wires at 4,000 lbs NESC heavy tension;

•   Evaluate and analyze structures adjacent to Structure “A”.  Modify, upgrade and 
	reinforce adjacent structures, if necessary;

•   Install new steel monopole and dead end Line 12;

•   Install two (2) new steel monopoles and dead end Line 131;

•   Break Line 131 into new Line 131 and Line 132 transmission lines that will be tied into 
	the Little Pond Station;

•   Remove Structure “A”;

•   Run transmission line into and out of the Little Pond Station (extension of Line 131 and 
	new section Line 132); and

•   Transmission structures shall be grounded to achieve a maximum resistance of 10 ohms 
	or less.

Note: Double circuit outages may not be approved by Connecting Transmission Owner or NYISO.  Connecting Transmission Owner may not allow outages during the Summer 
Operating Period which occurs during May 15 through September 15.

6-3

SERVICE AGREEMENT NO. 2833

ii.  SUFs at Mongaup 69 kV Station

The interconnection of the Small Generating Facility requires system modifications at the 
Connecting Transmission Owner’s existing Mongaup Station.  The SUFs shall consist of the 
following:

•   Establishment of a means of tripping and monitoring the status of the POI breaker prior 
	to auto-reclosing the remote Mongaup Station during momentary faults;

•   Establishment of fast clearing at the Mongaup Station for a stuck breaker condition.

•   Replacement of line protection system for Line 132;

•   Communication between Little Pond Station and Mongaup Station (leased line); and

•   Primary and backup DTT schemes.

iii. SUFs at Cuddebackville 69 kV Station

The interconnection of the Small Generating Facility requires system modifications at the Connecting Transmission Owner’s existing Cuddebackville Station.  The SUFs shall consist of 
the following:

•   Establishment of a means of tripping and monitoring the status of the POI breaker prior 
	to auto-reclosing the remote Cuddebackville Station during momentary faults;

•   Establishment of fast clearing at the Cuddebackville Station for a stuck breaker condition.

•   Replacement of line protection system for Line 131;

•   Communication between Little Pond Station and Cuddebackville Station (leased line); 
	and

•   Primary and backup DTT schemes.

iv. SUFs at Shoemaker 69 kV Station

The interconnection of the Small Generating Facility requires system modifications at the 
Connecting Transmission Owner’s existing Shoemaker Station.  The SUFs shall consist of the 
following:

•   Establishment of a means of tripping and monitoring the status of the POI breaker prior 
	to auto-reclosing the remote Shoemaker Station during momentary faults;

•   Establishment of fast clearing at the Shoemaker Station for a stuck breaker condition.

•   Modified line protection relay settings;

•   Replacement of line protection system for Line 131 and Line 13;

•   Communication between Little Pond Station and Shoemaker Station; and

•   Primary and backup DTT schemes.

D.	SCOPE OF WORK AND RESPONSIBILITIES

1.	Interconnection Customer’s Scope of Work and Responsibilities

As agreed upon by the Parties pursuant to Article 5.2 of this Agreement, the SASUFs

referenced above in Section B and the Other SUFs at the Little Pond Station referenced above in Section C(i) will be designed, procured, and constructed by the Interconnection Customer,

6-4

SERVICE AGREEMENT NO. 2833

subject to Connecting Transmission Owner’s review and approval, and in accordance with the Connecting Transmission Owner’s specifications and all applicable codes and standards, to the extent not inconsistent with NYISO Tariffs or procedures.

• 	Testing and commissioning requirements for SASUF to be completed by Interconnection

Customer based on testing requirements provided by CTO.

• 	Establishment of a means of communication between the protective devices at the new

Little Pond Station and the remote ends Shoemaker Station, Mongaup Station, and Cuddebackville Station.

• 	Connecting Transmission Owner will procure and install security equipment at the Little

Pond Station. Interconnection Customer is responsible for facilitating the infrastructure required for the security system. Cost of the Connecting Transmission Owner Security system to be reimbursed by Interconnection Customer.

• 	Multiple outages may be required for the transmission work. Interconnection Customer

shall be responsible for the reasonable cost associated with any additional work required 
for service continuity in accordance with Good Utility Practice, provided however that 
Connecting Transmission Owner shall provide Interconnection Customer an estimate of

the cost of such additional work prior to scheduling of any outage requiring such work. 
	All switching to be performed by Connecting Transmission Owner. 
 • The Interconnection Customer shall be responsible for performing short circuit studies 
	using the latest NYISO ASPEN case and developing relay settings as per Connecting 
	Transmission Owner’s protection specifications at the SASUF. The Connecting 
	Transmission Owner shall review and approve the short circuit study and relay settings 
	files prior to start of testing and commissioning at SASUF. The Interconnection 
	Customer shall provide a list of all the analog and digital points that will be connected to 
	the RTU. The Connecting Transmission Owner engineering team will provide the setting 
	files for the RTU devices only. The testing and commissioning from the RTU to the field 
	devices will be performed by Interconnection Customer. The Communication testing of 
	RTU to Connecting Transmission Owner’s O&R Energy Control Center shall be 
	performed by Connecting Transmission Owner staff.

• 	The Interconnection Customer shall be responsible for the design and construction of the

stormwater management system (the “Stormwater System”) and for maintenance of the 
Stormwater System until the Commercial Operation Date of the Small Generating 
Facility.  On and after the Commercial Operation Date of the Small Generating Facility, 
the Connecting Transmission Owner shall be responsible for the operation and 
maintenance of the Stormwater System, as noted below, provided that (i) the design for 
the Stormwater System shall be subject to the review, comment, and acceptance of the 
Connecting Transmission Owner prior to submittal to the applicable municipality in 
connection with permitting, and any changes to such design shall be subject to the prior 
review, comment and acceptance by the Connecting Transmission Owner, (ii) the internal 
and external costs of the Connecting Transmission Owner attributable to its review and 
comment described in subsection (i) of this paragraph shall be reimbursed by the 
Interconnection Customer within 30 days of receipt of invoice, (iii) the Stormwater 
System shall be constructed in accordance with the design accepted by the Connecting 
Transmission Owner, (iv) the Connecting Transmission Owner shall only be responsible 
for the operation and maintenance of the Stormwater System to the extent located within 
the Little Pond Station Parcel or along the access road from the public road to the Little

6-5

SERVICE AGREEMENT NO. 2833

Pond Station Parcel, and shall not be responsible for the operation or maintenance of the 
Stormwater System in other locations, including, without limitation, to the extent located 
inside of the Little Pond Solar Collector Substation yard or in the solar field, (v) any 
Stormwater System maintenance agreement contemplated with the applicable 
municipality shall be subject to the review, comment, and acceptance by the Connecting 
Transmission Owner prior to execution by the Interconnection Customer and the 
applicable municipality, and a copy of such fully executed agreement shall be provided to 
the Connecting Transmission Owner promptly upon its execution, (vi) the Little Pond 
Station Easement shall provide for the Connecting Transmission Owner’s obligations 
relating to the Stormwater System, including, without limitation, the grant of easement 
rights for the Connecting Transmission Owner to comply with such obligations and (vii) 
the Connecting Transmission Owner shall not be liable for storm or stormwater damage 
or other damage to the Interconnection Customer’s facilities not caused by the 
Connecting Transmission Owner (including any water runoff that exceeds the design 
capability of the Stormwater System).

2. 	Connecting Transmission Owner’s Scope of Work and Responsibilities

The SUFs located at the Little Pond Station will be owned, operated, and maintained by 
the Connecting Transmission Owner.  The SUFs located at the Little Pond Station and Other 
SUFs in Section C(i) of this Attachment 6 will be designed, procured and constructed by the 
Interconnection Customer subject to Connecting Transmission Owner’s review and approval, 
and in accordance with the Connecting Transmission Owner’s specifications. Connecting 
Transmission Owner’s Engineering Department will be reviewing and approving those designs. 
Connecting Transmission Owner may conduct construction oversight to Connecting 
Transmission Owner’s satisfaction. Connecting Transmission Owner will perform final 
checkout.  Within three months of completing the construction and installation of the SUFs, the 
Connecting Transmission Owner shall provide the Interconnection Customer with a final 
accounting report in accordance with Article 6.1.2 of this Agreement.  For purposes of the 
foregoing, completion of the construction and installation of the SUFs shall occur upon the 
Connecting Transmission Owner’s acceptance of the SUFs.  The costs associated for the review 
and approval of Interconnection Customer’s designs and construction oversight and checkout are 
included in Section E of this Attachment 6 below. These costs are to be reimbursed to the 
Connecting Transmission Owner by the Interconnection Customer.

Connecting Transmission Owner will procure and install security equipment at the Little Pond Station. Cost of the Connecting Transmission Owner Security system to be reimbursed by Interconnection Customer.

The remote, non-local SUFs referenced above in Sections C(ii), C(iii), and C(iv) will be designed, procured, and constructed by the Connecting Transmission Owner.

Connecting Transmission Owner shall:

▪   Conduct final phasing and required checkouts to Connecting Transmission 
	Owner’s system.

6-6

SERVICE AGREEMENT NO. 2833

E.	COST ESTIMATES RELATED TO DISTRIBUTION UPGRADES AND SYSTEM

UPGRADE FACILITIES

Description	Estimated Costs

Stand Alone System Upgrade Facilities	$5,888,600

Other System Upgrade Facilities - Little	$1,682,000

Pond Station

Other System Upgrade Facilities -	$1,018,060

Remote Stations

Total	$8,588,660*

*This amount includes, in 2020 dollars, $930,984 in Connecting Transmission Owner 
review and oversight costs for Interconnection Customer’s design and construction of the Stand 
Alone System Upgrade Facilities and the Other System Upgrade Facilities at the Little Pond 
Station.  Escalated to 2023 dollars, the total for O&R Review and Oversight Costs are 
$1,061,986.

6-7

SERVICE AGREEMENT NO. 2833

Attachment 7

Insurance Coverage

Interconnection Customer shall, at its own expense, maintain in force throughout the period of this Agreement, the following minimum insurance coverage, with insurers authorized to do business in the State of New York:

Commercial General Liability Insurance, including but not limited to, premises and

operations, personal injury, broad form property damage, broad form blanket contractual liability coverage products and completed operations coverage, coverage for explosion, collapse and 
underground hazards, independent contractors coverage, coverage for pollution to the extent 
normally available and punitive damages to the extent normally available using Insurance 
Services Office, Inc. Commercial General Liability Coverage (“ISO CG”) Form CG 00 01 04 13 or a form equivalent to or better than CG 00 01 04 13, with minimum limits of two million 
dollars ($2,000,000) per occurrence and five million dollars ($5,000,000) aggregate combined single limit for personal injury, bodily injury, including death and property damage.  A 
combination of Primary and Excess Liability is acceptable.

The insurance policy or policies shall be on an “occurrence” and not “claims-made” form of 
coverage and be in effect for at least three (3) years after completion of performance.  The 
insurance policy or policies shall be primary and non-contributory and name Consolidated 
Edison, Inc., Consolidated Edison Company of New York, Inc. and Orange & Rockland 
Utilities, Inc., Rockland Electric Company, Inc. and their subsidiary companies as additional 
insureds with respect to the Work and completed operations.  Endorsements CG 20 10 04 13 and 
CG 20 37 04 13 (or equivalent) are required. The policy will contain a waiver of subrogation.

Interconnection Customer shall carry statutory Workers Compensation and Employers Liability.

7-1

SERVICE AGREEMENT NO. 2833

Attachment 8

Initial Synchronization Date

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Orange and Rockland Utilities, Inc. Attn: Vice President, Operations 390 West Route 59

Spring Valley, NY 10977

Re:  Little Pond Solar Project Small Generating Facility

Dear	:

On [Date] [Interconnection Customer] initially synchronized the Small Generating Facility [specify units, if applicable].  This letter confirms that [Interconnection Customer]’s Initial Synchronization Date was [specify].

Thank you.

[Signature]

[Interconnection Customer Representative]

8-1

SERVICE AGREEMENT NO. 2833

Attachment 9

Commercial Operation Date

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Orange and Rockland Utilities, Inc. Attn: Vice President, Operations 390 West Route 59

Spring Valley, NY 10977

Re:    Little Pond Solar Project Small Generating Facility

Dear __________________:

On [Date] [Interconnection Customer] has completed Trial Operation of Unit No.  ___.  This 
letter confirms that [Interconnection Customer] commenced Commercial Operation of the 
Small Generating Facility [specify units, as applicable], effective as of [Date plus one day].

Thank you.

[Signature]

[Interconnection Customer Representative]

9-1

SERVICE AGREEMENT NO. 2833

Attachment 10

TERMS AND CONDITIONS Of

ORANGE AND ROCKLAND UTILITIES, INC. 
	CONSTRUCTION PROJECTS

Reference Number

For use with the Small Generator Interconnection Agreement by and among the New York

Independent System Operator, Inc.; Orange and Rockland Utilities, Inc.; and Little Pond Solar, 
LLC.

10-1

SERVICE AGREEMENT NO. 2833

1.	Definitions.  For purposes of these Terms and Conditions, the following definitions shall

apply:

Agreement	-

Connecting 
Transmission Owner

The  Small  Generator  Interconnection  Agreement  by  and  among Interconnection Customer, the NYISO and Connecting Transmission Owner, including all Appendices and Attachments to same and any and all  plans,  schedules,  specifications,  addenda  drawings  and  other documents, to the extent that they are directly or indirectly incorporated by reference in the Agreement.

Orange and Rockland Utilities, Inc.

Interconnection Customer	-	Little Pond Solar, LLC

Site	-	The area under and around Connecting Transmission Owner’s 69kV

Transmission Line L12/131 in which Interconnection Customer is to construct and install the equipment described in Attachment 6(C)(i) to effect   the   interconnection   of   Interconnection   Customer’s   Small Generating Facility.

Terms	-	These Terms and Conditions for Construction Projects .

Subcontractor	-	Any company or person, other than an employee of Interconnection

Customer, that furnishes any of the Work on behalf of Interconnection Customer.

Work	-	The construction and installation of the System Upgrade Facilities

(SUFs) described in Attachment 6(C)(i) within Connecting Transmission 
Owner ROW, and all labor and supervision, construction materials, 
equipment, tools and other aids to construction; equipment, materials, 
and other things of any nature necessary or proper for the completion of 
the project at the Site, whether or not expressly specified herein.

The words “hereof,” “herein,” “hereto” and “hereunder” as used in these Terms shall refer to these Terms, unless the context indicates otherwise.

2.	Specifications, Plans, and Drawings.

(a)	The  Work  shall  be  performed  in  strict  accordance  with  the

Agreement and the specifications, plans, and drawings.  No deviation is permitted 
unless approved in advance in writing by Connecting Transmission Owner.  The 
specifications, plans, and drawings and all other documents which are part of the 
Agreement are supplementary to each other.  Anything called for by any one of 
such documents shall be required to the same extent as if called for by all of them, 
and the Work shall be completed in every detail whether or not every item is 
specifically mentioned.  If there should be a conflict between the drawings and the

10-2

SERVICE AGREEMENT NO. 2833

writings that comprise the plans and specifications, the writings shall govern unless 
upon notice thereof Connecting Transmission Owner directs otherwise in writing.

(b) 	Connecting Transmission Owner may furnish to Interconnection 
Customer any additional plans, drawings, specifications or other documents which 
it considers necessary to illustrate or explain the Work in further detail, and 
Interconnection  Customer  shall  comply  with  the  requirements  of  all  such 
documents, provided that Connecting Transmission Owner may not change the 
scope of the Work without the written consent of Interconnection Customer and 
NYISO.

(c) 	Interconnection Customer shall, or shall cause the Subcontractors to, throughout the time during which the Work is being performed, keep at the Site available for inspection by Connecting Transmission Owner one complete and current set of the Agreement documents, including, but not limited to, the Agreement plans, specifications, and drawings, any additional documents furnished by Connecting Transmission Owner, and all shop and work drawings approved by Connecting Transmission Owner.

(d) 	Where required by the Agreement, Interconnection Customer shall, or shall cause the Subcontractors to, submit designated documents, such as drawings  and  process  procedures,  for  review  and  approval  by  Connecting Transmission Owner.  All proposed changes to or deviations from such documents after they have been approved shall also be submitted to Connecting Transmission Owner for review and approval prior to their implementation.

3.	Safeguards in Work.

(a)	Interconnection Customer shall, or shall cause the Subcontractors

to, provide and maintain at its/their own expense safe and sufficient entrance and 
exit ways, walkways, platforms, barricades, warning lights, scaffolds, ladders, 
runways for concrete carriers, hoists and all equipment, apparatus and appliances 
necessary or proper for carrying on the Work safely; shall not load any of the 
foregoing items or any part of any structure or equipment with a weight that will 
make it unsafe; shall make and keep the place of Work and the ways and approaches 
thereto well lighted, safe and free from avoidable danger, taking into account, 
without limitation, local conditions; and shall mark any faulty items “unsafe” until 
repaired  or  replaced. Subcontractor  movement  to  and  from  Connecting

Transmission Owner existing rights of way shall be confined to approved access 
roads and pathways as shown on the project plan and profile.  All other access shall 
be arranged by the subcontractor who will be responsible for all associated costs. 
Connecting Transmission Owner use of any access, outside the scope of the plan 
and profile, shall not confer the right for the subcontractor to use such access.

(b) 	Interconnection Customer shall, or shall cause the Subcontractors 
to, provide all permanent and temporary shoring, anchoring and bracing required 
by the nature of the Work to make all parts stable and rigid, even when such shoring,

10-3

SERVICE AGREEMENT NO. 2833

anchoring and bracing are not explicitly called for.  Interconnection Customer shall 
support and protect all buildings, bridges, roadways, conduits, wires, water pipes, 
gas pipes, sewers, pavements, curbing, sidewalks, fixtures and other public or 
private property that may be encountered or endangered in the prosecution of the 
Work.

(c) 	In accordance with the rest of this Attachment and without limitation thereof, Interconnection Customer shall, or shall cause the Subcontractors to, test all areas, excavations, openings, manholes, vaults and boxes, for an adequate supply of oxygen and for any and all toxic, harmful or combustible gases or fumes or other dangerous substances before and during the course of the Work and shall provide all the necessary equipment, including, but not limited to, all oxygen deficiency and gas testing apparatus required for such tests.

(d) 	Interconnection Customer shall, or shall cause the Subcontractors 
to, strictly observe safety requirements of applicable federal, state and municipal 
laws and regulations, including, without limitation, the Federal Occupational Safety 
and Health Act.  Interconnection Customer shall cause, or shall cause the 
Subcontractors to require, all equipment and structures, the place of Work and the 
ways and approaches thereto to meet the requirements of all governmental 
authorities.  Interconnection Customer shall maintain an accurate record of all cases 
of death, occupational disease or injury requiring medical attention or causing loss 
of time from work arising in connection with performance of the Work.

(e) 	Connecting Transmission Owner shall designate an authorized 
representative to monitor Interconnection Customer’s performance of the Work and 
shall promptly notify Interconnection Customer of such designation.  If in the 
opinion of Connecting Transmission Owner’s authorized representative the work 
practices or conditions created by Interconnection Customer are unsafe or fail to 
comply with applicable laws or regulations, Connecting Transmission Owner may 
halt the work until such practices and conditions are corrected.  If, when Connecting 
Transmission Owner’s authorized representative is not present at the site, a 
Connecting Transmission Owner employee directs Interconnection Customer to 
discontinue an operation because it may be unsafe or illegal, Interconnection 
Customer   shall   immediately   halt   the   questioned   operation   and,   if   the 
Interconnection Customer disagrees with the employee, shall contact Connecting 
Transmission Owner’s authorized representative for instructions.  Interconnection 
Customer shall obtain the employee’s name and employee identification number 
and report this information to Connecting Transmission Owner’s authorized 
representative.

(f) 	Interconnection Customer shall be responsible for any failure or neglect on its or its Subcontractor’s part to perform the obligations contained in this article, and shall defend and indemnify Connecting Transmission Owner against any liability resulting in whole or in part from such failure or neglect.

10-4

SERVICE AGREEMENT NO. 2833

4. 	Knowledge of Work Conditions and Requirements.

Interconnection Customer represents that it has visited and examined the site of the Work 
and satisfied itself as to the general and local conditions, particularly those relating to 
transportation, handling and storage of materials, availability of labor, water, drainage, 
power, roads, landing zones, weather, ground and other physical conditions at the site, and 
as to all other matters which could affect the Work.  Interconnection Customer also 
acknowledges that it has examined the specifications, drawings, and other Agreement 
documents and has satisfied itself as to the requirements of the Work, and has seen or had 
an opportunity to ask about all conditions which may affect the Work, including equipment 
or structures in place or to be in place, or work being or to be performed, which could 
interfere with the uninterrupted performance of the Work.  Interconnection Customer 
assumes any risk associated with its failure to examine the Work site, Agreement 
documents or all other available information provided to it prior to entering into the 
Agreement.

5.	Interconnection Customer’s Performance.

(a)	Interconnection Customer shall, or shall cause the Subcontractors

to, perform in good workmanlike manner and in accordance with Good Utility 
Practice all the Work required or reasonably implied by the Agreement, in 
accordance with the terms of the Agreement and such directions of Connecting 
Transmission Owner as any may be given from time to time.  Interconnection 
Customer’s performance shall include, except as otherwise specifically stated in the 
Agreement, everything requisite and necessary to complete the Work properly, 
notwithstanding the fact that not every item involved is specifically mentioned, 
including, but not limited to all materials, labor, tools, equipment, apparatus, water, 
lighting, heating, power, transportation, superintendence, temporary construction, 
site security and all other services and facilities of every nature necessary or 
appropriate for the execution of the Work on schedule.

(b) 	When work is performed on the Site, Interconnection Customer 
must provide at all times an on-site representative with full authority to act for 
Interconnection Customer.  The representative must be able to read, write, and 
thoroughly understand both English and any other languages spoken by persons 
performing work for Interconnection Customer and must be able to effectively 
communicate with those persons in their own language or languages.  In addition, 
Interconnection Customer’s representative must ensure that labeling, log book 
entries, completion of forms and all other tasks requiring a proficiency in English 
are performed clearly and correctly.  The continuation of the individual selected by 
Interconnection Customer in this role shall be subject to the continuing approval of 
Connecting Transmission Owner.

(c) 	Interconnection Customer shall, or shall cause the Subcontractors to, perform the Work in accordance with the following:

10-5

SERVICE AGREEMENT NO. 2833

(i) 	All equipment, tools, other construction aids and materials utilized by

Interconnection Customer and Subcontractors shall be of high quality and 
in good working order.  Interconnection Customer shall or shall cause the 
Subcontractors to, submit material safety data sheets (MSDS) for all

chemical and hazardous substances used in the Work.  If, in the opinion of 
Connecting Transmission Owner, any of Interconnection Customer’s or 
Subcontractor’s equipment, supplies, tools, other construction aids or 
materials are unsafe or inadequate, Interconnection Customer shall, or shall 
cause the Subcontractors to remove such items from the site immediately 
and replace them with safe and adequate substitutes at Interconnection 
Customer’s or Subcontractor’s expense.  Interconnection Customer shall be 
fully and solely responsible for and shall safeguard its equipment, tools, 
supplies, other construction aids and materials at all times.  Interconnection 
Customer shall, or shall cause the Subcontractors to provide adequate 
storage for all such items used in connection with the Work.

(ii) 	The use of public roadways and properties for the parking of employee

vehicles, construction equipment, receiving and placement shall be in accordance with the applicable laws and ordinances.  Access to all existing Connecting Transmission Owner rights of way shall be maintained and allowed during the entire performance of the Work.  Adjacent private properties shall not be entered or used for any such purpose without the written consent of the property owners.

(iii) 	Fire hydrants and stop valves adjacent to the Work shall be kept clear and

readily accessible to fire apparatus, and no material or other obstruction 
shall be placed, parked or stored within fifteen (15) feet of any hydrant or 
stop valve (or a greater distance if required by local law, rule or regulation). 
Interconnection Customer shall or shall cause the Subcontractors to, comply 
fully with all local rules and regulations relative to fire protection, shall keep 
the structure and premises free from burnable trash and debris, and shall 
exercise every precaution against fire.  This shall include, but not be limited 
to, posting a fire watch, with appropriate fire fighting equipment, during all 
welding, burning, stress relief and other heating operations.  Interconnection 
Customer shall, or shall cause the Subcontractors to, assure that the fire 
watch is informed of the site fire control procedures and remains posted 
during breakfast, lunch and dinner periods and until one hour after such 
heating operations have stopped.

6.	Connecting Transmission Owner’s Authority.

(a)	Connecting    Transmission    Owner,    in    consultation    with

Interconnection Customer, shall have the authority to decide any and all questions which arise in connection with the Work, and Connecting Transmission Owner’s decisions shall be conclusive and final.

10-6

SERVICE AGREEMENT NO. 2833

(b) 	Connecting Transmission Owner shall have the right to maintain a 
representative at the construction site.  Such representative may, on request, give 
Interconnection Customer reasonable assistance in interpreting the Agreement 
drawings,  specifications  and  plans,  but  such  assistance  shall  not  relieve 
Interconnection Customer of any duties (including, without limitation, those of 
giving notice to or securing the approval of Connecting Transmission Owner) 
arising under the Agreement.

7.	Warranties.

(a)	Interconnection Customer warrants the Work for a period of one (1)

year from the transfer of the Work, under the Agreement unless a longer period is specified or in an applicable municipal code or regulation, in which case the longer period shall apply:

(i) 	as to services, that they shall be rendered competently and by qualified

personnel in accordance with Good Utility Practice, and

(ii) 	as to materials, equipment, structures and other things, that they shall be

new and free from defects in title, material, workmanship and design, 
conform strictly to all applicable specifications, and be suitable for their 
intended use.  Interconnection Customer further warrants that the Work 
shall meet any and all tests and comply with all performance requirements 
contained in the Agreement.  The warranty of good title shall be unlimited 
in time.

(b) 	In the event any part or all of the Work fails to satisfy any of these 
warranties, upon written notice thereof from Connecting Transmission Owner to 
Interconnection  Customer,  Interconnection  Customer  shall,  at  no  cost  to 
Connecting Transmission Owner, promptly repair, replace, or reperform the 
defective Work, as directed by Connecting Transmission Owner, and do whatever 
else is necessary to cause the Work to satisfy all of the aforesaid warranties.  All 
work repaired, replaced or reperformed under the provisions of this Article shall be 
subject anew to this Article with the warranty period commencing upon completion 
of the repair, replacement, or reperformance.  If Interconnection Customer fails to 
correct any defective Work as aforesaid promptly after being notified thereof by 
Connecting Transmission Owner, then Connecting Transmission Owner may 
correct the defective work and charge Interconnection Customer for the costs and 
expenses it occurs in so doing.  Any defective parts removed in connection with 
repair or replacement shall be disposed of by Interconnection Customer at its 
expense.

8.	Labor.

(a)	Interconnection Customer shall, or shall cause the Subcontractors

to, unless otherwise specifically stated herein, provide all labor required to fully

10-7

SERVICE AGREEMENT NO. 2833

complete the Work.  This shall include all specialized workers that are required by 
the nature of the Work.  Interconnection Customer shall, or shall cause the 
Subcontractors to, employ on Work at the construction site only union labor from 
Building Trades locals having jurisdiction over the Work; to the extent such labor 
is available.  Interconnection Customer agrees to defend, save harmless and 
indemnify Connecting Transmission Owner, its trustees, officers, agents and 
employees against any and all liability arising in any way out of Interconnection 
Customer’s failure to comply with the foregoing provisions of this paragraph. 
Whenever Interconnection Customer knows or believes that any actual or potential 
labor dispute is delaying or threatening to delay the timely performance of the 
Work, Interconnection Customer shall immediately give Connecting Transmission 
Owner notice of the dispute, including all relevant information concerning the 
dispute.  If such notice is given orally, Interconnection Customer shall confirm it in 
writing within 24 hours.

(b) 	The Immigration Reform and Control Act of 1986 Pub. L. No. 99-
603 (the “Act”) makes it illegal for an employer to hire or employ an illegal alien. 
The Act also makes it a legal requirement for employers to establish an employment 
verification system which includes the employer’s checking specified documents 
to  establish  both  an  individual’s  identity  and  legal  authorization  to  work. 
Interconnection Customer represents and covenants that Interconnection Customer 
has complied and will comply with all the requirements of the Act with respect to 
all persons assigned or employed by Interconnection Customer in the performance 
of the Work.  Interconnection Customer agrees to defend, save harmless and 
indemnify Connecting Transmission Owner, its trustees, officers, agents and 
employees against any and all liability under the Act arising in any way out of 
services performed by or Connecting Transmission Owner’s use of persons 
furnished by Interconnection Customer.

(c) 	Interconnection  Customer  shall  not  employ  any  employee  of Connecting Transmission Owner or Consolidated Edison Company of New York, Inc.  to perform any Work without the prior written permission of Connecting Transmission Owner.

9. 	Permits, Codes, Laws and Regulations; Denial of Access and Removal for Noncompliance.

Interconnection Customer shall comply with and shall cause all its employees and Subcontractors 
(Interconnection Customer, its employees and any Subcontractors are known herein the “Permitted 
Persons”) to comply with all applicable laws, rules, regulations, and ordinances (including, but not 
limited to, Environmental Laws, as defined in the Agreement), as well as all regulations, 
procedures and directives of Connecting Transmission Owner.  Interconnection Customer shall be 
responsible for obtaining and maintaining all permits, licenses, and any other governmental 
permission required for, or in connection with, its portion of the Work Interconnection Customer 
shall cause any and all of the Permitted Persons who are not in compliance with such laws, rules, 
regulations, ordinances, procedures and directives or who otherwise engage in illegal conduct or 
conduct that threatens injury to persons or damage to property at the Site to be refused access to 
Site and, if present at the Site, to be immediately removed therefrom in a reasonable and peaceful

10-8

SERVICE AGREEMENT NO. 2833

manner.  If Interconnection Customer fails to comply with its obligations under the immediately 
preceding sentence, Connecting Transmission Owner, without any liability whatsoever to the 
Permitted Persons or others, may, but shall not be obligated to, cause any and all Permitted Persons 
who are not in compliance with such laws, rules, regulations, ordinances, procedures and directives 
to be refused access to the Site and to be immediately removed from the Site in a reasonable and 
peaceful manner.  Interconnection Customer shall defend, indemnify and hold Connecting 
Transmission Owner, its trustees, directors, officers, employees, affiliates and agents (collectively, 
the “Protected Parties”) harmless under the procedures applicable to the Section 7.3 indemnity in 
the Agreement from and against any and all claims, actions, causes of action, damages, loss and 
liability, including costs and expenses, legal and otherwise, and statutory or administrative fines, 
penalties, or forfeitures, which arise from or relate to refusing access to, removing, failing to refuse 
access to and/or failing to remove from the Site any and all Permitted Persons-so long as the actions 
of the Protected Parties do not amount to gross negligence or intentional wrongdoing.

10.	Quality Assurance/Quality Control.

Interconnection Customer shall establish and maintain a quality assurance/quality control program which shall include procedures for continuous control of all construction and comprehensive inspection and testing of all items of Work, including any Work performed by Subcontractors, so as to ensure conformance to the Agreement with respect to materials, workmanship, construction, finish, functional performance, and identification.  Interconnection Customer shall submit details of the Quality Assurance/Quality Control program accompanied by samples of all checklists and documentation with a detailed explanation of the process and frequency of document updates.  The Interconnection  Customer  shall  provide  Connecting  Transmission  Owner  with  complete installation details and checklists for each element (foundations, structures, wire and so forth) of the transmission line and substation portions of the project.  A complete compilation of all documents (including all required test reports) shall be included in a turnover package at the completion of the project to facilitate Connecting Transmission Owner compliance review and future operation and maintenance of the constructed facilities.

11.	Protection of Persons, Work and Property.

(a)	In  the  course  of  performing  the  Agreement,  Interconnection

Customer shall, or shall cause the Subcontractors to, at all times exercise reasonable 
precautions to protect persons and property and items of Work from physical injury 
or harm.  Interconnection Customer shall or shall cause the Subcontractors to, at 
its/their own expense design, furnish, and erect such barricades, fences and railings, 
give such warnings, display such lights, signals and signs, exercise such precautions 
against fire, adopt and enforce such rules and regulations, and take such other 
precautions as may be necessary, desirable or proper, or as may be reasonably 
directed by Connecting Transmission Owner.  Interconnection Customer shall, or 
shall cause the Subcontractors to, provide and maintain in good working order at 
all times an adequate, approved system for promptly extinguishing fires.  Fire 
alarms, extinguishing equipment and water lines shall be continually inspected by 
Interconnection Customer and shall at all-time be accessible and ready for 
immediate use.

10-9

SERVICE AGREEMENT NO. 2833

(b) 	Interconnection Customer shall, while on or about the Site, observe and comply with all fire, safety, hazard, “No Smoking”, and all other rules and regulations heretofore or hereafter prescribed by Connecting Transmission Owner. Safety hats shall be worn at all times in the Work area by Interconnection Customer’s employees.

(c) 	Interconnection Customer shall, or shall cause the Subcontractors 
to, at no additional cost to Connecting Transmission Owner, comply with all 
reasonable requests of Connecting Transmission Owner to enclose or specially 
protect Work, property or persons.  If Connecting Transmission Owner determines 
that Work, property or persons are not adequately protected after any such requests, 
then it may, without prejudice to any other rights it may have hereunder or under 
applicable law, order an immediate suspension of the Work in the affected area of 
the Site or take such steps as it deems reasonably necessary to protect Work, 
property or persons

(d) 	Interconnection  Customer  shall  promptly  report  in  writing  to 
Connecting Transmission Owner all accidents arising out of or in connection with 
the performance of the Agreement, whether on or adjacent to the construction site, 
which result in death, personal injury requiring medical treatment or absence from 
work or property damage, giving full details and statements of witnesses.  In 
addition, if death or serious injury or serious damage is caused, Interconnection 
Customer shall immediately report the accident by telephone to Connecting 
Transmission Owner.

(e) 	Interconnection Customer shall, or shall cause the Subcontractors to, provide at the construction site such equipment and medical facilities as are necessary to supply first aid service to any persons who may be injured in the course of performance of the Work and shall have standing arrangements for the removal and hospital treatment of such persons.  If any claim is made by any person against Interconnection Customer or any other contractor on account of any accident, Interconnection Customer shall promptly report it in writing to Connecting Transmission Owner, giving full details of the claim.

(f) 	Interconnection Customer will, or will cause the Subcontractors to, 
develop an Environmental Health and Safety Plan for Work on the Site that will be 
submitted  to  Connecting  Transmission  Owner  for  review.    Interconnection 
Customer will not be permitted to perform any field work until it has submitted to 
Connecting Transmission Owner and the Connecting Transmission Owner has 
accepted a site-specific health, safety, and environmental plan, which addresses all 
hazards that may be encountered, conforms to any and all requirements stated in 
the Agreement and incorporates all of the Connecting Transmission Owner’s 
comments on the plan.  The submitted plan for the transmission right-of-way shall 
provide a detailed “Emergency Response Plan” for each individual tower location 
and, for any tower locations within a rattlesnake area, a list of which hospitals have 
the appropriate anti-venom. The submitted plan shall also provide a description of 
any anticipated wastes that may be generated by the Interconnection Customer and

10-10

SERVICE AGREEMENT NO. 2833

its Subcontractors, including how waste will be stored, characterized, and disposed; the Interconnection Customer will not be permitted to transport any waste off-site or dispose of any waste until the Connecting Transmission Owner has reviewed and accepted the waste disposal scenario.

(g) 	If in the reasonable opinion of Interconnection Customer, greater precautions than those required herein or directed by Connecting Transmission Owner are reasonably advisable, Interconnection Customer shall implement such precautions and advise Connecting Transmission Owner thereof.  In the event of an emergency threatening injury to persons or damage to property Interconnection Customer shall take all necessary action immediately and shall promptly notify Connecting Transmission Owner thereof.

(h) 	Security.  As between Connecting Transmission Owner on the one 
hand and Interconnection Customer on the other, Interconnection Customer shall 
be solely responsible for securing and safeguarding (i) any and all Permitted 
Persons (and their possessions) while present at or about the Site, and any and all 
equipment,  tools,  supplies,  materials  and  other  personal  property  used  in 
connection with such work or brought onto or located at or about the Site by or on 
behalf of any and all Permitted Persons.  To the fullest extent permitted by law, 
Connecting Transmission Owner shall have no responsibility for any equipment, 
tools, supplies, materials or other personal property that may be brought onto or 
located at or about the Connecting Transmission Owner Transmission ROW and 
which is subsequently lost, stolen or damaged.  To the fullest extent permitted by 
law, the immediately preceding sentence shall apply even under circumstances 
where Connecting Transmission Owner may be negligent but shall not apply in the 
case  of  Connecting  Transmission  Owner’s  gross  negligence  or  intentional 
wrongdoing.

12.	Vehicle Spills.

Interconnection Customer is required to assure that all vehicles, including those of Subcontractors and suppliers, used in the performance of Work are maintained in good working condition and are not leaking any fluids.  Particular attention is to be paid, without limitation, to hydraulic systems on each vehicle.  The Environmental, Health and Safety Plan and Spill Response Plan shall specifically address the refueling of trucks, equipment and helicopters on the Connecting Transmission Owner ROW and property.

The driver of any such vehicle at the Site must immediately notify a Connecting Transmission Owner authorized representative in the event of a leak or spill from a vehicle or container carried on a vehicle while at the Site.  The driver must wait for instructions before moving the vehicle unless field conditions require it, and then, only to the nearest safe point.

The driver will be required to eliminate the leak or spill before leaving the Site.  Interconnection Customer shall be required to reimburse Connecting Transmission Owner for all costs associated with the cleanup of such leaks and spills.

10-11

SERVICE AGREEMENT NO. 2833

13.	Maintenance of Work Site.

Interconnection Customer shall, or shall cause the Subcontractors to at its/their own expense, store 
its apparatus, material, supplies and equipment in such orderly fashion as will not interfere with 
the progress of the Work or the work of any other contractors; clean up and remove on a daily 
basis, and more frequently if directed by the Connecting Transmission Owner representative, all 
refuse, rubbish, scrap materials, and debris so that at all times the Work site shall present a neat, 
orderly and workmanlike appearance; and remove all surplus material, falsework, and temporary 
structures, including any foundations thereof.  If, in the opinion of Connecting Transmission 
Owner, Interconnection Customer has failed to comply with any provisions of this Article, 
Connecting Transmission Owner may order any or all of the Work in the affected area be 
suspended until the conditions is corrected, and all costs associated therewith shall be borne by 
Interconnection Customer.  All permanent and temporary access gates to the rights of way shall 
remain closed at all times except when vehicles are transiting.  In no case shall gates be left open.

14. 	Subsurface Conditions Found Different.

Connecting Transmission Owner shall not be obliged to show any subsurface conditions on any 
drawing, plans or specifications it may furnish to Interconnection Customer or Subcontractor, and 
if none are shown that is not to be interpreted as indicating that there are none of significance to 
the Work.  Should Interconnection Customer encounter subsurface conditions at the site materially 
different from any that are shown on the drawings, plans or specifications, it shall immediately 
give notice to Connecting Transmission Owner of such conditions before the conditions are 
disturbed.  Connecting Transmission Owner will thereupon promptly investigate the conditions, 
and if it finds that they materially differ from those shown on the plans or indicated in the 
specifications it will make any changes necessary to revise the plans, drawings, or specifications 
to  reflect  the  actual  site  conditions,  at  the  cost  to  the  Interconnection  Customer.    The 
Interconnection Customer will also be responsible for all costs associated with the fact that the site 
conditions differ materially from those contained in the plans, drawings or specifications.

15.	Inspection and Tests and Correction of Defects.

(a)	Connecting Transmission Owner shall have the right to inspect any

and all records of Interconnection Customer or its Subcontractors whenever 
Connecting Transmission Owner believes that this is necessary to insure that the 
Work is proceeding and will proceed in full accordance with the requirements of 
the Agreement.  In addition, all parts of the Work shall throughout the time of 
performance  of  the  Agreement  be  subject  to  inspection  by  Connecting 
Transmission Owner.  To the extent permitted by the Agreement, Connecting 
Transmission Owner shall be the final judge of the quality and acceptability of the 
Work, the materials used therein, and the processes of manufacture and methods of 
construction employed in connection therewith.  Interconnection Customer shall, 
or shall cause the Subcontractors to, provide Connecting Transmission Owner’s 
representatives with safe and proper facilities for access to and inspection of the 
Work, both at the Site and at any plant or other source of supply where any 
equipment, material, or part may be located.  Connecting Transmission Owner shall 
have the right to witness any test Interconnection Customer or any third party acting

10-12

SERVICE AGREEMENT NO. 2833

on behalf of Interconnection Customer conducts relating to the Work, and 
Interconnection Customer shall give Connecting Transmission Owner advance 
written  notice  thereof.    The  test  results  shall  be  provided  to  Connecting 
Transmission Owner for concurrence as soon as practical, and found to be 
satisfactory only if accepted by Connecting Transmission Owner.  Connecting 
Transmission Owner shall have the right to require Interconnection Customer to 
perform reasonable additional tests at reasonable times and places The cost of any 
additional tests required by Connecting Transmission Owner shall be borne by 
Connecting Transmission Owner unless they disclose a defect or nonconformity in 
the Work, in which case the cost shall be borne by Interconnection Customer.

(b) 	No inspection, failure to inspect, or waiver of inspection on the part 
of Connecting Transmission Owner or anyone acting on its behalf shall relieve 
Interconnection Customer of its duty complete the Work in accordance with the 
Agreement.

(c) 	Should it appear to Connecting Transmission Owner at any time 
prior to the completion and acceptance of any segment of the Work, whether as a 
result of the aforementioned inspections and tests or otherwise, that any part of the 
Work in an uncompleted segment is not suitable or of good quality or fails to 
conform to the Agreement’s requirements, Connecting Transmission Owner shall 
have the option to :

(i)	halt the continuation of such segment of the Work; and

(ii)	require Interconnection Customer, at Interconnection Customer’s sole

expense and within such reasonable time as may be fixed by Connecting 
Transmission Owner, to reconstruct, replace or correct the applicable Work 
and remedy any damage to property of Connecting Transmission Owner 
and others occasioned by such Work or the materials, methods or processes 
employed in connection therewith, or, if Interconnection Customer does not 
comply with such requirement, then Connecting Transmission Owner may 
perform or have performed by another all of the aforementioned tasks and 
recover the cost thereof from Interconnection Customer; or

(iii) 	accept the unsuitable or nonconforming Work.

In any event, Interconnection Customer shall reimburse Connecting Transmission Owner for all costs for additional work performed by Connecting Transmission Owner’s other contractors to the extent they arise from Interconnection Customer’s unacceptable Work.

16.	Subcontracting.

(a)	Interconnection   Customer   shall,   notwithstanding   Connecting

Transmission  Owner’s  approval  of  a  particular  Subcontractor,  be  as  fully 
responsible for the acts and omissions of its Subcontractors and their agents as it is 
for its own acts and omission.  Should any approved Subcontractor fail to perform

10-13

SERVICE AGREEMENT NO. 2833

to the satisfaction of Connecting Transmission Owner, Connecting Transmission 
Owner shall have the right to rescind its approval and to require the Work 
subcontracted  to  be  performed  by  Interconnection  Customer  or  by  another 
approved Subcontractor.  Nothing contained herein shall create any contractual 
rights   in   any   Subcontractor   against   Connecting   Transmission   Owner. 
Interconnection Customer shall cause all subcontracts applicable to the Work to 
contain provisions which require the Subcontractor to provide the same insurance 
coverage as is required of Interconnection Customer naming both Connecting 
Transmission  Owner  and  Interconnection  Customer  as  additional  insureds. 
Subcontracts shall provide for Interconnection Customer the same rights against 
the Subcontractor as Connecting Transmission Owner has hereunder against 
Interconnection Customer and shall expressly state that such provisions shall also 
be for the benefit of Connecting Transmission Owner.

17. 	Title to Materials and Completed Work.

Interconnection Customer shall obtain and maintain title to all materials, equipment and structures 
to be installed by it in the Work, free from all liens, claims and encumbrances.  Title to all Work 
completed or in the course of construction and to all materials, equipment and structures shall be 
transferred to Connecting Transmission Owner in accordance with the Agreement.  Connecting 
Transmission Owner retains the right to require the correction of defective or non-conforming 
Work after acceptance by Connecting Transmission Owner if the defects or nonconforming 
elements of such work were not reasonably evident on inspection prior to acceptance of the Work.

18. 	Connecting Transmission Owner’s Performance.

Connecting Transmission Owner shall perform any action required of it by the Agreement in order to enable Interconnection Customer to perform.

19.	Liens.

Interconnection Customer shall defend, save harmless and indemnify Connecting Transmission 
Owner (as well as any owner of the real property on which the project is situated) against all claims, 
liens or attachments growing out of the demands of Subcontractors, mechanics, workmen, 
materialmen and furnishers of machinery, equipment, tools, or supplies, including commissary, in 
connection with the Work.  Interconnection Customer shall deliver the Work to Connecting 
Transmission Owner free and clear of all liens, claims, and encumbrances, and shall furnish 
Connecting Transmission Owner a certificate to that effect upon request.  If requested by 
Connecting   Transmission   Owner,   Interconnection   Customer   shall   furnish   Connecting 
Transmission Owner with a Interconnection Customer Affidavit - Final Full Release And Waiver 
of Lien document and, for each Subcontractor, a Subcontractor Affidavit - Final Full Release And 
Waiver of Lien document, duly executed and delivered by Interconnection Customer and its 
Subcontractors, as applicable.  Such documents shall, among other things, waive, release and 
discharge all claims and liens relating to the Work, the project or the Agreement and defend, 
indemnify and hold harmless Connecting Transmission Owner (as well as any owner of the real 
property on which the project is situated) from and against such claims and liens.  Such documents 
shall be in a form reasonably satisfactory to Connecting Transmission Owner and shall in all

10-14

SERVICE AGREEMENT NO. 2833

respects be read and interpreted consistent with Section 34 of the New York Lien Law (or its 
successor).  Any liens arising from Interconnection Customer’s Subcontractors, mechanics, 
workmen, materialmen and furnishers of machinery, equipment, tools, or supplies, including 
commissary, must be fully bonded or otherwise discharged by Subcontractor or Interconnection 
Customer in accordance with applicable law, within five (5) days of the filing of the lien.

20.	Other Contractors.

(a)	Interconnection   Customer   shall   fully   cooperate   with   other

contractors and any Connecting Transmission Owner employees at or near the site of the Work and carefully coordinate its own work with that performed by them. Interconnection Customer shall not commit or permit any act which will interfere with  the  performance  of  work  by  any  other  contractor  or  by  Connecting Transmission Owner.

(b) 	If any other contractor or any Subcontractor shall suffer loss or 
damage  through  acts  or  neglect  on  the  part  of  Interconnection  Customer, 
Interconnection Customer shall use its best efforts to settle the matter with such 
other contractor or Subcontractor.  If such other contractor or Subcontractor asserts 
any claim against Connecting Transmission Owner based on such loss or damage, 
Connecting Transmission Owner shall notify Interconnection Customer, and 
Interconnection Customer shall indemnify and save Connecting Transmission 
Owner harmless against any such claim and any loss or liability arising therefrom.

(c) 	Interconnection  Customer  and  its  Subcontractors  shall  keep informed of the progress and the details of work of other Connecting Transmission Owner contractors at the Work site (and of Connecting Transmission Owner) and shall notify Connecting Transmission Owner immediately of lack of progress or defective workmanship on the part of any of them (or of Connecting Transmission Owner).  Failure by Interconnection Customer to keep informed of other work in progress at the site or to give notice of lack of progress or defective workmanship by others shall be deemed an acceptance by Interconnection Customer of such other work insofar as it relates to or affects its own Work.

21.	Patents, Etc.

If Interconnection Customer, in performing this Agreement, employs, constructs or provides any 
design, process, material, tool or equipment covered by a patent, copyright, trademark or other 
proprietary right, Interconnection Customer shall, if it does not itself own such right, at its own 
expense secure permission prior to its use hereunder by securing a suitable agreement from the 
owner of such right.  Interconnection Customer shall indemnify and hold Connecting Transmission 
Owner harmless against any claim, suit or proceeding for infringement of any patent, copyright, 
trademark or other proprietary right brought against Connecting Transmission Owner, and any 
liability arising therefrom, arising out of the use or manufacture of any designs, processes, 
materials, tools or equipment provided to Connecting Transmission Owner or employed in the 
performance of the Work, except with respect to any equipment, process, material or design 
specified or developed by Connecting Transmission Owner.  Subject to the foregoing exception,

10-15

SERVICE AGREEMENT NO. 2833

Interconnection Customer shall provide for the defense of any such claim, suit or proceeding, and 
shall pay all costs and expenses in connection therewith, including compensation of experts and 
counsel, and all damages and costs awarded against Connecting Transmission Owner.  Connecting 
Transmission Owner shall notify Interconnection Customer of any such claim, suit or proceeding 
in  writing  and  give  Interconnection  Customer  authority,  information  and  assistance (at

Interconnection Customer’s expense) for the defense thereof.  In the event that the use of anything furnished or constructed hereunder is enjoined, Interconnection Customer shall promptly, at its own expense and at its option, either (a) procure for Connecting Transmission Owner the right to continue using it or (b) with the approval of Connecting Transmission Owner, (i) replace it with a noninfringing equivalent or (ii) modify it so it becomes noninfringing.

22.	Ownership of Documents.

Interconnection Customer shall make available to Connecting Transmission Owner, upon request, all  documents,  drawings,  plans,  specifications,  reports,  books,  photographs,  films,  tapes, recordings, models, and computer programs furnished or prepared by Interconnection Customer in connection with the Work (hereinafter “Materials”), and Connecting Transmission Owner shall have the unrestricted right to copy and reproduce the Materials, use them in any way it sees fit, and disclose them to others.  Interconnection Customer hereby assigns any and all copyrights in the  Materials  to  Connecting  Transmission  Owner,  and,  upon  the  request  of  Connecting Transmission Owner, Interconnection Customer shall execute any documents that Connecting Transmission Owner deems necessary to effectuate such assignments.

23. 	Compliance with Laws on Discrimination in Employment.

Interconnection Customer will not discriminate against any employee or applicant for employment 
because of race, color, religion, sex, age, ancestry or national origin.  Interconnection Customer 
will take affirmative action to insure that employees are treated, during employment, without 
regard to their race, color, religion, sex, age, ancestry, or national origin.  Such action shall include, 
but not be limited to, the following: employment, job classification, upgrading, demotion, 
promotion, layoff, termination or transfer, rates of pay or other forms of compensation and 
selection for training, including apprenticeship.  To the extent applicable, Interconnection 
Customer shall utilize commercially reasonable efforts to comply with and cause its subcontractors 
to comply with, Federal Acquisition Regulation (“FAR”) clause 52.203-6, “Restrictions on 
Subcontractor Sales to The Government (Jul 1985)”, FAR clause 52.203-7, “Anti-Kickback 
Procedures (Oct 1988)”, FAR clause 52.203-11, “Certification And Disclosure Regarding

Payments to Influence Certain Federal Transactions 	(Apr 1991)”, FAR clause 52.203-12,

“Limitation On Payment To Influence Certain Federal Transactions (Jan 1990)”, FAR clause

52.219-8, “Utilization Of Small Business Concerns and Small Disadvantaged Business Concerns 
(Feb 1990)”, FAR clause 52.219-9, “Small Business And Small Disadvantaged Business

Subcontracting Plan (Jan 1991)”, FAR clause 52.222-26, “Equal Opportunity (Apr 1984)”, FAR 
clause 52.222-35, “Affirmative Action For Special Disabled And Vietnam Era Veterans (Apr 
1984)”, FAR clause 52.222-36, “Affirmative Action For Handicapped Workers (Apr 1984)”, FAR 
clause 52.222-37, “Employment Reports On Special Disabled Veterans and Veterans Of the 
Vietnam  Era (Jan 1988)”,  and  FAR  clause 52.223-2, “Clean  Air  and  Water (1984)”.

Interconnection Customer certifies that neither it nor its principals is debarred, suspended or 
proposed for debarment by the Federal Government; that it does not and will not maintain or

10-16

SERVICE AGREEMENT NO. 2833

provide for its employees any segregated facilities (i.e., facilities that are segregated on the basis 
of race, color, religion, or national origin) at any of its establishments, and that it does not permit 
and will not permit its employees to perform their services at any location under its control where 
segregated facilities are maintained; and that any facility to be used in the performance of this 
Agreement is not listed on the Environmental Protection Agency List of Violating Facilities.

10-17