SERVICE AGREEMENT NO. 2710

SERVICE AGREEMENT NO. 2710   
 AMENDED AND RESTATED

MERCHANT TRANSMISSION FACILITY   
 INTERCONNECTION AGREEMENT

AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.   
 AND

NEW YORK POWER AUTHORITY   
 AND

CHPE LLC

Dated as of July 8, 2024

(Champlain Hudson Power Express)

SERVICE AGREEMENT NO. 2710

TABLE OF CONTENTS

Page Number

ARTICLE 1. DEFINITIONS 1

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION 10

2.1 Effective Date 10

2.2 Term of Agreement 10

2.3 Termination 10

2.4 Termination Costs 11

2.5 Disconnection 12

2.6 Survival 12

ARTICLE 3. REGULATORY FILINGS 12

ARTICLE 4. SCOPE OF INTERCONNECTION SERVICE 12

4.1 Provision of Service 12

4.2 No Transmission Delivery Service 13

4.3 No Other Services 13

ARTICLE 5. INTERCONNECTION FACILITIES ENGINEERING, PROCUREMENT,

AND CONSTRUCTION 13

5.1 Options 13

5.2 General Conditions Applicable to Option to Build 15

5.3 Liquidated Damages 17

5.4 Reserved 18

5.5 Equipment Procurement 18

5.6 Construction Commencement 18

5.7 Work Progress 19

5.8 Information Exchange 19

5.9 Other Interconnection Options 19

5.10 Developer’s Attachment Facilities (“DAF”) 20

5.11 Connecting Transmission Owner’s Attachment Facilities Construction 21

5.12 Access Rights 21

5.13 Lands of Other Property Owners 22

5.14 Permits 22

5.15 Early Construction of Base Case Facilities 22

5.16 Suspension 23

5.17 Taxes 23

5.18 Tax Status; Non-Jurisdictional Entities 28

5.19 Modification 29

ARTICLE 6. TESTING AND INSPECTION 30

6.1 Pre-Commercial Operation Date Testing and Modifications 30

6.2 Post-Commercial Operation Date Testing and Modifications 30

6.3 Right to Observe Testing 30

6.4 Right to Inspect 30

ARTICLE 7. METERING 31

7.1 General 31

7.2 Check Meters 31

7.3 Standards 31

i

SERVICE AGREEMENT NO. 2710

7.4 Testing of Metering Equipment 31

7.5 Metering Data 32

ARTICLE 8. COMMUNICATIONS 32

8.1 Developer Obligations 32

8.2 Remote Terminal Unit 32

8.3 No Annexation 33

ARTICLE 9. OPERATIONS 33

9.1 General 33

9.2 NYISO and Connecting Transmission Owner Obligations 33

9.3 Developer Obligations 33

9.4 Start-Up and Synchronization 34

9.5 Real and Reactive Power Control and Primary Frequency Response 34

9.6 Outages and Interruptions 35

9.7 Switching and Tagging Rules 38

9.8 Use of Attachment Facilities by Third Parties 38

9.9 Disturbance Analysis Data Exchange 39

9.10 Phasor Measurement Units 39

ARTICLE 10. MAINTENANCE 40

10.1 Connecting Transmission Owner Obligations 40

10.2 Developer Obligations 40

10.3 Coordination 40

10.4 Secondary Systems 40

10.5 Operating and Maintenance Expenses 40

ARTICLE 11. PERFORMANCE OBLIGATION 41

11.1 Developer’s Attachment Facilities 41

11.2 Connecting Transmission Owner’s Attachment Facilities 41

11.3 System Upgrade Facilities and System Deliverability Upgrades 41

11.4 Special Provisions for Affected Systems 41

11.5 Provision of Security 41

11.6 Developer Compensation for Emergency Services 42

11.7 Line Outage Costs 42

ARTICLE 12. INVOICE 42

12.1 General 42

12.2 Final Invoice 43

12.3 Payment 43

12.4 Disputes 43

ARTICLE 13. EMERGENCIES 43

13.1 Obligations 43

13.2 Notice 43

13.3 Immediate Action 44

13.4 NYISO and Connecting Transmission Owner Authority 44

13.5 Developer Authority 45

13.6 Limited Liability 45

ARTICLE 14. REGULATORY REQUIREMENTS AND GOVERNING LAW 45

14.1 Regulatory Requirements 45

14.2 Governing Law 46

ii

SERVICE AGREEMENT NO. 2710

ARTICLE 15. NOTICES 46

15.1 General 46

15.2 Billings and Payments 46

15.3 Alternative Forms of Notice 46

15.4 Operations and Maintenance Notice 46

ARTICLE 16. FORCE MAJEURE 46

ARTICLE 17. DEFAULT 47

17.1 General 47

17.2 Right to Terminate 47

ARTICLE 18. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE 47

18.1 Indemnity 47

18.2 No Consequential Damages 49

18.3 Insurance 49

ARTICLE 19. ASSIGNMENT 51

ARTICLE 20. SEVERABILITY 52

ARTICLE 21. COMPARABILITY 52

ARTICLE 22. CONFIDENTIALITY 52

22.1 Confidentiality 52

22.2 Term 52

22.3 Confidential Information 53

22.4 Scope 53

22.5 Release of Confidential Information 53

22.6 Rights 53

22.7 No Warranties 53

22.8 Standard of Care 54

22.9 Order of Disclosure 54

22.10 Termination of Agreement 54

22.11 Remedies 54

22.12 Disclosure to FERC, its Staff, or a State 55

22.13 Required Notices Upon Requests or Demands for Confidential Information . 55

ARTICLE 23. DEVELOPER AND CONNECTING TRANSMISSION OWNER NOTICES OF

ENVIRONMENTAL RELEASES 55

ARTICLE 24. INFORMATION REQUIREMENT 56

24.1 Information Acquisition 56

24.2 Information Submission by Connecting Transmission Owner 56

24.3 Updated Information Submission by Developer 56

24.4 Information Supplementation 57

ARTICLE 25. INFORMATION ACCESS AND AUDIT RIGHTS 57

25.1 Information Access 57

25.2 Reporting of Non-Force Majeure Events 57

25.3 Audit Rights 58

25.4 Audit Rights Periods 58

25.5 Audit Results 58

ARTICLE 26. SUBCONTRACTORS 58

26.1 General 58

26.2 Responsibility of Principal 59

iii

SERVICE AGREEMENT NO. 2710

26.3 No Limitation by Insurance 59

ARTICLE 27. DISPUTES 59

27.1 Submission 59

27.2 External Arbitration Procedures 59

27.3 Arbitration Decisions 60

27.4 Costs 60

27.5 Termination 60

ARTICLE 28. REPRESENTATIONS, WARRANTIES AND COVENANTS 60

28.1 General 60

ARTICLE 29. MISCELLANEOUS 61

29.1 Binding Effect 61

29.2 Conflicts 61

29.3 Rules of Interpretation 61

29.4 Compliance 62

29.5 Joint and Several Obligations 62

29.6 Entire Agreement 62

29.7 No Third Party Beneficiaries 62

29.8 Waiver 63

29.9 Headings 63

29.10 Multiple Counterparts 63

29.11 Amendment 63

29.12 Modification by the Parties 63

29.13 Reservation of Rights 63

29.14 No Partnership 64

29.15 Other Transmission Rights 64

Appendices

iv

SERVICE AGREEMENT NO. 2710

AMENDED AND RESTATED MERCHANT TRANSMISSION FACILITY   
 INTERCONNECTION AGREEMENT

THIS AMENDED AND RESTATED MERCHANT TRANSMISSION FACILITY

INTERCONNECTION AGREEMENT (“Agreement”) is made and entered into this 8th day of July, 2024, by and among CHPE LLC, a limited liability company organized and existing under the laws of the State of New York (“Developer”), the New York Independent System Operator, Inc., a not-for-profit corporation organized and existing under the laws of the State of New York (“NYISO”), and New York Power Authority a corporate municipal instrumentality organized and existing under the laws of the State of New York (“Connecting Transmission Owner”). Developer, the NYISO, or Connecting Transmission Owner each may be referred to as a “Party” or collectively referred to as the “Parties.”

RECITALS

WHEREAS, NYISO operates the New York State Transmission System and Connecting   
Transmission Owner owns certain facilities included in the New York State Transmission   
System;

WHEREAS, Developer’s proposed 1000 MW HVDC transmission facility (NYISO Queue No. 631) and its proposed 250 MW expansion of the transmission facility (NYISO Queue No. 887) are participating in the Class Year Interconnection Facilities Study for Class Year 2021, and both projects are collectively the Merchant Transmission Facility subject to this Agreement as   
detailed in Appendix C to this Agreement;

WHEREAS, Developer intends to own, lease and/or control and operate the Merchant Transmission Facility; and

WHEREAS, Developer, NYISO, and Connecting Transmission Owner have agreed to enter into this Agreement for the purpose of interconnecting the Merchant Transmission Facility with the New York State Transmission System;

NOW, THEREFORE, in consideration of and subject to the mutual covenants contained herein, it is agreed:

ARTICLE 1. DEFINITIONS

Whenever used in this Agreement with initial capitalization, the following terms shall have the

meanings specified in this Article 1. Terms used in this Agreement with initial capitalization that are not defined in this Article 1 shall have the meanings specified in Section 1 of the ISO OATT, Section 30.1 of Attachment X of the ISO OATT, Section 25.1.2 of Attachment S of the ISO   
OATT, the body of the LFIP or the body of this Agreement.

Affected System shall mean an electric system other than the transmission system owned, controlled or operated by the Connecting Transmission Owner that may be affected by the proposed interconnection.

1

SERVICE AGREEMENT NO. 2710

Affected System Operator shall mean the entity that operates an Affected System.

Affected Transmission Owner shall mean the New York public utility or authority (or its

designated agent) other than the Connecting Transmission Owner that (i) owns facilities used for the transmission of Energy in interstate commerce and provides Transmission Service under the Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State Transmission System where System Deliverability Upgrades, System Upgrade Facilities, or   
Network Upgrade Facilities are or will be installed pursuant to Attachment P, Attachment X, Attachment Z, or Attachment S to the ISO OATT.

Affiliate shall mean, with respect to a person or entity, any individual, corporation, partnership, firm, joint venture, association, joint-stock company, trust or unincorporated organization,   
directly or indirectly controlling, controlled by, or under common control with, such person or entity. The term “control” shall mean the possession, directly or indirectly, of the power to direct the management or policies of a person or an entity. A voting interest of ten percent or more shall create a rebuttable presumption of control.

Ancillary Services shall mean those services that are necessary to support the transmission of Capacity and Energy from resources to Loads while maintaining reliable operation of the New York State Transmission System in accordance with Good Utility Practice.

Applicable Laws and Regulations shall mean all duly promulgated applicable federal, state and local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or administrative orders, permits and other duly authorized actions of any Governmental Authority, including but not limited to Environmental Law.

Applicable Reliability Councils shall mean the NERC, the NPCC and the NYSRC.

Applicable Reliability Standards shall mean the requirements and guidelines of the Applicable Reliability Councils, and the Transmission District to which the Developer’s Merchant   
Transmission Facility is directly interconnected, as those requirements and guidelines are   
amended and modified and in effect from time to time; provided that no Party shall waive its   
right to challenge the applicability or validity of any requirement or guideline as applied to it in the context of this Agreement.

Attachment Facilities shall mean the Connecting Transmission Owner’s Attachment Facilities   
and the Developer’s Attachment Facilities. Collectively, Attachment Facilities include all   
facilities and equipment between the Merchant Transmission Facility and the Point of   
Interconnection, including any modification, additions or upgrades that are necessary to   
physically and electrically interconnect the Merchant Transmission Facility to the New York   
State Transmission System. Attachment Facilities are sole use facilities and shall not include   
Stand Alone System Upgrade Facilities, Distribution Upgrades, System Upgrade Facilities or   
System Deliverability Upgrades.

Base Case shall mean the base case power flow, short circuit, and stability data bases used for the Interconnection Studies by NYISO, Connecting Transmission Owner or Developer;   
described in Section 30.2.3 of the Standard Large Facility Interconnection Procedures.

2

SERVICE AGREEMENT NO. 2710

Breach shall mean the failure of a Party to perform or observe any material term or condition of this Agreement.

Breaching Party shall mean a Party that is in Breach of this Agreement.

Business Day shall mean Monday through Friday, excluding federal holidays.

Byway shall mean all transmission facilities comprising the New York State Transmission

System that are neither Highways nor Other Interfaces. All transmission facilities in Zone J and Zone K are Byways.

Calendar Day shall mean any day including Saturday, Sunday or a federal holiday.

Capacity Region shall mean one of four subsets of the Installed Capacity statewide markets   
comprised of (1) Rest of State (i.e., Load Zones A through F); (2) Lower Hudson Valley (i.e.,   
Load Zones G, H and I); (3) New York City (i.e., Load Zone J); and (4) Long Island (i.e., Load   
Zone K) , except for Class Year Interconnection Facility Studies conducted prior to Class Year   
2012, for which “Capacity Region” shall be defined as set forth in Section 25.7.3 of Attachment   
S to the ISO OATT.

Capacity Resource Interconnection Service (“CRIS”) shall mean the service provided by

NYISO to Developers that satisfy the NYISO Deliverability Interconnection Standard or that are   
otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT; such   
service being one of the eligibility requirements for participation as a NYISO Installed Capacity   
Supplier.

Class Year Deliverability Study shall mean an assessment, conducted by the NYISO staff in   
cooperation with Market Participants, to determine whether System Deliverability Upgrades are   
required for Class Year CRIS Projects under the NYISO Deliverability Interconnection Standard.

Commercial Operation shall mean the status of a Merchant Transmission Facility that has   
commenced transmitting electricity for sale, excluding electricity transmitted during Trial   
Operation.

Commercial Operation Date of a unit shall mean the date on which the Merchant Transmission Facility commences Commercial Operation as agreed to by the Parties, notice of which must be provided to the NYISO in the form of Appendix E-2 to this Agreement.

Confidential Information shall mean any information that is defined as confidential by Article 22 of this Agreement.

Connecting Transmission Owner shall mean the New York public utility or authority (or its designated agent) that (i) owns facilities used for the transmission of Energy in interstate   
commerce and provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an interest in the portion of the New York State Transmission System or Distribution System at the Point of Interconnection, and (iii) is a Party to this Agreement.

3

SERVICE AGREEMENT NO. 2710

Connecting Transmission Owner’s Attachment Facilities shall mean all facilities and

equipment owned, controlled or operated by the Connecting Transmission Owner from the Point   
of Change of Ownership to the Point of Interconnection as identified in Appendix A to this   
Agreement, including any modifications, additions or upgrades to such facilities and equipment.   
Connecting Transmission Owner’s Attachment Facilities are sole use facilities and shall not   
include Stand Alone System Upgrade Facilities, System Upgrade Facilities, or System   
Deliverability Upgrades.

Contingent Facilities shall mean those Attachment Facilities and System Upgrade Facilities   
and/or System Deliverability Upgrades associated with Class Year Projects upon which the   
Merchant Transmission Facility’s Class Year Project Cost Allocations are dependent, and if   
delayed or not built, could impact the actual costs and timing of the Merchant Transmission   
Facility’s Project Cost Allocation for System Upgrade Facilities or System Deliverability   
Upgrades.

Control Area shall mean an electric power system or combination of electric power systems to   
which a common automatic generation control scheme is applied in order to: (1) match, at all   
times, the power output of the Generators within the electric power system(s) and capacity and   
energy purchased from entities outside the electric power system(s), with the Load within the   
electric power system(s); (2) maintain scheduled interchange with other Control Areas, within   
the limits of Good Utility Practice; (3) maintain the frequency of the electric power system(s)   
within reasonable limits in accordance with Good Utility Practice; and (4) provide sufficient

generating capacity to maintain Operating Reserves in accordance with Good Utility Practice. A Control Area must be certified by the NPCC.

Default shall mean the failure of a Party in Breach of this Agreement to cure such Breach in accordance with Article 17 of this Agreement.

Developer shall mean an Eligible Customer developing a Merchant Transmission Facility, proposing to connect to the New York State Transmission System, in compliance with the NYISO Minimum Interconnection Standard.

Developer’s Attachment Facilities shall mean all facilities and equipment, as identified in

Appendix A of this Agreement, that are located between the Merchant Transmission Facility and the Point of Change of Ownership, including any modification, addition, or upgrades to such   
facilities and equipment necessary to physically and electrically interconnect the Merchant   
Transmission Facility to the New York State Transmission System. Developer’s Attachment   
Facilities are sole use facilities.

Distribution System shall mean the Connecting Transmission Owner’s facilities and equipment   
used to distribute electricity that are subject to FERC jurisdiction, and are subject to the   
NYISO’s Large Facility Interconnection Procedures in Attachment X to the ISO OATT or Small   
Generator Interconnection Procedures in Attachment Z to the ISO OATT under FERC Order   
Nos. 2003 and/or 2006. The term Distribution System shall not include LIPA’s distribution   
facilities.

4

SERVICE AGREEMENT NO. 2710

Distribution Upgrades shall mean the additions, modifications, and upgrades to the Connecting   
Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate   
interconnection of a Merchant Transmission Facility and render the transmission service   
necessary to affect the Developer’s wholesale sale of electricity in interstate commerce.   
Distribution Upgrades do not include Attachment Facilities, System Upgrade Facilities, or   
System Deliverability Upgrades. Distribution Upgrades are sole use facilities and shall not   
include Stand Alone System Upgrade Facilities, System Upgrade Facilities, or System   
Deliverability Upgrades.

Effective Date shall mean the date on which this Agreement becomes effective upon execution by the Parties, subject to acceptance by the Commission, or if filed unexecuted, upon the date specified by the Commission.

Emergency State shall mean the condition or state that the New York State Power System is in when an abnormal condition occurs that requires automatic or immediate manual action to   
prevent or limit loss of the New York State Transmission System or Generators that could   
adversely affect the reliability of the New York State Power System.

Energy Resource Interconnection Service (“ERIS”) shall mean the service provided by

NYISO to interconnect the Developer’s Merchant Transmission Facility to the New York State   
Transmission System or to the Distribution System in accordance with the NYISO Minimum   
Interconnection Standard, to enable the New York State Transmission System to receive Energy   
and Ancillary Services from the Merchant Transmission Facility, pursuant to the terms of the   
ISO OATT.

Environmental Law shall mean Applicable Laws and Regulations relating to pollution or protection of the environment or natural resources.

Federal Power Act shall mean the Federal Power Act, as amended, 16 U.S.C. §§ 791a et seq. (“FPA”).

FERC shall mean the Federal Energy Regulatory Commission (“Commission”) or its successor.

Force Majeure shall mean any act of God, labor disturbance, act of the public enemy, war,   
insurrection, riot, fire, storm or flood, explosion, breakage or accident to machinery or   
equipment, any order, regulation or restriction imposed by governmental, military or lawfully   
established civilian authorities, or any other cause beyond a Party’s control. A Force Majeure   
event does not include acts of negligence or intentional wrongdoing by the Party claiming Force   
Majeure.

Good Utility Practice shall mean any of the practices, methods and acts engaged in or approved   
by a significant portion of the electric industry during the relevant time period, or any of the   
practices, methods and acts which, in the exercise of reasonable judgment in light of the facts   
known at the time the decision was made, could have been expected to accomplish the desired   
result at a reasonable cost consistent with good business practices, reliability, safety and   
expedition. Good Utility Practice is not intended to be limited to the optimum practice, method,   
or act to the exclusion of all others, but rather to delineate acceptable practices, methods, or acts   
generally accepted in the region.

5

SERVICE AGREEMENT NO. 2710

Governmental Authority shall mean any federal, state, local or other governmental regulatory   
or administrative agency, court, commission, department, board, or other governmental   
subdivision, legislature, rulemaking board, tribunal, or other governmental authority having   
jurisdiction over any of the Parties, their respective facilities, or the respective services they   
provide, and exercising or entitled to exercise any administrative, executive, police, or taxing   
authority or power; provided, however, that such term does not include Developer, NYISO,   
Affected Transmission Owner, Connecting Transmission Owner, or any Affiliate thereof.

Hazardous Substances shall mean any chemicals, materials or substances defined as or

included in the definition of “hazardous substances,” “hazardous wastes,” “hazardous materials,” “hazardous constituents,” “restricted hazardous materials,” “extremely hazardous substances,” “toxic substances,” “radioactive substances,” “contaminants,” “pollutants,” “toxic pollutants” or words of similar meaning and regulatory effect under any applicable Environmental Law, or any other chemical, material or substance, exposure to which is prohibited, limited or regulated by any applicable Environmental Law.

Highway shall mean 115 kV and higher transmission facilities that comprise the following

NYCA interfaces: Dysinger East, West Central, Volney East, Moses South, Central East/Total   
East, and UPNY-ConEd, and their immediately connected, in series, bulk power system facilities   
in New York State. Each interface shall be evaluated to determine additional “in series”   
facilities, defined as any transmission facility higher than 115 kV that (a) is located in an   
upstream or downstream zone adjacent to the interface and (b) has a power transfer distribution   
factor (DFAX) equal to or greater than five percent when the aggregate of generation in zones or   
systems adjacent to the upstream zone or zones that define the interface is shifted to the   
aggregate of generation in zones or systems adjacent to the downstream zone or zones that define   
the interface. In determining “in series” facilities for Dysinger East and West Central interfaces,   
the 115 kV and 230 kV tie lines between NYCA and PJM located in LBMP Zones A and B shall   
not participate in the transfer. Highway transmission facilities are listed in ISO Procedures.

Initial Synchronization Date shall mean the date upon which the Merchant Transmission

Facility is initially synchronized and upon which Trial Operation begins, notice of which must be provided to the NYISO in the form of Appendix E-1.

In-Service Date shall mean the date upon which the Developer reasonably expects it will be

ready to begin use of the Connecting Transmission Owner’s Attachment Facilities to obtain back feed power.

Interconnection Facilities Study shall mean a study conducted by NYISO or a third party

consultant for the Developer to determine a list of facilities (including Connecting Transmission   
Owner’s Attachment Facilities, Distribution Upgrades, System Upgrade Facilities and System   
Deliverability Upgrades as identified in the Interconnection System Reliability Impact Study),   
the cost of those facilities, and the time required to interconnect the Merchant Transmission   
Facility with the New York State Transmission System or with the Distribution System. The   
scope of the study is defined in Section 30.8 of the Standard Large Facility Interconnection   
Procedures.

6

SERVICE AGREEMENT NO. 2710

Interconnection Facilities Study Agreement (“Class Year Study Agreement”) shall mean the form of agreement contained in Appendix 2 of the Standard Large Facility Interconnection   
Procedures for conducting the Interconnection Facilities Study.

Interconnection Request shall mean a Developer’s request, in the form of Appendix 1 to the   
Standard Large Facility Interconnection Procedures, in accordance with the Tariff, to   
interconnect a new Merchant Transmission Facility to the New York State Transmission System   
or to the Distribution System, or to materially increase the capacity of, or make a material   
modification to the operating characteristics of, an existing Merchant Transmission Facility that   
is interconnected with the New York State Transmission System or with the Distribution System.

Interconnection Study shall mean any of the following studies: the Optional Interconnection Feasibility Study, the Interconnection System Reliability Impact Study, and the Interconnection Facilities Study described in the Standard Large Facility Interconnection Procedures.

Interconnection System Reliability Impact Study (“SRIS”) shall mean an engineering study,   
conducted in accordance with Section 30.7 of the Standard Large Facility Interconnection   
Procedures, that evaluates the impact of the proposed Merchant Transmission Facility on the   
safety and reliability of the New York State Transmission System and, if applicable, an Affected   
System, to determine what Attachment Facilities, Distribution Upgrades and System Upgrade   
Facilities are needed for the proposed Merchant Transmission Facility of the Developer to   
connect reliably to the New York State Transmission System or to the Distribution System in a   
manner that meets the NYISO Minimum Interconnection Standard in Attachment X to the ISO   
OATT.

IRS shall mean the Internal Revenue Service.

Material Modification shall mean those modifications that have a material impact on the cost or timing of any Interconnection Request with a later queue priority date.

Merchant Transmission Facility shall mean generally a merchant facility for the transmission of electricity, and specifically the Developer’s facility for the transmission of electricity as   
described in this Agreement and the Appendices hereto.

Merchant Transmission Facility Interconnection Agreement shall mean this Agreement.

Metering Equipment shall mean all metering equipment installed or to be installed at the Point of Interconnection, including but not limited to instrument transformers, MWh-meters, data   
acquisition equipment, transducers, remote terminal unit, communications equipment, phone   
lines, and fiber optics.

NERC shall mean the North American Electric Reliability Council or its successor organization.

New York State Transmission System shall mean the entire New York State electric

transmission system, which includes (i) the Transmission Facilities Under ISO Operational Control; (ii) the Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities within the New York Control Area.

7

SERVICE AGREEMENT NO. 2710

Notice of Dispute shall mean a written notice of a dispute or claim that arises out of or in connection with this Agreement or its performance.

NPCC shall mean the Northeast Power Coordinating Council or its successor organization.

NYISO Deliverability Interconnection Standard - The standard that must be met, unless

otherwise provided for by Attachment S to the ISO OATT, by (i) any generation facility larger

than 2MW in order for that facility to obtain CRIS; (ii) any Class Year Transmission Project; (iii) any entity requesting External CRIS Rights, and (iv) any entity requesting a CRIS transfer   
pursuant to Section 25.9.5 of Attachment S to the ISO OATT. To meet the NYISO   
Deliverability Interconnection Standard, the Developer must, in accordance with the rules in   
Attachment S to the ISO OATT, fund or commit to fund any System Deliverability Upgrades identified for its project in the Class Year Deliverability Study.

NYISO Minimum Interconnection Standard - The reliability standard that must be met by   
any generation facility or Class Year Transmission Project that is subject to NYISO’s Large   
Facility Interconnection Procedures in Attachment X to the ISO OATT or the NYISO’s Small   
Generator Interconnection Procedures in Attachment Z, that is proposing to connect to the New   
York State Transmission System or Distribution System, to obtain ERIS. The Minimum   
Interconnection Standard is designed to ensure reliable access by the proposed project to the   
New York State Transmission System or to the Distribution System. The Minimum   
Interconnection Standard does not impose any deliverability test or deliverability requirement on   
the proposed interconnection.

NYSRC shall mean the New York State Reliability Council or its successor organization.

Other Interfaces shall mean the following interfaces into Capacity Regions: Lower Hudson

Valley [i.e., Rest of State (Load Zones A-F) to Lower Hudson Valley (Load Zones G, H and I)]; New York City [i.e., Lower Hudson Valley (Load Zones G, H and I) to New York City (Load Zone J)]; and Long Island [i.e., Lower Hudson Valley (Load Zones G, H and I) to Long Island (Load Zone K)], and the following Interfaces between the NYCA and adjacent Control Areas: PJM to NYISO, ISO-NE to NYISO, Hydro-Quebec to NYISO, and Norwalk Harbor   
(Connecticut) to Northport (Long Island) Cable.

Party or Parties shall mean NYISO, Connecting Transmission Owner, or Developer or any combination of the above.

Point of Change of Ownership shall mean the point, as set forth in Appendix A to this Agreement, where the Developer’s Attachment Facilities connect to the Connecting Transmission Owner’s Attachment Facilities.

Point of Interconnection shall mean the point, as set forth in Appendix A to this Agreement, where the Attachment Facilities connect to the New York State Transmission System or to the Distribution System.

Provisional Interconnection Service shall mean interconnection service provided by the ISO   
associated with interconnecting the Developer’s Merchant Transmission Facility to the New   
York State Transmission System (or Distribution System as applicable) and enabling the

8

SERVICE AGREEMENT NO. 2710

transmission system to receive electric energy from the Merchant Transmission Facility at the Point of Interconnection, pursuant to the terms of the Provisional Large Facility Interconnection Agreement and, if applicable, the ISO OATT.

Provisional Merchant Transmission Facility Interconnection Agreement shall mean the

interconnection agreement for Provisional Interconnection Service established between the ISO, Connecting Transmission Owner(s) and the Developer. This agreement shall take the form of the Merchant Transmission Facility Interconnection Agreement, modified for provisional   
purposes and type of facility.

Reasonable Efforts shall mean, with respect to an action required to be attempted or taken by a   
Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and   
are otherwise substantially equivalent to those a Party would use to protect its own interests.

Services Tariff shall mean the NYISO Market Administration and Control Area Tariff, as filed   
with the Commission, and as amended or supplemented from time to time, or any successor tariff   
thereto.

Stand Alone System Upgrade Facilities shall mean System Upgrade Facilities that are not part   
of an Affected System that a Developer may construct without affecting day-to-day operations of   
the New York State Transmission System during their construction. NYISO, the Connecting   
Transmission Owner and the Developer must agree as to what constitutes Stand Alone System   
Upgrade Facilities and identify them in Appendix A to this Agreement. If NYISO, the   
Connecting Transmission Owner and the Developer disagree about whether a particular System   
Upgrade Facility is a Stand Alone System Upgrade Facility, NYISO and the Connecting   
Transmission Owner must provide the Developer a written technical explanation outlining why   
NYISO and the Connecting Transmission Owner does not consider the System Upgrade Facility   
to be a Stand Alone System Upgrade Facility within fifteen (15) days of its determination.

Standard Large Facility Interconnection Procedures (“Large Facility Interconnection Procedures” or “LFIP”) shall mean the interconnection procedures applicable to an   
Interconnection Request pertaining to a Merchant Transmission Facility that are included in Attachment X of the ISO OATT.

System Deliverability Upgrades shall mean the least costly configuration of commercially available components of electrical equipment that can be used, consistent with Good Utility Practice and Applicable Reliability Requirements, to make the modifications or additions to Byways and Highways and Other Interfaces on the existing New York State Transmission   
System and Distribution System that are required for the proposed project to connect reliably to the system in a manner that meets the NYISO Deliverability Interconnection Standard at the requested level of Capacity Resource Interconnection Service.

System Protection Facilities shall mean the equipment, including necessary protection signal   
communications equipment, required to (1) protect the New York State Transmission System   
from faults or other electrical disturbances occurring at the Merchant Transmission Facility and

(2) protect the Merchant Transmission Facility from faults or other electrical system disturbances

9

SERVICE AGREEMENT NO. 2710

occurring on the New York State Transmission System or on other delivery systems or other   
generating systems to which the New York State Transmission System is directly connected.

System Upgrade Facilities shall mean the least costly configuration of commercially available   
components of electrical equipment that can be used, consistent with Good Utility Practice and   
Applicable Reliability Requirements, to make the modifications to the existing transmission   
system that are required to maintain system reliability due to: (i) changes in the system,   
including such changes as load growth and changes in load pattern, to be addressed in the form   
of generic generation or transmission projects; and (ii) proposed interconnections. In the case of   
proposed interconnection projects, System Upgrade Facilities are the modifications or additions   
to the existing New York State Transmission System that are required for the proposed project to   
connect reliably to the system in a manner that meets the NYISO Minimum Interconnection   
Standard.

Tariff shall mean the NYISO Open Access Transmission Tariff (“OATT”), as filed with the   
Commission, and as amended or supplemented from time to time, or any successor tariff.

Trial Operation shall mean the period during which Developer is engaged in on-site test   
operations and commissioning of the Merchant Transmission Facility prior to Commercial   
Operation.

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION

2.1 Effective Date.

This Agreement shall become effective upon execution by the Parties, subject to

acceptance by FERC, or if filed unexecuted, upon the date specified by FERC. The NYISO and Connecting Transmission Owner shall promptly file this Agreement with FERC upon execution in accordance with Article 3.

2.2 Term of Agreement.

Subject to the provisions of Article 2.3, this Agreement shall remain in effect for a period of thirty (30) years from the Effective Date and shall be automatically renewed for each   
successive one-year period thereafter.

2.3 Termination.

2.3.1 Written Notice.

This Agreement may be terminated by the Developer after giving the NYISO and

Connecting Transmission Owner ninety (90) Calendar Days advance written notice, or by the NYISO and Connecting Transmission Owner notifying FERC after the Merchant Transmission Facility permanently ceases Commercial Operation.

2.3.2 Default.

Any Party may terminate this Agreement in accordance with Article 17.

10

SERVICE AGREEMENT NO. 2710

2.3.3 Compliance.

Notwithstanding Articles 2.3.1 and 2.3.2, no termination of this Agreement shall become effective until the Parties have complied with all Applicable Laws and Regulations applicable to such termination, including the filing with FERC of a notice of termination of this Agreement, which notice has been accepted for filing by FERC.

2.4 Termination Costs.

If a Party elects to terminate this Agreement pursuant to Article 2.3.1 above, the

terminating Party shall pay all costs incurred (including any cancellation costs relating to orders   
or contracts for Attachment Facilities and equipment) or charges assessed by the other Parties, as   
of the date of the other Parties’ receipt of such notice of termination, that are the responsibility of   
the terminating Party under this Agreement. In the event of termination by a Party, all Parties   
shall use commercially Reasonable Efforts to mitigate the costs, damages and charges arising as   
a consequence of termination. Upon termination of this Agreement, unless otherwise ordered or   
approved by FERC:

2.4.1 With respect to any portion of the Connecting Transmission Owner’s Attachment   
Facilities that have not yet been constructed or installed, the Connecting Transmission Owner   
shall to the extent possible and with Developer’s authorization cancel any pending orders of, or   
return, any materials or equipment for, or contracts for construction of, such facilities; provided   
that in the event Developer elects not to authorize such cancellation, Developer shall assume all   
payment obligations with respect to such materials, equipment, and contracts, and the

Connecting Transmission Owner shall deliver such material and equipment, and, if necessary,

assign such contracts, to Developer as soon as practicable, at Developer’s expense. To the extent   
that Developer has already paid Connecting Transmission Owner for any or all such costs of   
materials or equipment not taken by Developer, Connecting Transmission Owner shall promptly   
refund such amounts to Developer, less any costs, including penalties incurred by the Connecting   
Transmission Owner to cancel any pending orders of or return such materials, equipment, or   
contracts.

If Developer terminates this Agreement, it shall be responsible for all costs incurred in association with Developer’s interconnection, including any cancellation costs relating to orders or contracts for Attachment Facilities and equipment, and other expenses including any System Upgrade Facilities and System Deliverability Upgrades for which the Connecting Transmission Owner has incurred expenses and has not been reimbursed by the Developer.

2.4.2 Connecting Transmission Owner may, at its option, retain any portion of such

materials, equipment, or facilities that Developer chooses not to accept delivery of, in which case Connecting Transmission Owner shall be responsible for all costs associated with procuring such materials, equipment, or facilities.

2.4.3 With respect to any portion of the Attachment Facilities, and any other facilities   
already installed or constructed pursuant to the terms of this Agreement, Developer shall be

11

SERVICE AGREEMENT NO. 2710

responsible for all costs associated with the removal, relocation or other disposition or retirement of such materials, equipment, or facilities.

2.5 Disconnection.

Upon termination of this Agreement, Developer and Connecting Transmission Owner will take all appropriate steps to disconnect the Developer’s Merchant Transmission Facility from the New York State Transmission System. All costs required to effectuate such   
disconnection shall be borne by the terminating Party, unless such termination resulted from the non-terminating Party’s Default of this Agreement or such non-terminating Party otherwise is responsible for these costs under this Agreement.

2.6 Survival.

This Agreement shall continue in effect after termination to the extent necessary to

provide for final billings and payments and for costs incurred hereunder; including billings and payments pursuant to this Agreement; to permit the determination and enforcement of liability and indemnification obligations arising from acts or events that occurred while this Agreement was in effect; and to permit Developer and Connecting Transmission Owner each to have access to the lands of the other pursuant to this Agreement or other applicable agreements, to   
disconnect, remove or salvage its own facilities and equipment.

ARTICLE 3. REGULATORY FILINGS

NYISO and Connecting Transmission Owner shall file this Agreement (and any

amendment hereto) with the appropriate Governmental Authority, if required. Any information   
related to studies for interconnection asserted by Developer to contain Confidential Information   
shall be treated in accordance with Article 22 of this Agreement and Attachment F to the ISO   
OATT. If the Developer has executed this Agreement, or any amendment thereto, the Developer   
shall reasonably cooperate with NYISO and Connecting Transmission Owner with respect to   
such filing and to provide any information reasonably requested by NYISO and Connecting   
Transmission Owner needed to comply with Applicable Laws and Regulations.

ARTICLE 4. SCOPE OF INTERCONNECTION SERVICE

4.1 Provision of Service.

NYISO will provide Developer with interconnection service of the following type for the term of this Agreement.

4.1.1 Product.

NYISO will provide Energy Resource Interconnection Service and Capacity Resource Interconnection Service to Developer at the Point of Interconnection.

4.1.2 Developer is responsible for ensuring that its actual Merchant Transmission

Facility output matches the scheduled delivery from the Merchant Transmission Facility to the   
New York State Transmission System, consistent with the scheduling requirements of the

12

SERVICE AGREEMENT NO. 2710

NYISO’s FERC-approved market structure, including ramping into and out of such scheduled delivery, as measured at the Point of Interconnection, consistent with the scheduling   
requirements of the ISO OATT and any applicable FERC-approved market structure.

4.2 No Transmission Delivery Service.

The execution of this Agreement does not constitute a request for, nor agreement to

provide, any Transmission Service under the ISO OATT, and does not convey any right to

deliver electricity to any specific customer or Point of Delivery. If Developer wishes to obtain Transmission Service on the New York State Transmission System, then Developer must request such Transmission Service in accordance with the provisions of the ISO OATT.

4.3 No Other Services.

The execution of this Agreement does not constitute a request for, nor agreement to

provide Energy, any Ancillary Services or Installed Capacity under the NYISO Market

Administration and Control Area Services Tariff (“Services Tariff”). If Developer wishes to

supply Energy, Installed Capacity or Ancillary Services, then Developer will make application to do so in accordance with the NYISO Services Tariff.

ARTICLE 5. INTERCONNECTION FACILITIES ENGINEERING,   
 PROCUREMENT, AND CONSTRUCTION

5.1 Options.

Unless otherwise mutually agreed to by Developer and Connecting Transmission Owner, Developer shall select the In-Service Date, Initial Synchronization Date, and Commercial   
Operation Date; and either the Standard Option or Alternate Option set forth below, and such   
dates and selected option shall be set forth in Appendix B hereto. At the same time, Developer   
shall indicate whether it elects to exercise the Option to Build set forth in Article 5.1.3 below. If the dates designated by the Developer are not acceptable to the Connecting Transmission Owner, the Connecting Transmission Owner shall so notify the Developer within thirty (30) Calendar   
Days. Upon receipt of the notification that Developer’s designated dates are not acceptable to   
the Connecting Transmission Owner, the Developer shall notify the Connecting Transmission   
Owner within thirty (30) Calendar Days whether it elects to exercise the Option to Build if it has not already elected to exercise the Option to Build.

5.1.1 Standard Option.

The Connecting Transmission Owner shall design, procure, and construct the Connecting   
Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System   
Deliverability Upgrades, using Reasonable Efforts to complete the Connecting Transmission   
Owner’s Attachment Facilities and System Upgrade Facilities and System Deliverability   
Upgrades by the dates set forth in Appendix B hereto. The Connecting Transmission Owner   
shall not be required to undertake any action which is inconsistent with its standard safety   
practices, its material and equipment specifications, its design criteria and construction   
procedures, its labor agreements, and Applicable Laws and Regulations. In the event the

13

SERVICE AGREEMENT NO. 2710

Connecting Transmission Owner reasonably expects that it will not be able to complete the Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades by the specified dates, the Connecting Transmission Owner shall promptly provide written notice to the Developer and NYISO, and shall undertake Reasonable Efforts to meet the earliest dates thereafter.

5.1.2 Alternate Option.

If the dates designated by Developer are acceptable to Connecting Transmission Owner,   
the Connecting Transmission Owner shall so notify Developer and NYISO within thirty (30)   
Calendar Days, and shall assume responsibility for the design, procurement and construction of   
the Connecting Transmission Owner’s Attachment Facilities by the designated dates. If   
Connecting Transmission Owner subsequently fails to complete Connecting Transmission   
Owner’s Attachment Facilities by the In-Service Date, to the extent necessary to provide back   
feed power; or fails to complete System Upgrade Facilities or System Deliverability Upgrades by   
the Initial Synchronization Date to the extent necessary to allow for Trial Operation at full power   
output, unless other arrangements are made by the Developer and Connecting Transmission   
Owner for such Trial Operation; or fails to complete the System Upgrade Facilities and System   
Deliverability Upgrades by the Commercial Operation Date, as such dates are reflected in   
Appendix B hereto; Connecting Transmission Owner shall pay Developer liquidated damages in   
accordance with Article 5.3, Liquidated Damages, provided, however, the dates designated by   
Developer shall be extended day for day for each day that NYISO refuses to grant clearances to   
install equipment.

5.1.3 Option to Build.

Developer shall have the option to assume responsibility for the design, procurement and   
construction of Connecting Transmission Owner’s Attachment Facilities and Stand Alone   
System Upgrade Facilities on the dates specified in Article 5.1.2; provided that if an Attachment   
Facility or Stand Alone System Upgrade Facility is needed for more than one Developer’s   
project, Developer’s option to build such facility shall be contingent on the agreement of all   
other affected Developers. NYISO, Connecting Transmission Owner and Developer must agree   
as to what constitutes Stand Alone System Upgrade Facilities and identify such Stand Alone   
System Upgrade Facilities in Appendix A hereto. Except for Stand Alone System Upgrade   
Facilities, Developer shall have no right to construct System Upgrade Facilities under this   
option.

5.1.4 Negotiated Option.

If the dates designated by Developer are not acceptable to the Connecting Transmission   
Owner, the Developer and Connecting Transmission Owner shall in good faith attempt to   
negotiate terms and conditions (including revision of the specified dates and liquidated damages,   
the provision of incentives or the procurement and construction of all facilities other than the   
Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade   
Facilities if the Developer elects to exercise the Option to Build under Article 5.1.3. If the two   
Parties are unable to reach agreement on such terms and conditions, then, pursuant to Article

14

SERVICE AGREEMENT NO. 2710

5.1.1 (Standard Option), Connecting Transmission Owner shall assume responsibility for the design, procurement and construction of all facilities other than the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities if the Developer elects to exercise the Option to Build.

5.2 General Conditions Applicable to Option to Build.

If Developer assumes responsibility for the design, procurement and construction of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities, the following conditions apply:

5.2.1 Developer shall engineer, procure equipment, and construct the Connecting   
Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities (or portions thereof) using Good Utility Practice and using standards and specifications provided in advance by the Connecting Transmission Owner;

5.2.2 Developer’s engineering, procurement and construction of the Connecting

Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities shall comply with all requirements of law to which Connecting Transmission Owner would be subject in the engineering, procurement or construction of the Connecting Transmission Owner’s   
Attachment Facilities and Stand Alone System Upgrade Facilities;

5.2.3 Developer agrees to comply with all applicable provisions of Section 220 of the New York Labor Law (“Section 220”), as it may be amended from time to time. Pursuant to the requirements of Section 220, Developer agrees that, for work performed on existing Connecting Transmission Owner facilities (i.e., “public work”):

(i) Each laborer, workman or mechanic shall be paid no less than the prevailing wages as defined in Section 220,

(ii) The filing of payrolls shall be made in a manner consistent with subdivision threea (3(a)) of Section 220; this is a condition precedent to payment of any sums due and owing to any person for work done upon the project, and

(iii) No laborer, worker, or mechanic shall be permitted or required to work more than   
eight hours in any one calendar day or more than five days in any one week except in   
cases of extraordinary emergency including fire, flood, or danger to life or property.

Developer reserves its rights set forth in Section 220 to obtain dispensation permitting laborers, workers and mechanics to work additional hours or days per week.

5.2.4 Connecting Transmission Owner shall review and approve the engineering design, equipment acceptance tests, and the construction of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities;

15

SERVICE AGREEMENT NO. 2710

5.2.5 Prior to commencement of construction, Developer shall provide to Connecting   
Transmission Owner and NYISO a schedule for construction of the Connecting Transmission   
Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities, and shall promptly   
respond to requests for information from Connecting Transmission Owner or NYISO;

5.2.6 At any time during construction, Connecting Transmission Owner shall have the right to gain unrestricted access to the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities and to conduct inspections of the same;

5.2.7 At any time during construction, should any phase of the engineering, equipment   
procurement, or construction of the Connecting Transmission Owner’s Attachment Facilities and   
Stand Alone System Upgrade Facilities not meet the standards and specifications provided by   
Connecting Transmission Owner, the Developer shall be obligated to remedy deficiencies in that   
portion of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System   
Upgrade Facilities;

5.2.8 Developer shall indemnify Connecting Transmission Owner and NYISO for

claims arising from the Developer’s construction of Connecting Transmission Owner’s

Attachment Facilities and Stand Alone System Upgrade Facilities under procedures applicable to Article 18.1 Indemnity;

5.2.9 Developer shall transfer control of Connecting Transmission Owner’s Attachment   
Facilities and Stand Alone System Upgrade Facilities to the Connecting Transmission Owner;

5.2.10 Unless the Developer and Connecting Transmission Owner otherwise agree,

Developer shall transfer ownership of Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to Connecting Transmission Owner;

5.2.11 Connecting Transmission Owner shall approve and accept for operation and maintenance the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to the extent engineered, procured, and constructed in accordance with this Article 5.2; and

5.2.12 Developer shall deliver to NYISO and Connecting Transmission Owner “as built” drawings, information, and any other documents that are reasonably required by NYISO or   
Connecting Transmission Owner to assure that the Attachment Facilities and Stand Alone   
System Upgrade Facilities are built to the standards and specifications required by Connecting   
Transmission Owner.

5.2.13 If Developer exercises the Option to Build pursuant to Article 5.1.3, the

Developer shall pay the Connecting Transmission Owner the agreed upon amount of

$10,785,000 for the Connecting Transmission Owner to execute the responsibilities enumerated   
to Connecting Transmission Owner under Article 5.2. The Connecting Transmission Owner

16

SERVICE AGREEMENT NO. 2710

shall invoice Developer for this total amount to be divided on a monthly basis pursuant to Article

12.

5.3 Liquidated Damages.

The actual damages to the Developer, in the event the Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades are not   
completed by the dates designated by the Developer and accepted by the Connecting   
Transmission Owner pursuant to subparagraphs 5.1.2 or 5.1.4, above, may include Developer’s fixed operation and maintenance costs and lost opportunity costs. Such actual damages are   
uncertain and impossible to determine at this time. Because of such uncertainty, any liquidated damages paid by the Connecting Transmission Owner to the Developer in the event that   
Connecting Transmission Owner does not complete any portion of the Connecting Transmission Owner’s Attachment Facilities, System Upgrade Facilities or System Deliverability Upgrades by the applicable dates, shall be an amount equal to 1/2 of 1 percent per day of the actual cost of the Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades, in the aggregate, for which Connecting Transmission Owner   
has assumed responsibility to design, procure and construct.

However, in no event shall the total liquidated damages exceed 20 percent of the actual

cost of the Connecting Transmission Owner Attachment Facilities and System Upgrade Facilities   
and System Deliverability Upgrades for which the Connecting Transmission Owner has assumed   
responsibility to design, procure, and construct. The foregoing payments will be made by the   
Connecting Transmission Owner to the Developer as just compensation for the damages caused   
to the Developer, which actual damages are uncertain and impossible to determine at this time,   
and as reasonable liquidated damages, but not as a penalty or a method to secure performance of   
this Agreement. Liquidated damages, when the Developer and Connecting Transmission Owner   
agree to them, are the exclusive remedy for the Connecting Transmission Owner’s failure to   
meet its schedule.

Further, Connecting Transmission Owner shall not pay liquidated damages to Developer   
if: (1) Developer is not ready to commence use of the Connecting Transmission Owner’s   
Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades to take   
the delivery of power for the Developer’s Merchant Transmission Facility’s Trial Operation or to   
transmit power from the Developer’s Merchant Transmission Facility on the specified dates,   
unless the Developer would have been able to commence use of the Connecting Transmission   
Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades   
to take the delivery of power for Developer’s Merchant Transmission Facility’s Trial Operation   
or to export power from the Developer’s Merchant Transmission Facility, but for Connecting   
Transmission Owner’s delay; (2) the Connecting Transmission Owner’s failure to meet the   
specified dates is the result of the action or inaction of the Developer or any other Developer   
who has entered into a Merchant Transmission Facility Interconnection Agreement with the   
Connecting Transmission Owner and NYISO, or action or inaction by any other Party, or any   
other cause beyond Connecting Transmission Owner’s reasonable control or reasonable ability to   
cure; (3) the Developer has assumed responsibility for the design, procurement and construction   
of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System   
Upgrade Facilities; or (4) the Connecting Transmission Owner and Developer have otherwise

17

SERVICE AGREEMENT NO. 2710

agreed. In no event shall NYISO have any liability whatever to Developer for liquidated

damages associated with the engineering, procurement or construction of Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades.

5.4 Reserved.

5.5 Equipment Procurement.

If responsibility for construction of the Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades is to be borne by the Connecting Transmission Owner, then the Connecting Transmission Owner shall commence design of the Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades and procure necessary equipment as soon as   
practicable after all of the following conditions are satisfied, unless the Developer and   
Connecting Transmission Owner otherwise agree in writing:

5.5.1 NYISO and Connecting Transmission Owner have completed the Interconnection Facilities Study pursuant to the Interconnection Facilities Study Agreement;

5.5.2 The NYISO has completed the required cost allocation analyses, and Developer   
has accepted its share of the costs for necessary System Upgrade Facilities and System   
Deliverability Upgrades in accordance with the provisions of Attachment S of the ISO OATT;

5.5.3 The Connecting Transmission Owner has received written authorization to

proceed with design and procurement from the Developer by the date specified in Appendix B hereto; and

5.5.4 The Developer has provided security to the Connecting Transmission Owner in accordance with Article 11.5 by the dates specified in Appendix B hereto.

5.6 Construction Commencement.

The Connecting Transmission Owner shall commence construction of the Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System   
Deliverability Upgrades for which it is responsible as soon as practicable after the following additional conditions are satisfied:

5.6.1 Approval of the appropriate Governmental Authority has been obtained for any facilities requiring regulatory approval;

5.6.2 Necessary real property rights and rights-of-way have been obtained, to the extent   
required for the construction of a discrete aspect of the Connecting Transmission Owner’s   
Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades;

5.6.3 The Connecting Transmission Owner has received written authorization to

proceed with construction from the Developer by the date specified in Appendix B hereto; and

18

SERVICE AGREEMENT NO. 2710

5.6.4 The Developer has provided security to the Connecting Transmission Owner in accordance with Article 11.5 by the dates specified in Appendix B hereto.

5.7 Work Progress.

The Developer and Connecting Transmission Owner will keep each other, and NYISO, advised periodically as to the progress of their respective design, procurement and construction efforts. Any Party may, at any time, request a progress report from the Developer or Connecting Transmission Owner. If, at any time, the Developer determines that the completion of the   
Connecting Transmission Owner’s Attachment Facilities will not be required until after the   
specified In-Service Date, the Developer will provide written notice to the Connecting   
Transmission Owner and NYISO of such later date upon which the completion of the   
Connecting Transmission Owner’s Attachment Facilities will be required.

5.8 Information Exchange.

As soon as reasonably practicable after the Effective Date, the Developer and Connecting Transmission Owner shall exchange information, and provide NYISO the same information, regarding the design and compatibility of their respective Attachment Facilities and   
compatibility of the Attachment Facilities with the New York State Transmission System, and shall work diligently and in good faith to make any necessary design changes.

5.9 Other Interconnection Options

5.9.1 Limited Operation.

If any of the Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades are not reasonably expected to be completed prior   
to the Commercial Operation Date of the Developer’s Merchant Transmission Facility, NYISO   
shall, upon the request and at the expense of Developer, in conjunction with the Connecting   
Transmission Owner, perform operating studies on a timely basis to determine the extent to   
which the Developer’s Merchant Transmission Facility and the Developer’s Attachment   
Facilities may operate prior to the completion of the Connecting Transmission Owner’s   
Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades consistent with Applicable Laws and Regulations, Applicable Reliability Standards, Good Utility Practice, and this Agreement. Connecting Transmission Owner and NYISO shall permit Developer to   
operate the Developer’s Merchant Transmission Facility and the Developer’s Attachment   
Facilities in accordance with the results of such studies.

5.9.2 Provisional Interconnection Service.

Prior to the completion of the Large Facility Interconnection Procedures and prior to

completion of requisite Attachment Facilities, Distribution Upgrades, System Upgrade Facilities,   
System Distribution Upgrades, or System Protection Facilities, the Developer may request an   
evaluation for Provisional Interconnection Service. NYISO, in conjunction with the Connecting   
Transmission Owner, shall determine, through available studies or additional studies as   
necessary, whether stability, short circuit, thermal, and/or voltage issues would arise if the

19

SERVICE AGREEMENT NO. 2710

Developer interconnects without modifications to the Merchant Transmission Facility or the

New York State Transmission System (or Distribution System as applicable). NYISO, in

conjunction with the Connecting Transmission Owner, shall determine whether any Attachment   
Facilities, Distribution Upgrades, System Upgrade Facilities, System Deliverability Upgrades, or   
System Protection Facilities, which are necessary to meet Applicable Laws and Regulations,   
Applicable Reliability Standards, and Good Utility Practice, are in place prior to the   
commencement of interconnection service from the Merchant Transmission Facility. Where   
available studies indicate that the Attachment Facilities, Distribution Upgrades, System Upgrade   
Facilities, System Deliverability Upgrades, or System Protection Facilities are required for the   
interconnection of a new, modified and/or expanded Merchant Transmission Facility but such   
facilities are not currently in place, NYISO, in conjunction with the Connecting Transmission   
Owner, will perform a study, at the Developer’s expense, to confirm the facilities that are   
required for Provisional Interconnection Service. The maximum permissible output of the   
Merchant Transmission Facility in the Provisional Merchant Transmission Facility   
Interconnection Agreement shall be studied, at the Developer’s expense, and updated annually.   
The NYISO shall issue the study’s findings in writing to the Developer and Connecting   
Transmission Owner(s). Following a determination by NYISO, in conjunction with the   
Connecting Transmission Owner, that the Developer may reliably provide Provisional   
Interconnection Service, NYISO shall tender to the Developer and Connecting Transmission   
Owner, a Provisional Large Facility Interconnection Agreement. NYISO, Developer, and   
Connecting Transmission Owner may execute the Provisional Merchant Transmission Facility   
Interconnection Agreement, or the Developer may request the filing of an unexecuted   
Provisional Merchant Transmission Facility Interconnection Agreement with the Commission.   
The Developer shall assume all risk and liabilities with respect to changes between the   
Provisional Merchant Transmission Facility Interconnection Agreement and the Merchant   
Transmission Facility Interconnection Agreement, including changes in output limits and the   
cost responsibilities for the Attachment Facilities, System Upgrade Facilities, System   
Deliverability Upgrades, and/or System Protection Facilities.

5.10 Developer’s Attachment Facilities (“DAF”).

Developer shall, at its expense, design, procure, construct, own and install the DAF, as set forth in Appendix A hereto.

5.10.1 DAF Specifications.

Developer shall submit initial specifications for the DAF, including System Protection Facilities, to Connecting Transmission Owner and NYISO at least one hundred eighty (180) Calendar Days prior to the Initial Synchronization Date; and final specifications for review and comment at least ninety (90) Calendar Days prior to the Initial Synchronization Date.   
Connecting Transmission Owner and NYISO shall review such specifications to ensure that the DAF are compatible with the technical specifications, operational control, and safety   
requirements of the Connecting Transmission Owner and NYISO and comment on such   
specifications within thirty (30) Calendar Days of Developer’s submission. All specifications provided hereunder shall be deemed to be Confidential Information.

20

SERVICE AGREEMENT NO. 2710

5.10.2 No Warranty.

The review of Developer’s final specifications by Connecting Transmission Owner and NYISO shall not be construed as confirming, endorsing, or providing a warranty as to the design, fitness, safety, durability or reliability of the Merchant Transmission Facility, or the DAF.   
Developer shall make such changes to the DAF as may reasonably be required by Connecting Transmission Owner or NYISO, in accordance with Good Utility Practice, to ensure that the DAF are compatible with the technical specifications, operational control, and safety   
requirements of the Connecting Transmission Owner and NYISO.

5.10.3 DAF Construction.

The DAF shall be designed and constructed in accordance with Good Utility Practice.   
Within one hundred twenty (120) Calendar Days after the Commercial Operation Date, unless   
the Developer and Connecting Transmission Owner agree on another mutually acceptable   
deadline, the Developer shall deliver to the Connecting Transmission Owner and NYISO “as-  
built” drawings, information and documents for the DAF, such as: a one-line diagram, a site plan   
showing the Merchant Transmission Facility and the DAF, plan and elevation drawings showing   
the layout of the DAF, a relay functional diagram, relaying AC and DC schematic wiring   
diagrams and relay settings for all facilities associated with the Developer’s step-up   
transformers, the facilities connecting the Merchant Transmission Facility to the step-up   
transformers and the DAF, and the impedances (determined by factory tests) for the associated   
step-up transformers and the Merchant Transmission Facility. The Developer shall provide to,   
and coordinate with, Connecting Transmission Owner and NYISO with respect to proposed   
specifications for the excitation system, automatic voltage regulator, Merchant Transmission   
Facility control and protection settings, transformer tap settings, and communications, if   
applicable.

5.11 Connecting Transmission Owner’s Attachment Facilities Construction.

The Connecting Transmission Owner’s Attachment Facilities shall be designed and

constructed in accordance with Good Utility Practice. Upon request, within one hundred twenty   
(120) Calendar Days after the Commercial Operation Date, unless the Connecting Transmission   
Owner and Developer agree on another mutually acceptable deadline, the Connecting   
Transmission Owner shall deliver to the Developer “as-built” drawings, relay diagrams,   
information and documents for the Connecting Transmission Owner’s Attachment Facilities set   
forth in Appendix A.

The Connecting Transmission Owner shall transfer operational control of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to the NYISO upon completion of such facilities.

5.12 Access Rights.

Upon reasonable notice and supervision by the Granting Party, and subject to any

required or necessary regulatory approvals, either the Connecting Transmission Owner or

Developer (“Granting Party”) shall furnish to the other of those two Parties (“Access Party”) at

21

SERVICE AGREEMENT NO. 2710

no cost any rights of use, licenses, rights of way and easements with respect to lands owned or   
controlled by the Granting Party, its agents (if allowed under the applicable agency agreement),   
or any Affiliate, that are necessary to enable the Access Party to obtain ingress and egress at the   
Point of Interconnection to construct, operate, maintain, repair, test (or witness testing), inspect,   
replace or remove facilities and equipment to: (i) interconnect the Merchant Transmission   
Facility with the New York State Transmission System; (ii) operate and maintain the Merchant   
Transmission Facility, the Attachment Facilities and the New York State Transmission System;   
and (iii) disconnect or remove the Access Party’s facilities and equipment upon termination of   
this Agreement. In exercising such licenses, rights of way and easements, the Access Party shall   
not unreasonably disrupt or interfere with normal operation of the Granting Party’s business and   
shall adhere to the safety rules and procedures established in advance, as may be changed from   
time to time, by the Granting Party and provided to the Access Party. The Access Party shall   
indemnify the Granting Party against all claims of injury or damage from third parties resulting   
from the exercise of the access rights provided for herein.

5.13 Lands of Other Property Owners.

If any part of the Connecting Transmission Owner’s Attachment Facilities and/or System   
Upgrade Facilities and/or System Deliverability Upgrades is to be installed on property owned   
by persons other than Developer or Connecting Transmission Owner, the Connecting   
Transmission Owner agrees, to the extent consistent with applicable law, at Developer’s expense   
to use efforts, similar in nature and extent to those that it typically undertakes for its own or   
affiliated generation or transmission facilities, including use of its eminent domain authority, and   
to the extent consistent with state law, to procure from such persons any rights of use, licenses,   
rights of way and easements that are necessary to construct, operate, maintain, test, inspect,   
replace or remove the Connecting Transmission Owner’s Attachment Facilities and/or System   
Upgrade Facilities and/or System Deliverability Upgrades upon such property. Notwithstanding   
the previous sentence, the Connecting Transmission Owner’s exercise of powers and rights to   
acquire real property or any rights in real property, pursuant to this Section 5.13, is subject to the   
provisions of the New York Public Authorities Law (or any amendments thereto), including   
Section 1007.

5.14 Permits.

NYISO, Connecting Transmission Owner and the Developer shall cooperate with each other in good faith in obtaining all permits, licenses and authorizations that are necessary to   
accomplish the interconnection in compliance with Applicable Laws and Regulations. With respect to this paragraph, Connecting Transmission Owner shall provide permitting assistance to the Developer comparable to that provided to the Connecting Transmission Owner’s own, or an Affiliate’s generation or transmission facilities, if any.

5.15 Early Construction of Base Case Facilities.

Developer may request Connecting Transmission Owner to construct, and Connecting   
Transmission Owner shall construct, subject to a binding cost allocation agreement reached in   
accordance with Attachment S to the ISO OATT, including Section 25.8.7 thereof, using   
Reasonable Efforts to accommodate Developer’s In-Service Date, all or any portion of any

22

SERVICE AGREEMENT NO. 2710

System Upgrade Facilities or System Deliverability Upgrades required for Developer to be

interconnected to the New York State Transmission System which are included in the Base Case of the Class Year Study for the Developer, and which also are required to be constructed for another Developer, but where such construction is not scheduled to be completed in time to   
achieve Developer’s In-Service Date.

5.16 Suspension.

Developer reserves the right, upon written notice to Connecting Transmission Owner and   
NYISO, to suspend at any time all work by Connecting Transmission Owner associated with the   
construction and installation of Connecting Transmission Owner’s Attachment Facilities and/or   
System Upgrade Facilities and/or System Deliverability Upgrades required for only that   
Developer under this Agreement with the condition that the New York State Transmission   
System shall be left in a safe and reliable condition in accordance with Good Utility Practice and   
the safety and reliability criteria of Connecting Transmission Owner and NYISO. In such event,   
Developer shall be responsible for all reasonable and necessary costs and/or obligations in   
accordance with Attachment S to the ISO OATT including those which Connecting   
Transmission Owner (i) has incurred pursuant to this Agreement prior to the suspension and (ii)   
incurs in suspending such work, including any costs incurred to perform such work as may be   
necessary to ensure the safety of persons and property and the integrity of the New York State   
Transmission System during such suspension and, if applicable, any costs incurred in connection   
with the cancellation or suspension of material, equipment and labor contracts which Connecting   
Transmission Owner cannot reasonably avoid; provided, however, that prior to canceling or   
suspending any such material, equipment or labor contract, Connecting Transmission Owner   
shall obtain Developer’s authorization to do so.

Connecting Transmission Owner shall invoice Developer for such costs pursuant to

Article 12 and shall use due diligence to minimize its costs. In the event Developer suspends

work by Connecting Transmission Owner required under this Agreement pursuant to this Article

5.16, and has not requested Connecting Transmission Owner to recommence the work required under this Agreement on or before the expiration of three (3) years following commencement of such suspension, this Agreement shall be deemed terminated. The three-year period shall begin on the date the suspension is requested, or the date of the written notice to Connecting   
Transmission Owner and NYISO, if no effective date is specified.

5.17 Taxes.

5.17.1 Developer Payments Not Taxable.

The Developer and Connecting Transmission Owner intend that all payments or property transfers made by Developer to Connecting Transmission Owner for the installation of the   
Connecting Transmission Owner’s Attachment Facilities and the System Upgrade Facilities and the System Deliverability Upgrades shall be non-taxable, either as contributions to capital, or as an advance, in accordance with the Internal Revenue Code and any applicable state income tax laws and shall not be taxable as contributions in aid of construction or otherwise under the   
Internal Revenue Code and any applicable state income tax laws.

23

SERVICE AGREEMENT NO. 2710

5.17.2 Representations and Covenants.

In accordance with IRS Notice 2001-82 and IRS Notice 88-129, as applicable to the   
Merchant Transmission Facility, Developer represents and covenants that (i) ownership of the   
electricity transmitted on the Merchant Transmission Facility will pass to another party prior to   
the transmission of the electricity on the New York State Transmission System from the Point of   
Interconnection, (ii) for income tax purposes, the amount of any payments and the cost of any   
property transferred to the Connecting Transmission Owner for the Connecting Transmission   
Owner’s Attachment Facilities will be capitalized by Developer as an intangible asset and   
recovered using the straight-line method over a useful life of twenty (20) years, and (iii) any   
portion of the Connecting Transmission Owner’s Attachment Facilities that is a “dual-use   
intertie,” within the meaning of IRS Notice 88-129, is reasonably expected to carry only a de   
minimis amount of electricity in the direction of the Merchant Transmission Facility. For this   
purpose, “de minimis amount” means no more than 5 percent of the total power flows in both   
directions, calculated in accordance with the “5 percent test” set forth in IRS Notice 88-129.   
This is not intended to be an exclusive list of the relevant conditions that must be met to conform   
to IRS requirements for non-taxable treatment.

At Connecting Transmission Owner’s request, Developer shall provide Connecting

Transmission Owner with a report from an independent engineer confirming its representation in clause (iii), above. Connecting Transmission Owner represents and covenants that the cost of the Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities paid for by Developer will have no net effect on the base upon which rates are determined.

5.17.3 Indemnification for the Cost Consequences of Current Tax Liability Imposed   
 Upon the Connecting Transmission Owner.

Notwithstanding Article 5.17.1, Developer shall protect, indemnify and hold harmless

Connecting Transmission Owner from the cost consequences of any current tax liability imposed against Connecting Transmission Owner as the result of payments or property transfers made by Developer to Connecting Transmission Owner under this Agreement, as well as any interest and penalties, other than interest and penalties attributable to any delay caused by Connecting   
Transmission Owner.

Connecting Transmission Owner shall not include a gross-up for the cost consequences   
of any current tax liability in the amounts it charges Developer under this Agreement unless (i)   
Connecting Transmission Owner has determined, in good faith, that the payments or property   
transfers made by Developer to Connecting Transmission Owner should be reported as income   
subject to taxation or (ii) any Governmental Authority directs Connecting Transmission Owner   
to report payments or property as income subject to taxation; provided, however, that Connecting   
Transmission Owner may require Developer to provide security, in a form reasonably acceptable   
to Connecting Transmission Owner (such as a parental guarantee or a letter of credit), in an   
amount equal to the cost consequences of any current tax liability under this Article 5.17.   
Developer shall reimburse Connecting Transmission Owner for such costs on a fully grossed-up   
basis, in accordance with Article 5.17.4, within thirty (30) Calendar Days of receiving written   
notification from Connecting Transmission Owner of the amount due, including detail about how   
the amount was calculated.

24

SERVICE AGREEMENT NO. 2710

This indemnification obligation shall terminate at the earlier of (1) the expiration of the ten-year testing period and the applicable statute of limitation, as it may be extended by the Connecting Transmission Owner upon request of the IRS, to keep these years open for audit or adjustment, or (2) the occurrence of a subsequent taxable event and the payment of any related indemnification obligations as contemplated by this Article 5.17.

5.17.4 Tax Gross-Up Amount.

Developer’s liability for the cost consequences of any current tax liability under this

Article 5.17 shall be calculated on a fully grossed-up basis. Except as may otherwise be agreed   
to by the parties, this means that Developer will pay Connecting Transmission Owner, in   
addition to the amount paid for the Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades, an amount equal to (1) the current taxes imposed on Connecting   
Transmission Owner (“Current Taxes”) on the excess of (a) the gross income realized by   
Connecting Transmission Owner as a result of payments or property transfers made by   
Developer to Connecting Transmission Owner under this Agreement (without regard to any   
payments under this Article 5.17) (the “Gross Income Amount”) over (b) the present value of   
future tax deductions for depreciation that will be available as a result of such payments or   
property transfers (the “Present Value Depreciation Amount”), plus (2) an additional amount   
sufficient to permit the Connecting Transmission Owner to receive and retain, after the payment   
of all Current Taxes, an amount equal to the net amount described in clause (1).

For this purpose, (i) Current Taxes shall be computed based on Connecting Transmission   
Owner’s composite federal and state tax rates at the time the payments or property transfers are   
received and Connecting Transmission Owner will be treated as being subject to tax at the   
highest marginal rates in effect at that time (the “Current Tax Rate”), and (ii) the Present Value   
Depreciation Amount shall be computed by discounting Connecting Transmission Owner’s   
anticipated tax depreciation deductions as a result of such payments or property transfers by   
Connecting Transmission Owner’s current weighted average cost of capital. Thus, the formula   
for calculating Developer’s liability to Connecting Transmission Owner pursuant to this Article

5.17.4 can be expressed as follows: (Current Tax Rate x (Gross Income Amount - Present Value Depreciation Amount))/(1 - Current Tax Rate). Developer’s estimated tax liability in the event taxes are imposed shall be stated in Appendix A, Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades.

5.17.5 Private Letter Ruling or Change or Clarification of Law.

At Developer’s request and expense, Connecting Transmission Owner shall file with the   
IRS a request for a private letter ruling as to whether any property transferred or sums paid, or to   
be paid, by Developer to Connecting Transmission Owner under this Agreement are subject to   
federal income taxation. Developer will prepare the initial draft of the request for a private letter   
ruling, and will certify under penalties of perjury that all facts represented in such request are   
true and accurate to the best of Developer’s knowledge. Connecting Transmission Owner and   
Developer shall cooperate in good faith with respect to the submission of such request.

25

SERVICE AGREEMENT NO. 2710

Connecting Transmission Owner shall keep Developer fully informed of the status of   
such request for a private letter ruling and shall execute either a privacy act waiver or a limited   
power of attorney, in a form acceptable to the IRS, that authorizes Developer to participate in all   
discussions with the IRS regarding such request for a private letter ruling. Connecting   
Transmission Owner shall allow Developer to attend all meetings with IRS officials about the   
request and shall permit Developer to prepare the initial drafts of any follow-up letters in   
connection with the request.

5.17.6 Subsequent Taxable Events.

If, within 10 years from the date on which the relevant Connecting Transmission Owner   
Attachment Facilities are placed in service, (i) Developer Breaches the covenants contained in   
Article 5.17.2, (ii) a “disqualification event” occurs within the meaning of IRS Notice 88-129, or   
(iii) this Agreement terminates and Connecting Transmission Owner retains ownership of the   
Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades, the Developer shall pay a tax gross-up for the cost   
consequences of any current tax liability imposed on Connecting Transmission Owner,   
calculated using the methodology described in Articles 5.17.3 and 5.17.4 and in accordance with   
IRS Notice 90-60.

5.17.7 Contests.

In the event any Governmental Authority determines that Connecting Transmission

Owner’s receipt of payments or property constitutes income that is subject to taxation,

Connecting Transmission Owner shall notify Developer, in writing, within thirty (30) Calendar   
Days of receiving notification of such determination by a Governmental Authority. Upon the   
timely written request by Developer and at Developer’s sole expense, Connecting Transmission   
Owner may appeal, protest, seek abatement of, or otherwise oppose such determination. Upon   
Developer’s written request and sole expense, Connecting Transmission Owner may file a claim   
for refund with respect to any taxes paid under this Article 5.17, whether or not it has received   
such a determination. Connecting Transmission Owner reserves the right to make all decisions   
with regard to the prosecution of such appeal, protest, abatement or other contest, including the   
selection of counsel and compromise or settlement of the claim, but Connecting Transmission   
Owner shall keep Developer informed, shall consider in good faith suggestions from Developer   
about the conduct of the contest, and shall reasonably permit Developer or an Developer

representative to attend contest proceedings.

Developer shall pay to Connecting Transmission Owner on a periodic basis, as invoiced   
by Connecting Transmission Owner, Connecting Transmission Owner’s documented reasonable   
costs of prosecuting such appeal, protest, abatement or other contest, including any costs   
associated with obtaining the opinion of independent tax counsel described in this Article 5.17.7.   
The Connecting Transmission Owner may abandon any contest if the Developer fails to provide   
payment to the Connecting Transmission Owner within thirty (30) Calendar Days of receiving   
such invoice. At any time during the contest, Connecting Transmission Owner may agree to a   
settlement either with Developer’s consent or after obtaining written advice from nationally-  
recognized tax counsel, selected by Connecting Transmission Owner, but reasonably acceptable

26

SERVICE AGREEMENT NO. 2710

to Developer, that the proposed settlement represents a reasonable settlement given the hazards   
of litigation. Developer’s obligation shall be based on the amount of the settlement agreed to by   
Developer, or if a higher amount, so much of the settlement that is supported by the written   
advice from nationally-recognized tax counsel selected under the terms of the preceding   
sentence. The settlement amount shall be calculated on a fully grossed-up basis to cover any   
related cost consequences of the current tax liability. The Connecting Transmission Owner may   
also settle any tax controversy without receiving the Developer’s consent or any such written   
advice; however, any such settlement will relieve the Developer from any obligation to   
indemnify Connecting Transmission Owner for the tax at issue in the contest (unless the failure   
to obtain written advice is attributable to the Developer’s unreasonable refusal to the   
appointment of independent tax counsel).

5.17.8 Refund.

In the event that (a) a private letter ruling is issued to Connecting Transmission Owner   
which holds that any amount paid or the value of any property transferred by Developer to   
Connecting Transmission Owner under the terms of this Agreement is not subject to federal   
income taxation, (b) any legislative change or administrative announcement, notice, ruling or   
other determination makes it reasonably clear to Connecting Transmission Owner in good faith   
that any amount paid or the value of any property transferred by Developer to Connecting   
Transmission Owner under the terms of this Agreement is not taxable to Connecting   
Transmission Owner, (c) any abatement, appeal, protest, or other contest results in a   
determination that any payments or transfers made by Developer to Connecting Transmission   
Owner are not subject to federal income tax, or (d) if Connecting Transmission Owner receives a   
refund from any taxing authority for any overpayment of tax attributable to any payment or   
property transfer made by Developer to Connecting Transmission Owner pursuant to this   
Agreement, Connecting Transmission Owner shall promptly refund to Developer the following:

(i) Any payment made by Developer under this Article 5.17 for taxes that is   
attributable to the amount determined to be non-taxable, together with interest thereon,

(ii) Interest on any amounts paid by Developer to Connecting Transmission Owner for such taxes which Connecting Transmission Owner did not submit to the taxing authority, calculated in accordance with the methodology set forth in FERC’s regulations at 18 C.F.R. §35.19a(a)(2)(iii) from the date payment was made by Developer to the date Connecting   
Transmission Owner refunds such payment to Developer, and

(iii) With respect to any such taxes paid by Connecting Transmission Owner, any   
refund or credit Connecting Transmission Owner receives or to which it may be entitled from   
any Governmental Authority, interest (or that portion thereof attributable to the payment   
described in clause (i), above) owed to the Connecting Transmission Owner for such   
overpayment of taxes (including any reduction in interest otherwise payable by Connecting   
Transmission Owner to any Governmental Authority resulting from an offset or credit);   
provided, however, that Connecting Transmission Owner will remit such amount promptly to   
Developer only after and to the extent that Connecting Transmission Owner has received a tax

27

SERVICE AGREEMENT NO. 2710

refund, credit or offset from any Governmental Authority for any applicable overpayment of income tax related to the Connecting Transmission Owner’s Attachment Facilities.

The intent of this provision is to leave both the Developer and Connecting Transmission Owner, to the extent practicable, in the event that no taxes are due with respect to any payment for Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades hereunder, in the same position they would have been in had no such tax payments been made.

5.17.9 Taxes Other Than Income Taxes.

Upon the timely request by Developer, and at Developer’s sole expense, Connecting

Transmission Owner shall appeal, protest, seek abatement of, or otherwise contest any tax (other   
than federal or state income tax) asserted or assessed against Connecting Transmission Owner   
for which Developer may be required to reimburse Connecting Transmission Owner under the   
terms of this Agreement. Developer shall pay to Connecting Transmission Owner on a periodic   
basis, as invoiced by Connecting Transmission Owner, Connecting Transmission Owner’s   
documented reasonable costs of prosecuting such appeal, protest, abatement, or other contest.   
Developer and Connecting Transmission Owner shall cooperate in good faith with respect to any   
such contest. Unless the payment of such taxes is a prerequisite to an appeal or abatement or   
cannot be deferred, no amount shall be payable by Developer to Connecting Transmission   
Owner for such taxes until they are assessed by a final, non-appealable order by any court or   
agency of competent jurisdiction. In the event that a tax payment is withheld and ultimately due   
and payable after appeal, Developer will be responsible for all taxes, interest and penalties, other   
than penalties attributable to any delay caused by Connecting Transmission Owner.

5.18 Tax Status; Non-Jurisdictional Entities.

5.18.1 Tax Status.

Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.   
Nothing in this Agreement is intended to adversely affect the tax status of any Party including   
the status of NYISO, or the status of any Connecting Transmission Owner with respect to the   
issuance of bonds including, but not limited to, Local Furnishing Bonds. Notwithstanding any   
other provisions of this Agreement, LIPA, NYPA and Consolidated Edison Company of New   
York, Inc. shall not be required to comply with any provisions of this Agreement that would

result in the loss of tax-exempt status of any of its Tax-Exempt Bonds or impair their ability to issue future tax-exempt obligations. For purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc., the interest on which is not included in gross income under the   
Internal Revenue Code.

5.18.2 Non-Jurisdictional Entities.

LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA, from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general ratemaking authority.

28

SERVICE AGREEMENT NO. 2710

5.19 Modification.

5.19.1 General.

Either the Developer or Connecting Transmission Owner may undertake modifications to   
its facilities covered by this Agreement. If either the Developer or Connecting Transmission   
Owner plans to undertake a modification that reasonably may be expected to affect the other   
Party’s facilities, that Party shall provide to the other Party, and to NYISO, sufficient   
information regarding such modification so that the other Party and NYISO may evaluate the   
potential impact of such modification prior to commencement of the work. Such information   
shall be deemed to be Confidential Information hereunder and shall include information   
concerning the timing of such modifications and whether such modifications are expected to   
interrupt the flow of electricity from the Merchant Transmission Facility. The Party desiring to   
perform such work shall provide the relevant drawings, plans, and specifications to the other   
Party and NYISO at least ninety (90) Calendar Days in advance of the commencement of the   
work or such shorter period upon which the Parties may agree, which agreement shall not   
unreasonably be withheld, conditioned or delayed.

In the case of Merchant Transmission Facility modifications that do not require

Developer to submit an Interconnection Request, the NYISO shall provide, within sixty (60) Calendar Days (or such other time as the Parties may agree), an estimate of any additional   
modifications to the New York State Transmission System, Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades   
necessitated by such Developer modification and a good faith estimate of the costs thereof. The Developer shall be responsible for the cost of any such additional modifications, including the cost of studying the impact of the Developer modification.

5.19.2 Standards.

Any additions, modifications, or replacements made to a Party’s facilities shall be

designed, constructed and operated in accordance with this Agreement, NYISO requirements and Good Utility Practice.

5.19.3 Modification Costs.

Developer shall not be assigned the costs of any additions, modifications, or replacements that Connecting Transmission Owner makes to the Connecting Transmission Owner’s   
Attachment Facilities or the New York State Transmission System to facilitate the   
interconnection of a third party to the Connecting Transmission Owner’s Attachment Facilities or the New York State Transmission System, or to provide Transmission Service to a third party under the ISO OATT, except in accordance with the cost allocation procedures in Attachment S of the ISO OATT. Developer shall be responsible for the costs of any additions, modifications, or replacements to the Developer’s Attachment Facilities that may be necessary to maintain or upgrade such Developer’s Attachment Facilities consistent with Applicable Laws and   
Regulations, Applicable Reliability Standards or Good Utility Practice.

29

SERVICE AGREEMENT NO. 2710

ARTICLE 6. TESTING AND INSPECTION

6.1 Pre-Commercial Operation Date Testing and Modifications.

Prior to the Commercial Operation Date, the Connecting Transmission Owner shall test   
the Connecting Transmission Owner’s Attachment Facilities (including required control   
technologies and protection systems) and System Upgrade Facilities and System Deliverability   
Upgrades and Developer shall test the Merchant Transmission Facility and the Developer’s   
Attachment Facilities to ensure their safe and reliable operation. Similar testing may be required   
after initial operation. Developer and Connecting Transmission Owner shall each make any   
modifications to its facilities that are found to be necessary as a result of such testing. Developer   
shall bear the cost of all such testing and modifications. Developer shall transmit test energy   
over the Merchant Transmission Facility only if it has arranged for the injection into the New   
York Control Area of such test energy in accordance with NYISO procedures.

6.2 Post-Commercial Operation Date Testing and Modifications.

Developer and Connecting Transmission Owner shall each at its own expense perform   
routine inspection and testing of its facilities and equipment in accordance with Good Utility   
Practice and Applicable Reliability Standards as may be necessary to ensure the continued   
interconnection of the Merchant Transmission Facility with the New York State Transmission   
System in a safe and reliable manner. Developer and Connecting Transmission Owner shall   
each have the right, upon advance written notice, to require reasonable additional testing of the   
other Party’s facilities, at the requesting Party’s expense, as may be in accordance with Good   
Utility Practice.

6.3 Right to Observe Testing.

Developer and Connecting Transmission Owner shall each notify the other Party, and the NYISO, in advance of its performance of tests of its Attachment Facilities and the Merchant Transmission Facility. The other Party, and the NYISO, shall each have the right, at its own expense, to observe such testing.

6.4 Right to Inspect.

Developer and Connecting Transmission Owner shall each have the right, but shall have   
no obligation to: (i) observe the other Party’s tests and/or inspection of any of its System   
Protection Facilities and other protective equipment; (ii) review the settings of the other Party’s   
System Protection Facilities and other protective equipment; and (iii) review the other Party’s   
maintenance records relative to the Attachment Facilities, the System Protection Facilities and   
other protective equipment. NYISO shall have these same rights of inspection as to the facilities   
and equipment of Developer and Connecting Transmission Owner. A Party may exercise these   
rights from time to time as it deems necessary upon reasonable notice to the other Party. The   
exercise or non-exercise by a Party of any such rights shall not be construed as an endorsement   
or confirmation of any element or condition of the Attachment Facilities or the System   
Protection Facilities or other protective equipment or the operation thereof, or as a warranty as to   
the fitness, safety, desirability, or reliability of same. Any information that a Party obtains

30

SERVICE AGREEMENT NO. 2710

through the exercise of any of its rights under this Article 6.4 shall be treated in accordance with Article 22 of this Agreement and Attachment F to the ISO OATT.

ARTICLE 7. METERING

7.1 General.

Developer and Connecting Transmission Owner shall each comply with applicable   
requirements of NYISO and the New York Public Service Commission when exercising its   
rights and fulfilling its responsibilities under this Article 7. Unless otherwise agreed by the   
Connecting Transmission Owner and NYISO approved meter service provider and Developer,   
the Connecting Transmission Owner shall install Metering Equipment at the Point of   
Interconnection prior to any operation of the Merchant Transmission Facility and shall own,   
operate, test and maintain such Metering Equipment. Net power flows including MW and   
MVAR, MWHR and loss profile data to and from the Merchant Transmission Facility shall be   
measured at the Point of Interconnection. Connecting Transmission Owner shall provide   
metering quantities, in analog and/or digital form, as required, to Developer or NYISO upon   
request. Developer shall bear all reasonable documented costs associated with the purchase,   
installation, operation, testing and maintenance of the Metering Equipment.

7.2 Check Meters.

Developer, at its option and expense, may install and operate, on its premises and on its   
side of the Point of Interconnection, one or more check meters to check Connecting   
Transmission Owner’s meters. Such check meters shall be for check purposes only and shall not   
be used for the measurement of power flows for purposes of this Agreement, except as provided   
in Article 7.4 below. The check meters shall be subject at all reasonable times to inspection and   
examination by Connecting Transmission Owner or its designee. The installation, operation and   
maintenance thereof shall be performed entirely by Developer in accordance with Good Utility   
Practice.

7.3 Standards.

Connecting Transmission Owner shall install, calibrate, and test revenue quality Metering Equipment including potential transformers and current transformers in accordance with   
applicable ANSI and PSC standards as detailed in the NYISO Control Center Communications Manual and in the NYISO Revenue Metering Requirements Manual.

7.4 Testing of Metering Equipment.

Connecting Transmission Owner shall inspect and test all of its Metering Equipment

upon installation and at least once every two (2) years thereafter. If requested to do so by

NYISO or Developer, Connecting Transmission Owner shall, at Developer’s expense, inspect or   
test Metering Equipment more frequently than every two (2) years. Connecting Transmission   
Owner shall give reasonable notice of the time when any inspection or test shall take place, and   
Developer and NYISO may have representatives present at the test or inspection. If at any time   
Metering Equipment is found to be inaccurate or defective, it shall be adjusted, repaired or   
replaced at Developer’s expense, in order to provide accurate metering, unless the inaccuracy or

31

SERVICE AGREEMENT NO. 2710

defect is due to Connecting Transmission Owner’s failure to maintain, then Connecting

Transmission Owner shall pay. If Metering Equipment fails to register, or if the measurement   
made by Metering Equipment during a test varies by more than two percent from the   
measurement made by the standard meter used in the test, Connecting Transmission Owner shall adjust the measurements by correcting all measurements for the period during which Metering   
Equipment was in error by using Developer’s check meters, if installed. If no such check meters are installed or if the period cannot be reasonably ascertained, the adjustment shall be for the   
period immediately preceding the test of the Metering Equipment equal to one-half the time from the date of the last previous test of the Metering Equipment. The NYISO shall reserve the right   
to review all associated metering equipment installation on the Developer’s or Connecting   
Transmission Owner’s property at any time.

7.5 Metering Data.

At Developer’s expense, the metered data shall be telemetered to one or more locations   
designated by Connecting Transmission Owner, Developer and NYISO. Such telemetered data   
shall be used, under normal operating conditions, as the official measurement of the amount of   
energy delivered from the Merchant Transmission Facility to the Point of Interconnection.

ARTICLE 8. COMMUNICATIONS

8.1 Developer Obligations.

In accordance with applicable NYISO requirements, Developer shall maintain

satisfactory operating communications with Connecting Transmission Owner and NYISO.

Developer shall provide standard voice line, dedicated voice line and facsimile communications   
at its Merchant Transmission Facility control room or central dispatch facility through use of   
either the public telephone system, or a voice communications system that does not rely on the   
public telephone system. Developer shall also provide the dedicated data circuit(s) necessary to   
provide Developer data to Connecting Transmission Owner and NYISO as set forth in Appendix   
D hereto. The data circuit(s) shall extend from the Merchant Transmission Facility to the   
location(s) specified by Connecting Transmission Owner and NYISO. Any required   
maintenance of such communications equipment shall be performed by Developer. Operational   
communications shall be activated and maintained under, but not be limited to, the following   
events: system paralleling or separation, scheduled and unscheduled shutdowns, equipment   
clearances, and hourly and daily load data.

8.2 Remote Terminal Unit.

Prior to the Initial Synchronization Date of the Merchant Transmission Facility, a Remote   
Terminal Unit, or equivalent data collection and transfer equipment acceptable to the Parties,   
shall be installed by Developer, or by Connecting Transmission Owner at Developer’s expense,   
to gather accumulated and instantaneous data to be telemetered to the location(s) designated by   
Connecting Transmission Owner and NYISO through use of a dedicated point-to-point data   
circuit(s) as indicated in Article 8.1. The communication protocol for the data circuit(s) shall be   
specified by Connecting Transmission Owner and NYISO. Instantaneous bi-directional analog

32

SERVICE AGREEMENT NO. 2710

real power and reactive power flow information must be telemetered directly to the location(s) specified by Connecting Transmission Owner and NYISO.

Each Party will promptly advise the appropriate other Party if it detects or otherwise learns of any metering, telemetry or communications equipment errors or malfunctions that require the attention and/or correction by that other Party. The Party owning such equipment shall correct such error or malfunction as soon as reasonably feasible.

8.3 No Annexation.

Any and all equipment placed on the premises of a Party shall be and remain the property of the Party providing such equipment regardless of the mode and manner of annexation or   
attachment to real property, unless otherwise mutually agreed by the Party providing such   
equipment and the Party receiving such equipment.

ARTICLE 9. OPERATIONS

9.1 General.

Each Party shall comply with Applicable Laws and Regulations and Applicable

Reliability Standards. Each Party shall provide to the other Parties all information that may

reasonably be required by the other Parties to comply with Applicable Laws and Regulations and Applicable Reliability Standards.

9.2 NYISO and Connecting Transmission Owner Obligations.

Connecting Transmission Owner and NYISO shall cause the New York State

Transmission System and the Connecting Transmission Owner’s Attachment Facilities to be operated, maintained and controlled in a safe and reliable manner in accordance with this   
Agreement and the NYISO Tariffs. Connecting Transmission Owner and NYISO may provide operating instructions to Developer consistent with this Agreement, NYISO procedures and Connecting Transmission Owner’s operating protocols and procedures as they may change from time to time. Connecting Transmission Owner and NYISO will consider changes to their   
respective operating protocols and procedures proposed by Developer.

9.3 Developer Obligations.

Developer shall at its own expense operate, maintain and control the Merchant

Transmission Facility and the Developer’s Attachment Facilities in a safe and reliable manner   
and in accordance with this Agreement. Developer shall operate the Merchant Transmission   
Facility and the Developer’s Attachment Facilities in accordance with NYISO and Connecting   
Transmission Owner requirements, as such requirements are set forth or referenced in Appendix   
C hereto. Appendix C will be modified to reflect changes to the requirements as they may   
change from time to time. Any Party may request that the appropriate other Party or Parties   
provide copies of the requirements set forth or referenced in Appendix C hereto.

33

SERVICE AGREEMENT NO. 2710

9.4 Start-Up and Synchronization.

Consistent with the mutually acceptable procedures of the Developer and Connecting

Transmission Owner, the Developer is responsible for the proper synchronization of the

Merchant Transmission Facility to the New York State Transmission System in accordance with NYISO and Connecting Transmission Owner procedures and requirements.

9.5 Real and Reactive Power Control and Primary Frequency Response.

9.5.1 Power Factor Design Criteria

Developer shall design the Merchant Transmission Facility to maintain an effective power delivery at maximum rated power of 0.95 inductive to 0.95 capacitive at the Point of Interconnection.

9.5.2 Voltage Schedules.

Once the Developer has synchronized the Merchant Transmission Facility with the New   
York State Transmission System, NYISO shall require Developer to operate the Merchant   
Transmission Facility to produce or absorb reactive power within the design capability of the   
Merchant Transmission Facility set forth in Article 9.5.1 (Power Factor Design Criteria).   
NYISO’s voltage schedules shall treat all sources of reactive power in the New York Control   
Area in an equitable and not unduly discriminatory manner. NYISO shall exercise Reasonable   
Efforts to provide Developer with such schedules in accordance with NYISO procedures, and   
may make changes to such schedules as necessary to maintain the reliability of the New York   
State Transmission System. Developer shall operate the Merchant Transmission Facility to   
maintain the specified output voltage or power factor at the Point of Interconnection within the   
design capability of the Merchant Transmission Facility set forth in Article 9.5.1 (Power Factor   
Design Criteria) as directed by the Connecting Transmission Owner’s system operator or the   
NYISO. If Developer is unable to maintain the specified voltage or power factor, it shall   
promptly notify NYISO.


9.5.3 Payment for Reactive Power.

NYISO shall pay Developer for reactive power or voltage support service that Developer provides from the Merchant Transmission Facility in accordance with the provisions of Rate Schedule 2 of the NYISO Services Tariff.

9.5.4 Voltage Regulators.

Whenever the Merchant Transmission Facility is operated in parallel with the New York   
State Transmission System, the automatic voltage regulators shall be in automatic operation at all   
times. If the Merchant Transmission Facility’s automatic voltage regulators are not capable of such   
automatic operation, the Developer shall immediately notify NYISO, or its designated representative,   
and ensure that such Merchant Transmission Facility’s real and reactive power are within the design   
capability of the Merchant Transmission Facility’s transmission facilities and steady state stability   
limits and NYISO system operating (thermal, voltage and transient stability) limits. Developer shall

34



SERVICE AGREEMENT NO. 2710

not cause its Merchant Transmission Facility to disconnect automatically or instantaneously from the New York State Transmission System or trip any transmission facilities comprising the Merchant Transmission Facility for an under or over frequency condition unless the abnormal frequency   
condition persists beyond the limits set forth in Table 1 below.

9.6 Outages and Interruptions.

9.6.1 Outages.

9.6.1.1 Outage Authority and Coordination.

Developer and Connecting Transmission Owner may each, in accordance with NYISO   
procedures and Good Utility Practice and in coordination with the other Party, remove from   
service any of its respective Attachment Facilities or System Upgrade Facilities and System   
Deliverability Upgrades that may impact the other Party’s facilities as necessary to perform   
maintenance or testing or to install or replace equipment. Absent an Emergency State, the Party   
scheduling a removal of such facility(ies) from service will use Reasonable Efforts to schedule   
such removal on a date and time mutually acceptable to both the Developer and the Connecting   
Transmission Owner. In all circumstances either Party planning to remove such facility(ies)   
from service shall use Reasonable Efforts to minimize the effect on the other Party of such   
removal.

9.6.1.2 Outage Schedules.

The Connecting Transmission Owner shall post scheduled outages of its transmission   
facilities on the NYISO OASIS. Developer shall submit its planned maintenance schedules for   
the Merchant Transmission Facility to Connecting Transmission Owner and NYISO for a   
minimum of a rolling thirty-six month period. Developer shall update its planned maintenance   
schedules as necessary. NYISO may direct, or the Connecting Transmission Owner may   
request, Developer to reschedule its maintenance as necessary to maintain the reliability of the   
New York State Transmission System. Compensation to Developer for any additional direct   
costs that the Developer incurs as a result of rescheduling maintenance, including any additional   
overtime, breaking of maintenance contracts or other costs above and beyond the cost the   
Developer would have incurred absent the request to reschedule maintenance, shall be in   
accordance with the ISO OATT. Developer will not be eligible to receive compensation, if   
during the twelve (12) months prior to the date of the scheduled maintenance, the Developer had   
modified its schedule of maintenance activities other than at the direction of the NYISO or   
request of the Connecting Transmission Owner.

35

SERVICE AGREEMENT NO. 2710

9.6.1.3 Outage Restoration.

If an outage on the Attachment Facilities or System Upgrade Facilities or System

Deliverability Upgrades of the Connecting Transmission Owner or Developer adversely affects the other Party’s operations or facilities, the Party that owns the facility that is out of service   
shall use Reasonable Efforts to promptly restore such facility(ies) to a normal operating   
condition consistent with the nature of the outage. The Party that owns the facility that is out of service shall provide the other Party and NYISO, to the extent such information is known,   
information on the nature of the Emergency State, an estimated time of restoration, and any   
corrective actions required. Initial verbal notice shall be followed up as soon as practicable with written notice explaining the nature of the outage.

9.6.2 Interruption of Service. If required by Good Utility Practice or Applicable   
Reliability Standards to do so, the NYISO or Connecting Transmission Owner may require   
Developer to interrupt or reduce transmission of electricity over the Merchant Transmission Facility if such transmission could adversely affect the ability of NYISO and Connecting   
Transmission Owner to perform such activities as are necessary to safely and reliably operate and maintain the New York State Transmission System. The following provisions shall apply to any interruption or reduction permitted under this Article 9.6.2:

9.6.2.1 The interruption or reduction shall continue only for so long as reasonably necessary under Good Utility Practice;

9.6.2.2 Any such interruption or reduction shall be made on an equitable, nondiscriminatory basis with respect to all generating and merchant transmission facilities directly connected to the New York State Transmission System;

9.6.2.3 When the interruption or reduction must be made under circumstances

which do not allow for advance notice, NYISO or Connecting Transmission Owner shall notify Developer by telephone as soon as practicable of the reasons for the curtailment, interruption, or reduction, and, if known, its expected duration. Telephone notification shall be followed by written notification as soon as practicable;

9.6.2.4 Except during the existence of an Emergency State, when the interruption or reduction can be scheduled without advance notice, NYISO or Connecting Transmission Owner shall notify Developer in advance regarding the timing of such scheduling and further notify Developer of the expected duration. NYISO or Connecting Transmission Owner shall coordinate with each other and the Developer using Good Utility Practice to schedule the   
interruption or reduction during periods of least impact to the Developer, the Connecting   
Transmission Owner and the New York State Transmission System;

9.6.2.5 The Parties shall cooperate and coordinate with each other to the extent necessary in order to restore the Merchant Transmission Facility, Attachment Facilities, and the New York State Transmission System to their normal operating state, consistent with system conditions and Good Utility Practice.

36

SERVICE AGREEMENT NO. 2710

9.6.3 Under-Frequency and Over Frequency Conditions.

The New York State Transmission System is designed to automatically activate a load-  
shed program as required by the NPCC in the event of an under-frequency system disturbance.   
Developer shall implement under-frequency and over-frequency relay set points for the   
Merchant Transmission Facility as required by the NPCC to ensure “ride through” capability of   
the New York State Transmission System. Merchant Transmission Facility response to   
frequency deviations of predetermined magnitudes, both under-frequency and over-frequency   
deviations, shall be studied and coordinated with the NYISO and Connecting Transmission   
Owner in accordance with Good Utility Practice. The term “ride through” as used herein shall   
mean the ability of a Merchant Transmission Facility to stay connected to and synchronized with   
the New York State Transmission System during system disturbances within a range of under-  
frequency and over-frequency conditions, in accordance with Good Utility Practice and with   
NPCC Regional Reliability Reference Directory # 12, or its successor.

9.6.4 System Protection and Other Control Requirements.

9.6.4.1 System Protection Facilities. Developer shall, at its expense, install,   
operate and maintain System Protection Facilities as a part of the Merchant Transmission   
Facility or Developer’s Attachment Facilities. Connecting Transmission Owner shall install at   
Developer’s expense any System Protection Facilities that may be required on the Connecting   
Transmission Owner’s Attachment Facilities or the New York State Transmission System as a   
result of the interconnection of the Merchant Transmission Facility and Developer’s Attachment   
Facilities.

9.6.4.2 The protection facilities of both the Developer and Connecting

Transmission Owner shall be designed and coordinated with other systems in accordance with Good Utility Practice and Applicable Reliability Standards.

9.6.4.3 The Developer and Connecting Transmission Owner shall each be

responsible for protection of its respective facilities consistent with Good Utility Practice and Applicable Reliability Standards.

9.6.4.4 The protective relay design of the Developer and Connecting

Transmission Owner shall each incorporate the necessary test switches to perform the tests

required in Article 6 of this Agreement. The required test switches will be placed such that they allow operation of lockout relays while preventing breaker failure schemes from operating and causing unnecessary breaker operations and/or the tripping of the Developer’s Merchant   
Transmission Facility or the Connecting Transmission Owner’s facilities.

9.6.4.5 The Developer and Connecting Transmission Owner will each test, operate and maintain System Protection Facilities in accordance with Good Utility Practice, NERC and NPCC criteria.

9.6.4.6 Prior to the In-Service Date, and again prior to the Commercial Operation   
Date, the Developer and Connecting Transmission Owner shall each perform, or their agents   
shall perform, a complete calibration test and functional trip test of the System Protection

37

SERVICE AGREEMENT NO. 2710

Facilities. At intervals suggested by Good Utility Practice and following any apparent

malfunction of the System Protection Facilities, the Developer and Connecting Transmission Owner shall each perform both calibration and functional trip tests of its System Protection Facilities. These tests do not require the tripping of any in-service generation unit. These tests do, however, require that all protective relays and lockout contacts be activated.

9.6.5 Requirements for Protection.

In compliance with NPCC requirements and Good Utility Practice, Developer shall   
provide, install, own, and maintain relays, circuit breakers and all other devices necessary to remove any fault contribution of the Merchant Transmission Facility to any short circuit   
occurring on the New York State Transmission System not otherwise isolated by Connecting Transmission Owner’s equipment, such that the removal of the fault contribution shall be   
coordinated with the protective requirements of the New York State Transmission System.   
Developer shall be solely responsible to disconnect the Merchant Transmission Facility and Developer’s other equipment if conditions on the New York State Transmission System could adversely affect the Merchant Transmission Facility.

9.6.6 Power Quality.

Neither the facilities of Developer nor the facilities of Connecting Transmission Owner   
shall cause excessive voltage flicker nor introduce excessive distortion to the sinusoidal voltage   
or current waves as defined by ANSI Standard C84.1-1989, in accordance with IEEE Standard   
519, or any applicable superseding electric industry standard. In the event of a conflict between   
ANSI Standard C84.1-1989, or any applicable superseding electric industry standard, ANSI   
Standard C84.1-1989, or the applicable superseding electric industry standard, shall control.

9.7 Switching and Tagging Rules.

The Developer and Connecting Transmission Owner shall each provide the other Party a copy of its switching and tagging rules that are applicable to the other Party’s activities. Such switching and tagging rules shall be developed on a nondiscriminatory basis. The Parties shall comply with applicable switching and tagging rules, as amended from time to time, in obtaining clearances for work or for switching operations on equipment.

9.8 Use of Attachment Facilities by Third Parties.

9.8.1 Purpose of Attachment Facilities.

Except as may be required by Applicable Laws and Regulations, or as otherwise agreed to among the Parties, the Attachment Facilities shall be constructed for the sole purpose of   
interconnecting the Merchant Transmission Facility to the New York State Transmission System and shall be used for no other purpose.

38

SERVICE AGREEMENT NO. 2710

9.8.2 Third Party Users.

If required by Applicable Laws and Regulations or if the Parties mutually agree, such   
agreement not to be unreasonably withheld, to allow one or more third parties to use the   
Connecting Transmission Owner’s Attachment Facilities, or any part thereof, Developer will be   
entitled to compensation for the capital expenses it incurred in connection with the Attachment   
Facilities based upon the pro rata use of the Attachment Facilities by Connecting Transmission   
Owner, all third party users, and Developer, in accordance with Applicable Laws and   
Regulations or upon some other mutually-agreed upon methodology. In addition, cost   
responsibility for ongoing costs, including operation and maintenance costs associated with the   
Attachment Facilities, will be allocated between Developer and any third party users based upon   
the pro rata use of the Attachment Facilities by Connecting Transmission Owner, all third party   
users, and Developer, in accordance with Applicable Laws and Regulations or upon some other   
mutually agreed upon methodology. If the issue of such compensation or allocation cannot be   
resolved through such negotiations, it shall be submitted to FERC for resolution.

9.9 Disturbance Analysis Data Exchange.

The Parties will cooperate with one another and the NYISO in the analysis of

disturbances to either the Merchant Transmission Facility or the New York State Transmission   
System by gathering and providing access to any information relating to any disturbance,   
including information from disturbance recording equipment, protective relay targets, breaker   
operations and sequence of events records, and any disturbance information required by Good   
Utility Practice.

9.10 Phasor Measurement Units

A Developer or the Connecting Transmission Owner shall install, at Developer’s

expense, a phasor measurement unit (“PMU”) if the Developer meets the following criteria: (1)   
completed a Class Year after Class Year 2017; and (2) proposes a new Large Facility that either

(a) has a maximum net output equal to or greater than 100 MW or (b) requires, as Attachment Facilities or System Upgrade Facilities, a new substation of 230kV or above.

The PMU shall be installed on the high side of the Point of Interconnection. The PMU   
must be capable of performing phasor measurements at a minimum of 60 samples per second   
which are synchronized via a high-accuracy satellite clock. To the extent Developer or   
Connecting Transmission Owner installs similar quality equipment, such as relays or digital fault   
recorders, that can collect data at least at the same rate as PMUs and which data is synchronized   
via a high-accuracy satellite clock, such equipment would satisfy this requirement.

Developer or Connecting Transmission Owner shall be required to install, at Developer’s   
expense, PMU equipment, which includes the communication circuit capable of carrying the   
PMU data to the Connecting Transmission Owner’s data concentrator. Connecting Transmission   
Owner will store the PMU data locally for thirty days. The Developer’s and Connecting   
Transmission Owner’s responsibilities concerning the PMU and PMU equipment shall be set   
forth in Appendix A to this Agreement. Connecting Transmission Owner shall provide the   
NYISO all necessary and requested information through its and the NYISO’s synchrophasor

39

SERVICE AGREEMENT NO. 2710

system, including the following: (a) gross MW and MVAR measured at the high side of the

Point of Interconnection; (b) terminal voltage and current magnitudes and angles at the high side of the Point of Interconnection; (c) terminal frequency and frequency rate of change at the high side of the Point of Interconnection; and (d) breaker status, if available. The Connecting   
Transmission Owner will provide for the ongoing support and maintenance of the network   
communications linking its data concentrator to the NYISO, consistent with ISO Procedures detailing the obligations related to SCADA data.

ARTICLE 10. MAINTENANCE

10.1 Connecting Transmission Owner Obligations.

Connecting Transmission Owner shall maintain its transmission facilities and Attachment Facilities in a safe and reliable manner and in accordance with this Agreement.

10.2 Developer Obligations.

Developer shall maintain its Merchant Transmission Facility and Attachment Facilities in a safe and reliable manner and in accordance with this Agreement.

10.3 Coordination.

The Developer and Connecting Transmission Owner shall confer regularly to coordinate   
the planning, scheduling and performance of preventive and corrective maintenance on the   
Merchant Transmission Facility and the Attachment Facilities. The Developer and Connecting   
Transmission Owner shall keep NYISO fully informed of the preventive and corrective   
maintenance that is planned, and shall schedule all such maintenance in accordance with NYISO   
procedures.

10.4 Secondary Systems.

The Developer and Connecting Transmission Owner shall each cooperate with the other   
in the inspection, maintenance, and testing of control or power circuits that operate below 600   
volts, AC or DC, including, but not limited to, any hardware, control or protective devices,   
cables, conductors, electric raceways, secondary equipment panels, transducers, batteries,   
chargers, and voltage and current transformers that directly affect the operation of Developer or   
Connecting Transmission Owner’s facilities and equipment which may reasonably be expected   
to impact the other Party. The Developer and Connecting Transmission Owner shall each   
provide advance notice to the other Party, and to NYISO, before undertaking any work on such   
circuits, especially on electrical circuits involving circuit breaker trip and close contacts, current   
transformers, or potential transformers.

10.5 Operating and Maintenance Expenses.

Subject to the provisions herein addressing the use of facilities by others, and except for   
operations and maintenance expenses associated with modifications made for providing   
interconnection or transmission service to a third party and such third party pays for such   
expenses, Developer shall be responsible for all reasonable expenses including overheads,

40

SERVICE AGREEMENT NO. 2710

associated with: (1) owning, operating, maintaining, repairing, and replacing Developer’s

Attachment Facilities; and (2) operation, maintenance, repair and replacement of Connecting Transmission Owner’s Attachment Facilities. The Connecting Transmission Owner shall be entitled to the recovery of incremental operating and maintenance expenses that it incurs associated with System Upgrade Facilities and System Deliverability Upgrades if and to the extent provided for under Attachment S to the ISO OATT.

ARTICLE 11. PERFORMANCE OBLIGATION

11.1 Developer’s Attachment Facilities.

Developer shall design, procure, construct, install, own and/or control the Developer’s Attachment Facilities described in Appendix A hereto, at its sole expense.

11.2 Connecting Transmission Owner’s Attachment Facilities.

Connecting Transmission Owner shall design, procure, construct, install, own and/or control the Connecting Transmission Owner’s Attachment Facilities described in Appendix A hereto, at the sole expense of the Developer.

11.3 System Upgrade Facilities and System Deliverability Upgrades.

Connecting Transmission Owner shall design, procure, construct, install, and own the

System Upgrade Facilities and System Deliverability Upgrades described in Appendix A hereto. The responsibility of the Developer for costs related to System Upgrade Facilities and System   
Deliverability Upgrades shall be determined in accordance with the provisions of Attachment S to the ISO OATT.

11.4 Special Provisions for Affected Systems.

For the re-payment of amounts advanced to Affected System Operator for System

Upgrade Facilities or System Deliverability Upgrades, the Developer and Affected System

Operator shall enter into an agreement that provides for such re-payment, but only if

responsibility for the cost of such System Upgrade Facilities or System Deliverability Upgrades is not to be allocated in accordance with Attachment S to the ISO OATT. The agreement shall specify the terms governing payments to be made by the Developer to the Affected System Operator as well as the re-payment by the Affected System Operator.

11.5 Provision of Security.

At least thirty (30) Calendar Days prior to the commencement of the procurement,

installation, or construction of a discrete portion of a Connecting Transmission Owner’s

Attachment Facilities, Developer shall provide Connecting Transmission Owner, at Developer’s   
option, a guarantee, a surety bond, letter of credit or other form of security that is reasonably   
acceptable to Connecting Transmission Owner and is consistent with the Uniform Commercial   
Code of the jurisdiction identified in Article 14.2.1 of this Agreement. Such security for   
payment shall be in an amount sufficient to cover the cost for the Developer’s share of   
constructing, procuring and installing the applicable portion of Connecting Transmission

41

SERVICE AGREEMENT NO. 2710

Owner’s Attachment Facilities, and shall be reduced on a dollar-for-dollar basis for payments made to Connecting Transmission Owner for these purposes.

In addition:

11.5.1 The guarantee must be made by an entity that meets the commercially

reasonable creditworthiness requirements of Connecting Transmission Owner, and contains

terms and conditions that guarantee payment of any amount that may be due from Developer, up to an agreed-to maximum amount.

11.5.2 The letter of credit must be issued by a financial institution reasonably

acceptable to Connecting Transmission Owner and must specify a reasonable expiration date.

11.5.3 The surety bond must be issued by an insurer reasonably acceptable to Connecting Transmission Owner and must specify a reasonable expiration date.

11.5.4 Attachment S to the ISO OATT shall govern the Security that Developer provides for System Upgrade Facilities and System Deliverability Upgrades.

11.6 Developer Compensation for Emergency Services.

If, during an Emergency State, the Developer provides services at the request or direction of the NYISO or Connecting Transmission Owner, the Developer will be compensated for such services in accordance with the NYISO Services Tariff.

11.7 Line Outage Costs.

Notwithstanding anything in the ISO OATT to the contrary, the Connecting Transmission Owner may propose to recover line outage costs associated with the installation of Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System   
Deliverability Upgrades on a case-by-case basis.

ARTICLE 12. INVOICE

12.1 General.

The Developer and Connecting Transmission Owner shall each submit to the other Party,   
on a monthly basis, invoices of amounts due for the preceding month. Each invoice shall state   
the month to which the invoice applies and fully describe the services and equipment provided.   
The Developer and Connecting Transmission Owner may discharge mutual debts and payment   
obligations due and owing to each other on the same date through netting, in which case all   
amounts one Party owes to the other Party under this Agreement, including interest payments or   
credits, shall be netted so that only the net amount remaining due shall be paid by the owing   
Party.

42

SERVICE AGREEMENT NO. 2710

12.2 Final Invoice.

Within six months after completion of the construction of the Connecting Transmission   
Owner’s Attachment Facilities and the System Upgrade Facilities and System Deliverability   
Upgrades, Connecting Transmission Owner shall provide an invoice of the final cost of the   
construction of the Connecting Transmission Owner’s Attachment Facilities and the System   
Upgrade Facilities and System Deliverability Upgrades, determined in accordance with   
Attachment S to the ISO OATT, and shall set forth such costs in sufficient detail to enable   
Developer to compare the actual costs with the estimates and to ascertain deviations, if any, from   
the cost estimates. Connecting Transmission Owner shall refund to Developer any amount by   
which the actual payment by Developer for estimated costs exceeds the actual costs of   
construction within thirty (30) Calendar Days of the issuance of such final construction invoice.

12.3 Payment.

Invoices shall be rendered to the paying Party at the address specified in Appendix F

hereto. The Party receiving the invoice shall pay the invoice within thirty (30) Calendar Days of   
receipt. All payments shall be made in immediately available funds payable to the other Party,   
or by wire transfer to a bank named and account designated by the invoicing Party. Payment of   
invoices will not constitute a waiver of any rights or claims the paying Party may have under this   
Agreement.

12.4 Disputes.

In the event of a billing dispute between Connecting Transmission Owner and Developer,   
Connecting Transmission Owner shall continue to perform under this Agreement as long as   
Developer: (i) continues to make all payments not in dispute; and (ii) pays to Connecting   
Transmission Owner or into an independent escrow account the portion of the invoice in dispute,   
pending resolution of such dispute. If Developer fails to meet these two requirements for   
continuation of service, then Connecting Transmission Owner may provide notice to Developer   
of a Default pursuant to Article 17. Within thirty (30) Calendar Days after the resolution of the   
dispute, the Party that owes money to the other Party shall pay the amount due with interest   
calculated in accord with the methodology set forth in FERC’s Regulations at 18 C.F.R. §

35.19a(a)(2)(iii).

ARTICLE 13. EMERGENCIES

13.1 Obligations.

Each Party shall comply with the Emergency State procedures of NYISO, the applicable Reliability Councils, Applicable Laws and Regulations, and any emergency procedures agreed to by the NYISO Operating Committee.

13.2 Notice.

NYISO or, as applicable, Connecting Transmission Owner shall notify Developer

promptly when it becomes aware of an Emergency State that affects the Connecting

Transmission Owner’s Attachment Facilities or the New York State Transmission System that

43

SERVICE AGREEMENT NO. 2710

may reasonably be expected to affect Developer’s operation of the Merchant Transmission

Facility or the Developer’s Attachment Facilities. Developer shall notify NYISO and

Connecting Transmission Owner promptly when it becomes aware of an Emergency State that affects the Merchant Transmission Facility or the Developer’s Attachment Facilities that may reasonably be expected to affect the New York State Transmission System or the Connecting Transmission Owner’s Attachment Facilities. To the extent information is known, the   
notification shall describe the Emergency State, the extent of the damage or deficiency, the expected effect on the operation of Developer’s or Connecting Transmission Owner’s facilities and operations, its anticipated duration and the corrective action taken and/or to be taken. The initial notice shall be followed as soon as practicable with written notice.

13.3 Immediate Action.

Unless, in Developer’s reasonable judgment, immediate action is required, Developer

shall obtain the consent of Connecting Transmission Owner, such consent to not be unreasonably withheld, prior to performing any manual switching operations at the Merchant Transmission   
Facility or the Developer’s Attachment Facilities in response to an Emergency State either   
declared by NYISO, Connecting Transmission Owner or otherwise regarding New York State   
Transmission System.

13.4 NYISO and Connecting Transmission Owner Authority.

13.4.1 General.

NYISO or Connecting Transmission Owner may take whatever actions with regard to the   
New York State Transmission System or the Connecting Transmission Owner’s Attachment   
Facilities it deems necessary during an Emergency State in order to (i) preserve public health and   
safety, (ii) preserve the reliability of the New York State Transmission System or the Connecting   
Transmission Owner’s Attachment Facilities, (iii) limit or prevent damage, and (iv) expedite   
restoration of service.

NYISO and Connecting Transmission Owner shall use Reasonable Efforts to minimize   
the effect of such actions or inactions on the Merchant Transmission Facility or the Developer’s   
Attachment Facilities. NYISO or Connecting Transmission Owner may, on the basis of   
technical considerations, require the Merchant Transmission Facility to mitigate an Emergency   
State by taking actions necessary and limited in scope to remedy the Emergency State, including,   
but not limited to, directing Developer to shut-down, start-up, increase or decrease the real or   
reactive power output of the Merchant Transmission Facility; implementing a reduction or   
disconnection pursuant to Article 13.4.2; directing the Developer to assist with blackstart (if   
available) or restoration efforts; or altering the outage schedules of the Merchant Transmission   
Facility and the Developer’s Attachment Facilities. Developer shall comply with all of the   
NYISO and Connecting Transmission Owner’s operating instructions concerning Merchant   
Transmission Facility real power and reactive power output within the manufacturer’s design   
limitations of the Merchant Transmission Facility’s equipment that is in service and physically   
available for operation at the time, in compliance with Applicable Laws and Regulations.

44

SERVICE AGREEMENT NO. 2710

13.4.2 Reduction and Disconnection.

NYISO or Connecting Transmission Owner may reduce Energy Resource

Interconnection Service and Capacity Resource Interconnection Service or disconnect the

Merchant Transmission Facility or the Developer’s Attachment Facilities, when such reduction   
or disconnection is necessary under Good Utility Practice due to an Emergency State. These   
rights are separate and distinct from any right of Curtailment of NYISO pursuant to the ISO   
OATT. When NYISO or Connecting Transmission Owner can schedule the reduction or   
disconnection in advance, NYISO or Connecting Transmission Owner shall notify Developer of   
the reasons, timing and expected duration of the reduction or disconnection. NYISO or   
Connecting Transmission Owner shall coordinate with the Developer using Good Utility Practice   
to schedule the reduction or disconnection during periods of least impact to the Developer and   
the New York State Transmission System. Any reduction or disconnection shall continue only   
for so long as reasonably necessary under Good Utility Practice. The Parties shall cooperate   
with each other to restore the Merchant Transmission Facility, the Attachment Facilities, and the   
New York State Transmission System to their normal operating state as soon as practicable   
consistent with Good Utility Practice.

13.5 Developer Authority.

Consistent with Good Utility Practice and this Agreement, the Developer may take

whatever actions or inactions with regard to the Merchant Transmission Facility or the

Developer’s Attachment Facilities during an Emergency State in order to (i) preserve public

health and safety, (ii) preserve the reliability of the Merchant Transmission Facility or the

Developer’s Attachment Facilities, (iii) limit or prevent damage, and (iv) expedite restoration of service. Developer shall use Reasonable Efforts to minimize the effect of such actions or   
inactions on the New York State Transmission System and the Connecting Transmission   
Owner’s Attachment Facilities. NYISO and Connecting Transmission Owner shall use   
Reasonable Efforts to assist Developer in such actions.

13.6 Limited Liability.

Except as otherwise provided in Article 11.6 of this Agreement, no Party shall be liable   
to another Party for any action it takes in responding to an Emergency State so long as such   
action is made in good faith and is consistent with Good Utility Practice and the NYISO Tariffs.

ARTICLE 14. REGULATORY REQUIREMENTS AND GOVERNING LAW

14.1 Regulatory Requirements.

Each Party’s obligations under this Agreement shall be subject to its receipt of any

required approval or certificate from one or more Governmental Authorities in the form and

substance satisfactory to the applying Party, or the Party making any required filings with, or

providing notice to, such Governmental Authorities, and the expiration of any time period

associated therewith. Each Party shall in good faith seek and use its Reasonable Efforts to obtain   
such other approvals. Nothing in this Agreement shall require Developer to take any action that   
could result in its inability to obtain, or its loss of, status or exemption under the Federal Power

45

SERVICE AGREEMENT NO. 2710

Act or the Public Utility Holding Company Act of 2005 or the Public Utility Regulatory Policies Act of 1978, as amended.

14.2 Governing Law.

14.2.1 The validity, interpretation and performance of this Agreement and each of its

provisions shall be governed by the laws of the state of New York, without regard to its conflicts of law principles.

14.2.2 This Agreement is subject to all Applicable Laws and Regulations.

14.2.3 Each Party expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, rules, or regulations of a Governmental Authority.

ARTICLE 15. NOTICES

15.1 General.

Unless otherwise provided in this Agreement, any notice, demand or request required or permitted to be given by a Party to the other Parties and any instrument required or permitted to be tendered or delivered by a Party in writing to the other Parties shall be effective when   
delivered and may be so given, tendered or delivered, by recognized national courier, or by   
depositing the same with the United States Postal Service with postage prepaid, for delivery by certified or registered mail, addressed to the Party, or personally delivered to the Party, at the   
address set out in Appendix F hereto.

A Party may change the notice information in this Agreement by giving five (5) Business Days written notice prior to the effective date of the change.

15.2 Billings and Payments.

Billings and payments shall be sent to the addresses set out in Appendix F hereto.

15.3 Alternative Forms of Notice.

Any notice or request required or permitted to be given by a Party to the other Parties and not required by this Agreement to be given in writing may be so given by telephone, facsimile or email to the telephone numbers and email addresses set out in Appendix F hereto.

15.4 Operations and Maintenance Notice.

Developer and Connecting Transmission Owner shall each notify the other Party, and

NYISO, in writing of the identity of the person(s) that it designates as the point(s) of contact with respect to the implementation of Articles 9 and 0 of this Agreement.

ARTICLE 16. FORCE MAJEURE

16.1 Economic hardship is not considered a Force Majeure event.

46

SERVICE AGREEMENT NO. 2710

16.2 A Party shall not be responsible or liable, or deemed, in Default with respect to   
any obligation hereunder, (including obligations under Article 4 of this Agreement) , other than   
the obligation to pay money when due, to the extent the Party is prevented from fulfilling such   
obligation by Force Majeure. A Party unable to fulfill any obligation hereunder (other than an   
obligation to pay money when due) by reason of Force Majeure shall give notice and the full   
particulars of such Force Majeure to the other Parties in writing or by telephone as soon as

reasonably possible after the occurrence of the cause relied upon. Telephone notices given

pursuant to this Article shall be confirmed in writing as soon as reasonably possible and shall

specifically state full particulars of the Force Majeure, the time and date when the Force Majeure occurred and when the Force Majeure is reasonably expected to cease. The Party affected shall exercise due diligence to remove such disability with reasonable dispatch, but shall not be   
required to accede or agree to any provision not satisfactory to it in order to settle and terminate a strike or other labor disturbance.

ARTICLE 17. DEFAULT

17.1 General.

No Breach shall exist where such failure to discharge an obligation (other than the

payment of money) is the result of Force Majeure as defined in this Agreement or the result of an   
act or omission of the other Parties. Upon a Breach, the non-Breaching Parties shall give written   
notice of such to the Breaching Party. The Breaching Party shall have thirty (30) Calendar Days   
from receipt of the Breach notice within which to cure such Breach; provided however, if such   
Breach is not capable of cure within thirty (30) Calendar Days, the Breaching Party shall   
commence such cure within thirty (30) Calendar Days after notice and continuously and   
diligently complete such cure within ninety (90) Calendar Days from receipt of the Breach   
notice; and, if cured within such time, the Breach specified in such notice shall cease to exist.

17.2 Right to Terminate.

If a Breach is not cured as provided in this Article 17, or if a Breach is not capable of

being cured within the period provided for herein, the non-Breaching Parties acting together shall thereafter have the right to declare a Default and terminate this Agreement by written notice at any time until cure occurs, and be relieved of any further obligation hereunder and, whether or not those Parties terminate this Agreement, to recover from the defaulting Party all amounts due hereunder, plus all other damages and remedies to which they are entitled at law or in equity. The provisions of this Article will survive termination of this Agreement.

ARTICLE 18. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE

18.1 Indemnity.

Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and save

harmless, as applicable, the other Parties (each an “Indemnified Party”) from, any and all

damages, losses, claims, including claims and actions relating to injury to or death of any person   
or damage to property, the alleged violation of any Environmental Law, or the release or   
threatened release of any Hazardous Substance, demand, suits, recoveries, costs and expenses,

47

SERVICE AGREEMENT NO. 2710

court costs, attorney fees, and all other obligations by or to third parties (any and all of these a   
“Loss”), arising out of or resulting from (i) the Indemnified Party’s performance of its   
obligations under this Agreement on behalf of the Indemnifying Party, except in cases where the   
Indemnifying Party can demonstrate that the Loss of the Indemnified Party was caused by the   
gross negligence or intentional wrongdoing of the Indemnified Party or (ii) the violation by the   
Indemnifying Party of any Environmental Law or the release by the Indemnifying Party of any   
Hazardous Substance.

18.1.1 Indemnified Party.

If a Party is entitled to indemnification under this Article 18 as a result of a claim by a third party, and the Indemnifying Party fails, after notice and reasonable opportunity to proceed under Article 18.1.3, to assume the defense of such claim, such Indemnified Party may at the expense of the Indemnifying Party contest, settle or consent to the entry of any judgment with respect to, or pay in full, such claim.

18.1.2 Indemnifying Party.

If an Indemnifying Party is obligated to indemnify and hold any Indemnified Party

harmless under this Article 18, the amount owing to the Indemnified Party shall be the amount of such Indemnified Party’s actual Loss, net of any insurance or other recovery.

18.1.3 Indemnity Procedures.

Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or investigation as to which   
the indemnity provided for in Article 18.1 may apply, the Indemnified Party shall notify the   
Indemnifying Party of such fact. Any failure of or delay in such notification shall not affect a   
Party’s indemnification obligation unless such failure or delay is materially prejudicial to the   
Indemnifying Party.

Except as stated below, the Indemnifying Party shall have the right to assume the defense   
thereof with counsel designated by such Indemnifying Party and reasonably satisfactory to the   
Indemnified Party. If the defendants in any such action include one or more Indemnified Parties   
and the Indemnifying Party and if the Indemnified Party reasonably concludes that there may be   
legal defenses available to it and/or other Indemnified Parties which are different from or   
additional to those available to the Indemnifying Party, the Indemnified Party shall have the right   
to select separate counsel to assert such legal defenses and to otherwise participate in the defense   
of such action on its own behalf. In such instances, the Indemnifying Party shall only be   
required to pay the fees and expenses of one additional attorney to represent an Indemnified   
Party or Indemnified Parties having such differing or additional legal defenses.

The Indemnified Party shall be entitled, at its expense, to participate in any such action,   
suit or proceeding, the defense of which has been assumed by the Indemnifying Party.   
Notwithstanding the foregoing, the Indemnifying Party (i) shall not be entitled to assume and   
control the defense of any such action, suit or proceedings if and to the extent that, in the opinion

48

SERVICE AGREEMENT NO. 2710

of the Indemnified Party and its counsel, such action, suit or proceeding involves the potential

imposition of criminal liability on the Indemnified Party, or there exists a conflict or adversity of   
interest between the Indemnified Party and the Indemnifying Party, in such event the   
Indemnifying Party shall pay the reasonable expenses of the Indemnified Party, and (ii) shall not   
settle or consent to the entry of any judgment in any action, suit or proceeding without the   
consent of the Indemnified Party, which shall not be unreasonably withheld, conditioned or   
delayed.

18.2 No Consequential Damages.

Other than the liquidated damages heretofore described and the indemnity obligations set   
forth in Article 18.1, in no event shall any Party be liable under any provision of this Agreement   
for any losses, damages, costs or expenses for any special, indirect, incidental, consequential, or   
punitive damages, including but not limited to loss of profit or revenue, loss of the use of   
equipment, cost of capital, cost of temporary equipment or services, whether based in whole or in   
part in contract, in tort, including negligence, strict liability, or any other theory of liability;   
provided, however, that damages for which a Party may be liable to another Party under separate   
agreement will not be considered to be special, indirect, incidental, or consequential damages   
hereunder.

18.3 Insurance.

Developer and Connecting Transmission Owner shall each, at its own expense, procure and maintain in force throughout the period of this Agreement and until released by the other   
Parties, the following minimum insurance coverages, with insurance companies licensed to   
write insurance or approved eligible surplus lines carriers in the state of New York with a   
minimum A.M. Best rating of A or better for financial strength, and an A.M. Best financial size category of VIII or better:

18.3.1 Employers’ Liability and Workers’ Compensation Insurance providing

statutory benefits in accordance with the laws and regulations of New York State.

18.3.2 Commercial General Liability (“CGL”) Insurance including premises and

operations, personal injury, broad form property damage, broad form blanket contractual liability   
coverage products and completed operations coverage, coverage for explosion, collapse and   
underground hazards, independent contractors coverage, coverage for pollution to the extent   
normally available and punitive damages to the extent normally available using Insurance   
Services Office, Inc. Commercial General Liability Coverage (“ISO CG”) Form CG 00 01 04 13   
or a form equivalent to or better than CG 00 01 04 13, with minimum limits of Two Million   
Dollars ($2,000,000) per occurrence and Two Million Dollars ($2,000,000) aggregate combined   
single limit for personal injury, bodily injury, including death and property damage.

18.3.3 Comprehensive Automobile Liability Insurance for coverage of owned

and non-owned and hired vehicles, trailers or semi-trailers designed for travel on public roads, with a minimum, combined single limit of One Million Dollars ($1,000,000) per occurrence for bodily injury, including death, and property damage.

49

SERVICE AGREEMENT NO. 2710

18.3.4 If applicable, the Commercial General Liability and Comprehensive

Automobile Liability Insurance policies should include contractual liability for work in

connection with construction or demolition work on or within 50 feet of a railroad, or a separate Railroad Protective Liability Policy should be provided.

18.3.5 Excess Liability Insurance over and above the Employers’ Liability,

Commercial General Liability and Comprehensive Automobile Liability Insurance coverages, with a minimum combined single limit of Twenty Million Dollars ($20,000,000) per occurrence and Twenty Million Dollars ($20,000,000) aggregate. The Excess policies should contain the same extensions listed under the Primary policies.

18.3.6 The Commercial General Liability Insurance, Comprehensive Automobile

Insurance and Excess Liability Insurance policies of Developer and Connecting Transmission

Owner shall name the other Party, its parent, associated and Affiliate companies and their

respective directors, officers, agents, servants and employees (“Other Party Group”) as additional   
insureds using ISO CG Endorsements: CG 20 33 04 13, and CG 20 37 04 13 or CG 20 10 04 13   
and CG 20 37 04 13 or equivalent to or better forms. All policies shall contain provisions   
whereby the insurers waive all rights of subrogation in accordance with the provisions of this   
Agreement against the Other Party Group and provide thirty (30) Calendar days advance written   
notice to the Other Party Group prior to anniversary date of cancellation or any material change   
in coverage or condition.

18.3.7 The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Liability Insurance policies shall contain provisions that specify that the policies are primary and non-contributory. Developer and Connecting Transmission Owner shall each be responsible for its respective deductibles or retentions.

18.3.8 The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Liability Insurance policies, if written on a Claims First Made Basis, shall be maintained in full force and effect for at least three (3) years after termination of this Agreement, which coverage may be in the form of tail coverage or extended reporting period coverage if agreed by the Developer and Connecting Transmission Owner.

18.3.9 If applicable, Pollution Liability Insurance in an amount no less than

$7,500,000 per occurrence and $7,500,000 in the aggregate. The policy will provide coverage for claims resulting from pollution or other environmental impairment arising out of or in   
connection with work performed on the premises by the other party, its contractors and and/or subcontractors. Such insurance is to include coverage for, but not be limited to, cleanup, third party bodily injury and property damage and remediation and will be written on an occurrence basis. The policy shall name the Other Party Group as additional insureds, be primary and   
contain a waiver of subrogation.

18.3.10 The requirements contained herein as to the types and limits of all

insurance to be maintained by the Developer and Connecting Transmission Owner are not

50

SERVICE AGREEMENT NO. 2710

intended to and shall not in any manner, limit or qualify the liabilities and obligations assumed by those Parties under this Agreement.

18.3.11 Within ninety (90) days following execution of this Agreement, and as

soon as practicable after the end of each fiscal year or at the renewal of the insurance policy and in any event within ninety (90) days thereafter, Developer and Connecting Transmission Owner shall provide certificate of insurance for all insurance required in this Agreement, executed by each insurer or by an authorized representative of each insurer.

18.3.12 Notwithstanding the foregoing, Developer and Connecting Transmission

Owner may each self-insure to meet the minimum insurance requirements of Articles 18.3.1   
through 18.3.9 to the extent it maintains a self-insurance program; provided that, such Party’s   
senior debt is rated at investment grade, or better, by Standard & Poor’s and that its self-  
insurance program meets the minimum insurance requirements of Articles 18.3.1 through 18.3.9.   
In the event that a Party is permitted to self-insure pursuant to this Article 18.3.12, it shall notify   
the other Party that it meets the requirements to self-insure and that its self-insurance program   
meets the minimum insurance requirements in a manner consistent with that specified in Articles

18.3.1 through 18.3.9 and provide evidence of such coverages. For any period of time that a Party’s senior debt is unrated by Standard & Poor’s or is rated at less than investment grade by Standard & Poor’s, such Party shall comply with the insurance requirements applicable to it under Articles 18.3.1 through 18.3.9.

18.3.13 Developer and Connecting Transmission Owner agree to report to each

other in writing as soon as practical all accidents or occurrences resulting in injuries to any person, including death, and any property damage arising out of this Agreement.

18.3.14 Subcontractors of each party must maintain the same insurance

requirements stated under Articles 18.3.1 through 18.3.9 and comply with the Additional Insured requirements herein. In addition, their policies must state that they are primary and non-  
contributory and contain a waiver of subrogation.

ARTICLE 19. ASSIGNMENT

This Agreement may be assigned by a Party only with the written consent of the other

Parties; provided that a Party may assign this Agreement without the consent of the other Parties   
to any Affiliate of the assigning Party with an equal or greater credit rating and with the legal   
authority and operational ability to satisfy the obligations of the assigning Party under this   
Agreement; provided further that a Party may assign this Agreement without the consent of the   
other Parties in connection with the sale, merger, restructuring, or transfer of a substantial   
portion or all of its assets, including the Attachment Facilities it owns, so long as the assignee in   
such a transaction directly assumes in writing all rights, duties and obligations arising under this   
Agreement; and provided further that the Developer shall have the right to assign this   
Agreement, without the consent of the NYISO or Connecting Transmission Owner, for collateral   
security purposes to aid in providing financing for the Merchant Transmission Facility, provided   
that the Developer will promptly notify the NYISO and Connecting Transmission Owner of any   
such assignment. Any financing arrangement entered into by the Developer pursuant to this   
Article will provide that prior to or upon the exercise of the secured party’s, trustee’s or

51

SERVICE AGREEMENT NO. 2710

mortgagee’s assignment rights pursuant to said arrangement, the secured creditor, the trustee or   
mortgagee will notify the NYISO and Connecting Transmission Owner of the date and   
particulars of any such exercise of assignment right(s) and will provide the NYISO and   
Connecting Transmission Owner with proof that it meets the requirements of Articles 11.5 and

18.3. Any attempted assignment that violates this Article is void and ineffective. Any

assignment under this Agreement shall not relieve a Party of its obligations, nor shall a Party’s obligations be enlarged, in whole or in part, by reason thereof. Where required, consent to assignment will not be unreasonably withheld, conditioned or delayed.

ARTICLE 20. SEVERABILITY

If any provision in this Agreement is finally determined to be invalid, void or

unenforceable by any court or other Governmental Authority having jurisdiction, such

determination shall not invalidate, void or make unenforceable any other provision, agreement or   
covenant of this Agreement; provided that if the Developer (or any third party, but only if such   
third party is not acting at the direction of the Connecting Transmission Owner) seeks and   
obtains such a final determination with respect to any provision of the Alternate Option (Article

5.1.2), or the Negotiated Option (Article 5.1.4), then none of these provisions shall thereafter have any force or effect and the rights and obligations of Developer and Connecting   
Transmission Owner shall be governed solely by the Standard Option (Article 5.1.1).

ARTICLE 21. COMPARABILITY

The Parties will comply with all applicable comparability and code of conduct laws, rules and regulations, as amended from time to time.

ARTICLE 22. CONFIDENTIALITY

22.1 Confidentiality.

Certain information exchanged by the Parties during the term of this Agreement shall   
constitute confidential information (“Confidential Information”) and shall be subject to this   
Article 22.

If requested by a Party receiving information, the Party supplying the information shall provide in writing, the basis for asserting that the information referred to in this Article warrants confidential treatment, and the requesting Party may disclose such writing to the appropriate Governmental Authority. Each Party shall be responsible for the costs associated with affording confidential treatment to its information.

22.2 Term.

During the term of this Agreement, and for a period of three (3) years after the expiration or termination of this Agreement, except as otherwise provided in this Article 22, each Party shall hold in confidence and shall not disclose to any person Confidential Information.

52

SERVICE AGREEMENT NO. 2710

22.3 Confidential Information.

The following shall constitute Confidential Information: (1) any non-public information that is treated as confidential by the disclosing Party and which the disclosing Party identifies as Confidential Information in writing at the time, or promptly after the time, of disclosure; or (2) information designated as Confidential Information by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

22.4 Scope.

Confidential Information shall not include information that the receiving Party can

demonstrate: (1) is generally available to the public other than as a result of a disclosure by the   
receiving Party; (2) was in the lawful possession of the receiving Party on a non-confidential   
basis before receiving it from the disclosing Party; (3) was supplied to the receiving Party   
without restriction by a third party, who, to the knowledge of the receiving Party after due   
inquiry, was under no obligation to the disclosing Party to keep such information confidential;

(4) was independently developed by the receiving Party without reference to Confidential

Information of the disclosing Party; (5) is, or becomes, publicly known, through no wrongful act   
or omission of the receiving Party or Breach of this Agreement; or (6) is required, in accordance   
with Article 22.9 of this Agreement, Order of Disclosure, to be disclosed by any Governmental   
Authority or is otherwise required to be disclosed by law or subpoena, or is necessary in any   
legal proceeding establishing rights and obligations under this Agreement. Information   
designated as Confidential Information will no longer be deemed confidential if the Party that   
designated the information as confidential notifies the other Party that it no longer is   
confidential.

22.5 Release of Confidential Information.

No Party shall release or disclose Confidential Information to any other person, except to   
its Affiliates (limited by FERC Standards of Conduct requirements), subcontractors, employees,   
consultants, or to parties who may be considering providing financing to or equity participation   
with Developer, or to potential purchasers or assignees of a Party, on a need-to-know basis in   
connection with this Agreement, unless such person has first been advised of the confidentiality   
provisions of this Article 22 and has agreed to comply with such provisions. Notwithstanding   
the foregoing, a Party providing Confidential Information to any person shall remain primarily   
responsible for any release of Confidential Information in contravention of this Article 22.

22.6 Rights.

Each Party retains all rights, title, and interest in the Confidential Information that each Party discloses to the other Party. The disclosure by each Party to the other Parties of   
Confidential Information shall not be deemed a waiver by any Party or any other person or entity of the right to protect the Confidential Information from public disclosure.

22.7 No Warranties.

By providing Confidential Information, no Party makes any warranties or representations   
as to its accuracy or completeness. In addition, by supplying Confidential Information, no Party

53

SERVICE AGREEMENT NO. 2710

obligates itself to provide any particular information or Confidential Information to the other   
Parties nor to enter into any further agreements or proceed with any other relationship or joint   
venture.

22.8 Standard of Care.

Each Party shall use at least the same standard of care to protect Confidential Information it receives as it uses to protect its own Confidential Information from unauthorized disclosure, publication or dissemination. Each Party may use Confidential Information solely to fulfill its obligations to the other Parties under this Agreement or its regulatory requirements, including the ISO OATT and NYISO Services Tariff. The NYISO shall, in all cases, treat the information it receives in accordance with the requirements of Attachment F to the ISO OATT.

22.9 Order of Disclosure.

If a court or a Government Authority or entity with the right, power, and apparent

authority to do so requests or requires any Party, by subpoena, oral deposition, interrogatories,

requests for production of documents, administrative order, or otherwise, to disclose Confidential   
Information, that Party shall provide the other Parties with prompt notice of such request(s) or   
requirement(s) so that the other Parties may seek an appropriate protective order or waive   
compliance with the terms of this Agreement. Notwithstanding the absence of a protective order   
or waiver, the Party may disclose such Confidential Information which, in the opinion of its   
counsel, the Party is legally compelled to disclose. Each Party will use Reasonable Efforts to   
obtain reliable assurance that confidential treatment will be accorded any Confidential   
Information so furnished.

22.10 Termination of Agreement.

Upon termination of this Agreement for any reason, each Party shall, within ten (10)   
Calendar Days of receipt of a written request from the other Parties, use Reasonable Efforts to   
destroy, erase, or delete (with such destruction, erasure, and deletion certified in writing to the   
other Parties) or return to the other Parties, without retaining copies thereof, any and all written   
or electronic Confidential Information received from the other Parties pursuant to this   
Agreement.

22.11 Remedies.

The Parties agree that monetary damages would be inadequate to compensate a Party for   
another Party’s Breach of its obligations under this Article 22. Each Party accordingly agrees   
that the other Parties shall be entitled to equitable relief, by way of injunction or otherwise, if the   
first Party Breaches or threatens to Breach its obligations under this Article 22, which equitable   
relief shall be granted without bond or proof of damages, and the receiving Party shall not plead   
in defense that there would be an adequate remedy at law. Such remedy shall not be deemed an   
exclusive remedy for the Breach of this Article 22, but shall be in addition to all other remedies   
available at law or in equity. The Parties further acknowledge and agree that the covenants

contained herein are necessary for the protection of legitimate business interests and are

reasonable in scope. No Party, however, shall be liable for indirect, incidental, or consequential

54

SERVICE AGREEMENT NO. 2710

or punitive damages of any nature or kind resulting from or arising in connection with this Article 22.

22.12 Disclosure to FERC, its Staff, or a State.

Notwithstanding anything in this Article 22 to the contrary, and pursuant to 18 C.F.R.   
section 1b.20, if FERC or its staff, during the course of an investigation or otherwise, requests   
information from one of the Parties that is otherwise required to be maintained in confidence   
pursuant to this Agreement or the ISO OATT, the Party shall provide the requested information   
to FERC or its staff, within the time provided for in the request for information. In providing the   
information to FERC or its staff, the Party must, consistent with 18 C.F.R. section 388.112,   
request that the information be treated as confidential and non-public by FERC and its staff and   
that the information be withheld from public disclosure. Parties are prohibited from notifying   
the other Parties to this Agreement prior to the release of the Confidential Information to the   
Commission or its staff. The Party shall notify the other Parties to the Agreement when it is   
notified by FERC or its staff that a request to release Confidential Information has been received   
by FERC, at which time the Parties may respond before such information would be made public,   
pursuant to 18 C.F.R. section 388.112. Requests from a state regulatory body conducting a   
confidential investigation shall be treated in a similar manner if consistent with the applicable   
state rules and regulations. A Party shall not be liable for any losses, consequential or otherwise,   
resulting from that Party divulging Confidential Information pursuant to a FERC or state   
regulatory body request under this paragraph.

22.13 Required Notices Upon Requests or Demands for Confidential Information

Except as otherwise expressly provided herein, no Party shall disclose Confidential

Information to any person not employed or retained by the Party possessing the Confidential

Information, except to the extent disclosure is (i) required by law; (ii) reasonably deemed by the   
disclosing Party to be required to be disclosed in connection with a dispute between or among   
the Parties, or the defense of litigation or dispute; (iii) otherwise permitted by consent of the   
other Party, such consent not to be unreasonably withheld; or (iv) necessary to fulfill its   
obligations under this Agreement, the ISO OATT or the NYISO Services Tariff. Prior to any   
disclosures of a Party’s Confidential Information under this subparagraph, or if any third party or   
Governmental Authority makes any request or demand for any of the information described in   
this subparagraph, the disclosing Party agrees to promptly notify the other Party in writing and   
agrees to assert confidentiality and cooperate with the other Party in seeking to protect the   
Confidential Information from public disclosure by confidentiality agreement, protective order or   
other reasonable measures.

ARTICLE 23. DEVELOPER AND CONNECTING TRANSMISSION OWNER   
 NOTICES OF ENVIRONMENTAL RELEASES

Developer and Connecting Transmission Owner shall each notify the other Party, first   
orally and then in writing, of the release of any Hazardous Substances, any asbestos or lead   
abatement activities, or any type of remediation activities related to the Merchant Transmission   
Facility or the Attachment Facilities, each of which may reasonably be expected to affect the   
other Party. The notifying Party shall: (i) provide the notice as soon as practicable, provided

55

SERVICE AGREEMENT NO. 2710

such Party makes a good faith effort to provide the notice no later than twenty-four hours after   
such Party becomes aware of the occurrence; and (ii) promptly furnish to the other Party copies   
of any publicly available reports filed with any Governmental Authorities addressing such   
events.

ARTICLE 24. INFORMATION REQUIREMENT

24.1 Information Acquisition.

Connecting Transmission Owner and Developer shall each submit specific information regarding the electrical characteristics of their respective facilities to the other, and to NYISO, as described below and in accordance with Applicable Reliability Standards.

24.2 Information Submission by Connecting Transmission Owner.

The initial information submission by Connecting Transmission Owner shall occur no   
later than one hundred eighty (180) Calendar Days prior to Trial Operation and shall include   
New York State Transmission System information necessary to allow the Developer to select   
equipment and meet any system protection and stability requirements, unless otherwise mutually   
agreed to by the Developer and Connecting Transmission Owner. On a monthly basis   
Connecting Transmission Owner shall provide Developer and NYISO a status report on the   
construction and installation of Connecting Transmission Owner’s Attachment Facilities and   
System Upgrade Facilities and System Deliverability Upgrades, including, but not limited to, the   
following information: (1) progress to date; (2) a description of the activities since the last   
report; (3) a description of the action items for the next period; and (4) the delivery status of   
equipment ordered.

24.3 Updated Information Submission by Developer.

The updated information submission by the Developer, including manufacturer

information, shall occur no later than one hundred eighty (180) Calendar Days prior to the Trial Operation. Developer shall submit a completed copy of the Merchant Transmission Facility data requirements contained in Appendix 1 to the Standard Large Facility Interconnection Procedures. It shall also include any additional information provided to Connecting Transmission Owner for the Interconnection Facilities Study. Information in this submission shall be the most current   
Merchant Transmission Facility design or expected performance data. Information submitted for stability models shall be compatible with NYISO standard models. If there is no compatible   
model, the Developer will work with a consultant mutually agreed to by the Parties to develop and supply a standard model and associated information.

If the Developer’s data is different from what was originally provided to Connecting

Transmission Owner and NYISO pursuant to an Interconnection Study Agreement among

Connecting Transmission Owner, NYISO and Developer and this difference may be reasonably   
expected to affect the other Parties’ facilities or the New York State Transmission System, but   
does not require the submission of a new Interconnection Request, then NYISO will conduct   
appropriate studies to determine the impact on the New York State Transmission System based   
on the actual data submitted pursuant to this Article 24.3. Such studies will provide an estimate

56

SERVICE AGREEMENT NO. 2710

of any additional modifications to the New York State Transmission System, Connecting

Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System

Deliverability Upgrades based on the actual data and a good faith estimate of the costs thereof. The Developer shall not begin Trial Operation until such studies are completed. The Developer shall be responsible for the cost of any modifications required by the actual data, including the cost of any required studies.

24.4 Information Supplementation.

Prior to the Commercial Operation Date, the Developer and Connecting Transmission   
Owner shall supplement their information submissions described above in this Article 24 with   
any and all “as-built” Merchant Transmission Facility information or “as-tested” performance   
information that differs from the initial submissions or, alternatively, written confirmation that   
no such differences exist. The Developer shall conduct tests on the Merchant Transmission   
Facility as required by Good Utility Practice. Developer shall provide the Connecting

Transmission Owner and NYISO validated test recordings showing the responses of the Merchant Transmission Facility.

Subsequent to the Commercial Operation Date, the Developer shall provide Connecting   
Transmission Owner and NYISO any information changes due to equipment replacement, repair,   
or adjustment. Connecting Transmission Owner shall provide the Developer and NYISO any   
information changes due to equipment replacement, repair or adjustment in the directly   
connected substation or any adjacent Connecting Transmission Owner substation that may affect   
the Merchant Transmission Facility or Developer Attachment Facilities equipment ratings,   
protection or operating requirements. The Developer and Connecting Transmission Owner shall   
provide such information no later than thirty (30) Calendar Days after the date of the equipment   
replacement, repair or adjustment.

ARTICLE 25. INFORMATION ACCESS AND AUDIT RIGHTS

25.1 Information Access.

Each Party (“Disclosing Party”) shall make available to another Party (“Requesting

Party”) information that is in the possession of the Disclosing Party and is necessary in order for   
the Requesting Party to: (i) verify the costs incurred by the Disclosing Party for which the   
Requesting Party is responsible under this Agreement; and (ii) carry out its obligations and   
responsibilities under this Agreement. The Parties shall not use such information for purposes   
other than those set forth in this Article 25.1 of this Agreement and to enforce their rights under   
this Agreement.

25.2 Reporting of Non-Force Majeure Events.

Each Party (the “Notifying Party”) shall notify the other Parties when the Notifying Party   
becomes aware of its inability to comply with the provisions of this Agreement for a reason other   
than a Force Majeure event. The Parties agree to cooperate with each other and provide   
necessary information regarding such inability to comply, including the date, duration, reason for   
the inability to comply, and corrective actions taken or planned to be taken with respect to such

57

SERVICE AGREEMENT NO. 2710

inability to comply. Notwithstanding the foregoing, notification, cooperation or information

provided under this Article shall not entitle the Party receiving such notification to allege a cause for anticipatory breach of this Agreement.

25.3 Audit Rights.

Subject to the requirements of confidentiality under Article 22 of this Agreement, each   
Party shall have the right, during normal business hours, and upon prior reasonable notice to   
another Party, to audit at its own expense the other Party’s accounts and records pertaining to the   
other Party’s performance or satisfaction of its obligations under this Agreement. Such audit   
rights shall include audits of the other Party’s costs, calculation of invoiced amounts, and each   
Party’s actions in an Emergency State. Any audit authorized by this Article shall be performed   
at the offices where such accounts and records are maintained and shall be limited to those   
portions of such accounts and records that relate to the Party’s performance and satisfaction of   
obligations under this Agreement. Each Party shall keep such accounts and records for a period   
equivalent to the audit rights periods described in Article 25.4 of this Agreement.

25.4 Audit Rights Periods.

25.4.1 Audit Rights Period for Construction-Related Accounts and Records.

Accounts and records related to the design, engineering, procurement, and construction of Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades shall be subject to audit for a period of twenty-four months   
following Connecting Transmission Owner’s issuance of a final invoice in accordance with   
Article 12.2 of this Agreement.

25.4.2 Audit Rights Period for All Other Accounts and Records.

Accounts and records related to a Party’s performance or satisfaction of its obligations   
under this Agreement other than those described in Article 25.4.1 of this Agreement shall be   
subject to audit as follows: (i) for an audit relating to cost obligations, the applicable audit rights   
period shall be twenty-four months after the auditing Party’s receipt of an invoice giving rise to   
such cost obligations; and (ii) for an audit relating to all other obligations, the applicable audit   
rights period shall be twenty-four months after the event for which the audit is sought.

25.5 Audit Results.

If an audit by a Party determines that an overpayment or an underpayment has occurred, a notice of such overpayment or underpayment shall be given to the other Party together with   
those records from the audit which support such determination.

ARTICLE 26. SUBCONTRACTORS

26.1 General.

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,

58

SERVICE AGREEMENT NO. 2710

however, that each Party shall require its subcontractors to comply with all applicable terms and conditions of this Agreement in providing such services and each Party shall remain primarily liable to the other Parties for the performance of such subcontractor.

26.2 Responsibility of Principal.

The creation of any subcontract relationship shall not relieve the hiring Party of any of its obligations under this Agreement. The hiring Party shall be fully responsible to the other Parties for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been made; provided, however, that in no event shall the NYISO or Connecting Transmission Owner be liable for the actions or inactions of the Developer or its subcontractors with respect to   
obligations of the Developer under Article 5 of this Agreement. Any applicable obligation   
imposed by this Agreement upon the hiring Party shall be equally binding upon, and shall be construed as having application to, any subcontractor of such Party.

26.3 No Limitation by Insurance.

The obligations under this Article 26 will not be limited in any way by any limitation of subcontractor’s insurance.

ARTICLE 27. DISPUTES

27.1 Submission.

In the event any Party has a dispute, or asserts a claim, that arises out of or in connection   
with this Agreement or its performance (a “Dispute”), such Party shall provide the other Parties   
with written notice of the Dispute (“Notice of Dispute”). Such Dispute shall be referred to a   
designated senior representative of each Party for resolution on an informal basis as promptly as   
practicable after receipt of the Notice of Dispute by the other Parties. In the event the designated   
representatives are unable to resolve the Dispute through unassisted or assisted negotiations   
within thirty (30) Calendar Days of the other Parties’ receipt of the Notice of Dispute, such   
Dispute may, upon mutual agreement of the Parties, be submitted to arbitration and resolved in   
accordance with the arbitration procedures set forth below. In the event the Parties do not agree   
to submit such Dispute to arbitration, each Party may exercise whatever rights and remedies it   
may have in equity or at law consistent with the terms of this Agreement.

27.2 External Arbitration Procedures.

Any arbitration initiated under this Agreement shall be conducted before a single neutral   
arbitrator appointed by the Parties. If the Parties fail to agree upon a single arbitrator within ten

(10) Calendar Days of the submission of the Dispute to arbitration, each Party shall choose one   
arbitrator who shall sit on a three-member arbitration panel. In each case, the arbitrator(s) shall   
be knowledgeable in electric utility matters, including electric transmission and bulk power   
issues, and shall not have any current or past substantial business or financial relationships with   
any party to the arbitration (except prior arbitration). The arbitrator(s) shall provide each of the   
Parties an opportunity to be heard and, except as otherwise provided herein, shall conduct the   
arbitration in accordance with the Commercial Arbitration Rules of the American Arbitration   
Association (“Arbitration Rules”) and any applicable FERC regulations or RTO rules; provided,

59

SERVICE AGREEMENT NO. 2710

however, in the event of a conflict between the Arbitration Rules and the terms of this Article 27, the terms of this Article 27 shall prevail.

27.3 Arbitration Decisions.

Unless otherwise agreed by the Parties, the arbitrator(s) shall render a decision within

ninety (90) Calendar Days of appointment and shall notify the Parties in writing of such decision   
and the reasons therefor. The arbitrator(s) shall be authorized only to interpret and apply the   
provisions of this Agreement and shall have no power to modify or change any provision of this   
Agreement in any manner. The decision of the arbitrator(s) shall be final and binding upon the   
Parties, and judgment on the award may be entered in any court having jurisdiction. The   
decision of the arbitrator(s) may be appealed solely on the grounds that the conduct of the   
arbitrator(s), or the decision itself, violated the standards set forth in the Federal Arbitration Act   
or the Administrative Dispute Resolution Act. The final decision of the arbitrator must also be   
filed with FERC if it affects jurisdictional rates, terms and conditions of service, Attachment   
Facilities, System Upgrade Facilities, or System Deliverability Upgrades.

27.4 Costs.

Each Party shall be responsible for its own costs incurred during the arbitration process   
and for the following costs, if applicable: (1) the cost of the arbitrator chosen by the Party to sit   
on the three member panel; or (2) one-third the cost of the single arbitrator jointly chosen by the   
Parties.

27.5 Termination.

Notwithstanding the provisions of this Article 27, any Party may terminate this

Agreement in accordance with its provisions or pursuant to an action at law or equity. The issue of whether such a termination is proper shall not be considered a Dispute hereunder.

ARTICLE 28. REPRESENTATIONS, WARRANTIES AND COVENANTS

28.1 General.

Each Party makes the following representations, warranties and covenants:

28.1.1 Good Standing.

Such Party is duly organized, validly existing and in good standing under the laws of the state in which it is organized, formed, or incorporated, as applicable; that it is qualified to do business in the state or states in which the Merchant Transmission Facility, Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades owned by such Party, as   
applicable, are located; and that it has the corporate power and authority to own its properties, to carry on its business as now being conducted and to enter into this Agreement and carry out the transactions contemplated hereby and perform and carry out all covenants and obligations on its part to be performed under and pursuant to this Agreement.

60

SERVICE AGREEMENT NO. 2710

28.1.2 Authority.

Such Party has the right, power and authority to enter into this Agreement, to become a   
Party hereto and to perform its obligations hereunder. This Agreement is a legal, valid and   
binding obligation of such Party, enforceable against such Party in accordance with its terms,   
except as the enforceability thereof may be limited by applicable bankruptcy, insolvency,   
reorganization or other similar laws affecting creditors’ rights generally and by general equitable   
principles (regardless of whether enforceability is sought in a proceeding in equity or at law).

28.1.3 No Conflict.

The execution, delivery and performance of this Agreement does not violate or conflict with the organizational or formation documents, or bylaws or operating agreement, of such   
Party, or any judgment, license, permit, order, material agreement or instrument applicable to or binding upon such Party or any of its assets.

28.1.4 Consent and Approval.

Such Party has sought or obtained, or, in accordance with this Agreement will seek or obtain, each consent, approval, authorization, order, or acceptance by any Governmental   
Authority in connection with the execution, delivery and performance of this Agreement, and it will provide to any Governmental Authority notice of any actions under this Agreement that are required by Applicable Laws and Regulations.

ARTICLE 29. MISCELLANEOUS

29.1 Binding Effect.

This Agreement and the rights and obligations hereof, shall be binding upon and shall inure to the benefit of the successors and permitted assigns of the Parties hereto.

29.2 Conflicts.

If there is a discrepancy or conflict between or among the terms and conditions of this cover agreement and the Appendices hereto, the terms and conditions of this cover agreement shall be given precedence over the Appendices, except as otherwise expressly agreed to in   
writing by the Parties.

29.3 Rules of Interpretation.

This Agreement, unless a clear contrary intention appears, shall be construed and

interpreted as follows: (1) the singular number includes the plural number and vice versa; (2)

reference to any person includes such person’s successors and assigns but, in the case of a Party,   
only if such successors and assigns are permitted by this Agreement, and reference to a person in   
a particular capacity excludes such person in any other capacity or individually; (3) reference to   
any agreement (including this Agreement), document, instrument or tariff means such   
agreement, document, instrument, or tariff as amended or modified and in effect from time to

61

SERVICE AGREEMENT NO. 2710

time in accordance with the terms thereof and, if applicable, the terms hereof; (4) reference to   
any Applicable Laws and Regulations means such Applicable Laws and Regulations as   
amended, modified, codified, or reenacted, in whole or in part, and in effect from time to time,   
including, if applicable, rules and regulations promulgated thereunder; (5) unless expressly stated   
otherwise, reference to any Article, Section or Appendix means such Article of this Agreement   
or such Appendix to this Agreement, or such Section to the Standard Large Facility   
Interconnection Procedures or such Appendix to the Standard Large Facility Interconnection   
Procedures, as the case may be; (6) “hereunder”, “hereof’, “herein”, “hereto” and words of   
similar import shall be deemed references to this Agreement as a whole and not to any particular   
Article or other provision hereof or thereof; (7) “including” (and with correlative meaning   
“include”) means including without limiting the generality of any description preceding such   
term; and (8) relative to the determination of any period of time, “from” means “from and   
including”, “to” means “to but excluding” and “through” means “through and including”.

29.4 Compliance.

Each Party shall perform its obligations under this Agreement in accordance with

Applicable Laws and Regulations, Applicable Reliability Standards, the ISO OATT and Good Utility Practice. To the extent a Party is required or prevented or limited in taking any action by such regulations and standards, such Party shall not be deemed to be in Breach of this Agreement for its compliance therewith. When any Party becomes aware of such a situation, it shall notify the other Parties promptly so that the Parties can discuss the amendment to this Agreement that is appropriate under the circumstances.

29.5 Joint and Several Obligations.

Except as otherwise stated herein, the obligations of NYISO, Developer and Connecting Transmission Owner are several, and are neither joint nor joint and several.

29.6 Entire Agreement.

This Agreement, including all Appendices and Schedules attached hereto, constitutes the   
entire agreement between the Parties with reference to the subject matter hereof, and supersedes   
all prior and contemporaneous understandings or agreements, oral or written, between the Parties   
with respect to the subject matter of this Agreement. There are no other agreements,   
representations, warranties, or covenants which constitute any part of the consideration for, or   
any condition to, either Party’s compliance with its obligations under this Agreement.

29.7 No Third Party Beneficiaries.

This Agreement is not intended to and does not create rights, remedies, or benefits of any character whatsoever in favor of any persons, corporations, associations, or entities other than the Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their successors in interest and permitted their assigns.

62

SERVICE AGREEMENT NO. 2710

29.8 Waiver.

The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver of any

obligation, right, or duty of, or imposed upon, such Party. Any waiver at any time by either   
Party of its rights with respect to this Agreement shall not be deemed a continuing waiver or a waiver with respect to any other failure to comply with any other obligation, right, duty of this Agreement. Termination or Default of this Agreement for any reason by the Developer shall not constitute a waiver of the Developer’s legal rights to obtain Capacity Resource Interconnection Service and Energy Resource Interconnection Service from the NYISO and Connecting   
Transmission Owner in accordance with the provisions of the ISO OATT. Any waiver of this Agreement shall, if requested, be provided in writing.

29.9 Headings.

The descriptive headings of the various Articles of this Agreement have been inserted for convenience of reference only and are of no significance in the interpretation or construction of this Agreement.

29.10 Multiple Counterparts.

This Agreement may be executed in two or more counterparts, each of which is deemed an original but all constitute one and the same instrument.

29.11 Amendment.

The Parties may by mutual agreement amend this Agreement, by a written instrument duly executed by all three of the Parties.

29.12 Modification by the Parties.

The Parties may by mutual agreement amend the Appendices to this Agreement, by a   
written instrument duly executed by all three of the Parties. Such an amendment shall become   
effective and a part of this Agreement upon satisfaction of all Applicable Laws and Regulations.

29.13 Reservation of Rights.

NYISO and Connecting Transmission Owner shall have the right to make unilateral   
filings with FERC to modify this Agreement with respect to any rates, terms and conditions,   
charges, classifications of service, rule or regulation under section 205 or any other applicable   
provision of the Federal Power Act and FERC’s rules and regulations thereunder, and Developer   
shall have the right to make a unilateral filing with FERC to modify this Agreement pursuant to   
section 206 or any other applicable provision of the Federal Power Act and FERC’s rules and   
regulations thereunder; provided that each Party shall have the right to protest any such filing by   
another Party and to participate fully in any proceeding before FERC in which such   
modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties   
or of FERC under sections 205 or 206 of the Federal Power Act and FERC’s rules and

63

SERVICE AGREEMENT NO. 2710

regulations thereunder, except to the extent that the Parties otherwise mutually agree as provided   
herein.

29.14 No Partnership.

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership among the Parties or to impose any partnership

obligation or partnership liability upon any Party. No Party shall have any right, power or

authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, any other Party.

29.15 Other Transmission Rights.

Notwithstanding any other provision of this Agreement, nothing herein shall be construed   
as relinquishing or foreclosing any rights, including but not limited to firm transmission rights,   
capacity rights, or transmission congestion rights that the Developer shall be entitled to, now or   
in the future under any other agreement or tariff as a result of, or otherwise associated with, the   
transmission capacity, if any, created by the System Upgrade Facilities and System   
Deliverability Upgrades.

64

SERVICE AGREEMENT NO. 2710

IN WITNESS WHEREOF, the Parties have executed this Agreement in duplicate originals,   
each of which shall constitute and be an original effective Agreement between the Parties.

New York Independent System Operator, Inc.

By:

Name:

Title:

Date:

New York Power Authority

By:

Name:

Title:

Date:

CHPE LLC

By:

Name:

Title:

Date:

65

SERVICE AGREEMENT NO. 2710

APPENDICES

Appendix A

Attachment Facilities and System Upgrade Facilities

Appendix B

Milestones

Appendix C

Interconnection Details

Appendix D

Security Arrangements Details

Appendix E-1

Initial Synchronization Date

Appendix E-2

Commercial Operation Date

Appendix F

Addresses for Delivery of Notices and Billings

SERVICE AGREEMENT NO. 2710

APPENDIX A

ATTACHMENT FACILITIES AND SYSTEM UPGRADE FACILITIES

1. Attachment Facilities

(a) Developer’s Attachment Facilities (“DAF”):

The Developer’s Attachment Facilities include all of the facilities between the

Developer’s side of the Point of Change of Ownership (“PCO”) and the Merchant Transmission Facility. As depicted in Figure A-3 to this Appendix A, the DAF will be comprised of the   
following facilities:

• One (1) 345kV SF6 circuit breaker, 3000A, 63kA interrupting current, 1300kV BIL,

provided with 18 bushing current transformers (“CTs”) (6 CTs on each bus side bushing);

2 CT cores 3000/5A multi ratio (“MR”) accuracy C800, 2 CT cores 3150/1A, 2 CT cores 3150/1A 5PR20;

• One (1) 345kV motor operated disconnect switch (3phase) 3000A, 63kA withstand

current;

• Two (2) 345kV motor operated grounding switches (3phase), 63kA withstand current;

• Three (3) 345kV/69-115V capacitor voltage transformers (“CVTs”) for relaying and

metering, 3 secondary windings, accuracy: 0.3ZZ, 1800/3000-1;

• Three (3) 345kV surge arresters, station class, maximum continuously operating voltage

(“MCOV”) 289kV;

• Bus work, 3000A continuous, 1300kV BIL;

• Steel structure for equipment and bus supports;

• Foundations/piles;

• Grounding materials, below ground and above ground;

• Control, metering, and protection systems;

• Conduit and control cables; and

• 345 kV lead line from the converter station to be located in Astoria, New York to the

PCO, including:

o Conductor, twin bundle conductor, 2x795 kcmil ACSR 26/7 “DRAKE”;

o 2 X optical ground wire (“OPGW”);

o Steel towers/poles and foundations; and

o 345kV XLPE cables, 345kV XLPE cable splices, duct banks, connectors, and

potheads.

A-1

SERVICE AGREEMENT NO. 2710

(b) Connecting Transmission Owner’s Attachment Facilities (“CTOAFs”):

The Connecting Transmission Owner’s Attachment Facilities include the facilities

between the PCO and the Point of Interconnection (“POI”). The PCO and the POI are

designated in Figure A-1 to this Appendix A. As depicted in Figure A-1, the CTOAFs include the following major electrical and physical equipment:

• One (1) set of three phase 362kV maximum (345kV nominal) GIS voltage transformers

(relaying and metering)

o Two secondary windings, accuracy: 0.3Z 1800/3000:1

o One secondary winding, accuracy 0.3Z, 0.6ZZ 1800/3000:1;

• One (1) set of three phase 362kV maximum (345kV nominal) GIS ring core current

transformers (revenue metering)

o 1500/5A single ratio (“SR”), revenue meter accuracy 0.15S‐B0.1‐1.8, TRF=2;

• Two (2) sets of three phase 362kV maximum (345kV nominal) GIS ring core current

transformers (relaying)

o 3000/5A multi ratio (“MR”), relay accuracy C800, TRF=1.5;

• One (1) set of three phase 362kV maximum (345kV nominal) GIS motor operated

disconnect and grounding switches

o 3000A continuous, 63kA Interrupting current;

• One (1) set of three phase 362kV maximum (345kV nominal) GIS fast acting grounding

switches;

• One (1) set of three phase GIS surge arresters

o Station class, 312kV duty cycle, 245kV maximum continuously operating voltage

(“MCOV”);

• 345kV GIS bus

o 3000A continuous, 1300kV BIL;

• Steel structures for 345kV GIS bus support per design and for GIS transition at PCO;

• Foundations/piles;

• Grounding materials, below grade and above grade;

• Control, metering, and protection systems;

• Conduit and control cables; and

• GIS miscellaneous equipment (e.g., gaskets, bolts, supports).

Pursuant to Article 5.1.3 of this Agreement, Developer has exercised its option to build the CTOAFs as detailed in Section 3 of this Appendix A.

The new Point of Interconnection (“POI”) at the Astoria Annex 345 kV GIS Substation is   
within Zone J North with Connecting Transmission Owner as the metering authority. Consistent   
with Section 7.3 of this Agreement, metering equipment shall be in compliance with the NYISO   
Revenue Metering Requirements, the New York State Department of Public Service Approved   
Meter List dated 8/15/2022 or the most current revision at the time of detailed design (i.e., at the   
time Developer achieves the Long Lead Item Purchase Milestone in Appendix B), and NERC   
FAC-001-3 (Facility Interconnection Requirements). Associated voltage transformers and current   
transformers are required to meet NYISO Manual 25 on Revenue Metering Requirements.

A-2

SERVICE AGREEMENT NO. 2710

2. System Upgrade Facilities

The Merchant Transmission Facility shall interconnect at the Connecting Transmission   
Owner’s existing Astoria Annex 345 kV GIS Substation (“Astoria Annex Substation”) between   
new breakers 4 and 6 (new Bus Section 6). The POI and PCO are described in Appendix C.

(a) Stand Alone System Upgrade Facilities

None.

(b) Other System Upgrade Facilities

The interconnection of the Merchant Transmission Facility requires the expansion of Connecting Transmission Owner’s Astoria Annex Substation from a four (4) breaker ring bus configuration to a six (6) breaker ring bus configuration.

Pursuant to Article 5.1.3, Developer may not exercise as a right the option to build the System Upgrade Facilities other than Stand Alone System Upgrade Facilities. However,   
Connecting Transmission Owner and Developer have agreed that Developer shall perform the design, procurement, and construction of the Other SUFs described in this Appendix A and that Developer perform this Other System Facilities work consistent with the requirements applicable to Stand-Alone SUFs in Article 5.2 of this Agreement.

i. Summary of Changes at the Astoria Annex Substation to Accommodate Merchant Transmission Facility

As illustrated in Figure A-1, the Astoria Annex Substation currently provides the interface among:

• Connecting Transmission Owner’s existing 345 kV feeders FDR Q35L and FDR Q35M,   
 which connect to Consolidated Edison Company of New York, Inc.’s (“Con Edison’s”)   
 East 13th Street 345 kV Substation;

• Con Edison’s feeder FDR 34091, which connects to Con Edison’s 138 kV Astoria East   
 Substation (also referred to as 138 kV Astoria East PAR); and

• The existing 345/16.5 kV Developer’s Attachment Facilities owned by Astoria Energy   
 LLC for the Astoria Energy II generating facility.

In connection with modifications to the Astoria Annex Substation to accommodate the Merchant Transmission Facility, the substation will also provide the interface with:

• The 345kV AC line to the converter substation for the Merchant Transmission Facility   
 located in Astoria, Queens, New York; and

• Connecting Transmission Owner’s 345 kV cable from the Astoria Annex Substation to   
 Con Edison’s Rainey Substation (FDR Y19).

A-3

SERVICE AGREEMENT NO. 2710

As illustrated in Figure A-1, as part of the expansion to a six breaker GIS ring bus at the Astoria Annex Substation, the following changes will be made to the interfaces at the Astoria Annex Substation:

• The existing Con Edison 345kV E13th St. Substation connection via Q35M transmission

line will transition from being between existing breakers 2 and 5 (Bus Section 5) to being between existing breaker 5 and new breaker 6 (new Bus Section 5).

• The proposed connection at the Astoria Annex Substation for the 345 kV cable to Con

Edison’s Rainey Substation (FDR Y19) will be between existing breaker 2 and new

breaker 4 (new Bus Section 4).

• New Geotech testing for the design associated with this project is required.

• New soil testing, removal and disposal are required.

• As part of the Storm Hardening Initiatives and requirements for Flood-Resistant

Construction within the NYC Department of Buildings after Hurricane Sandy, a survey shall be initiated by the Developer for the Astoria Annex Substation. The cost associated with storm hardening was not covered in the Q631/Q887 Part 1 Facilities Study and   
additional study is required per NYC Building Code Appendix G Flood -Resistant   
Construction which references ASCE 24‐14. Any additional costs associated with storm hardening will be allocated in accordance with the requirements in Section 25.8.6.4 of Attachment S to the NYISO OATT to the extent applicable.

Responsible party to follow the more stringent design standards as prescribed by either   
NYC Building Code or the NYS Building Code. Currently, The NYS Building Code   
references ASCE 24-14 (Code Reference Book) requiring design of critical infrastructure   
to the HIGHER of 3’ above the Base Flood Elevation or the 500-year flood as indicated   
by the FEMA Firm maps, which governs over the current NYC Building Code.

• From a security standpoint, Con Edison monitors access and control to all of Connecting

Transmission Owner’s Astoria Annex Substation. If the NPCC re‐classifies the Astoria   
Annex Substation due to the interconnection of the Merchant Transmission Facility,   
additional upgrades may be required. Any additional costs associated with additional   
upgrades due to the reclassification of the Astoria Annex Substation will be allocated in   
accordance with requirements in Section 25.8.6.4 of Attachment S to the NYISO OATT   
to the extent applicable.

A-4

SERVICE AGREEMENT NO. 2710

ii. Equipment and Physical Equipment Required for Modifications to Astoria Annex Substation to Accommodate Merchant Transmission Facility

The expansion of the Astoria Annex Substation shall include, but is not limited to, the following major electrical and physical equipment:

NOTE: Specific details of this installation will be handled in the detailed design and review   
process.

As further described in Section 3 of this Appendix A, Developer Election of Option to Build, Developer shall adhere to Connecting Transmission Owner’s applicable processes and   
policies in execution of the Astoria Annex Substation expansion including, engineering, design, procurement, construction, quality assurance, and documentation processes. The equipment   
specifications and design standards shall be in accordance with Con Edison’s design   
requirements and subject to review and approval by both Connecting Transmission Owner and Con Edison. However, revisions to such specifications and standards that occur after 30%   
design packages have been issued by Connecting Transmission Owner will not be imposed on Developer to avoid the need for any redesigns.

• Two (2) SF6, GIS circuit breakers 362kV maximum (345kV nominal) nominal system   
 voltage

o 3000A continuous, 1300 kV BIL, 63kA interrupting;

• Twelve (12) sets of three phase 362kV maximum (345kV nominal) GIS ring core current   
 transformers (relaying)

o 3000/5A multi ratio (“MR”), relay accuracy C800, TRF=1.5;

• Two (2) sets of three phase 362kV maximum (345kV nominal) GIS ring core current   
 transformers (metering)

o 3000/5A multi ratio (“MR”), meter accuracy 0.3B2.0, TRF=1.5;

• Four (4) sets of three phase 362kV maximum (345kV nominal) GIS motor operated   
 disconnect/grounding switches

o 3000A continuous, 1300 kV BIL, 63kA Interrupting current; and

• Two (2) sets of three phase 362kV maximum (345kV nominal) GIS voltage transformers   
 (relaying and metering)

o Three secondary windings, accuracy: 0.3Z, 1800/3000:1.

NOTE: BIL ratings of Gas Insulated Switchgear assemblies to be finalized in Insulation Coordination Study during detailed design.

In addition, the Other SUFs include the following additional equipment at the Astoria Annex Substation:

• 345kV GIS structures (including GIS to underground cable termination structures);

• 345kV GIS bus work;

• Conduit and trench;

• Control cabling;

• Foundations/piles;

A-5

SERVICE AGREEMENT NO. 2710

• Grounding materials;

• One (1) new prefabricated control enclosure including:

o New 1st Line Relay & DC Panel Room #2:

▪ Four (4) 1st Line relaying, control, and communication panels; and ▪ One (1) 125 VDC distribution panel;

▪ One (1) new cable termination cabinet ▪ Auxiliary enclosure systems

o New 2nd Line Relay & DC Panel Room #2:

▪ Four (4) 2nd Line relaying, control, and communication panels; and ▪ One (1) 125 VDC distribution panel;

▪ One (1) new cable termination cabinet   
 ▪ Auxiliary enclosure systems   
 • Existing Control/HMI Room:

o Existing Revenue Metering Cabinet

▪ One (1) primary revenue meter;   
▪ One (1) backup revenue meter;

o One (1) AC switchboard; and

o One (1) 125 VDC switchboard;

• Existing Comm Room #1:

o 1st Line fiber patch panel and SCADA equipment;

• Existing Comm Room #2:

o 2nd Line fiber patch panel and SCADA equipment.

Substation Physical Requirements include but are not limited to:

Foundations: New foundations required for new control enclosure and for new equipment.

Tray/Conduit/Cable: New trough, tray, conduit, and cable required for all new equipment and to reroute circuits to existing equipment.

Concrete duct bank/Cable Trench - Two new isolated and separated underground cable systems protected by concrete to connect 1st Line Relay Room #1 to 1st Line Relay Room #2 and 2nd Line Relay Room #1 to 2nd Line Relay Room #2.

Grounding: Grounding for new equipment in accordance with applicable codes, standards, Connecting Transmission Owner’s requirements and Con Edison’s specifications.

Fence: The station fence will be modified to accommodate the new prefabricated control enclosure.

Control Enclosure: New 1st Line Relay Panel & DC Panel Room #2 and new 2nd Line Relay   
Panel & DC Panel Room #2 to be constructed to accommodate the new protective relaying   
panels per SUF design. The minimum required auxiliary systems, such as fire   
detection/notification, alarms, security, HVAC, heating, lighting, and receptacles shall be   
installed for both new relay rooms in the control enclosure. No spare equipment considerations

A-6

SERVICE AGREEMENT NO. 2710

nor future expansion considerations shall be required in the design or construction of the new control enclosure.

Battery/Charger: Existing, to be verified if supports the additional DC load per design and upgrade if necessary.

AC Station Service: Existing, to be verified if supports the additional AC load per design and upgrade if necessary.

Sequence of Events Recorder (“SER”)/Digital Fault Recorder (“DFR”)Equipment: Existing, to be verified if supports the additional required inputs per design and upgrade if necessary.

RTU: Existing, to be verified if supports the additional required inputs per design and upgrade if necessary.

Lightning Protection: N/A.

Bus Layout: Per Con Edison’s TRANSMISSION PLANNING CRITERIA (EP-7100-10

paragraph 1.7), “Interconnection plans will avoid overhead crossings of other feeders and

associated substation bus sections, provide adequate separation and when necessary independent   
routing of underground feeders, and provide separation of control and relay protection wiring.”   
Crossing gas insulated sections of 345kV Y19 (Astoria-Rainey Cable)/Q631 is acceptable per   
Con Edison.

Phasor Measurement Unit Requirements

In accordance with Article 9.10 of this Agreement, the Developer will also be responsible for

installing at the Astoria Annex Substation one (1) phasor measurement unit (“PMU”) and optical   
transport network equipment and its associated equipment for transmitting PMU data to NYPA   
and NYISO. Connecting Transmission Owner will own, operate, and maintain this equipment.

Protective Relaying Requirements:

The conceptual Main One Line Diagram (Dwg. No. 3022107-001) is provided in Figure A-1 to this Appendix A. Eight (8) new relay panels are required.

A proposed standalone control enclosure will contain two (2) rooms: 1st Line Relay & DC Panel   
Room #2 and 2nd Line Relay and DC Panel Room #2. Each room will contain four (4) relay   
control panels, one (1) 125 VDC distribution panel, and one (1) cable termination cabinet for   
interfacing with the existing control building. The relays in these new rooms will protect the two

(2) new transmission lines being connected to the Astoria Annex Substation ring bus and

associated GIS equipment. Spare equipment and future expansion considerations shall not be required as related to protective relaying.

I. Control Room “1st Line Protection”

• Existing Bus Section 1 - Existing 345kV FDR.Q35L connection:

A-7

SERVICE AGREEMENT NO. 2710

o Existing Panel 1-1A - no equipment update

o Existing Panel 1-1B - no equipment update

o Existing Panel 1-1C - no equipment update

• Existing Bus Section 2 - Existing 345kV FDR.G13 connection:

o Existing Panel 2-1A - no equipment update

o Existing Panel 2-1B - no equipment update

• Existing Bus Section 3 - Existing 345kV Astoria PAR 138kV:

o Existing Panel 3-1A - no equipment update

o Existing Panel 3-1B - no equipment update

o Existing Panel FDR 34091 - no equipment update

• Existing Bus Section 5 - Existing 345kV FDR Q35M:

o Existing Panel 5-1A - no equipment update

o Existing Panel 5-1B - no equipment update

o Existing Panel 5-1C - no equipment update

II. Control Room “2nd Line Protection”

• Existing Bus Section 1 - Existing 345kV FDR.Q35L connection:

o Existing Panel 1-2A - no equipment update

o Existing Panel 1-2B - no equipment update

o Existing Panel 1-2C - no equipment update

• Existing Bus Section 2 - Existing 345kV FDR.G13 connection:

o Existing Panel 2-2A - no equipment update

o Existing Panel 2-2B - no equipment update

• Existing Bus Section 3 - Existing 345kV Astoria PAR 138kV:

o Existing Panel 3-2A - no equipment update

o Existing Panel 3-2B - no equipment update

o Existing Panel FDR 34091 - no equipment update

• Existing Bus Section 5 - Existing 345kV FDR Q35M:

o Existing Panel 5-2A - no equipment update

o Existing Panel 5-2B - no equipment update

o Existing Panel 5-2C - no equipment update

III. New Control Room “1st Line Protection” #2

• New Bus Section 4 - New 345kV Astoria-Rainey Cable connection (FDR Y19):

o New Panel 4-1A

▪ Line Differential and direct transfer trip (“DTT”): 85-1 ▪ BKR 4 Failure (50/62-1/4)

▪ LOR relays for 85-1 and breaker failure, FT test switches

o New Panel 4-1B

▪ Bus Diff 87B/BS#4

A-8

SERVICE AGREEMENT NO. 2710

▪ Communication /fiber equipment ▪ FT test switches

• New Bus Section 6 - New 345kV feeder - single circuit tie line approximately 0.3 miles   
 in length within the Astoria complex from the Merchant Transmission Facility   
 (Q631/Q887):

o New Panel 6-1A

▪ Line Differential and direct transfer trip (“DTT”): 85-1 ▪ BKR 6 Failure (50/62-1/6)

▪ LOR relays for 85-1 and breaker failure, FT test switches

o New Panel 6-1B

▪ Bus Diff 87B/BS#6

▪ Communication /fiber equipment ▪ FT test switches

IV. New Control Room “2nd Line Protection” #2

• New Bus Section 4 - New 345kV Astoria-Rainey Cable connection (FDR Y19):

o New Panel 4-2A

▪ Line Differential and direct transfer trip (“DTT”): 85-2 ▪ BKR 4 Failure (50/62-2/4)

▪ LOR relays for 85-2 and breaker failure, FT test switches

o New Panel 4-2B

▪ Communication /fiber equipment ▪ FT test switches

• New Bus Section 6 - New 345kV feeder - single circuit tie line approximately 0.3 miles   
 in length within the Astoria complex from the Merchant Transmission Facility   
 (Q631/Q887):

o New Panel 6-2A

▪ Line Differential and direct transfer trip (“DTT”): 85-2 ▪ BKR 6 Failure (50/62-2/6)

▪ LOR relays for 85-2 and breaker failure, FT test switches

o New Panel 6-2B

▪ Communication /fiber equipment ▪ FT test switches

V. Control Room at Developer’s Attachment Facilities

• New 345kV Feeder - Astoria Annex Substation 345kV line:

o New 1st Line Relay Panel

▪ Line Differential and direct transfer trip (“DTT”): 85 ▪ BKR Failure (50/62)

▪ LOR relays for 85 and breaker failure, FT test switches

o New 2nd Line Relay Panel

▪ Line Differential and direct transfer trip (“DTT”): 85 ▪ BKR Failure (50/62)

▪ LOR relays for 85 and breaker failure, FT test switches

A-9

SERVICE AGREEMENT NO. 2710

o New SCADA Panel

▪ Communication /fiber equipment

Revenue Meter:

• Two (2) new revenue meters for the Merchant Transmission Facility will be installed in   
 the existing Connecting Transmission Owner’s metering cabinet, located in the Astoria   
 Annex control room.

iii. Astoria-Rainey Cable (FDR Y19)

Pursuant to Section 25.6.1.4.1 of Attachment S of the NYISO OATT, Developer elected to construct the Astoria-Rainey Cable as a System Upgrade Facility that is more extensive than the minimum facilities required to reliably interconnect the Merchant Transmission Facility project and is reasonably related to the interconnection of the project (“Elective SUF”). The   
demarcation points for the Astoria-Rainey Cable are the 345 kV cable potheads exiting the   
Astoria Annex Substation and Con Edison’s Rainey Substation.

As further described in Section 3 of this Appendix A, Developer Election of Option to   
Build, Developer shall adhere to Connecting Transmission Owner’s applicable processes and   
policies in execution of the Astoria-Rainey Cable including, engineering, design, procurement,   
construction, quality assurance, and documentation processes. The equipment specifications and   
design standards shall be in accordance with Connecting Transmission Owner’s design   
requirements and subject to review and approval by Connecting Transmission Owner.

The major equipment to accommodate the Astoria-Rainey Cable project at the Astoria Annex Substation include the following:

• One (1) set of three phase 362kV maximum (345kV nominal) GIS voltage transformers   
 (relaying and metering)

o Three secondary windings, accuracy: 0.3Z, 1800/3000:1;

• Two (2) sets of three phase 362kV maximum (345kV nominal) GIS ring core current   
 transformers (relaying)

o 3000/5A multi ratio (“MR”), relay accuracy C800, TRF=2;

• One (1) set of three phase 362kV maximum (345kV nominal) GIS motor operated   
 disconnect and grounding switches

o 3000A continuous, 63kA interrupting current;

• One (1) set of three phase 362kV maximum (345kV nominal) GIS fast acting grounding   
 switches;

• One (1) set of three phase GIS surge arresters

o Station class, 312kV duty cycle, 245kV maximum continuously operating voltage   
 (“MCOV”);

• 345kV GIS bus

o 3000A continuous, 1300kV BIL;

• Steel structures for 345kV GIS bus support per design and for GIS transition at PCO;   
• 345kV XLPE cables, 345kV XLPE cable splices, duct banks, connectors, and potheads

• Foundations/piles;

A-10

SERVICE AGREEMENT NO. 2710

• Grounding materials, below grade and above grade;

• Control, metering, and protection systems;

• Conduit and control cables; and

• GIS miscellaneous equipment.

Additional upgrades will be required at Con Edison’s Rainey Substation. In addition, the existing single circuit connection from the Con Edison PAR to the Astoria East 138 kV   
substation will be upgraded to provide a Long Term Emergency (“LTE”) rating of at least 333 MW. As described in Section 4 of this Appendix A below, these upgrades will be addressed through a separate Transmission Facility Interconnection Agreement among the NYISO,   
Connecting Transmission Owner, Con Edison, and Developer.

The Connecting Transmission Owner shall supply standard drawings and equipment

specifications for the Developer to finalize the design for the Connecting Transmission Owner’s review and approval. The Developer will coordinate the work and necessary outages with   
Connecting Transmission Owner.

iv. Replacement of Overdutied Breakers at Valley Stream 138 kV Substation

The Class Year Interconnection Facilities Study for Class Year 2021 (“Class Year

Study”) determined that seven 138 kV breakers at the Long Island Power Authority’s (“LIPA”) Valley Stream 138 kV Substation must be replaced as they will be overdutied due to certain   
Class Year 2021 projects, including the Merchant Transmission Facility (“Breaker Replacement Upgrades”). However, as a result of the withdrawal of certain of the impacted Class Year 2021 projects following the conclusion of the Class Year Study, the NYISO subsequently determined that this work is no longer required.

3. Developer Election of Option to Build

Pursuant to Article 5.1.3 of this Agreement, the Developer has chosen the option to build   
the CTOAFs and will construct the Other System Upgrade Facilities and Elective SUF as   
described in this Appendix A, all of which facilities will be transferred to the Connecting   
Transmission Owner. The Developer will be responsible for the engineering, design,   
procurement, construction, installation, testing, commissioning, and transfer of such facilities in   
accordance with Connecting Transmission Owner’s or Con Edison’s applicable standards and   
procedures (including NYPA Division 1 Project Requirements Specifications, NYPA Design   
Criteria Rev 10, Environmental, Health, and Safety Requirements for Construction at Authority   
Facilities and Projects, NYPA EH&S Technical Specifications Checklist and applicable NERC   
Reliability Standards and NPCC directives), to the extent such standards are not inconsistent   
with the terms of this Agreement, the NYISO OATT, or applicable NYISO procedures.   
Equipment procurement for the facilities that will be turned over to the Connecting Transmission   
Owner shall comply with its procurement process including its Appendix P and other NERC CIP   
program requirements.

In the event that a Party becomes aware that Applicable Laws and Regulations or the   
requirements and guidelines of Applicable Reliability Councils have been modified that could

A-11

SERVICE AGREEMENT NO. 2710

affect the safe or reliable operations of the CTOAF, Other System Upgrade Facilities or Elective SUF the Party shall notify the other Parties promptly, so that the Parties can mutually agree upon an amendment, if needed, of this Agreement.

4. Affected Systems

The interconnection of the Merchant Transmission Facility will require System Upgrade Facilities at Con Edison’s Rainey Substation to accommodate the new underground 345 kV   
cable from the Astoria Annex Substation, as well as the reconductoring of the overhead portions of Con Edison’s Line #34091 from the Astoria Annex Substation to the Astoria East 138 kV   
PAR. This work will be addressed through a separate Transmission Facility Interconnection   
Agreement (NYISO OATT Service Agreement No. 2772) among the NYISO, Connecting   
Transmission Owner, Con Edison, and Developer. As detailed in the executed Service   
Agreement 2772, the Connecting Transmission Owner shall provide operational metering   
information (MW, MVAr, etc) concerning the Merchant Transmission Facility to the Con Edison control center from the Connecting Transmission Owner’s operational meter at the Astoria   
Annex Substation via the Remote Terminal Unit.

5. System Deliverability Upgrades

None.

6. Special Studies

NYISO performed Subsynchronous Torsional Interaction (“SSTI”) screening analysis using Unit Interaction Factor (“UIF”) threshold of 0.10 for CY21 projects and existing   
generation units. The Merchant Transmission Facility project (NYISO Queue Position Nos. Q631/Q887) was tested against the existing Astoria Energy II generator.

Pursuant to Section 6.1 of NYISO Class Year 2021 System Upgrade Facilities (SUF) and System Deliverability Upgrade (SDU) Report (October 17, 2022), it is recommended for new HVDC/inverter-based resource interconnections that the actual design prevent unwanted   
potential SSTI with existing nearby generation units, and for new generation control actual   
design prevent unwanted potential SSTI with existing nearby HVDC/inverter-based generation. Based on this, Developer will perform a detailed SSTI analysis for the Merchant Transmission Facility project during the detailed engineering phase of the project.

7. Cost Estimates\*

Description Estimated Cost

Connecting Transmission Owner’s Attachment Facilities $9,150,000

System Upgrade Facilities $174,910,000

Total $184,0630,000

A-12

SERVICE AGREEMENT NO. 2710

\* These cost estimates do not include the costs for the work on Con Edison’s or LIPA’s system associated with the interconnection of the Merchant Transmission Facility, which work is   
addressed under separate agreements, or the costs of the SSTI analysis.

8. O&M for CTOAFS

Pursuant to Section 10.5 of this Agreement, Developer shall pay the reasonable expenses (including overheads) for the operation, maintenance, repair and replacement of CTOAFs. Such expenses are calculated as follows:

a) Contractor expenses for labor, equipment and materials. These expenses shall be

invoiced as the actual amount of the Contractors’ invoices. Connecting Transmission Owner shall also be entitled to a fee of 5 % of such amount(s).

b) Connecting Transmission Owner’s labor, craft and salaried personnel directly working on

the operation, maintenance or repair of the Connecting Transmission Owner’s

Attachment Facilities. These expenses shall be invoiced on the basis of Connecting

Transmission Owner’s standard labor rate times the number of hours worked (including   
adjustment for overtime hours, if applicable). Such standard rate is subject to change in   
accordance with Connecting Transmission Owner’s normal budgeting practices.

c) Equipment and materials purchased by the Connecting Transmission Owner (other than

those covered under subsection (a), above). These expenses shall be invoiced on the basis of the actual cost of such material. Connecting Transmission Owner shall also be entitled to a fee of 15% of such amount(s).

d) Use of vehicles and construction equipment. These expenses shall be invoiced at

Connecting Transmission Owner’s cost. Connecting Transmission Owner shall also be entitled to a fee of 10% of such amount(s).

e) Miscellaneous expenses (e.g. local utility charges for power; local telephone/

communication fees; other fees such as FAA licenses). These expenses shall be invoiced at Connecting Transmission Owner’s cost. Connecting Transmission Owner shall also be entitled to a fee of 5% of such amount(s).

9. Transfer of Property

Pursuant to Section 5.2.10 of this Agreement, upon completion of construction, testing, and   
acceptance of the Astoria Annex Substation improvements and the Astoria-Rainey Cable by the   
Connecting Transmission Owner, Developer will (a) convey to the Connecting Transmission   
Owner property rights sufficient to allow the CTO to operate and maintain the SUF and CTOAF.   
(including assignable consents issued by the City of New York) including any required right of   
way as depicted in Site Plan (to be provided by the Developer), and (b) will transfer to Connecting   
Transmission Owner title to the CTOAFs and SUFs constructed thereon or therein, all free and   
clear of any liens and encumbrances. All conveyance documents consistent with Connecting   
Transmission Owner requirements, including those in the Design Criteria for Developer   
Connection to New York Power Authority’s Transmission System document, and will be subject

A-13

SERVICE AGREEMENT NO. 2710

to prior review by, and in form acceptable to, Connecting Transmission Owner. Connecting

Transmission Owner will provide the Developer an easement, permit, or contractual access right   
over such transferred property to allow Developer access to the SUFs and CTOAF. The   
Connecting Transmission Owner shall, at its discretion and at its expense, maintain any required   
right of way for its purposes only. Any additional access or maintenance of any required right of   
way requested or required by Developer or others with whom Developer has obtained an   
easement, permit or other property interest or contractual access rights for the site access road,   
including, but not limited to, snow removal, shall be the responsibility of the Developer.

10. Engineering Services Provided by Connecting Transmission Owner

The Connecting Transmission Owner will perform its review and approval of engineering   
designs as required in Article 5.2.4 of this Agreement in the manner described in this Section 10.   
The Connecting Transmission Owner and Developer’s contact information concerning the   
performance of the engineering services described in this Section 10 are included in Appendix F   
of this Agreement.

The Connecting Transmission Owner shall only provide engineering services for

equipment and structures to which it is contemplated that title will be transferred to the

Connecting Transmission Owner under this Agreement. The Connecting Transmission Owner is not providing engineering services with respect to any other equipment or structures.

Developer’s engineering drawings for the interconnection of the Merchant Transmission Facility shall be submitted to the Connecting Transmission Owner and be stamped by a   
Professional Engineer. If Developer revises any of the drawings, the revised drawings shall be resubmitted to the Connecting Transmission Owner and shall indicate all changes made from the prior submission by highlighting or circling the change. Upon receipt of the Developer’s   
drawings, the Connecting Transmission Owner shall timely commence its review and provide comments to Developer within 30 calendar days from the date of receipt.

After completing its review, the Connecting Transmission Owner shall send written

notice to Developer either: (1) approving the drawings; or (2) detailing any deficiencies and nonconformance with the Connecting Transmission Owner’s criteria and specifications and   
applicable design requirements, including copies of any relevant design criteria documents and supporting information. To the extent necessary, Developer shall correct any deficiencies and non-conformance and submit revised design criteria information to the Connecting Transmission Owner for further review and acceptance.

11. Connecting Transmission Owner’s and Developer’s Responsibilities Concerning

Attachment Facilities and System Upgrade Facilities

Responsibility Matrix for CTO and Developer Scope

Concerning Attachment Facilities and System Upgrade Facilities

Task Connecting

Transmission Owner Developer Scope

Scope

A-14

SERVICE AGREEMENT NO. 2710

1

Connecting Transmission Owner’s Attachment Facilities

• Merchant Transmission   
 Facility interconnection at

Astoria Annex Substation   
(from POI at Astoria Annex

Substation to Point of Change of Ownership (PCO)

demarcation)

• Review & approve   
 the engineering,

design &

procurement

• Oversight for   
 construction/installa

tion, testing,   
commissioning

Engineer, design, procure,   
 construct/install, test,   
 commission

Other System Upgrade Facilities Connecting

(SUF) at Astoria Annex 345kV GIS Transmission Owner Developer Scope

Substation Scope

2.1

2.2

• Expansion of the existing   
 Astoria Annex Substation

from a (4) four breaker ring bus to a (6) six breaker ring bus configuration.

• FDR Q35M relocation on the   
 new Bus Section 5 of the six

(6) breaker ring bus configuration

345 kV HVAC Transmission Line between Astoria Converter Station and Astoria Annex

Review & approves

NYPA to review and approves pothead   
structures at Astoria Annex (PCO)

Engineer, design, procure,   
 construct/install, test,

commission

Engineer, design, procure,   
 construct/install, test,   
 commission

Other System Upgrade Facilities   
(“SUF”) for Astoria-Rainey Cable

Connecting

Transmission Owner Scope

Developer Scope

A-15

SERVICE AGREEMENT NO. 2710

2.3 • Design of the duct bank

• XLPE cable design

• Pulling calculations and plans • Cable Joint design

• Environmental review for the   
 route

• Route excavation design • Rating calculations

• Manhole design • Grounding design • FATs

• Final tests

2.4 • Installation of the concrete duct

bank for XLPE cable • Cable pulling

• Joint installation

• Termination at Astoria Annex   
 and Rainey

• Manhole installation

Review & approves

Construction oversight

Engineer, design, procure,   
 construct/install, test,

commission

Engineer, design, procure,   
 construct/install, test,   
 commission

Specific Task with Protection and Connecting

Control Scope for the expanded Transmission Owner Developer Scope

Astoria Annex Substation Scope

Protection application document with

3 high level sketches of protection and Review & approves Develop & submit

communication schemes

4 Drawing package Review & approves Develop & submit

A-16

SERVICE AGREEMENT NO. 2710

Finalize drawing package

5

(Professional Engineer (“PE”) Sealed Issued For Construction (“IFC”)

Drawings)

For record keeping

Develop & submit

6 Final drawing package approved Review & approves Develop & submit

7

Develop bill of materials and bid specification

Review & approves

Develop & submit

Procurement of new control enclosure Engineer, design, procure,

8 including all protection and control Review & approves construct/install, test,

relaying. commission

Perform design and settings

development to ensure all BPS NERC

9

and NPCC requirements are met including but not limited to PRC002, PRC023, PRC027, PRC026,   
Directory 11, Directory 4

Review & approves

Develop & submit

Developer to ensure that the project’s

10

expanded Astoria Annex Substation is accurately represented in the NYISO Aspen model

Review & approves

Develop & submit

Must provide calculations and final

11

12

values of new line parameters (facility thermal ratings including impedance, mutual coupling & susceptance)

All as-built drawings comments to be updated electronically

Review & approves

Review & approves

Develop & submit

Develop & submit

Developer is required to perform

protection coordination studies for the

13 project’s expanded Astoria Annex Review & approves Develop & submit

Substation utilizing the ASPEN NYISO model.

14 Develop relay settings & calculations Review & approves Develop & submit

A-17

SERVICE AGREEMENT NO. 2710

15

NPCC Directory 4 presentation and approval

Support

Develop & submit

16 Program relay settings

Review & approves

Develop, Execute relay   
 settings & submit

17 Perform test settings Review & approves Develop, test & submit

18

19

20

21

22

23

24

25

Construction/installation

Testing and commissioning ensure all   
PRC005 requirements are adhered to

Task associated with SCADA/RTU Scope for the expanded Astoria

Annex Substation

SCADA/RTU Points and Protocol address development

Provide specifications

Procure equipment   
Physical installation

Testing

Commissioning

Oversight

Witness testing

Connecting

Transmission Owner   
 Scope (Per Con

Edison’s

Requirements

Subject to NYPA’s   
 Review)

Review and approve

Develop & submit   
review final design

specs

Review & approves

Oversight

Testing with control   
 room is Connecting   
Transmission Owner

responsibility

Responsible

Construction & installation

Submit testing and   
commissioning plan,

Perform testing and   
 commissioning

Developer Scope

Develop & submit

Incorporate in final design   
 and

Modify/develop additional   
 specifications as needed   
Procure, develop & submit

Complete physical

installation; Developer to be   
available to troubleshooting

physical wiring changes   
 during testing

Developer responsible to   
 local testing, ensure

everything is up and   
 running

Coordinate with CHPE   
Astoria converter station   
 side

A-18

SERVICE AGREEMENT NO. 2710

NOTE: Remote End Connecting Transmission Owner location includes Energy Management System and SCADA Model updates and other upgrades required associated with the Merchant Transmission Facility to be implemented at Connecting Transmission Owner’s Energy Control Center and at Con Edison Control Room monitoring, assessing, and controlling if applicable.

Refer to Figure A-4 - Communication Block Diagram for guidance on equipment and telemetry roles and responsibilities.

Task associated with

communication protocol scope for Connecting

the expanded Astoria Annex Transmission Owner Developer Scope

Substation (NERC CIP Program Scope

Requirements)

26

27

28

29

30

For the expanded Astoria Annex Substation

and CTOAF scope associated with security system that meets

Connecting Transmission Owner’s   
NERC CIP program requirements   
(physical, electronic, and Cyber) and   
secure to Medium Impact assets;

Complete Connecting Transmission Owner NERC CIP program

requirements for design, engineering, procurement and construction

Project turn over and closeout

• IFC drawings, real estate   
 transfer, turn over packages

• Submit final as-built drawings   
• OEM, supplier, contractor or

subcontractor warranties

Environmental Requirements

Drawings, calculations and design for oil containment required to meet Spill

Prevention Control and   
Countermeasure (“SPCC”)   
regulations, as applicable

Professional Engineer (“PE”) sealed certified Spill

Prevention Control and   
Countermeasure (“SPCC”)

Review & approves

Review & approve

Review & approve

Connecting

Transmission Owner   
 Scope

Review

Review

Develop & submit

Develop & submit

Develop & submit

Developer Scope

Develop & submit

Develop & submit

A-19

SERVICE AGREEMENT NO. 2710

Plan and equipment

registrations before turnover

31

32

33

33.1

Complete an unredacted copy of Environmental

Management and Construction Plan (“EM&CP”) including:

• Segment 22 (Astoria   
 Annex) and 23 (ARCable)

and any related studies and recommendations

Real Estate Requirements

Real Estate Permit Application package (Permit to do work on land or under the jurisdiction of the New York Power Authority)

NYPA Real Estate Standards Requirements 10-24-2022

Real Estate Requirements and timely Phase I and Phase II Environmental Site Assessment (“ESA”) naming

NYPA as the user required within 180 days prior to transferring the

easement to NYPA for the following scope:

Astoria-Rainey Cable termination at Astoria Complex - secure Easement with Con Edison, Phase I ESA

required

For Information and   
 Record

Connecting

Transmission Owner   
 Scope

Review and approve

Review and approve

Review and approve

Develop & submit

Developer Scope

Develop & submit

Develop & submit

Acquire and transfer

Astoria-Rainey Cable termination at

Rainey substation - secure Easement Review and approve Acquire and transfer

with Con Edison, Phase I ESA   
required

Astoria-Rainey Cable route in the streets of NY City - Secure

necessary consent to build, own,

Review and approve

Acquire and transfer as   
 applicable

A-20

SERVICE AGREEMENT NO. 2710

maintain, and operate. Phase I ESA if applicable.

Astoria Annex GIS expansion -  
secure Easement as required by final   
design. Phase I ESA as applicable.

Other Permits

34 Construction/Building Permits

required by Authority Having Jurisdiction (“AHJ”) for

• Astoria Annex GIS

switchgear expansion   
to a 6-breaker ring   
within the existing   
building

• New control

building/enclosures for Relay rooms

• Astoria-Rainey Cable

Special Studies

Subsynchronous Torsional   
35 Interaction (“SSTI”) Analysis

Review and approve-

CTO to Review as applicable

NYISO/CTO Scope

Review and Approve

Acquire and transfer

Developer Scope

• Developer to acquire   
 associated permits with

NY City, NYPA and other permits as required by the project

• This may not be an   
 exhaustive list subject to

Developer’s   
confirmation.

• NY City Department of   
 Building (“DOB”) to

issue building permit for GIS switchgear

expansion to a 6- breaker ring within the existing building if it impacts

building occupancy

• NY City DOB to issue   
 building permit for new

control enclosures

• NY City DOB to issue   
 Construction permit for

Astoria-Rainey Cable

Developer Scope

Developer will be

responsible for the SSTI   
study costs and any upgrade

A-21

SERVICE AGREEMENT NO. 2710

costs resulting from such

studies

Bus flow analysis of 6-breaker   
 ring bus configuration at Astoria   
36 Annex substation

CTO to Review and Developer will be

Approve responsible for the Bus flow

analysis study costs and any upgrade costs resulting from   
 such studies

A-22

SERVICE AGREEMENT NO. 2710

FIGURE A-1 -Astoria Annex 345 kV Substation Expansion

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

A-23

SERVICE AGREEMENT NO. 2710

Figure A-2 - Simplified Diagram

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

A-24

SERVICE AGREEMENT NO. 2710

FIGURE A- 3-DAF One Line Diagram

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

A-25

SERVICE AGREEMENT NO. 2710

FIGURE A- 4 - COMMUNICATION BLOCK DIAGRAM

[CONTAINS CEII - THIS PAGE REMOVED FROM PUBLIC VERSION]

A-26

SERVICE AGREEMENT NO. 2710

APPENDIX B

MILESTONES

1. Selection Option Pursuant to Article 5.1

Pursuant to Article 5.1.3, Developer has elected the Option to Build for the Connecting   
Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities.

As permitted by Section 29.2, with respect to Connecting Transmission Owner’s

recovery of its costs incurred in executing its responsibilities in Article 5.2 of this Agreement, the Parties expressly agree that the terms and conditions of the Appendices of this Agreement shall take precedence over the provisions of this Agreement in case of a discrepancy or conflict between or among the terms and conditions of same.

Pursuant to the requirements in Articles 5.2.13 and 12.1 of this Agreement, the

Connecting Transmission Owner shall invoice Developer on a monthly basis for the actual costs that Connecting Transmission Owner incurred during the preceding month in executing its   
responsibilities under Article 5.2 and further detailed in the Appendices of this Agreement.   
Additionally, the Parties hereby agree that the agreed upon amount in Article 5.2.13 of this   
Agreement is only an estimate, and that the Connecting Transmission Owner shall be owed, and the Developer shall pay, all of the Connecting Transmission Owner’s costs reasonably incurred in executing its responsibilities under Article 5.2 of this Agreement. Developer reserves its right to challenge the reasonableness of Connecting Transmission Owner’s costs by making a   
unilateral filing with FERC pursuant to section 206 of the FPA.

2. Milestones

Task Milestone Date Responsible Party

1 Complete Phase I environmental site Q2, 2024 Developer

assessments (and Phase II, as applicable),

permitting and environmental studies

2 Execute Interconnection Agreement Q2, 2024 NYISO/ Connecting

Transmission

Owner/Developer

3 Commence Engineering Completed Developer

4 Engineering and 30% design Developer

design for CTOAF

and SUFs (30%, Q1, 2024

60%, 90% design

packages) 60% design Q1, 2024 Developer

90% design Q2, 2024 Developer

B-1

SERVICE AGREEMENT NO. 2710

Task Milestone

5 Project Plan

6 Complete NYPA Division 1

Specification including any referenced documents such as:

• EHS Requirements for Construction   
 Specification (EHS-001) for Astoria

Annex substation upgrades

• Environmental Health and Safety   
 Technical Specifications Checklist

for Astoria Annex substation upgrades

• Construction Inspection Monitoring   
 Program (“CIMP”)

• CIMP Workbook

7 Long Lead Item Purchases

8 NPCC presentation on Directory 4

requirements

9 Commence Construction

10 Substation construction complete

11 Testing & Commissioning, Complete

Construction (Substation, ARCable and Q631 tie-in to Astoria Annex)

12 Submit As-Built Drawings (yellow lines)

13 Complete Real estate and pre-transfer

environmental due diligence (Phase I/II ESAs)

14 Transfer care, custody, and control of

CTOAF/SUF to CTO   
15 In Service Date

Date Responsible Party

Q1, 2024 Developer

Q1, 2024 Developer

Q4, 2023 Developer

Q4, 2024 Developer

Q2, 2024 Developer

Q4, 2025 Developer

Q1, 2026 Developer

Q1, 2026 Developer

180 days Developer/Connecting

Prior to Transmission Owner Transfer of

Easement

Q1, 2026 Developer

May 2026 Developer/ Connecting

Transmission Owner

B-2

SERVICE AGREEMENT NO. 2710

Task Milestone Date Responsible Party

16 Initial Synchronization Date May 2026 Developer/ Connecting

Transmission Owner

17 Commercial Operation Date May 2026 Developer/ Connecting

Transmission Owner

NOTE: These are approximate dates that are subject to change once firm dates becomes

available during the detailed engineering phase of the Merchant Transmission Facility project, subject to the requirements in the NYISO Tariffs and ISO Procedures for modifying the   
Commercial Operation Date.

The following notes apply to all work performed as required by this Agreement or by Connecting Transmission Owner:

A. Connecting Transmission Owner work durations do not include holiday work; if a

Connecting Transmission Owner holiday occurs during an event on these Milestones, then effected dates shall be extended day-for-day.

B. All Connecting Transmission Owner outage durations necessary to interconnect

Developer’s project are dependent on favorable weather conditions where the work is being   
performed. Unfavorable weather conditions may extend the length of such outage   
durations.

C. Transmission System emergencies take precedence over all work and could significantly

impact the schedule and durations.

D. Connecting Transmission Owner schedules its resources months in advance, and its ability

to reschedule manpower is limited by resource allocation to other Connecting Transmission   
Owner projects and tasks. If Developer misses a scheduled Milestone that directly affects   
performance of a Connecting Transmission Owner’s Milestone, performance or completion   
of Connecting Transmission Owner’s relevant Milestone may be delayed until the   
Connecting Transmission Owner can reschedule its manpower to work on the assigned   
task.

E. The Closeout/Turnover Package shall consist of the following: As-built drawings,

Punchlist, Record Drawings, all equipment, QA/QC installation, commissioning, Engineer of Record Professional Engineer certification, color markup of design, drawings and   
warranties, and all documentation necessary for demonstrating compliance with applicable NERC Reliability Standards and NPCC directories.

3. Security

Developer accepted its Project Cost Allocation for System Upgrade Facilities identified   
in connection with the Merchant Transmission Facility in the Class Year Study for Class Year

B-3

SERVICE AGREEMENT NO. 2710

2021 and posted Security to Connecting Transmission Owner in the amount of $174,910,000 for the System Upgrade Facilities on Connecting Transmission Owner’s system.

Connecting Transmission Owner and Developer agree that Developer is not required to provide security for CTOAFs.

B-4

SERVICE AGREEMENT NO. 2710

APPENDIX C

INTERCONNECTION DETAILS

1. Description of Facilities including Point of Interconnection

The Merchant Transmission Facility is the U.S. portion of a 1,250 MW HVDC (AC input

- DC conversion - AC output) transmission project that will interconnect Hydro Quebec’s Hertel   
735 kV Substation with the Connecting Transmission Owner’s Astoria Annex Substation. The   
Merchant Transmission Facility will interconnect at the U.S.-Canada border with the   
approximately 33-mile Quebec portion of the transmission project that will be developed by   
Hydro-Québec TransÉnergie. The Merchant Transmission Facility will consist of (i) a +/- 400   
kV DC cable system extending from the international border to Queens, New York and (ii) a   
1250 MW HVDC converter station to be constructed in Astoria, Queens, New York. The   
Merchant Transmission Facility will have a maximum north to south summer and winter transfer   
limit of 1,250 MW. The Merchant Transmission Facility will have only unidirectional flow from   
the control area operated by Hydro-Québec TransÉnergie to the New York Control Area.

The Merchant Transmission Facility includes a 339 mile (‐/+400 kV) symmetric

monopole HVDC underground cable will be constructed and installed from the converter

substation to a 400/345 kV converter station located in Astoria, Queens, New York. The facility   
will use HVDC Voltage Source Converter (“VSC”) technology, and has a reactive capability of

0.95 inductive to 0.95 capacitive at maximum rated power. The converter station in Astoria, New York will convert the 400 kV DC to 345 kV AC. This converter station will connect to Connecting Transmission Owner’s Astoria Annex Substation via a 1600 ft overhead/200 ft underground transmission line.

The Point of Interconnection (“POI”) is located at the Connecting Transmission Owner’s   
existing Astoria Annex Substation between new Breakers 4 and 6 (new Bus Section 6). The   
Point of Change of Ownership (“PCO”) is located at the Gas to Cable Bushing at the west side   
building wall of the Connecting Transmission Owner’s substation structure where the   
transmission line enters the building. The location of the POI and PCO is illustrated in Figure A-  
1.

2. Developer Operating Requirements

(a) Developer shall comply with all provisions of NYISO tariffs and procedures, as amended

from time to time.

(b) The NYISO and Developer will develop an operating agreement concerning the

operation of the Merchant Transmission Facility. The Merchant Transmission Facility shall not enter into service prior to the effective date of the operating agreement. If the NYISO   
determines that any conforming modifications to this Agreement are required in connection with the operating agreement, the NYISO will coordinate with the Connecting Transmission Owner and Developer concerning the review of the modifications and the amendment of this Agreement pursuant to Articles 29.11 and 29.12 of this Agreement.

C-1

SERVICE AGREEMENT NO. 2710

APPENDIX D

SECURITY ARRANGEMENTS DETAILS

Infrastructure security of New York State Transmission System equipment and

operations and control hardware and software is essential to ensure day-to-day New York State Transmission System reliability and operational security. The Commission will expect the   
NYISO, all Transmission Owners, all Developers and all other Market Participants to comply with the recommendations offered by the President’s Critical Infrastructure Protection Board and, eventually, best practice recommendations from the electric reliability authority. All public utilities will be expected to meet basic standards for system infrastructure and operational   
security, including physical, operational, and cyber-security practices.

D-1

SERVICE AGREEMENT NO. 2710

APPENDIX E-1

INITIAL SYCHRONIZATION DATE

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

New York Power Authority

Sr. Vice President Transmission New York Power Authority   
Zeltmann 500MW Power Project 31-03 20th Avenue

Astoria, NY 11105-2014   
Phone: (718) 267-5603

Re: Merchant Transmission Facility

Dear :

On [Date] [Developer] initially synchronized the Merchant Transmission Facility. This letter confirms [Developer]’s Initial Synchronization Date was [specify].

Thank you.

[Signature]

[Developer Representative]

E-2

SERVICE AGREEMENT NO. 2710

APPENDIX E-2

COMMERCIAL OPERATION DATE

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

New York Power Authority

Sr. Vice President Transmission Zeltmann 500MW Power Project 31-03 20th Avenue

Astoria, NY 11105-2014   
Phone: (718) 267-5603

Re: \_\_\_\_\_\_\_\_\_\_\_\_\_ Merchant Transmission Facility

Dear \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_:

On [Date] [Developer] has completed Trial Operation. This letter confirms that [Developer]

commenced Commercial Operation of the Merchant Transmission Facility, effective as of [Date plus one day].

Thank you.

[Signature]

[Developer Representative]

E-2

SERVICE AGREEMENT NO. 2710

APPENDIX F

ADDRESSES FOR DELIVERY OF NOTICES AND BILLINGS

Notices:

NYISO:

Before commercial operation of the Merchant Transmission Facility:

New York Independent System Operator, Inc.

Attn: Vice President, System and Resource Planning

10 Krey Boulevard

Rensselaer, NY 12144   
Phone: (518) 356-6000   
Fax: (518) 356-6118

After commercial operation of the Merchant Transmission Facility:

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144   
Phone: (518) 356-6000   
Fax: (518) 356-6118

Connecting Transmission Owner:   
New York Power Authority   
Sr. Vice President Transmission   
Zeltmann 500MW Power Project   
31-03 20th Avenue

Astoria, NY 11105-2014   
Phone: (718) 267-5603

Developer:

CHPE LLC

Attn: General Counsel

623 Fifth Avenue, 20th Floor   
New York, NY 10022   
Phone: (917) 886-6832

With electronic copy to:

jeremiah.sheehan@transmissiondevelopers.com   
bob.harrison@transmissiondevelopers.com

Billings and Payments:

F-1

SERVICE AGREEMENT NO. 2710

Connecting Transmission Owner:   
New York Power Authority   
Sr. Vice President Transmission   
New York Power Authority   
Zeltmann 500MW Power Project   
31-03 20th Avenue

Astoria, NY 11105-2014   
Phone: (718) 267-5603

Or

Wire payments to:

New York Power Authority Operating Fund c/o

J.P. Morgan Chase N.A.   
ABA No. 021000021   
Account No. 573-804206

Developer:

CHPE LLC

Attn: General Counsel

623 Fifth Avenue, 20th Floor   
New York, NY 10022   
Phone: (917) 886-6832

With electronic copy to:

jeremiah.sheehan@transmissiondevelopers.com   
bob.harrison@transmissiondevelopers.com

Alternative Forms of Delivery of Notices (telephone, facsimile or email):

NYISO:

Before commercial operation of the Merchant Transmission Facility:

New York Independent System Operator, Inc.

Attn: Vice President, System and Resource Planning

10 Krey Boulevard

Rensselaer, NY 12144   
Phone: (518) 356-6000   
Fax: (518) 356-6118

E-mail: interconnectionsupport@nyiso.com

After commercial operation of the Merchant Transmission Facility:

F-2

SERVICE AGREEMENT NO. 2710

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144   
Phone: (518) 356-6000   
Fax: (518) 356-6118

E-mail: interconnectionsupport@nyiso.com

Connecting Transmission Owner:

Saul Rojas

New York Power Authority

Sr. Vice President Transmission New York Power Authority   
Zeltmann 500MW Power Project 31-03 20th Avenue

Astoria, NY 11105-2014   
Phone: (718) 267-5603

Email address: Saul.Rojas@nypa.gov

Developer:

CHPE LLC

Attn: General Counsel

623 Fifth Avenue, 20th Floor   
New York, NY 10022   
Phone: (917) 886-6832

With electronic copy to:

jeremiah.sheehan@transmissiondevelopers.com   
bob.harrison@transmissiondevelopers.com

F-3