SERVICE AGREEMENT NO. 2720

SERVICE AGREEMENT NO. 2720

AMENDED AND RESTATED

STANDARD SMALL GENERATOR

INTERCONNECTION AGREEMENT

AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.,

NIAGARA MOHAWK POWER CORPORATION

D/B/A NATIONAL GRID,

AND

DOLAN SOLAR, LLC

Dated as of December 3, 2024

(Dolan Solar Project)

SERVICE AGREEMENT NO. 2720

TABLE OF CONTENTS

Article 1

1.1

Scope and Limitations of Agreement ...................................................................2

Applicability ........................................................................................................... 2

Purpose.................................................................................................................... 2

Scope of Interconnection Service ........................................................................... 2

Limitations.............................................................................................................. 2

Responsibilities of the Parties................................................................................. 2

Parallel Operation Obligations................................................................................ 4

Metering.................................................................................................................. 4

Reactive Power and Primary Frequency Response ................................................ 4

Capitalized Terms ................................................................................................... 8

1.2

1.3

1.4

1.5

1.6

1.7

1.8

1.9

Article 2

Inspection, Testing, Authorization, and Right of Access ...................................9

Equipment Testing and Inspection.......................................................................... 9

Authorization Required Prior to Parallel Operation ............................................... 9

Right of Access..................................................................................................... 10

2.1

2.2

2.3

Article 3

Effective Date, Term, Termination, and Disconnection...................................11

Effective Date ....................................................................................................... 11

Term of Agreement............................................................................................... 11

Termination........................................................................................................... 11

Temporary Disconnection..................................................................................... 12

3.1

3.2

3.3

3.4

Article 4

Cost Responsibility for Interconnection Facilities and Distribution

Upgrades...............................................................................................................14

Interconnection Facilities...................................................................................... 14

Distribution Upgrades........................................................................................... 14

4.1

4.2

Article 5

Cost Responsibility for System Upgrade Facilities and System

Deliverability Upgrades.......................................................................................15

Applicability ......................................................................................................... 15

System Upgrades .................................................................................................. 15

Special Provisions for Affected Systems.............................................................. 15

5.1

5.2

5.3

Article 6

Billing, Payment, Milestones, and Financial Security ......................................16

Billing and Payment Procedures and Final Accounting ....................................... 16

Milestones............................................................................................................. 16

Financial Security Arrangements.......................................................................... 17

6.1

6.2

6.3

Article 7

Assignment, Liability, Indemnity, Force Majeure, Consequential

Damages, and Default..........................................................................................18

Assignment ........................................................................................................... 18

Limitation of Liability........................................................................................... 18

Indemnity.............................................................................................................. 18

Consequential Damages........................................................................................ 19

Force Majeure....................................................................................................... 20

7.1

7.2

7.3

7.4

7.5

i

SERVICE AGREEMENT NO. 2720

7.6 Breach and Default ............................................................................................... 20

Article 8

Insurance ..............................................................................................................22

Confidentiality......................................................................................................23

Disputes.................................................................................................................25

Taxes......................................................................................................................26

Miscellaneous........................................................................................................27

Article 9

Article 10

Article 11

Article 12

12.1 Governing Law, Regulatory Authority, and Rules ............................................... 27

12.2 Amendment........................................................................................................... 27

12.3 No Third-Party Beneficiaries................................................................................ 27

12.4 Waiver................................................................................................................... 27

12.5 Entire Agreement.................................................................................................. 27

12.6 Multiple Counterparts........................................................................................... 28

12.7 No Partnership ...................................................................................................... 28

12.8 Severability ........................................................................................................... 28

12.9 Security Arrangements.......................................................................................... 28

12.10 Environmental Releases........................................................................................ 28

12.11 Subcontractors....................................................................................................... 28

12.12 Reservation of Rights............................................................................................ 29

Article 13

Notices ...................................................................................................................30

13.1 General.................................................................................................................. 30

13.2 Billing and Payment.............................................................................................. 31

13.3 Alternative Forms of Notice ................................................................................. 31

13.4 Designated Operating Representative................................................................... 32

13.5 Changes to the Notice Information....................................................................... 33

Article 14

Signatures .............................................................................................................34

Attachment 1 Glossary of Terms

Attachment 2 Detailed Scope of Work, Including Description and Costs of the Small Generating

Facility, Interconnection Facilities, and Metering Equipment

Attachment 3 One-line Diagram Depicting the Small Generating Facility, Interconnection

Facilities, Metering Equipment, and Upgrades

Attachment 4 Milestones

Attachment 5 Additional Operating Requirements for the New York State Transmission System,

the Distribution System and Affected Systems Needed to Support the Interconnection

Customer’s Needs

Attachment 6 Connecting Transmission Owner’s Description of its Upgrades and Best Estimate

of Upgrade Costs

Attachment 7 Insurance Coverage

ii

SERVICE AGREEMENT NO. 2720

Attachment 8 Initial Synchronization Date

Attachment 9 Commercial Operation Date

iii

SERVICE AGREEMENT NO. 2720

This Amended and Restated Standard Small Generator Interconnection Agreement

(“Agreement” or “SGIA”) is made and entered into this 3rd day of December, 2024, by and

among the New York Independent System Operator, Inc., a not-for-profit corporation organized

and existing under the laws of the State of New York (“NYISO”) and Niagara Mohawk Power

Corporation d/b/a National Grid, a corporation organized and existing under the laws of the State

of New York (“Connecting Transmission Owner”), and Dolan Solar, LLC, a limited liability

company organized and existing under the laws of the State of Delaware (“Interconnection

Customer”) each hereinafter sometimes referred to individually as “Party” or referred to

collectively as the “Parties.”

In consideration of the mutual covenants set forth herein, the Parties agree as follows:

1

SERVICE AGREEMENT NO. 2720

Article 1 Scope and Limitations of Agreement

1.1 Applicability

This Agreement shall be used for all Interconnection Requests submitted under the Small

Generator Interconnection Procedures (SGIP) except for those submitted under the 10 kW

Inverter Process contained in SGIP Attachment 5.

1.2

Purpose

This Agreement governs the terms and conditions under which the Interconnection

Customer’s Small Generating Facility will interconnect with, and operate in parallel with, the

New York State Transmission System or the Distribution System.

1.3

Scope of Interconnection Service

1.3.1 The NYISO will provide Energy Resource Interconnection Service to

Interconnection Customer at the Point of Interconnection.

1.3.2 This Agreement does not constitute an agreement to purchase or deliver the

Interconnection Customer’s power. The purchase or delivery of power and other

services that the Interconnection Customer may require will be covered under

separate agreements, if any, or applicable provisions of NYISO’s or Connecting

Transmission Owner’s tariffs. The Interconnection Customer will be responsible

for separately making all necessary arrangements (including scheduling) for

delivery of electricity in accordance with the applicable provisions of the ISO

OATT and Connecting Transmission Owner’s tariff. The execution of this

Agreement does not constitute a request for, nor agreement to, provide Energy,

any Ancillary Services or Installed Capacity under the NYISO Services Tariff or

any Connecting Transmission Owner’s tariff. If Interconnection Customer wishes

to supply or purchase Energy, Installed Capacity or Ancillary Services, then

Interconnection Customer will make application to do so in accordance with the

NYISO Services Tariff or Connecting Transmission Owner’s tariff.

1.4

Limitations

Nothing in this Agreement is intended to affect any other agreement by and among the

NYISO, Connecting Transmission Owner and the Interconnection Customer, except as otherwise

expressly provided herein.

1.5

Responsibilities of the Parties

1.5.1 The Parties shall perform all obligations of this Agreement in accordance with all

Applicable Laws and Regulations, Operating Requirements, and Good Utility

Practice.

1.5.2 The Interconnection Customer shall construct, interconnect, operate and maintain

its Small Generating Facility and construct, operate, and maintain its

2

SERVICE AGREEMENT NO. 2720

Interconnection Facilities in accordance with the applicable manufacturer’s

recommended maintenance schedule, and in accordance with this Agreement, and

with Good Utility Practice.

1.5.3 The Connecting Transmission Owner shall construct, operate, and maintain its

Interconnection Facilities and Upgrades covered by this Agreement in accordance

with this Agreement, and with Good Utility Practice. If all the Parties agree, the

Interconnection Customer may construct the Connecting Transmission Owner’s

Interconnection Facilities and Upgrades as specified in Attachment 2.

1.5.4 The Interconnection Customer agrees to construct its facilities or systems in

accordance with applicable specifications that meet or exceed those provided by

the National Electrical Safety Code, the American National Standards Institute,

IEEE, Underwriter’s Laboratory, and Operating Requirements in effect at the time

of construction and other applicable national and state codes and standards. The

Interconnection Customer agrees to design, install, maintain, and operate its Small

Generating Facility so as to reasonably minimize the likelihood of a disturbance

adversely affecting or impairing the system or equipment of the Connecting

Transmission Owner or Affected Systems.

1.5.5 The Connecting Transmission Owner and Interconnection Customer shall operate,

maintain, repair, and inspect, and shall be fully responsible for the facilities that it

now or subsequently may own unless otherwise specified in the Attachments to

this Agreement. Each of those Parties shall be responsible for the safe

installation, maintenance, repair and condition of their respective lines and

appurtenances on their respective sides of the point of change of ownership. The

Connecting Transmission Owner and the Interconnection Customer, as

appropriate, shall provide Interconnection Facilities that adequately protect the

Connecting Transmission Owner’s electric system, personnel, and other persons

from damage and injury. The allocation of responsibility for the design,

installation, operation, maintenance and ownership of Interconnection Facilities

shall be delineated in the Attachments to this Agreement.

1.5.6 The NYISO shall coordinate with all Affected Systems to support the

interconnection. The Connecting Transmission Owner shall cooperate with the

NYISO in these efforts.

1.5.7 The Interconnection Customer shall ensure “frequency ride through” capability

and “voltage ride through” capability of its Small Generating Facility. The

Interconnection Customer shall enable these capabilities such that its Small

Generating Facility shall not disconnect automatically or instantaneously from the

system or equipment of the Connecting Transmission Owner and any Affected

Systems for a defined under-frequency or over-frequency condition, or an under-

voltage or over-voltage condition, as tested pursuant to section 2.1 of this

agreement. The defined conditions shall be in accordance with Good Utility

Practice and consistent with any standards and guidelines that are applied to other

generating facilities in the Balancing Authority Area on a comparable basis. The

3

SERVICE AGREEMENT NO. 2720

Small Generating Facility’s protective equipment settings shall comply with the

Transmission Owner’s automatic load-shed program. The Transmission Owner

shall review the protective equipment settings to confirm compliance with the

automatic load-shed program. The term “ride through” as used herein shall mean

the ability of a Small Generating Facility to stay connected to and synchronized

with the system or equipment of the Transmission Owner and any Affected

Systems during system disturbances within a range of conditions, in accordance

with Good Utility Practice and consistent with any standards and guidelines that

are applied to other generating facilities in the Balancing Authority on a

comparable basis. The term “frequency ride through” as used herein shall mean

the ability of a Small Generating Facility to stay connected to and synchronized

with the system or equipment of the Transmission Owner and any Affected

Systems during system disturbances within a range of under-frequency and over-

frequency conditions, in accordance with Good Utility Practice and consistent

with any standards and guidelines that are applied to other generating facilities in

the Balancing Authority Area on a comparable basis. The term “voltage ride

through” as used herein shall mean the ability of a Small Generating Facility to

stay connected to and synchronized with the system or equipment of the

Transmission Owner and any Affected Systems during system disturbances

within a range of under-voltage and over-voltage conditions, in accordance with

Good Utility Practice and consistent with any standards and guidelines that are

applied to other generating facilities in the Balancing Authority Area on a

comparable basis.

1.6

Parallel Operation Obligations

Once the Small Generating Facility has been authorized to commence parallel operation,

the Interconnection Customer shall abide by all rules and procedures pertaining to the parallel

operation of the Small Generating Facility in the applicable control area, including, but not

limited to: (1) the rules and procedures concerning the operation of generation set forth in the

NYISO tariffs or ISO Procedures or the Connecting Transmission Owner’s tariff; (2) any

requirements consistent with Good Utility Practice or that are necessary to ensure the safe and

reliable operation of the Transmission System or Distribution System; and (3) the Operating

Requirements set forth in Attachment 5 of this Agreement.

1.7

Metering

The Interconnection Customer shall be responsible for the Connecting Transmission

Owner’s reasonable and necessary cost for the purchase, installation, operation, maintenance,

testing, repair, and replacement of metering and data acquisition equipment specified in

Attachments 2 and 3 of this Agreement. The Interconnection Customer’s metering (and data

acquisition, as required) equipment shall conform to applicable industry rules and Operating

Requirements.

1.8

Reactive Power and Primary Frequency Response

1.8.1 Power Factor Design Criteria

4

SERVICE AGREEMENT NO. 2720

1.8.1.1 Synchronous Generation. The Interconnection Customer shall design its

Small Generating Facility to maintain a composite power delivery at continuous

rated power output at the Point of Interconnection at a power factor within the

range of 0.95 leading to 0.95 lagging, unless the NYISO or the Transmission

Owner in whose Transmission District the Small Generating Facility

interconnects has established different requirements that apply to all similarly

situated generators in the New York Control Area or Transmission District (as

applicable) on a comparable basis, in accordance with Good Utility Practice.

1.8.1.2 Non-Synchronous Generation. The Interconnection Customer shall

design its Small Generating Facility to maintain a composite power delivery at

continuous rated power output at the high-side of the generator substation at a

power factor within the range of 0.95 leading to 0.95 lagging, unless the NYISO

or the Transmission Owner in whose Transmission District the Small Generating

Facility interconnects has established a different power factor range that applies to

all similarly situated non-synchronous generators in the control area or

Transmission District (as applicable) on a comparable basis, in accordance with

Good Utility Practice. This power factor range standard shall be dynamic and can

be met using, for example, power electronics designed to supply this level of

reactive capability (taking into account any limitations due to voltage level, real

power output, etc.) or fixed and switched capacitors, or a combination of the two.

This requirement shall only apply to newly interconnecting non-synchronous

generators that have not yet executed a Facilities Study Agreement as of

September 21, 2016.

1.8.2 The NYISO is required to pay the Interconnection Customer for reactive power,

or voltage support service, that the Interconnection Customer provides from the

Small Generating Facility in accordance with Rate Schedule 2 of the NYISO

Services Tariff.

1.8.3 Primary Frequency Response. Interconnection Customer shall ensure the primary

frequency response capability of its Small Generating Facility by installing,

maintaining, and operating a functioning governor or equivalent controls. The

term “functioning governor or equivalent controls” as used herein shall mean the

required hardware and/or software that provides frequency responsive real power

control with the ability to sense changes in system frequency and autonomously

adjust the Small Generating Facility’s real power output in accordance with the

droop and deadband parameters and in the direction needed to correct frequency

deviations. Interconnection Customer is required to install a governor or

equivalent controls with the capability of operating: (1) with a maximum 5

percent droop and ±0.036 Hz deadband; or (2) in accordance with the relevant

droop, deadband, and timely and sustained response settings from an approved

Applicable Reliability Standard providing for equivalent or more stringent

parameters. The droop characteristic shall be: (1) based on the nameplate

capacity of the Small Generating Facility, and shall be linear in the range of

frequencies between 59 to 61 Hz that are outside of the deadband parameter; or

(2) based on an approved Applicable Reliability Standard providing for an

5

SERVICE AGREEMENT NO. 2720

equivalent or more stringent parameter. The deadband parameter shall be: the

range of frequencies above and below nominal (60 Hz) in which the governor or

equivalent controls is not expected to adjust the Small Generating Facility’s real

power output in response to frequency deviations. The deadband shall be

implemented: (1) without a step to the droop curve, that is, once the frequency

deviation exceeds the deadband parameter, the expected change in the Small

Generating Facility’s real power output in response to frequency deviations shall

start from zero and then increase (for under-frequency deviations) or decrease (for

over-frequency deviations) linearly in proportion to the magnitude of the

frequency deviation; or (2) in accordance with an approved Applicable Reliability

Standard providing for an equivalent or more stringent parameter.

Interconnection Customer shall notify NYISO that the primary frequency

response capability of the Small Generating Facility has been tested and

confirmed during commissioning. Once Interconnection Customer has

synchronized the Small Generating Facility with the New York State

Transmission System, Interconnection Customer shall operate the Small

Generating Facility consistent with the provisions specified in Articles 1.8.3.1 and

1.8.3.2 of this Agreement. The primary frequency response requirements

contained herein shall apply to both synchronous and non-synchronous Small

Generating Facilities.

1.8.3.1 Governor or Equivalent Controls. Whenever the Small Generating Facility

is operated in parallel with the New York State Transmission System,

Interconnection Customer shall operate the Small Generating Facility with its

governor or equivalent controls in service and responsive to frequency.

Interconnection Customer shall: (1) in coordination with NYISO, set the

deadband parameter to: (1) a maximum of ±0.036 Hz and set the droop parameter

to a maximum of 5 percent; or (2) implement the relevant droop and deadband

settings from an approved Applicable Reliability Standard that provides for

equivalent or more stringent parameters. Interconnection Customer shall be

required to provide the status and settings of the governor and equivalent controls

to NYISO and/or the Connecting Transmission Owner upon request. If

Interconnection Customer needs to operate the Small Generating Facility with its

governor or equivalent controls not in service, Interconnection Customer shall

immediately notify NYISO and the Connecting Transmission Owner, and provide

both with the following information: (1) the operating status of the governor or

equivalent controls (i.e., whether it is currently out of service or when it will be

taken out of service); (2) the reasons for removing the governor or equivalent

controls from service; and (3) a reasonable estimate of when the governor or

equivalent controls will be returned to service. Interconnection Customer shall

make Reasonable Efforts to return its governor or equivalent controls into service

as soon as practicable. Interconnection Customer shall make Reasonable Efforts

to keep outages of the Small Generating Facility’s governor or equivalent controls

to a minimum whenever the Small Generating Facility is operated in parallel with

the New York State Transmission System.

6

SERVICE AGREEMENT NO. 2720

1.8.3.2 Timely and Sustained Response. Interconnection Customer shall ensure

that the Small Generating Facility’s real power response to sustained frequency

deviations outside of the deadband setting is automatically provided and shall

begin immediately after frequency deviates outside of the deadband, and to the

extent the Small Generating Facility has operating capability in the direction

needed to correct the frequency deviation. Interconnection Customer shall not

block or otherwise inhibit the ability of the governor or equivalent controls to

respond and shall ensure that the response is not inhibited, except under certain

operational constraints including, but not limited to, ambient temperature

limitations, physical energy limitations, outages of mechanical equipment, or

regulatory requirements. The Small Generating Facility shall sustain the real

power response at least until system frequency returns to a value within the

deadband setting of the governor or equivalent controls. An Applicable

Reliability Standard with equivalent or more stringent requirements shall

supersede the above requirements.

1.8.3.3 Exemptions. Small Generating Facilities that are regulated by the United

States Nuclear Regulatory Commission shall be exempt from Articles 1.8.3,

1.8.3.1, and 1.8.3.2 of this Agreement. Small Generating Facilities that are

behind the meter generation that is sized-to-load (i.e., the thermal load and the

generation are near-balanced in real-time operation and the generation is primarily

controlled to maintain the unique thermal, chemical, or mechanical output

necessary for the operating requirements of its host facility) shall be required to

install primary frequency response capability requirements in accordance with the

droop and deadband capability requirements specified in Article 1.8.3, but shall

be otherwise exempt from the operating requirements in Articles 1.8.3, 1.8.3.1,

1.8.3.2, and 1.8.3.4 of this Agreement.

1.8.3.4 Electric Storage Resources. Interconnection Customer interconnecting an

electric storage resource shall establish an operating range in Attachment 5 of its

SGIA that specifies a minimum state of charge and a maximum state of charge

between which the electric storage resource will be required to provide primary

frequency response consistent with the conditions set forth in Articles 1.8.3,

1.8.3.1, 1.8.3.2, and 1.8.3.3 of this Agreement. Attachment 5 shall specify

whether the operating range is static or dynamic, and shall consider (1) the

expected magnitude of frequency deviations in the interconnection; (2) the

expected duration that system frequency will remain outside of the deadband

parameter in the interconnection; (3) the expected incidence of frequency

deviations outside of the deadband parameter in the interconnection; (4) the

physical capabilities of the electric storage resource; (5) operational limitations of

the electric storage resources due to manufacturer specification; and (6) any other

relevant factors agreed to by the NYISO, Connecting Transmission Owner, and

Interconnection Customer. If the operating range is dynamic, then Attachment 5

must establish how frequently the operating range will be reevaluated and the

factors that may be considered during its reevaluation.

7

SERVICE AGREEMENT NO. 2720

Interconnection Customer’s electric storage resource is required to provide timely

and sustained primary frequency response consistent with Article 1.8.3.2 of this

Agreement when it is online and dispatched to inject electricity to the New York

State Transmission System and/or receive electricity from the New York State

Transmission System. This excludes circumstances when the electric storage

resource is not dispatched to inject electricity to the New York State Transmission

System and/or dispatched to receive electricity from the New York State

Transmission System. If Interconnection Customer’s electric storage resource is

charging at the time of a frequency deviation outside of its deadband parameter, it

is to increase (for over-frequency deviations) or decrease (for under-frequency

deviations) the rate at which it is charging in accordance with its droop parameter.

Interconnection Customer’s electric storage resource is not required to change

from charging to discharging, or vice versa, unless the response necessitated by

the droop and deadband settings requires it to do so and it is technically capable

of making such a transition.

1.9

Capitalized Terms

Capitalized terms used herein shall have the meanings specified in the Glossary of Terms

in Attachment 1 or the body of this Agreement. Capitalized terms used herein that are not so

defined shall have the meanings specified in Appendix 1 of Attachment Z, Section 25.1.2 of

Attachment S, or Section 30.1 of Attachment X of the ISO OATT.

8

SERVICE AGREEMENT NO. 2720

Article 2 Inspection, Testing, Authorization, and Right of Access

2.1 Equipment Testing and Inspection

2.1.1 The Interconnection Customer shall test and inspect its Small Generating Facility

and Interconnection Facilities prior to interconnection. The Interconnection

Customer shall notify the NYISO and the Connecting Transmission Owner of

such activities no fewer than five Business Days (or as may be agreed to by the

Parties) prior to such testing and inspection. Testing and inspection shall occur on

a Business Day. The Connecting Transmission Owner may, at its own expense,

send qualified personnel to the Small Generating Facility site to inspect the

interconnection and observe the testing. The Interconnection Customer shall

provide the NYISO and Connecting Transmission Owner a written test report

when such testing and inspection is completed. The Small Generating Facility

may not commence parallel operations if the NYISO, in consultation with the

Connecting Transmission Owner, finds that the Small Generating Facility has not

been installed as agreed upon or may not be operated in a safe and reliable

manner.

2.1.2 The NYISO and Connecting Transmission Owner shall each provide the

Interconnection Customer written acknowledgment that it has received the

Interconnection Customer’s written test report. Such written acknowledgment

shall not be deemed to be or construed as any representation, assurance,

guarantee, or warranty by the NYISO or Connecting Transmission Owner of the

safety, durability, suitability, or reliability of the Small Generating Facility or any

associated control, protective, and safety devices owned or controlled by the

Interconnection Customer or the quality of power produced by the Small

Generating Facility.

2.2

Authorization Required Prior to Parallel Operation

2.2.1 The NYISO, in consultation with the Connecting Transmission Owner, shall use

Reasonable Efforts to list applicable parallel Operating Requirements in

Attachment 5 of this Agreement. Additionally, the NYISO, in consultation with

the Connecting Transmission Owner, shall notify the Interconnection Customer of

any changes to these requirements as soon as they are known. The NYISO and

Connecting Transmission Owner shall make Reasonable Efforts to cooperate with

the Interconnection Customer in meeting requirements necessary for the

Interconnection Customer to commence parallel operations by the in-service date.

2.2.2 The Interconnection Customer shall not operate its Small Generating Facility in

parallel with the New York State Transmission System or the Distribution System

without prior written authorization of the NYISO. The NYISO, in consultation

with the Connecting Transmission Owner, will provide such authorization once

the NYISO receives notification that the Interconnection Customer has complied

with all applicable parallel Operating Requirements. Such authorization shall not

be unreasonably withheld, conditioned, or delayed.

9

SERVICE AGREEMENT NO. 2720

2.3

Right of Access

2.3.1 Upon reasonable notice, the NYISO and/or Connecting Transmission Owner may

send a qualified person to the premises of the Interconnection Customer at or

immediately before the time the Small Generating Facility first produces energy

to inspect the interconnection, and observe the commissioning of the Small

Generating Facility (including any required testing), startup, and operation for a

period of up to three Business Days after initial start-up of the unit. In addition,

the Interconnection Customer shall notify the NYISO and Connecting

Transmission Owner at least five Business Days prior to conducting any on-site

verification testing of the Small Generating Facility.

2.3.2 Following the initial inspection process described above, at reasonable hours, and

upon reasonable notice, or at any time without notice in the event of an

emergency or hazardous condition, the NYISO and Connecting Transmission

Owner each shall have access to the Interconnection Customer’s premises for any

reasonable purpose in connection with the performance of the obligations

imposed on them by this Agreement or if necessary to meet their legal obligation

to provide service to their customers.

2.3.3 Each Party shall be responsible for its own costs associated with following this

article.

10

SERVICE AGREEMENT NO. 2720

Article 3 Effective Date, Term, Termination, and Disconnection

3.1 Effective Date

This Agreement shall become effective upon execution by the Parties subject to

acceptance by FERC (if applicable), or if filed unexecuted, upon the date specified by the FERC.

The NYISO and Connecting Transmission Owner shall promptly file, or cause to be filed, this

Agreement with FERC upon execution, if required. If the Agreement is disputed and the

Interconnection Customer requests that it be filed with FERC in an unexecuted form, the NYISO

shall file, or cause to be filed, this Agreement and the NYISO shall identify the disputed

language.

3.2

Term of Agreement

This Agreement shall become effective on the Effective Date and shall remain in effect

for a period of twenty (20) years from the Effective Date and shall be automatically renewed for

each successive one-year period thereafter, unless terminated earlier in accordance with article

3.3 of this Agreement.

3.3

Termination

No termination shall become effective until the Parties have complied with all Applicable

Laws and Regulations applicable to such termination, including the filing with FERC of a notice

of termination of this Agreement (if required), which notice has been accepted for filing by

FERC.

3.3.1 The Interconnection Customer may terminate this Agreement at any time by

giving the NYISO and Connecting Transmission Owner 20 Business Days written

notice. The NYISO may terminate this Agreement after the Small Generating

Facility is Retired.

3.3.2 Any Party may terminate this Agreement after Default pursuant to article 7.6.

3.3.3 Upon termination of this Agreement, the Small Generating Facility will be

disconnected from the New York State Transmission System or the Distribution

System, as applicable. All costs required to effectuate such disconnection shall be

borne by the terminating Party, unless such termination resulted from the non-

terminating Party’s Default of this SGIA or such non-terminating Party otherwise

is responsible for these costs under this SGIA.

3.3.4 The termination of this Agreement shall not relieve any Party of its liabilities and

obligations, owed or continuing at the time of the termination. The

Interconnection Customer shall pay all amounts in excess of any deposit or other

security without interest within 30 calendar days after receipt of the invoice for

such amounts. If the deposit or other security exceeds the invoice, the Connecting

Transmission Owner shall refund such excess within 30 calendar days of the

invoice without interest. If the Interconnection Customer disputes an amount to

be paid the Interconnection Customer shall pay the disputed amount to the

11

SERVICE AGREEMENT NO. 2720

Connecting Transmission Owner or into an interest bearing escrow account,

pending resolution of the dispute in accordance with Article 10 of this Agreement.

To the extent the dispute is resolved in the Interconnection Customer’s favor, that

portion of the disputed amount will be returned to the Interconnection Customer

with interest at rates applicable to refunds under the Commission’s regulations.

To the extent the dispute is resolved in the Connecting Transmission Owner’s

favor, that portion of any escrowed funds and interest will be released to the

Connecting Transmission Owner.

3.3.5 The limitations of liability, indemnification and confidentiality provisions of this

Agreement shall survive termination or expiration of this Agreement.

3.4

Temporary Disconnection

Temporary disconnection shall continue only for so long as reasonably necessary under

Good Utility Practice.

3.4.1 Emergency Conditions

“Emergency Condition” shall mean a condition or situation: (1) that in the judgment of

the Party making the claim is imminently likely to endanger life or property; or (2) that, in the

case of the NYISO or Connecting Transmission Owner, is imminently likely (as determined in a

non-discriminatory manner) to cause a material adverse effect on the security of, or damage to

the New York State Transmission System or Distribution System, the Connecting Transmission

Owner’s Interconnection Facilities or the electric systems of others to which the New York State

Transmission System or Distribution System is directly connected; or (3) that, in the case of the

Interconnection Customer, is imminently likely (as determined in a non-discriminatory manner)

to cause a material adverse effect on the security of, or damage to, the Small Generating Facility

or the Interconnection Customer’s Interconnection Facilities. Under Emergency Conditions, the

NYISO or Connecting Transmission Owner may immediately suspend interconnection service

and temporarily disconnect the Small Generating Facility. The NYISO or Connecting

Transmission Owner shall notify the Interconnection Customer promptly when it becomes aware

of an Emergency Condition that may reasonably be expected to affect the Interconnection

Customer’s operation of the Small Generating Facility. The Interconnection Customer shall

notify the NYISO and Connecting Transmission Owner promptly when it becomes aware of an

Emergency Condition that may reasonably be expected to affect the New York State

Transmission System or Distribution System or any Affected Systems. To the extent

information is known, the notification shall describe the Emergency Condition, the extent of the

damage or deficiency, the expected effect on the operation of each Party’s facilities and

operations, its anticipated duration, and the necessary corrective action.

3.4.2 Routine Maintenance, Construction, and Repair

The NYISO or Connecting Transmission Owner may interrupt interconnection service or

curtail the output of the Small Generating Facility and temporarily disconnect the Small

Generating Facility from the New York State Transmission System or Distribution System when

necessary for routine maintenance, construction, and repairs on the New York State

12

SERVICE AGREEMENT NO. 2720

Transmission System or Distribution System. The NYISO or the Connecting Transmission

Owner shall provide the Interconnection Customer with five Business Days notice prior to such

interruption. The NYISO and Connecting Transmission Owner shall use Reasonable Efforts to

coordinate such reduction or temporary disconnection with the Interconnection Customer.

3.4.3 Forced Outages

During any forced outage, the NYISO or Connecting Transmission Owner may suspend

interconnection service to the Interconnection Customer to effect immediate repairs on the New

York State Transmission System or the Distribution System. The NYISO shall use Reasonable

Efforts to provide the Interconnection Customer with prior notice. If prior notice is not given,

the NYISO shall, upon request, provide the Interconnection Customer written documentation

after the fact explaining the circumstances of the disconnection.

3.4.4 Adverse Operating Effects

The NYISO or Connecting Transmission Owner shall notify the Interconnection

Customer as soon as practicable if, based on Good Utility Practice, operation of the Small

Generating Facility may cause disruption or deterioration of service to other customers served

from the same electric system, or if operating the Small Generating Facility could cause damage

to the New York State Transmission System, the Distribution System or Affected Systems, or if

disconnection is otherwise required under Applicable Reliability Standards or the ISO OATT.

Supporting documentation used to reach the decision to disconnect shall be provided to the

Interconnection Customer upon request. If, after notice, the Interconnection Customer fails to

remedy the adverse operating effect within a reasonable time, the NYISO or Connecting

Transmission Owner may disconnect the Small Generating Facility. The NYISO or Connecting

Transmission Owner shall provide the Interconnection Customer with five Business Day notice

of such disconnection, unless the provisions of article 3.4.1 apply.

3.4.5 Modification of the Small Generating Facility

The Interconnection Customer must receive written authorization from the NYISO and

Connecting Transmission Owner before making any change to the Small Generating Facility that

may have a material impact on the safety or reliability of the New York State Transmission

System or the Distribution System. Such authorization shall not be unreasonably withheld.

Modifications shall be done in accordance with Good Utility Practice. If the Interconnection

Customer makes such modification without the prior written authorization of the NYISO and

Connecting Transmission Owner, the Connecting Transmission Owner shall have the right to

temporarily disconnect the Small Generating Facility. If disconnected, the Small Generating

Facility will not be reconnected until the unauthorized modifications are authorized or removed.

3.4.6 Reconnection

The Parties shall cooperate with each other to restore the Small Generating Facility,

Interconnection Facilities, and the New York State Transmission System and Distribution

System to their normal operating state as soon as reasonably practicable following a temporary

disconnection.

13

SERVICE AGREEMENT NO. 2720

Article 4 Cost Responsibility for Interconnection Facilities and Distribution Upgrades

4.1 Interconnection Facilities

4.1.1 The Interconnection Customer shall pay for the cost of the Interconnection

Facilities itemized in Attachment 2 of this Agreement. The NYISO, in

consultation with the Connecting Transmission Owner, shall provide a best

estimate cost, including overheads, for the purchase and construction of its

Interconnection Facilities and provide a detailed itemization of such costs. Costs

associated with Interconnection Facilities may be shared with other entities that

may benefit from such facilities by agreement of the Interconnection Customer,

such other entities, the NYISO, and the Connecting Transmission Owner.

4.1.2 The Interconnection Customer shall be responsible for its share of all reasonable

expenses, including overheads, associated with (1) owning, operating,

maintaining, repairing, and replacing its own Interconnection Facilities, and

(2) operating, maintaining, repairing, and replacing the Connecting Transmission

Owner’s Interconnection Facilities, as set forth in Attachment 2 to this

Agreement.

4.2

Distribution Upgrades

The Connecting Transmission Owner shall design, procure, construct, install, and own

the Distribution Upgrades described in Attachment 6 of this Agreement. If the Connecting

Transmission Owner and the Interconnection Customer agree, the Interconnection Customer may

construct Distribution Upgrades. The actual cost of the Distribution Upgrades, including

overheads, shall be directly assigned to the Interconnection Customer. The Interconnection

Customer shall be responsible for its share of all reasonable expenses, including overheads,

associated with owning, operating, maintaining, repairing, and replacing the Distribution

Upgrades, as set forth in Attachment 6 to this Agreement.

14

SERVICE AGREEMENT NO. 2720

Article 5 Cost Responsibility for System Upgrade Facilities and System Deliverability

Upgrades

5.1

Applicability

No portion of this article 5 shall apply unless the interconnection of the Small Generating

Facility requires System Upgrade Facilities or System Deliverability Upgrades.

5.2

System Upgrades

The Connecting Transmission Owner shall procure, construct, install, and own the

System Upgrade Facilities and System Deliverability Upgrades described in Attachment 6 of this

Agreement. To the extent that design work is necessary in addition to that already accomplished

in the Class Year Interconnection Facilities Study for the Interconnection Customer, the

Connecting Transmission Owner shall perform or cause to be performed such work. If all the

Parties agree, the Interconnection Customer may construct System Upgrade Facilities and

System Deliverability Upgrades.

5.2.1 As described in Section 32.3.5.3 of the SGIP in Attachment Z of the ISO OATT,

the responsibility of the Interconnection Customer for the cost of the System

Upgrade Facilities and System Deliverability Upgrades described in Attachment 6

of this Agreement shall be determined in accordance with Attachment S of the

ISO OATT, as required by Section 32.3.5.3.2 of Attachment Z. The

Interconnection Customer shall be responsible for all System Upgrade Facility

costs as required by Section 32.3.5.3.2 of Attachment Z or its share of any System

Upgrade Facilities and System Deliverability Upgrades costs resulting from the

final Attachment S process, as applicable, and Attachment 6 to this Agreement

shall be revised accordingly.

5.2.2 Pending the outcome of the Attachment S cost allocation process, if applicable,

the Interconnection Customer may elect to proceed with the interconnection of its

Small Generating Facility in accordance with Section 32.3.5.3 of the SGIP.

5.3

Special Provisions for Affected Systems

For the repayment of amounts advanced to the Affected System Operator for System

Upgrade Facilities or System Deliverability Upgrades, the Interconnection Customer and

Affected System Operator shall enter into an agreement that provides for such repayment, but

only if responsibility for the cost of such System Upgrade Facilities is not to be allocated in

accordance with Attachment S of the ISO OATT. The agreement shall specify the terms

governing payments to be made by the Interconnection Customer to the Affected System

Operator as well as the repayment by the Affected System Operator.

15

SERVICE AGREEMENT NO. 2720

Article 6 Billing, Payment, Milestones, and Financial Security

6.1 Billing and Payment Procedures and Final Accounting

6.1.1 The Connecting Transmission Owner shall bill the Interconnection Customer for

the design, engineering, construction, and procurement costs of Interconnection

Facilities and Upgrades contemplated by this Agreement on a monthly basis, or as

otherwise agreed by those Parties and as set forth in Section 2 of Attachment 4 of

this Agreement. The Interconnection Customer shall pay all invoice amounts

within 30 calendar days after receipt of the invoice.

6.1.2 Within three months of completing the construction and installation of the

Connecting Transmission Owner’s Interconnection Facilities and/or Upgrades

described in the Attachments to this Agreement, the Connecting Transmission

Owner shall provide the Interconnection Customer with a final accounting report

of any difference between (1) the Interconnection Customer’s cost responsibility

for the actual cost of such facilities or Upgrades, and (2) the Interconnection

Customer’s previous aggregate payments to the Connecting Transmission Owner

for such facilities or Upgrades. If the Interconnection Customer’s cost

responsibility exceeds its previous aggregate payments, the Connecting

Transmission Owner shall invoice the Interconnection Customer for the amount

due and the Interconnection Customer shall make payment to the Connecting

Transmission Owner within 30 calendar days. If the Interconnection Customer’s

previous aggregate payments exceed its cost responsibility under this Agreement,

the Connecting Transmission Owner shall refund to the Interconnection Customer

an amount equal to the difference within 30 calendar days of the final accounting

report.

6.1.3 If the Interconnection Customer disputes an amount to be paid, the

Interconnection Customer shall pay the disputed amount to the Connecting

Transmission Owner or into an interest bearing escrow account, pending

resolution of the dispute in accordance with Article 10 of this Agreement. To the

extent the dispute is resolved in the Interconnection Customer’s favor, that portion

of the disputed amount will be credited or returned to the Interconnection

Customer with interest at rates applicable to refunds under the Commission’s

regulations. To the extent the dispute is resolved in the Connecting Transmission

Owner’s favor, that portion of any escrowed funds and interest will be released to

the Connecting Transmission Owner.

6.2

Milestones

Subject to the provisions of the SGIP, the Parties shall agree on milestones for which

each Party is responsible and list them in Attachment 4 of this Agreement. A Party’s obligations

under this provision may be extended by agreement. If a Party anticipates that it will be unable

to meet a milestone for any reason other than a Force Majeure event, it shall immediately notify

the other Parties of the reason(s) for not meeting the milestone and: (1) propose the earliest

reasonable alternate date by which it can attain this and future milestones, and (2) requesting

16

SERVICE AGREEMENT NO. 2720

appropriate amendments to Attachment 4. The Party affected by the failure to meet a milestone

shall not unreasonably withhold agreement to such an amendment unless: (1) it will suffer

significant uncompensated economic or operational harm from the delay, (2) attainment of the

same milestone has previously been delayed, or (3) it has reason to believe that the delay in

meeting the milestone is intentional or unwarranted notwithstanding the circumstances explained

by the Party proposing the amendment.

6.3

Financial Security Arrangements

At least 20 Business Days prior to the commencement of the design, procurement,

installation, or construction of a discrete portion of the Connecting Transmission Owner’s

Interconnection Facilities and Upgrades, the Interconnection Customer shall provide the

Connecting Transmission Owner, at the Interconnection Customer’s option, a guarantee, a surety

bond, letter of credit or other form of security that is reasonably acceptable to the Connecting

Transmission Owner and is consistent with the Uniform Commercial Code of the jurisdiction

where the Point of Interconnection is located. Such security for payment shall be in an amount

sufficient to cover the costs for constructing, designing, procuring, and installing the applicable

portion of the Connecting Transmission Owner’s Interconnection Facilities and Upgrades and

shall be reduced on a dollar-for-dollar basis for payments made to the Connecting Transmission

Owner under this Agreement during its term. The Connecting Transmission Owner may draw

on any such security to the extent that the Interconnection Customer fails to make any payments

due under this Agreement. In addition:

6.3.1 The guarantee must be made by an entity that meets the creditworthiness

requirements of the Connecting Transmission Owner, and contain terms and

conditions that guarantee payment of any amount that may be due from the

Interconnection Customer, up to an agreed-to maximum amount.

6.3.2 The letter of credit or surety bond must be issued by a financial institution or

insurer reasonably acceptable to the Connecting Transmission Owner and must

specify a reasonable expiration date.

6.3.3 Notwithstanding the above, Security posted for System Upgrade Facilities for a

Small Generating Facility required to enter the Class Year process, or cash or

Security provided for System Deliverability Upgrades, shall meet the

requirements for Security contained in Attachment S to the ISO OATT.

17

SERVICE AGREEMENT NO. 2720

Article 7 Assignment, Liability, Indemnity, Force Majeure, Consequential Damages,

and Default

7.1

Assignment

This Agreement, and each and every term and condition hereof, shall be binding upon

and inure to the benefit of the Parties hereto and their respective successors and assigns. This

Agreement may be assigned by any Party upon 15 Business Days prior written notice and

opportunity to object by the other Parties; provided that:

7.1.1 A Party may assign this Agreement without the consent of the other Parties to any

affiliate of the assigning Party with an equal or greater credit rating and with the

legal authority and operational ability to satisfy the obligations of the assigning

Party under this Agreement, provided that the Interconnection Customer promptly

notifies the NYISO and the Connecting Transmission Owner of any such

assignment. A Party may assign this Agreement without the consent of the other

Parties in connection with the sale, merger, restructuring, or transfer of a

substantial portion of all of its assets, including the Interconnection Facilities it

owns, so long as the assignee in such a transaction directly assumes all rights,

duties and obligation arising under this Agreement.

7.1.2 The Interconnection Customer shall have the right to assign this Agreement,

without the consent of the NYISO or Connecting Transmission Owner, for

collateral security purposes to aid in providing financing for the Small Generating

Facility.

7.1.3 Any attempted assignment that violates this article is void and ineffective.

Assignment shall not relieve a Party of its obligations, nor shall a Party’s

obligations be enlarged, in whole or in part, by reason thereof. An assignee is

responsible for meeting the same financial, credit, and insurance obligations as

the Interconnection Customer. Where required, consent to assignment will not be

unreasonably withheld, conditioned or delayed.

7.2

Limitation of Liability

Each Party’s liability to the other Parties for any loss, cost, claim, injury, liability, or

expense, including reasonable attorney’s fees, relating to or arising from any act or omission in

its performance of this Agreement, shall be limited to the amount of direct damage actually

incurred. In no event shall any Party be liable to the other Parties for any indirect, special,

consequential, or punitive damages.

7.3

Indemnity

7.3.1 This provision protects each Party from liability incurred to third parties as a

result of carrying out the provisions of this Agreement. Liability under this

provision is exempt from the general limitations on liability found in article 7.2.

18

SERVICE AGREEMENT NO. 2720

7.3.2 Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and

hold harmless the other Parties (each an “ Indemnified Party”) from, any and all

damages, losses, claims, including claims and actions relating to injury to or death

of any person or damage to property, the alleged violation of any Environmental

Law, or the release or threatened release of any Hazardous Substance, demand,

suits, recoveries, costs and expenses, court costs, attorney fees, and all other

obligations by or to third parties (any and all of these a “Loss”), arising out of or

resulting from: (i) the Indemnified Party’s performance under this Agreement on

behalf of the Indemnifying Party, except in cases where the Indemnifying Party

can demonstrate that the Loss of the Indemnified Party was caused by the gross

negligence or intentional wrongdoing by the Indemnified Party, or (ii) the

violation by the Indemnifying Party of any Environmental Law or the release by

the Indemnifying Party of a Hazardous Substance.

7.3.3 If a Party is entitled to indemnification under this article as a result of a claim by a

third party, and the Indemnifying Party fails, after notice and reasonable

opportunity to proceed under this article, to assume the defense of such claim,

such Indemnified Party may at the expense of the Indemnifying Party contest,

settle or consent to the entry of any judgment with respect to, or pay in full, such

claim.

7.3.4 If an Indemnifying Party is obligated to indemnify and hold any Indemnified

Party harmless under this article, the amount owing to the Indemnified Party shall

be the amount of such Indemnified Party’s actual loss, net of any insurance or

other recovery.

7.3.5 Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or

investigation as to which the indemnity provided for in this article may apply, the

Indemnified Party shall notify the Indemnifying Party of such fact. Any failure of

or delay in such notification shall not affect a Party’s indemnification obligation

unless such failure or delay is materially prejudicial to the Indemnifying Party.

7.4

Consequential Damages

Other than as expressly provided for in this Agreement, no Party shall be liable under any

provision of this Agreement for any losses, damages, costs or expenses for any special, indirect,

incidental, consequential, or punitive damages, including but not limited to loss of profit or

revenue, loss of the use of equipment, cost of capital, cost of temporary equipment or services,

whether based in whole or in part in contract, in tort, including negligence, strict liability, or any

other theory of liability; provided, however, that damages for which a Party may be liable to

another Party under another agreement will not be considered to be special, indirect, incidental,

or consequential damages hereunder.

19

SERVICE AGREEMENT NO. 2720

7.5

Force Majeure

7.5.1 As used in this article, a “Force Majeure Event” shall mean “any act of God, labor

disturbance, act of the public enemy, war, insurrection, riot, fire, storm or flood,

explosion, breakage or accident to machinery or equipment, any order, regulation

or restriction imposed by governmental, military or lawfully established civilian

authorities, or any other cause beyond a Party’s control. A Force Majeure Event

does not include an act of negligence or intentional wrongdoing.” For the

purposes of this article, this definition of Force Majeure shall supersede the

definitions of Force Majeure set out in Section 32.10.1 of the ISO OATT.

7.5.2 If a Force Majeure Event prevents a Party from fulfilling any obligations under

this Agreement, the Party affected by the Force Majeure Event (“Affected Party”)

shall promptly notify the other Parties, either in writing or via the telephone, of

the existence of the Force Majeure Event. The notification must specify in

reasonable detail the circumstances of the Force Majeure Event, its expected

duration, and the steps that the Affected Party is taking to mitigate the effects of

the event on its performance. The Affected Party shall keep the other Parties

informed on a continuing basis of developments relating to the Force Majeure

Event until the event ends. The Affected Party will be entitled to suspend or

modify its performance of obligations under this Agreement (other than the

obligation to make payments) only to the extent that the effect of the Force

Majeure Event cannot be mitigated by the use of Reasonable Efforts. The

Affected Party will use Reasonable Efforts to resume its performance as soon as

possible.

7.6

Breach and Default

7.6.1 No Breach of this Agreement shall exist where such failure to discharge an

obligation (other than the payment of money) is the result of a Force Majeure

Event or the result of an act or omission of the other Parties. Upon a Breach, the

non-breaching Party shall give written notice of such Breach to the Breaching

Party. Except as provided in article 7.6.2, the Breaching Party shall have 60

calendar days from receipt of the Breach notice within which to cure such Breach;

provided however, if such Breach is not capable of cure within 60 calendar days,

the Breaching Party shall commence such cure within 20 calendar days after

notice and continuously and diligently complete such cure within six months from

receipt of the Breach notice; and, if cured within such time, the Breach specified

in such notice shall cease to exist.

7.6.2 If a Breach is not cured as provided in this article, or if a Breach is not capable of

being cured within the period provided for herein, a Default shall exist and the

non-defaulting Parties acting together shall thereafter have the right to terminate

this Agreement, in accordance with article 3.3 hereof, by written notice to the

defaulting Party at any time until cure occurs, and be relieved of any further

obligation hereunder and, whether or not those Parties terminate this Agreement,

to recover from the defaulting Party all amounts due hereunder, plus all other

20

SERVICE AGREEMENT NO. 2720

damages and remedies to which they are entitled at law or in equity. The

provisions of this article shall survive termination of this Agreement.

7.6.3 In cases where the Interconnection Customer has elected to proceed under

Section 32.3.5.3 of the SGIP, if the Interconnection Request is withdrawn or

deemed withdrawn pursuant to the SGIP during the term of this Agreement, this

Agreement shall terminate.

21

SERVICE AGREEMENT NO. 2720

Article 8 Insurance

8.1

The Interconnection Customer shall, at its own expense, maintain in force general

liability insurance without any exclusion for liabilities related to the interconnection

undertaken pursuant to this Agreement. The amount of such insurance shall be sufficient

to insure against all reasonably foreseeable direct liabilities given the size and nature of

the generating equipment being interconnected, the interconnection itself, and the

characteristics of the system to which the interconnection is made. Such insurance

coverage is specified in Attachment 7 to this Agreement. The Interconnection Customer

shall obtain additional insurance only if necessary as a function of owning and operating

a generating facility. Such insurance shall be obtained from an insurance provider

authorized to do business in New York State where the interconnection is located.

Certification that such insurance is in effect shall be provided upon request of the

Connecting Transmission Owner, except that the Interconnection Customer shall show

proof of insurance to the Connecting Transmission Owner no later than ten Business

Days prior to the anticipated commercial operation date. An Interconnection Customer

of sufficient creditworthiness may propose to self-insure for such liabilities, and such a

proposal shall not be unreasonably rejected.

8.2

8.3

The NYISO and Connecting Transmission Owner agree to maintain general liability

insurance or self-insurance consistent with the existing commercial practice. Such

insurance or self-insurance shall not exclude the liabilities undertaken pursuant to this

Agreement.

The Parties further agree to notify one another whenever an accident or incident occurs

resulting in any injuries or damages that are included within the scope of coverage of

such insurance, whether or not such coverage is sought.

22

SERVICE AGREEMENT NO. 2720

Article 9 Confidentiality

9.1

Confidential Information shall mean any confidential and/or proprietary information

provided by one Party to the other Party that is clearly marked or otherwise designated

“Confidential.” For purposes of this Agreement all design, operating specifications, and

metering data provided by the Interconnection Customer shall be deemed Confidential

Information regardless of whether it is clearly marked or otherwise designated as such.

Confidential Information shall include, without limitation, information designated as

such by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

9.2

Confidential Information does not include information previously in the public domain,

required to be publicly submitted or divulged by Governmental Authorities (after notice

to the other Party and after exhausting any opportunity to oppose such publication or

release), or necessary to be divulged in an action to enforce this Agreement. Each Party

receiving Confidential Information shall hold such information in confidence and shall

not disclose it to any third party nor to the public without the prior written authorization

from the Party providing that information, except to fulfill obligations under this

Agreement, or to fulfill legal or regulatory requirements.

9.2.1 Each Party shall employ at least the same standard of care to protect Confidential

Information obtained from the other Parties as it employs to protect its own

Confidential Information.

9.2.2 Each Party is entitled to equitable relief, by injunction or otherwise, to enforce its

rights under this provision to prevent the release of Confidential Information

without bond or proof of damages, and may seek other remedies available at law

or in equity for breach of this provision.

9.3

Notwithstanding anything in this article to the contrary, and pursuant to 18 CFR §

lb.20, if FERC, during the course of an investigation or otherwise, requests

information from one of the Parties that is otherwise required to be maintained in

confidence pursuant to this Agreement, the Party shall provide the requested

information to FERC, within the time provided for in the request for information.

In providing the information to FERC, the Party may, consistent with 18 CFR §

388.112, request that the information be treated as confidential and non-public by

FERC and that the information be withheld from public disclosure. Each Party is

prohibited from notifying the other Parties to this Agreement prior to the release

of the Confidential Information to FERC. The Party shall notify the other Parties

to this Agreement when it is notified by FERC that a request to release

Confidential Information has been received by FERC, at which time either of the

Parties may respond before such information would be made public, pursuant to

18 CFR § 388.112. Requests from a state regulatory body conducting a

confidential investigation shall be treated in a similar manner if consistent with

the applicable state rules and regulations.

9.4

Consistent with the provisions of this article 9, the Parties to this Agreement will

cooperate in good faith to provide each other, Affected Systems, Affected System

23

SERVICE AGREEMENT NO. 2720

Operators, and state and federal regulators the information necessary to carry out

the terms of the SGIP and this Agreement.

24

SERVICE AGREEMENT NO. 2720

Article 10 Disputes

10.1 The NYISO, Connecting Transmission Owner and Interconnection Customer agree to

attempt to resolve all disputes arising out of the interconnection process according to the

provisions of this article.

10.2 In the event of a dispute, the Parties will first attempt to promptly resolve it on an

informal basis. The NYISO will be available to the Interconnection Customer and

Connecting Transmission Owner to help resolve any dispute that arises with respect to

performance under this Agreement. If the Parties cannot promptly resolve the dispute on

an informal basis, then any Party shall provide the other Parties with a written Notice of

Dispute. Such notice shall describe in detail the nature of the dispute.

10.3 If the dispute has not been resolved within two Business Days after receipt of the notice,

any Party may contact FERC’s Dispute Resolution Service (“DRS”) for assistance in

resolving the dispute.

10.4 The DRS will assist the Parties in either resolving their dispute or in selecting an

appropriate dispute resolution venue (e.g., mediation, settlement judge, early neutral

evaluation, or technical expert) to assist the Parties in resolving their dispute. The result

of this dispute resolution process will be binding only if the Parties agree in advance.

DRS can be reached at 1-877-337-2237 or via the internet at

http://www.ferc.gov/legal/adr.asp.

10.5 Each Party agrees to conduct all negotiations in good faith and will be responsible for

one-third of any costs paid to neutral third-parties.

10.6 If any Party elects to seek assistance from the DRS, or if the attempted dispute resolution

fails, then any Party may exercise whatever rights and remedies it may have in equity or

law consistent with the terms of this Agreement.

25

SERVICE AGREEMENT NO. 2720

Article 11 Taxes

11.1 The Parties agree to follow all applicable tax laws and regulations, consistent with FERC

policy and Internal Revenue Service requirements.

11.2 Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.

Nothing in this Agreement is intended to adversely affect the tax status of any Party

including the status of NYISO, or the status of any Connecting Transmission Owner with

respect to the issuance of bonds including, but not limited to, Local Furnishing Bonds.

Notwithstanding any other provisions of this Agreement, LIPA, NYPA and Consolidated

Edison Company of New York, Inc. shall not be required to comply with any provisions

of this Agreement that would result in the loss of tax-exempt status of any of their Tax-

Exempt Bonds or impair their ability to issue future tax-exempt obligations. For

purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long

Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc.,

the interest on which is not included in gross income under the Internal Revenue Code.

11.3 LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA,

from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s

general ratemaking authority.

11.4 Any payments due to the Connecting Transmission Owner under this Agreement shall be

adjusted to include any tax liability incurred by the Connecting Transmission Owner with

respect to the interconnection request which is the subject of this Agreement. Such

adjustments shall be made in accordance with the provisions of Article 5.17 of the LGIA

in Attachment X of the ISO OATT. Except where otherwise noted, all costs, deposits,

financial obligations and the like specified in this Agreement shall be assumed not to

reflect the impact of applicable taxes.

26

SERVICE AGREEMENT NO. 2720

Article 12 Miscellaneous

12.1 Governing Law, Regulatory Authority, and Rules

The validity, interpretation and enforcement of this Agreement and each of its provisions

shall be governed by the laws of the state of New York, without regard to its conflicts of law

principles. This Agreement is subject to all Applicable Laws and Regulations. Each Party

expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, or

regulations of a Governmental Authority.

12.2 Amendment

The Parties may amend this Agreement by a written instrument duly executed by the

Parties, or under article 12.12 of this Agreement.

12.3 No Third-Party Beneficiaries

This Agreement is not intended to and does not create rights, remedies, or benefits of any

character whatsoever in favor of any persons, corporations, associations, or entities other than the

Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their

successors in interest and where permitted, their assigns. Notwithstanding the foregoing, any

subcontractor of the Connecting Transmission Owner or NYISO assisting either of those Parties

with the Interconnection Request covered by this Agreement shall be entitled to the benefits of

indemnification provided for under Article 7.3 of this Agreement and the limitation of liability

provided for in Article 7.2 of this Agreement.

12.4 Waiver

12.4.1 The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver

of any obligation, right, or duty of, or imposed upon, such Party.

12.4.2 Any waiver at any time by a Party of its rights with respect to this Agreement

shall not be deemed a continuing waiver or a waiver with respect to any other

failure to comply with any other obligation, right, duty of this Agreement.

Termination or default of this Agreement for any reason by Interconnection

Customer shall not constitute a waiver of the Interconnection Customer’s legal

rights to obtain an interconnection from the NYISO. Any waiver of this

Agreement shall, if requested, be provided in writing.

12.5 Entire Agreement

This Agreement, including all Attachments, constitutes the entire agreement between the

Parties with reference to the subject matter hereof, and supersedes all prior and contemporaneous

understandings or agreements, oral or written, between the Parties with respect to the subject

matter of this Agreement. There are no other agreements, representations, warranties, or

covenants which constitute any part of the consideration for, or any condition to, any Party’s

compliance with its obligations under this Agreement.

27

SERVICE AGREEMENT NO. 2720

12.6 Multiple Counterparts

This Agreement may be executed in two or more counterparts, each of which is deemed

an original but all constitute one and the same instrument.

12.7 No Partnership

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership between the Parties or to impose any partnership

obligation or partnership liability upon any Party. No Party shall have any right, power or

authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an

agent or representative of, or to otherwise bind, another Party.

12.8 Severability

If any provision or portion of this Agreement shall for any reason be held or adjudged to

be invalid or illegal or unenforceable by any court of competent jurisdiction or other

Governmental Authority, (1) such portion or provision shall be deemed separate and

independent, (2) the Parties shall negotiate in good faith to restore insofar as practicable the

benefits to each Party that were affected by such ruling, and (3) the remainder of this Agreement

shall remain in full force and effect.

12.9 Security Arrangements

Infrastructure security of electric system equipment and operations and control hardware

and software is essential to ensure day-to-day reliability and operational security. FERC expects

the NYISO, the Connecting Transmission Owner, Market Participants, and Interconnection

Customers interconnected to electric systems to comply with the recommendations offered by

the President’s Critical Infrastructure Protection Board and, eventually, best practice

recommendations from the electric reliability authority. All public utilities are expected to meet

basic standards for system infrastructure and operational security, including physical,

operational, and cyber-security practices.

12.10 Environmental Releases

Each Party shall notify the other Parties, first orally and then in writing, of the release of

any hazardous substances, any asbestos or lead abatement activities, or any type of remediation

activities related to the Small Generating Facility or the Interconnection Facilities, each of which

may reasonably be expected to affect the other Parties. The notifying Party shall: (1) provide the

notice as soon as practicable, provided such Party makes a good faith effort to provide the notice

no later than 24 hours after such Party becomes aware of the occurrence, and (2) promptly

furnish to the other Parties copies of any publicly available reports filed with any governmental

authorities addressing such events.

12.11 Subcontractors

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,

28

SERVICE AGREEMENT NO. 2720

however, that each Party shall require its subcontractors to comply with all applicable terms and

conditions of this Agreement in providing such services and each Party shall remain primarily

liable to the other Parties for the performance of such subcontractor.

12.11.1

The creation of any subcontract relationship shall not relieve the hiring

Party of any of its obligations under this Agreement. The hiring Party

shall be fully responsible to the other Parties to the extent provided for in

Articles 7.2 and 7.3 above for the acts or omissions of any subcontractor

the hiring Party hires as if no subcontract had been made; provided,

however, that in no event shall the NYISO or Connecting Transmission

Owner be liable for the actions or inactions of the Interconnection

Customer or its subcontractors with respect to obligations of the

Interconnection Customer under this Agreement. Any applicable

obligation imposed by this Agreement upon the hiring Party shall be

equally binding upon, and shall be construed as having application to, any

subcontractor of such Party.

12.11.2

The obligations under this article will not be limited in any way by any

limitation of subcontractor’s insurance.

12.12 Reservation of Rights

Nothing in this Agreement shall alter the right of the NYISO or Connecting Transmission

Owner to make unilateral filings with FERC to modify this Agreement with respect to any rates,

terms and conditions, charges, classifications of service, rule or regulation under Section 205 or

any other applicable provision of the Federal Power Act and FERC’s rules and regulations

thereunder which rights are expressly reserved herein, and the existing rights of the

Interconnection Customer to make a unilateral filing with FERC to modify this Agreement under

any applicable provision of the Federal Power Act and FERC’s rules and regulations are also

expressly reserved herein; provided that each Party shall have the right to protest any such filing

by another Party and to participate fully in any proceeding before FERC in which such

modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties

or of FERC under Sections 205 or 206 of the Federal Power Act and FERC’s rules and

regulations, except to the extent that the Parties otherwise agree as provided herein.

29

SERVICE AGREEMENT NO. 2720

Article 13 Notices

13.1 General

Unless otherwise provided in this Agreement, any written notice, demand, or request

required or authorized in connection with this Agreement shall be deemed properly given if

delivered in person, delivered by recognized national courier service, or sent by first class mail,

postage prepaid, to the person specified below:

If to the Interconnection Customer:

Dolan Solar, LLC

Attention: Eric Millard, Chief Commercial Officer

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

With Copy to:

Dolan Solar, LLC

Attention: Corporate Counsel

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

If to the Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a National Grid

Attention: Kevin Reardon

Address: 40 Sylvan Road

City: Waltham

State: MA

Zip: 02541-1120

Phone: (781) 907-2411

If to the NYISO:

Before Commercial Operation of the Small Generating Facility

New York Independent System Operator, Inc.

Attention: Vice President, System and Resource Planning

Address: 10 Krey Boulevard

City: Rensselaer

State: NY

Zip: 12144

Phone: (518) 356-6000

After Commercial Operation:

New York Independent System Operator, Inc.

Attention: Vice President, Operations

Address: 10 Krey Boulevard

30

SERVICE AGREEMENT NO. 2720

City: Rensselaer

State: NY

Zip: 12144

Phone: (518) 356-6000

13.2 Billing and Payment

Billings and payments shall be sent to the addresses set out below:

Interconnection Customer:

Dolan Solar, LLC

Attention: Eric Millard, Chief Commercial Officer

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

With Copy to:

Dolan Solar, LLC

Attention: Corporate Counsel

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a National Grid

Attention: Kevin Reardon

Address: 40 Sylvan Road

City: Waltham

State: MA

Zip: 02541-1120

13.3 Alternative Forms of Notice

Any notice or request required or permitted to be given by either Party to the other and

not required by this Agreement to be given in writing may be so given by telephone or e-mail to

the telephone numbers and e-mail addresses set out below:

If to the Interconnection Customer:

Dolan Solar, LLC

Attention: Eric Millard, Chief Commercial Officer

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

E-mail: emillard@csenergy.com

With Copy to:

Dolan Solar, LLC

Attention: Corporate Counsel

Address: 2045 Lincoln Highway

31

SERVICE AGREEMENT NO. 2720

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

E-mail: legal@csenergy.com

If to the Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a National Grid

Attention: Kevin Reardon

Address: 40 Sylvan Road

City: Waltham

Phone: (781) 907-2411

E-mail: Kevin.Reardon@nationalgrid.com

State: MA

Zip: 02541-1120

If to the NYISO:

New York Independent System Operator, Inc.

Attention: Vice President, Operations

Address: 10 Krey Boulevard

City: Rensselaer

Phone: (518) 356-6000

E-mail: interconnectionsupport@nyiso.com

State: NY

Zip: 12144

13.4 Designated Operating Representative

The Parties may also designate operating representatives to conduct the communications

which may be necessary or convenient for the administration of this Agreement. This person

will also serve as the point of contact with respect to operations and maintenance of the Party’s

facilities.

Interconnection Customer’s Operating Representative:

Dolan Solar, LLC

Attention: Eric Millard, Chief Commercial Officer

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

E-mail: emillard@csenergy.com

With Copy to:

Dolan Solar, LLC

Attention: Corporate Counsel

Address: 2045 Lincoln Highway

City: Edison State: NJ Zip: 08817

Phone: 732-860-4660

E-mail: legal@csenergy.com

32

SERVICE AGREEMENT NO. 2720

Connecting Transmission Owner’s Operating Representative:

Niagara Mohawk Power Corporation d/b/a National Grid

Attention: Kevin Reardon

Address: 40 Sylvan Road

City: Waltham

State: MA

Zip: 02541-1120

Phone: (781) 907-2411

E-mail: Kevin.Reardon@nationalgrid.com

NYISO’s Operating Representative:

New York Independent System Operator, Inc.

Attention: Vice President, Operations

Address: 10 Krey Boulevard

City: Rensselaer

Phone: (518) 356-6000

E-mail: interconnectionsupport@nyiso.com

State: NY

Zip: 12144

13.5 Changes to the Notice Information

Either Party may change this information by giving five Business Days written notice

prior to the effective date of the change.

33

SERVICE AGREEMENT NO. 2720

Article 14 Signatures

IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their

respective duly authorized representatives.

For the New York Independent System Operator, Inc.

By:

Name: _________________________

Title:

Date: __________________________

For Niagara Mohawk Power Corporation d/b/a National Grid

By:

Name:

Title: __________________________

Date: __________________________

For Dolan Solar, LLC

By:

Name: __________________________

Title: ___________________________

Date: ___________________________

34

SERVICE AGREEMENT NO. 2720

Attachment 1

Glossary of Terms

Affected System – An electric system other than the transmission system owned, controlled or

operated by the Connecting Transmission Owner that may be affected by the proposed

interconnection.

Affected System Operator – Affected System Operator shall mean the operator of any Affected

System.

Affected Transmission Owner –The New York public utility or authority (or its designated

agent) other than the Connecting Transmission Owner that: (i) owns facilities used for the

transmission of Energy in interstate commerce and provides Transmission Service under the

Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State

Transmission System where System Deliverability Upgrades or System Upgrade Facilities are

installed pursuant to Attachment Z and Attachment S to the ISO OATT.

Applicable Laws and Regulations – All duly promulgated applicable federal, state and local

laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or

administrative orders, permits and other duly authorized actions of any Governmental Authority,

including but not limited to Environmental Law.

Applicable Reliability Standards – The criteria, requirements and guidelines of the North

American Electric Reliability Council, the Northeast Power Coordinating Council, the New York

State Reliability Council and related and successor organizations, or the Transmission District to

which the Interconnection Customer’s Small Generating Facility is directly interconnected, as

those criteria, requirements and guidelines are amended and modified and in effect from time to

time; provided that no Party shall waive its right to challenge the applicability of or validity of

any criterion, requirement or guideline as applied to it in the context of Attachment Z to the ISO

OATT and this Agreement. For the purposes of this Agreement, this definition of Applicable

Reliability Standards shall supersede the definition of Applicable Reliability Standards set out in

Attachment X to the ISO OATT.

Base Case – The base case power flow, short circuit, and stability data bases used for the

Interconnection Studies by NYISO, Connecting Transmission Owner or Interconnection

Customer; described in Section 32.2.3 of the Large Facility Interconnection Procedures.

Breach - The failure of a Party to perform or observe any material term or condition of this

Agreement.

Business Day – Monday through Friday, excluding federal holidays.

Capacity Resource Interconnection Service –The service provided by NYISO to

Interconnection Customers that satisfy the NYISO Deliverability Interconnection Standard or

that are otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT;

1-1

SERVICE AGREEMENT NO. 2720

such service being one of the eligibility requirements for participation as a NYISO Installed

Capacity Supplier.

Commercial Operation shall mean the status of the Small Generating Facility that has

commenced generating electricity for sale, excluding electricity generated during Trial

Operation, notice of which must be provided to the NYISO in the form of Attachment 9 to this

Agreement.

Commercial Operation Date of a unit shall mean the date on which the Large Generating

Facility commences Commercial Operation as agreed to by the Parties, notice of which must be

provided to the NYISO in the form of Attachment 9 to this Agreement.

Connecting Transmission Owner – The New York public utility or authority (or its designated

agent) that: (i) owns facilities used for the transmission of Energy in interstate commerce and

provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an

interest in the portion of the New York State Transmission System or Distribution System at the

Point of Interconnection, and (iii) is a Party to the Standard Small Generator Interconnection

Agreement.

Default – The failure of a Party in Breach of this Agreement to cure such Breach under the

Small Generator Interconnection Agreement.

Distribution System – The Transmission Owner’s facilities and equipment used to distribute

electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s Large Facility

Interconnection Procedures in Attachment X to the ISO OATT or Small Generator

Interconnection Procedures in Attachment Z to the ISO OATT under FERC Order Nos. 2003

and/or 2006. For the purpose of this Agreement, the term Distribution System shall not include

LIPA’s distribution facilities.

Distribution Upgrades – The additions, modifications, and upgrades to the Connecting

Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate

interconnection of the Small Generating Facility and render the transmission service necessary to

effect the Interconnection Customer’s wholesale sale of electricity in interstate commerce.

Distribution Upgrades do not include Interconnection Facilities or System Upgrade Facilities or

System Deliverability Upgrades.

Energy Resource Interconnection Service – The service provided by NYISO to interconnect

the Interconnection Customer’s Small Generating Facility to the New York State Transmission

System or Distribution System in accordance with the NYISO Minimum Interconnection

Standard, to enable the New York State Transmission System to receive Energy and Ancillary

Services from the Small Generating Facility, pursuant to the terms of the ISO OATT.

Force Majeure – Any act of God, labor disturbance, act of the public enemy, war, insurrection,

riot, fire, storm or flood, explosion, breakage or accident to machinery or equipment, any order,

regulation or restriction imposed by governmental, military or lawfully established civilian

authorities, or any other cause beyond a Party’s control. A Force Majeure event does not include

an act of negligence or intentional wrongdoing. For the purposes of this Agreement, this

1-2

SERVICE AGREEMENT NO. 2720

definition of Force Majeure shall supersede the definitions of Force Majeure set out in Section

32.2.11 of the NYISO Open Access Transmission Tariff.

Good Utility Practice – Any of the practices, methods and acts engaged in or approved by a

significant portion of the electric industry during the relevant time period, or any of the practices,

methods and acts which, in the exercise of reasonable judgment in light of the facts known at the

time the decision was made, could have been expected to accomplish the desired result at a

reasonable cost consistent with good business practices, reliability, safety and expedition. Good

Utility Practice is not intended to be limited to the optimum practice, method, or act to the

exclusion of all others, but rather to be acceptable practices, methods, or acts generally accepted

in the region.

Governmental Authority – Any federal, state, local or other governmental regulatory or

administrative agency, court, commission, department, board, or other governmental subdivision,

legislature, rulemaking board, tribunal, or other governmental authority having jurisdiction over

the Parties, their respective facilities, or the respective services they provide, and exercising or

entitled to exercise any administrative, executive, police, or taxing authority or power; provided,

however, that such term does not include the Interconnection Customer, NYISO, Affected

Transmission Owner, Connecting Transmission Owner or any Affiliate thereof.

Initial Synchronization Date shall mean the date upon which the Small Generating Facility is

initially synchronized and upon which Trial Operation begins, notice of which must be provided

to the NYISO in the form of Attachment 9.

In-Service Date shall mean the date upon which the Developer reasonably expects it will be

ready to begin use of the Connecting Transmission Owner’s Interconnection Facilities to obtain

back feed power.

Interconnection Customer – Any entity, including the Transmission Owner or any of the

affiliates or subsidiaries, that proposes to interconnect its Small Generating Facility with the New

York State Transmission System or the Distribution System.

Interconnection Facilities – The Connecting Transmission Owner’s Interconnection Facilities

and the Interconnection Customer’s Interconnection Facilities. Collectively, Interconnection

Facilities include all facilities and equipment between the Small Generating Facility and the

Point of Interconnection, including any modification, additions or upgrades that are necessary to

physically and electrically interconnect the Small Generating Facility to the New York State

Transmission System or the Distribution System. Interconnection Facilities are sole use facilities

and shall not include Distribution Upgrades or System Upgrade Facilities.

Interconnection Request – The Interconnection Customer’s request, in accordance with the

Tariff, to interconnect a new Small Generating Facility, or to materially increase the capacity of,

or make a material modification to the operating characteristics of, an existing Small Generating

Facility that is interconnected with the New York State Transmission System or the Distribution

System. For the purposes of this Agreement, this definition of Interconnection Request shall

supersede the definition of Interconnection Request set out in Attachment X to the ISO OATT.

1-3

SERVICE AGREEMENT NO. 2720

Interconnection Study – Any study required to be performed under Sections 32.2 or 32.3 of the

SGIP.

Material Modification – A modification that has a material impact on the cost or timing of any

Interconnection Request with a later queue priority date.

New York State Transmission System – The entire New York State electric transmission

system, which includes: (i) the Transmission Facilities under ISO Operational Control; (ii) the

Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities

within the New York Control Area.

NYISO Deliverability Interconnection Standard – The standard that must be met, unless

otherwise provided for by Attachment S to the ISO OATT, by (i) any generation facility larger

than 2MW in order for that facility to obtain CRIS; (ii) any Class Year Transmission Project

proposing to interconnect to the New York State Transmission System and receive Unforced

Capacity Delivery Rights; (iii) any entity requesting External CRIS Rights, and (iv) any entity

requesting a CRIS transfer pursuant to Section 25.9.5 of Attachment S to the ISO OATT. To

meet the NYISO Deliverability Interconnection Standard, the Interconnection Customer must, in

accordance with the rules in Attachment S to the ISO OATT, fund or commit to fund any System

Deliverability Upgrades identified for its project in the Class Year Deliverability Study.

NYISO Minimum Interconnection Standard – The reliability standard that must be met by

any generation facility or Class Year Transmission Project that is subject to NYISO’s Large

Facility Interconnection Procedures in Attachment X to the ISO OATT or the NYISO’s Small

Generator Interconnection Procedures in this Attachment Z, that is proposing to connect to the

New York State Transmission System or Distribution System, to obtain ERIS. The Minimum

Interconnection Standard is designed to ensure reliable access by the proposed project to the

New York State Transmission System or to the Distribution System. The Minimum

Interconnection Standard does not impose any deliverability test or deliverability requirement on

the proposed interconnection.

Operating Requirements – Any operating and technical requirements that may be applicable

due to Regional Transmission Organization, Independent System Operator, control area, or the

Connecting Transmission Owner’s requirements, including those set forth in the Small Generator

Interconnection Agreement. Operating Requirements shall include Applicable Reliability

Standards.

Party or Parties – The NYISO, Connecting Transmission Owner, Interconnection Customer or

any combination of the above.

Point of Interconnection – The point where the Interconnection Facilities connect with the New

York State Transmission System or the Distribution System.

Reasonable Efforts – With respect to an action required to be attempted or taken by a Party

under this Agreement, efforts that are timely and consistent with Good Utility Practice and are

otherwise substantially equivalent to those a Party would use to protect its own interests.

1-4

SERVICE AGREEMENT NO. 2720

Small Generating Facility – The Interconnection Customer’s facility, no larger than 20 MW for

the production and/or storage for later injection of electricity identified in the Interconnection

Request if proposing to interconnect to the New York State Transmission System or Distribution

System, but shall not include (i) facilities proposing to simply receive power from the New York

State Transmission System or the Distribution System; (ii) facilities proposing to interconnect to

the New York State Transmission System or the Distribution System made solely for the purpose

of generation with no wholesale sale for resale nor to net metering; (iii) facilities proposing to the

New York State Transmission System or the Distribution System made solely for the purpose of

net metering; (iv) facilities proposing to interconnect to LIPA’s distribution facilities; and (v) the

Interconnection Customer’s Interconnection Facilities. A facility will be treated as a single

Small Generating Facility if all units within the facility are behind a single facility meter, even if

such units are different technology types.

System Deliverability Upgrades – The least costly configuration of commercially available

components of electrical equipment that can be used, consistent with Good Utility Practice and

Applicable Reliability Requirements, to make the modifications or additions to the existing New

York State Transmission System that are required for the proposed project to connect reliably to

the system in a manner that meets the NYISO Deliverability Interconnection Standard for

Capacity Resource Interconnection Service.

System Upgrade Facilities – The least costly configuration of commercially available

components of electrical equipment that can be used, consistent with Good Utility Practice and

Applicable Reliability Requirements to make the modifications to the existing transmission

system that are required to maintain system reliability due to: (i) changes in the system,

including such changes as load growth and changes in load pattern, to be addressed in the form

of generic generation or transmission projects; and (ii) proposed interconnections. In the case of

proposed interconnection projects, System Upgrade Facilities are the modification or additions to

the existing New York State Transmission System that are required for the proposed project to

connect reliably to the system in a manner that meets the NYISO Minimum Interconnection

Standard.

Tariff – The NYISO’s Open Access Transmission Tariff, as filed with the FERC, and as

amended or supplemented from time to time, or any successor tariff.

Trial Operation shall mean the period during which Interconnection Customer is engaged in on-

site test operations and commissioning of the Small Generating Facility prior to Commercial

Operation.

Upgrades – The required additions and modifications to the Connecting Transmission Owner’s

portion of the New York State Transmission System or the Distribution System at or beyond the

Point of Interconnection. Upgrades may be System Upgrade Facilities or System Deliverability

Upgrades Distribution Upgrades. Upgrades do not include Interconnection Facilities.

1-5

SERVICE AGREEMENT NO. 2720

Attachment 2

Detailed Scope of Work, Including Description and Costs of the Small Generating Facility,

Interconnection Facilities, and Metering Equipment

Equipment, including the Small Generating Facility, Interconnection Facilities, and

metering equipment shall be itemized and identified as being owned by the Interconnection

Customer, or the Connecting Transmission Owner. The NYISO, in consultation with the

Connecting Transmission Owner, will provide a best estimate itemized cost, including

overheads, of its Interconnection Facilities and metering equipment, and a best estimate itemized

cost of the annual operation and maintenance expenses associated with its Interconnection

Facilities and metering equipment.

A.

PROJECT DESCRIPTION

The Interconnection Customer is constructing a 20 MW solar generating facility (the

“Small Generating Facility”) in the town of Fort Edward, New York. The Small Generating

Facility will consist of five (5) SMA SC4600-UP 4.6MVA solar inverters, each connected to a

4.6MVA 34.5kV/690V pad mount transformer with integral disconnect and fuses. The five (5)

step-up transformers are daisy chained together using 34.5kV direct buried solid dielectric cable

(“Collection Feeder Line”). The home run of the feeder ties to the Interconnection Customer’s

collector station (“Dolan Solar Collector Station”) where it is stepped up to 115kV via a 25MVA

34.5/115kV transformer.

The Point of Interconnection (“POI”) for the Small Generating Facility is located on

Connecting Transmission Owner’s 115kV Mohican-Battenkill line 15 between existing

structures 64 and 66. The POI will be approximately 7.43 miles from Connecting Transmission

Owner’s Battenkill Substation and approximately 6.74 miles from Connecting Transmission

Owner’s Mohican Substation. The interconnection to the New York State Transmission System

will be via a tap.

The Point of Change of Ownership (“PCO”) shall be at the line side connection of the

Interconnection Customer’s disconnect switch located on the Interconnection Customer’s

termination structure inside the Dolan Solar Collector Station. The Connecting Transmission

Owner shall own the insulators, whips and hardware connections to the Interconnection

Customer’s disconnect switch. The POI and PCO are detailed in Figure 1 in Attachment 3.

B.

INTERCONNECTION CUSTOMER’S INTERCONNECTION FACILITIES

The Interconnection Customer’s Interconnection Facilities (“ICIF”) include all of the

facilities between the Interconnection Customer’s side of the PCO and the Small Generating

Facility, except the Connecting Transmission Owner-owned revenue metering and remote

terminal unit (“RTU”) described in Section C below. The ICIF will be located on property

owned or leased by the Interconnection Customer. As depicted on the one-line diagram in

Attachment 3, the ICIF consist of the following:

2-1

SERVICE AGREEMENT NO. 2720

1.

Dolan Solar Collector Substation

• one (1) three phase, three winding, 115-34.5/12.47kV grounded wye-grounded wye, delta

step-up transformer rated 15/20/25MVA (ONAN/ONAF/ONAF), with impedance of 9%;

• six (6) 96kV, 76kV maximum continuous operating voltage (“MCOV”) station class

surge arresters;

• one (1) 115kV, 1200A, 550kV basic insulation level (“BIL”) group operated air break

switch;

• one (1) 115kV, 2000A, 550kV BIL, 40 kAIC SF-6 circuit breaker w/ 3 sets of current

transformers (“CTs”);

• three (3) 115kV voltage transformers (“VTs”);

• six (6) 24.4kV MCOV station class surge arresters;

• one (1) 38kV, 1200A, 150kV BIL, 25kAIC vacuum circuit breaker;

• one (1) 38kV, 1200A, group operated disconnect switch;

• three (3) 38kV, 1200A hookstick switches;

• three (3) 19.9kV voltage transformers 300:1; and

• one (1) 50kVA 19.9kV – 120/240V station service transformer.

2.

System Protection

a) Line 15

Line 15 shall be protected using a permissive overreaching transfer trip (“POTT”) for the

A package and step distance as the B package. Direct transfer trip (“DTT”) will be used between

the Dolan Solar Collector Station and the line terminals at Connecting Transmission Owner’s

Battenkill and Mohican Substations to ensure removal of the generation. This will require the

installation of two (2) RFL GARD8000 tele-protection sets at the Dolan Solar Collector Station.

The Connecting Transmission Owner will provide details on the GARD 8000 model number

with the Connecting Transmission Owner’s logic during detailed design.

The Interconnection Customer is to provide redundant 115kV line protection to remove

the generation for line faults. Two sets of multi-ratio CT’s shall be provided for these schemes.

b) Transformer

The 115–34.5kV transformer shall be protected by two independent protection systems;

one must be a transformer differential. If overcurrent protection is used for the other system,

then both phase and ground time and instantaneous protection shall be provided. Each of the two

schemes must operate separate lockout relays to trip and block the necessary breakers.

c) Breaker

Breaker failure protection shall be provided for the 115kV breaker. This protection must

trip the appropriate adjacent breakers and send direct transfer trip to the Mohican and Battenkill

Substations. For loss of SF6, the breaker must trip and block close. (Note: When the Small

Generating Facility’s interrupter fails to interrupt for internal station faults and loss of SF

2-2

SERVICE AGREEMENT NO. 2720

condition, the Interconnection Customer is not to rely on the Connecting Transmission Owner’s

115kV system for remote backup.)

DTT receive from the Battenkill and Mohican Substations will be required to trip the

Interconnection Customer’s 115kV breaker for a line relay operation, or breaker failure at the

Battenkill and Mohican Substations. The Interconnection Customer shall provide on/off

switches for the DTT schemes.

3.

Telecommunications Circuit

A new Telco fiber facility will be required at the Dolan Solar Collector Station for

protection systems and data transmittal. The new fiber facility shall provide:

•

•

one (1) DS1 circuit from the Dolan Solar Collector Station to the Battenkill Substation;

one (1) DS1 circuit from the Dolan Solar Collector Station to the Mohican Substation;

and

•

one (1) Verizon Type 2 ethernet MPLS circuit for energy management system-remote

terminal unit (“EMS-RTU”).

The Interconnection Customer is responsible for ordering the fiber facility required at the

Dolan Solar Collector Station and provisioning the T1 MPLS circuit. The Connecting

Transmission Owner will procure the Verizon DS1 circuits from the Dolan Solar Collector

Station to the Battenkill and Mohican Substations.

(Note: Verizon may retire T1 services in the future. If T1 circuits are not available at the

time of project implementation, alternative technologies will be required which could change the

overall cost of the telecom solution.)

To the extent the Small Generating Facility’s feeder lines, communication circuits, access

roads, and/or driveways cross Connecting Transmission Owner-owned transmission or

distribution circuits, such crossings must be reviewed by the Connecting Transmission Owner in

accordance with the Property Transaction Review Requirements described in Appendix F to the

Facilities Study for the Small Generating Facility. Per the Project Specific Specifications (as

defined below), feeder line crossings shall be underground so as to maintain the reliability of

service provided by the Connecting Transmission Owner to other customers via the impacted

transmission and distribution facilities.

C.

CONNECTING TRANSMISSION OWNER’S INTERCONNECTION

FACILITIES

As depicted on the one-line diagram in Attachment 3, the Connecting Transmission

Owner’s Interconnection Facilities (“CTOIF”) consist of the following constructed or installed

between the POI and PCO, as well as the revenue metering and RTU located at the Dolan Solar

Collector Substation.

1.

Revenue Metering

2-3

SERVICE AGREEMENT NO. 2720

The Connecting Transmission Owner owned revenue metering shall be located at the

Dolan Solar Collector Station on the generator side of the 115kV breaker and shall consist of:

• three (3) combination current/voltage transformer (CT/PT) units (manufacturer and

model shall be ABB/Kuhlman KXM-550, GE Grid Solutions KOTEF 123.ER, or

other Connecting Transmission Owner specified equivalent); and

• one (1) revenue meter.

The ratios of the CTs and PTs will be provided upon review of the Interconnection

Customer’s design documents according to Connecting Transmission Owner’s Electric System

Bulletin (“ESB”) 752.

(Note: The Connecting Transmission Owner’s revenue metering CTs and PTs cannot be

used to feed the Interconnection Customer’s check meter.)

The metering of any redundant or standby station service provisions at the Dolan Solar

Collector Station shall be added in accordance with the Connecting Transmission Owner’s retail

tariff, PSC No. 220 and the Connecting Transmission Owner’s ESB 750.

2.

EMS-RTU

The Connecting Transmission Owner will procure and provide the RTU to the

Interconnection Customer for installation on the mounting panel. The RTU cabinet is typically

42" H x 30" W x 12" D shall be wall-mounted with the bottom edge 36" above the floor with a 5-

foot clear working space in front of the mounting panel.

3.

Line 15 Tap

The Dolan Solar Collector Station is to be located approximately 154 feet east of Line 15

and will be oriented perpendicular to the transmission lines. The Small Generating Facility will

interconnect to Line 15 between structure 64 and 66 via a radial tap. Based on the location of the

Dolan Solar Collector Station, the radial tap will require removal of one (1) double circuit double

shieldwire steel suspension structure and installation of:

• one (1) double circuit double shieldwire steel deadend tapping structure on caisson

foundation;

• two (2) vertical switch structures with vertical switches;

• three (3) floating deadend assemblies to connect the new switches;

• approximately 155 circuit feet of 795 ACSR 26/7 “DRAKE”; and

• approximately 155 linear feet of 3/8” EHS steel shieldwire.

The Connection Transmission Owner and the Interconnection Customer agree that the

Connecting Transmission Owner shall endeavor in good faith to use commercially reasonable

efforts to design and site all components of the Line 15 Tap equipment, including vertical switch

structures, as close as reasonably practical to the Dolan Solar Collector Station for the purpose of

2-4

SERVICE AGREEMENT NO. 2720

simplifying any real estate or permitting needs, so long as the design and siting of such

equipment is in accordance with Good Utility Practice.

D.

SCOPE OF WORK AND RESPONSIBILITIES

1. Interconnection Customer’s Scope of Work and Responsibilities

The Interconnection Customer shall design, procure, construct, install, own, operate, and

maintain the Interconnection Customer’s Interconnection Facilities in accordance with the

following requirements, to the extent not inconsistent with the terms of this Agreement, the ISO

OATT, or applicable NYISO procedures: the NYISO’s requirements; industry standards and

specifications; regulatory requirements; the Connecting Transmission Owner’s applicable

Electric System Bulletins (“ESBs”), provided at the following website:

https://www.nationalgridus.com/ProNet/Technical-Resources/Electric-Specifications; the

Connecting Transmission Owner’s System Protection and Interconnection Customer Attachment

Facilities Electric Installation Specification for the Dolan Solar Project (“Project Specific

Specifications”) provided as Appendix C to the Facilities Study for the Small Generating

Facility; and Good Utility Practice. The Interconnection Customer shall submit all engineering

design and electrical specifications associated with Interconnection Customer’s Interconnection

Facilities to the Connecting Transmission Owner for its review and acceptance in accordance

with the ESBs and Project Specific Specifications.

The Interconnection Customer shall install a meter panel in accordance with the Project

Specific Specifications and ESB 756A.

As per ESB 756A and the Project Specific Specifications, the Interconnection Customer

shall mount the RTU cabinet indoors and within 15 feet of the meter(s), and remote from:

• heavy traffic areas, work areas, and loading areas;

• heat producing or high electrostatic or electromagnetic field producing equipment; and

• station batteries.

New right-of-way (“ROW”) will be required for the construction, operation, and

maintenance of the tap line and must accommodate the 125’ x 125’ work pads (temporary)

required for the installation of the new structures. The Interconnection Customer is responsible

for obtaining the property/easements needed for the tap line, access roads to/from the tap, and

work pads, in accordance with the standards set forth in the Standards and Requirements

Relating to Third Party Acquisition and Transfer of Real Property Interests to Niagara Mohawk

Power Corporation for Electric Facilities and Survey Specifications, dated January 2019. The

Interconnection Customer is also responsible for all permitting.

Upon termination of the Agreement, Interconnection Customer shall be responsible for

all costs associated with the decommissioning and removal of Interconnection Facilities.

2.

Connecting Transmission Owner’s Scope of Work and Responsibilities

2-5

SERVICE AGREEMENT NO. 2720

Connecting Transmission Owner shall provide the CT/PT units and the Interconnection

Customer shall mount them, make grounding connections, and complete all primary wiring. In

addition, the Connecting Transmission Owner shall provide the meter socket enclosure for the

Interconnection Customer to install near the Connecting Transmission Owner’s RTU.

The Connecting Transmission Owner shall:

• provide, run, and wire both ends of the color-coded cable for the revenue metering

instrument transformer secondary wiring;

• perform all terminations; and

• supply and install the meter.

The revenue meter may require a communications link to the RTU. The Connecting

Transmission Owner will specify and run those communications cables.

The Connecting Transmission Owner shall complete all wiring, testing, and

commissioning of the RTU.

The Connecting Transmission Owner shall engineer, design, construct, own, and

maintain the Line 15 Tap.

2-6

SERVICE AGREEMENT NO. 2720

E.

ESTIMATED COSTS OF INTERCONNECTION FACILITIES

The total estimated costs (+30%/-15%) of the work associated with the Interconnection

Facilities required for the interconnection of the Small Generating Facility are presented in the

table below.

As described in the Facilities Study for the Small Generating Facility, the estimates

provided herein:

Assume:

• 5X10 construction work week;

• outages are available;

• all major material is delivered to site (i.e., no costs are included for transport from

storage);

• existing equipment to remain is functional.

Exclude (as applicable):

• discussions and negotiations of issued interconnection study;

• application fees;

• applicable surcharges;

• overall project sales tax;

• property taxes;

2-7

SERVICE AGREEMENT NO. 2720

• line switching;

• property/easement acquisitions;

• access roads and any associated matting;

• future operation and maintenance costs;

• recurring monthly communications circuits’ charges, if any, responsible by the

Interconnection Customer to the communications utility;

• soil testing;

• adverse field conditions such as rock, water, weather, and Interconnection Customer

electrical equipment obstructions;

• environmental mitigation;

• extended engineering to minimize outage time or Connecting Transmission Owner’s

public duty to serve;

• extended craft labor hours, to minimize outage and/or construction time;

• property transactions reviews associated with Interconnection Customer’s requests to

occupy the Connecting Transmission Owner’s rights-of-way and/or fee owned property

(such reviews were outside the scope of the Facilities Study); or

• any required permits.

Cost adders estimated for overtime will be based on 1.5 and 2 times labor rates if

required for work beyond normal business hours. Meals and equipment are also extra costs

incurred for overtime labor.

F.

O&M EXPENSES FOR INTERCONNECTION FACILITIES

In accordance with Article 4.1.2 of this Agreement, the Interconnection Customer shall

be responsible for all reasonable expenses associated with the operation, maintenance, repair and

replacement of the Connecting Transmission Owner’s Interconnection Facilities, as such

facilities are detailed in this Attachment 2 (“O&M Expenses”).

The Interconnection Customer shall have the option to pay such O&M Expenses either

under the procedure described in Option 1 or in Option 2 below.

Option 1: Fixed On-Going Charge Payment:

The Connecting Transmission Owner will invoice and Interconnection Customer

shall pay an annual payment to the Connecting Transmission Owner equal to the

product of the Gross Plant Investment associated with the Connecting

Transmission Owner’s Interconnection Facilities and the Annual Transmission

Ongoing Charge Factor, for the term of this Agreement.

For purposes of this Agreement, Gross Plant Investment shall mean the

investment from the plant account records associated with the Connecting

Transmission Owner’s Interconnection Facilities for the Small Generating

Facility.

2-8

SERVICE AGREEMENT NO. 2720

All payments due to be made by the Interconnection Customer shall be made

within thirty (30) days after receiving an invoice from the Connecting

Transmission Owner. Connecting Transmission Owner will bill Interconnection

Customer for the O&M Expenses on a quarterly basis.

The Project’s Gross Plant Investment associated with the Connecting

Transmission Owner’s Interconnection Facilities shall be established in writing by

the Connecting Transmission Owner no later than 90 days following commercial

operation.

The Annual Transmission On-Going Charge Factor shall be calculated annually

each July based on the Connecting Transmission Owner’s most recent FERC

Form 1 data and will equal the sum of the Revenue Requirement Components as

identified in O&M Attachment 1 divided by the Total Gross Plant of the

Connecting Transmission Owner. Total Gross Plant shall equal the sum of Item

Nos. A (1)(a)(b)(c) in O&M Attachment 1.

Option 2: Quarterly Actual O&M Expenses

The Interconnection Customer shall pay for all actual O&M Expenses incurred by

the Connecting Transmission Owner, which expenses shall be billed by the

Connecting Transmission Owner quarterly as accumulated during the quarter for

which they were incurred.

All payments due to be made by the Interconnection Customer shall be made

within thirty (30) days after receiving an invoice from the Connecting

Transmission Owner, which invoice shall be issued after the end of each quarter

for the most recent quarter.

Selection by Interconnection Customer

The Interconnection Customer shall select which option for paying such O&M

Expenses by providing written notice to the Connecting Transmission Owner

within thirty (30) days after the Gross Connecting Transmission Owner’s

Interconnection Facilities Plant Investment cost and the most recent Annual

Transmission Ongoing Charge Factor have been provided to the Interconnection

Customer. If the Interconnection Customer fails to provide timely notice to the

Connecting Transmission Owner of the option selected, the Interconnection

Customer will be deemed to have selected Option 2: Quarterly Actual O&M

Expenses.

2-9

SERVICE AGREEMENT NO. 2720

O&M ATTACHMENT 1

Capitalized terms used in this calculation will have the following definitions:

Allocation Factor

(1)

General Plant Allocation Factor shall equal Electric General Plant divided by the sum of

Electric General Plant plus gas general plant as reported in the Annual Report filed with the New

York State Public Service Commission.

(2)

Gross Transmission Plant Allocation Factor shall equal the total investment in

Transmission Plant in Service divided by the sum of the total Transmission Plant in Service plus

the total Distribution Plant in Service, excluding Intangible Plant, General Plant and Common

Plant.

(3)

Transmission Wages and Salaries Allocation Factor shall equal the ratio of Connecting

Transmission Owner Transmission-related direct electric wages and salaries including any direct

wages or salaries charged to Connecting Transmission Owner by a Connecting Transmission

Owner Affiliate to Connecting Transmission Owner’s total electric direct wages and salaries

including any wages charged to Connecting Transmission Owner by a Connecting Transmission

Owner Affiliate excluding any electric administrative and general wages and salaries.

Ratebase and Expense items

(1)

Administrative and General Expense shall equal electric expenses as recorded in FERC

Account Nos. 920-935.

(2)

Amortization of Investment Tax Credits shall equal electric credits as recorded in FERC

Account No. 411.4.

(3)

Distribution Plant in Service shall equal the gross plant balance as recorded in FERC

Account Nos. 360 – 374.

(4)

Electric Common Plant shall equal the balance of Common Plant recorded in FERC

Account Nos. 389-399 multiplied by the General Plant Allocation Factor.

(5)

General Plant shall equal electric gross general plant balance recorded in FERC Account

Nos. 389-399.

(6)

Materials and Supplies shall equal electric materials and supplies balance as recorded in

FERC Account No. 154.

(7)

Payroll Taxes shall equal those electric payroll tax expenses as recorded in FERC

Account Nos. 408.100, 408.110 and 408.130.

(8)

Prepayments shall equal electric prepayment balance as recorded in FERC Account

No. 165.

2-10

SERVICE AGREEMENT NO. 2720

(9) Real Estate Tax Expenses shall equal electric transmission-related real estate tax expense

as recorded in FERC Account No. 408.140 and 408.180.

(10) Transmission Operation and Maintenance Expense shall equal electric expenses as

recorded in FERC Account Nos. 560, 562-573.

(11) Transmission Plant in Service shall equal the gross plant balance as recorded in FERC

Account Nos. 350-359.

(12) Transmission Revenue Credits shall equal the revenue reported in Account 456

(13) Transmission Related Bad Debt Expense shall equal Bad Debt Expense as reported in

Account 904 related to transmission billing.

(14) Wholesale Metering Cost shall equal any costs associated with any Revenue or Remote

Terminal Unit (RTU) meters and associated equipment located at an internal or external tie at

voltages equal to or greater than 23V. The cost shall be determined by multiplying the number of

wholesale meters in FERC Account No. 370.3 by the average cost of the meters plus the average

costs of installation.

In the event that the above-referenced FERC accounts are renumbered, renamed, or

otherwise modified, the above sections shall be deemed amended to incorporate such

renumbered, renamed, modified or additional accounts.

Revenue Requirement Components

The Revenue Requirement Components shall be the sum of Connecting Transmission

Owner’s (A) Return and Associated Income Taxes, (B) Transmission Related Real Estate Tax

Expense, (C) Transmission Related Amortization of Investment Tax Credits, (D) Transmission

Related Payroll Tax Expense (E) Transmission Operation and Maintenance Expense, (F)

Transmission Related Administrative and General Expenses, less (G) Revenue Credits, plus (H)

Bad Debt Expense.

A.

Return and Associated Income Taxes shall equal the product of the Transmission

Investment Base as identified in A(1) below and the Cost of Capital Rate.

1.

Transmission Investment Base shall be defined as

Transmission Related General Plant plus Transmission Related Common

Plant plus Transmission Related Regulatory Assets plus Transmission

Related Prepayments plus Transmission Related Materials and Supplies

plus Transmission Related Cash Working Capital.

(a)

Transmission Plant in Service shall equal the balance of Total

investment in Transmission Plant plus Wholesale Metering Cost.

(b)

Transmission Related General Plant shall equal the balance of

investment in General Plant multiplied by the Transmission Wages

and Salaries Allocation Factor.

2-11

SERVICE AGREEMENT NO. 2720

(c)

Transmission Related Common Plant shall equal Electric Common

Plant multiplied by the Gross Transmission Plant Allocation Factor

and multiplied by the Transmission Wages and Salaries Allocation

Factor.

(d)

Transmission Related Regulatory Assets shall equal balances in

FERC Account Nos. 182.3 and 254 for state and federal regulatory

assets and liabilities related to FAS109, and excess AFUDC

multiplied by the Gross Transmission Plant Allocation Factor

(e)

(f)

Transmission Related Prepayments shall equal the electric balance

of Prepayments multiplied by the Gross Transmission Plant

Allocation Factor.

Transmission Related Materials and Supplies shall equal the balance

of Materials and Supplies assigned to Transmission added to the

remainder of Material and Supplies not directly assigned to either

Transmission or Distribution multiplied by the Gross Transmission

Plant Allocation Factor.

(g)

Transmission Related Cash Working Capital shall be a 12.5%

allowance (45 days/360 days) of the Transmission Operation and

Maintenance Expense (less FERC Account 565: Transmission of

Electricity by Others) and Transmission-Related Administrative and

General Expense.

2.

Cost of Capital Rate

The Cost of Capital Rate shall equal the proposed Weighted Costs of Capital

plus Federal Income Taxes and State Income Taxes.

(a)

The Weighted Costs of Capital will be calculated for the

Transmission Investment Base using Connecting Transmission

Owner’s actual capital structure and will equal the sum of (i), (ii),

and (iii) below:

(i)

the long-term debt component, which equals the product of

the actual weighted average embedded cost to maturity of

Connecting Transmission Owner’s long-term debt then

outstanding and the actual long-term debt capitalization

ratio.

(ii)

the preferred stock component, which equals the product of

the actual weighted average embedded cost to maturity of

Connecting Transmission Owner’s preferred stock then

outstanding and the actual preferred stock capitalization

ratio;

2-12

SERVICE AGREEMENT NO. 2720

(iii) the return on equity component, shall be the product of the

allowed ROE of 10.30% or such value as most recently

approved by the Commission plus a 50 basis point adder (per

FERC Order 697 and 697-A, if authorized by the

Commission for the Connecting Transmission Owner) and

Connecting Transmission Owner’s actual common equity

capitalization ratio.

(b)

Federal Income Tax shall equal

A x Federal Income Tax Rate

(1 - Federal Income Tax Rate)

where A is the sum of the preferred stock component and the return

on equity component, each as determined in Sections 2.(a)(ii) and

for the ROE set forth in 2.(a)(iii) above

(c)

State Income Tax shall equal

(A + Federal Income Tax) x State Income Tax Rate

(1 – State Income Tax Rate)

Where A is the sum of the preferred stock component and the return on

equity component as determined in A.2.(a)(ii) and A.2.(a)(iii) above and

Federal income Tax is determined in 2.(b) above.

B.

Transmission Related Real Estate Tax Expense shall equal the Real Estate Tax

Expenses multiplied by the Gross Plant Allocation Factor.

C.

Transmission Related Amortization of Investment Tax Credits shall equal the

electric Amortization of Investment Tax Credits multiplied by the Gross Transmission Plant

Allocation Factor.

D.

Transmission Related Payroll Tax Expense shall equal Payroll Taxes multiplied by

the Transmission Wages and Salaries Allocation Factor.

E.

Transmission Operation and Maintenance Expense shall equal the Transmission

Operation and Maintenance Expense as previously defined.

F.

Transmission Related Administrative and General Expenses shall equal the sum

of the electric Administrative and General Expenses multiplied by the Transmission Wages and

Salaries Allocation Factor.

G.

Revenue Credits shall equal all Transmission revenue recorded in FERC account

456.

H.

Transmission Related Bad Debt Expense shall equal Transmission Related Bad

Debt Expense as previously defined.

2-13

SERVICE AGREEMENT NO. 2720

Attachment 3

One-line Diagram Depicting the Small Generating Facility, Interconnection Facilities, Metering Equipment, and Upgrades

3-1

SERVICE AGREEMENT NO. 2720

Attachment 4

Milestones

1. Milestones

In-Service Date: December 2026

Critical milestones and responsibility as agreed to by the Parties:

MILESTONE

DATE

RESPONSIBLE

PARTY

1.

Execute Interconnection

Agreement

Interconnection

Customer/Connecting

Transmission Owner

Completed

11/2024

2.

3.

Provide initial prepayment for

engineering and procurement

Issue written authorization to

proceed with engineering and

procurement

Interconnection Customer

11/2024

Interconnection Customer

4.

Complete Cost Estimate Update

in accordance with NYISO

OATT Section 40.6.3.5.3

Project initiation

Connecting Transmission

Owner

01/2025

02/2025

03/2025

5.

6.

Connecting Transmission

Owner

Connecting Transmission

Owner/Interconnection

Customer

Project management level

kickoff meeting

7.

Provide property rights

documentation (i.e., options,

deeds, easements, etc.) to

Connecting Transmission Owner

for review

04/2025

04/2025

Interconnection Customer

Interconnection Customer

8.

9.

Start engineering on

Interconnection Customer’s

Interconnection Facilities

Provide final civil plans for

Collector Station with surveyed

location and height of

termination structure, grading

plan, access roads, and wetlands

delineation maps (in CAD

format)

Start engineering on all System

Upgrade Facilities and

04/2025

05/2025

Interconnection Customer

10.

Connecting Transmission

Owner

4-1

SERVICE AGREEMENT NO. 2720

MILESTONE

DATE

RESPONSIBLE

PARTY

Connecting Transmission

Owner’s Interconnection

Facilities

11.

12.

Start procurement for

Interconnection Customer’s

Interconnection Facilities

Start procurement for System

Upgrade Facilities and

Connecting Transmission

Owner’s Interconnection

Facilities

Complete procurement for

Interconnection Customer’s

Interconnection Facilities

Start construction of

05/2025

08/2025

08/2025

Interconnection Customer

Connecting Transmission

Owner

13.

14.

Interconnection Customer

Interconnection Customer’s

Interconnection Facilities

(including but not limited to site

civil preparation and foundation

work)

08/2025

08/2025

Interconnection Customer

Interconnection Customer

15.

16.

Provide prepayment/security for

construction

Provide written authorization to

proceed with construction of

System Upgrade Facilities

(“SUF”) and Connecting

Transmission Owner’s

08/2025

10/2025

Interconnection Customer

Interconnection Facilities

(“CTOIF”)

Complete engineering on

Interconnection Customer’s

Interconnection Facilities

(including Connecting

Transmission Owner approvals)

Complete construction of

Interconnection Customer’s

Interconnection Facilities

including all telecom circuits

installation and provisioning, as

well as all make ready work for

revenue metering and RTU

Complete engineering on SUF

and CTOIF

17.

18.

Connecting Transmission

Owner/Interconnection

Customer

03/2026

04/2026

Interconnection Customer

19.

Connecting Transmission

Owner

4-2

SERVICE AGREEMENT NO. 2720

MILESTONE

DATE

RESPONSIBLE

PARTY

20.

21.

22.

23.

24.

Deliver property rights to CTO

for SUF and CTOIF

Start construction of SUF and

CTOIF

Start construction of the Line 15

Tap (CTOIF)

Complete procurement for SUF

and CTOIF

04/2026

06/2026

06/2026

08/2026

Interconnection Customer

Connecting Transmission

Owner

Connecting Transmission

Owner

Connecting Transmission

Owner

Provide Connecting

Transmission Owner the NYISO

assigned PTID number and

associated project name (must be

provided at least 2 months in

advance of synchronization)

Complete construction and

testing of SUF and CTOIF

Field verification and witness

testing of Interconnection

Customer’s Interconnection

Facilities

Interconnection

Customer

09/2026

25.

26.

Connecting Transmission

Owner

10/2026

11/2026

Connecting Transmission

Owner/Interconnection

Customer

27.

28.

Initial Synchronization Date

Interconnection

Customer/Connecting

Transmission Owner

11/2026

11/2026

Complete testing and

commissioning

Interconnection Customer

29.

30.

31.

In-Service Date

12/2026

12/2026

Interconnection Customer

Interconnection Customer

Commercial Operations Date

Submit Interconnection

Customer’s Interconnection

Facilities as builts

Complete as builts for SUF and

CTOIF

Complete review/acceptance of

Interconnection Customer’s

Interconnection Facilities as

builts

Complete project closeout and

final invoicing

02/2027

04/2027

Interconnection Customer

32.

33.

Connecting Transmission

Owner

Connecting Transmission

Owner

05/2027

07/2027

34.

Connecting Transmission

Owner

These milestones are contingent upon, but not limited to, outage scheduling, and the

Interconnection Customer’s successful compliance with all interconnection requirements and

timely completion of its obligations in Project Specific Specifications and this Agreement. Due to

the COVID-19 pandemic, the Connecting Transmission Owner’s ability to deliver this project in

4-3

SERVICE AGREEMENT NO. 2720

accordance with these milestones may be at risk. Any such impacts shall be addressed in

accordance with Article 6.2 of this Agreement.

2. Security Arrangement

As agreed upon by the Connecting Transmission Owner and Interconnection Customer

pursuant to Article 6.1.1 of this Agreement, the Interconnection Customer shall, at the

Interconnection Customer’s discretion, either (i) make prepayments (in lieu of posting the security

contemplated by Article 6.3 of this Agreement), or (ii) provide security installments to Connecting

Transmission Owner in the form contemplated by Article 6.3 of this Agreement, in each case for

its estimated costs to design, engineer, procure, construct, and install Connecting Transmission

Owner’s Interconnection Facilities and Upgrades. Interconnection Customer shall make such

prepayment or security installments in accordance with the following schedule:

(1)

$962,500, such prepayment amount or security amount to be provided at least

twenty (20) Business Days prior to Interconnection Customer’s issuance of the

written authorization to proceed with engineering and procurement. Such amount

to be provided as contemplated by Milestones 2 and 3 in the table contained in

Section 1 of this Attachment 4; and

(2)

$1,682,700 such prepayment or security amount to be provided at least twenty (20)

Business Days prior to Interconnection Customer’s issuance of the written

authorization to proceed with construction. Such amount to be provided as

contemplated by Milestones 14 and 16 in the table contained in Section 1 of this

Attachment 4; and

The actual amount of the prepayment or security to be provided by Interconnection

Customer may be adjusted by Connecting Transmission Owner following completion of

engineering for Connecting Transmission Owner’s Interconnection Facilities and System Upgrade

Facilities; Connecting Transmission Owner shall provide written notice to Interconnection

Customer of the adjusted prepayment or security amount, together with reasonable supporting

documentation of the related cost estimates.

If at any time after Interconnection Customer has made a prepayment of amounts due in

accordance with this Section 2 of Attachment 4, Interconnection Customer provides Connecting

Transmission Owner with security satisfying the requirements of Article 6.3 in an amount at least

equal to the amount required to be provided as of such date by this Section 2, Connecting

Transmission Owner will refund to Interconnection Customer any prepayment or portion thereof

that Interconnection Customer has made prior to the date such alternate security is provided and

that has not been applied against Interconnection Customer’s payment obligations as of such date.

The Connecting Transmission Owner shall not be obligated to commence engineering,

procurement, or construction, as applicable, unless the Connecting Transmission Owner has

received the corresponding prepayment or security installment as contemplated above.

4-4

SERVICE AGREEMENT NO. 2720

As agreed to by Interconnection Customer and Connecting Transmission Owner, the

Connecting Transmission Owner shall issue Interconnection Customer an invoice on a monthly

basis detailing Interconnection Customer’s cost responsibility under this Agreement and providing

the net amount, if any, due to Connecting Transmission Owner after Connecting Transmission

Owner has applied any prepayment amounts towards settlement of the invoice. For the avoidance

of doubt, Connecting Transmission Owner shall apply the full amount of any prepayment amount

held by Connecting Transmission Owner against Interconnection Customer’s cost responsibility

under this Agreement before Interconnection Customer is required to pay any amount in excess of

such prepayment amount. If any amount is due from Interconnection Customer, it shall make such

payments pursuant to Article 6.1.1 of this Agreement. The amount of any security provided by

Interconnection Customer under this Section 2 shall be reduced for payments made by

Interconnection Customer as provided in Article 6.3 of this Agreement.

4-5

SERVICE AGREEMENT NO. 2720

Attachment 5

Additional Operating Requirements for the New York State Transmission System, the

Distribution System and Affected Systems Needed to Support the Interconnection

Customer’s Needs

The NYISO, in consultation with the Connecting Transmission Owner, shall also provide

requirements that must be met by the Interconnection Customer prior to initiating parallel

operation with the New York State Transmission System or the Distribution System.

(a) The Interconnection Customer must comply with all applicable NYISO tariffs and

procedures, as amended from time to time.

(b) To the extent not inconsistent with the terms of this Agreement, the ISO OATT, or

applicable NYISO procedures, Interconnection Customer must comply with Connecting

Transmission Owner’s operating instructions and requirements, which requirements shall include

the dedicated data circuits, including system protection circuits, to be maintained by

Interconnection Customer in accordance with Article 1.5 of this Agreement. Interconnection

Customer must also comply with the applicable requirements as set out in the Connecting

Transmission Owner’s ESBs, which have been identified and provided to the Interconnection

Customer as amended from time to time, to the extent not inconsistent with the terms of this

Agreement or applicable NYISO tariffs and procedures. Upon the Connecting Transmission

Owner’s notice to the Interconnection Customer of amendments to the ESBs, the Interconnection

Customer has 30 days to comply with such amendments.

5-1

SERVICE AGREEMENT NO. 2720

Attachment 6

Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of

Upgrade Costs

The NYISO, in consultation with the Connecting Transmission Owner, shall describe

Upgrades and provide an itemized best estimate of the cost, including overheads, of the

Upgrades and annual operation and maintenance expenses associated with such Upgrades. The

Connecting Transmission Owner shall functionalize Upgrade costs and annual expenses as either

transmission or distribution related.

The cost estimate for System Upgrade Facilities and System Deliverability Upgrades

shall be taken from the ISO OATT Attachment S cost allocation process or applicable

Interconnection Study, as required by Section 32.3.5.3.2 of Attachment Z. The cost estimate for

Distribution Upgrades shall include the costs of Distribution Upgrades that are reasonably

allocable to the Interconnection Customer at the time the estimate is made, and the costs of any

Distribution Upgrades not yet constructed that were assumed in the Interconnection Studies for

the Interconnection Customer but are, at the time of the estimate, an obligation of an entity other

than the Interconnection Customer.

The cost estimates for Distribution Upgrades, System Upgrade Facilities, and System

Deliverability Upgrades are estimates. The Interconnection Customer is ultimately responsible

for the actual cost of the Distribution Upgrades, System Upgrade Facilities, and System

Deliverability Upgrades needed for its Small Generating Facility, as that is determined under

Attachments S, X, and Z of the ISO OATT.

A.

B.

C.

DISTRIBUTION UPGRADES

None.

STAND-ALONE SYSTEM UPGRADE FACILITIES (“SUF”)

None.

OTHER SYSTEM UPGRADE FACILITIES (“SUF”)

The interconnection of the Small Generating Facility will require the following System

Upgrade Facilities at the Connecting Transmission Owner’s Mohican and Battenkill Substations.

1. Mohican Substation

All modifications shall be completed in the Mohican Substation yard and control house.

a) Line 15 Protection Packages

6-1

SERVICE AGREEMENT NO. 2720

The existing Line 15 protection is a POTT for the ‘A’ package and step distance for the

‘B’ package. The existing A package relay is a SEL-321 and will be reused and reset to

accommodate the generation. However, the existing B package relay is a SEL-221 which cannot

be reset to accommodate the generation and will be replaced with an ERLPhase LPro. DTT

transmit and receive to the Dolan Solar Collector Station will be added. DTT will be sent to the

Dolan Solar Collector Station for a line relay operation and R15 breaker failure. DTT for

breaker failure will be received from the Dolan Solar Collector Station. The ‘A’ package line

relay will be used for DTT receive supervision and will be used to trip and drive reclosing to

lockout. The existing electromechanical reclosing relays shall be replaced with one (1) SEL351

6 relay to allow addition of drive to lockout (“DTL”) for DTT receive. A GARD8000 will be

added for DTT to and from the Dolan Solar Collector Station.

b) Controls and Integration

The existing RTU is sufficient for the scope of this project. Spare I/O points will be used

to accommodate the additions required.

c) Telecommunications

The Mohican Substation has an existing Verizon copper facility terminated in a High

Voltage Protection (“HVP”) Positron shelf. Preliminary analysis indicates that it is possible that

the new T1 circuit can be installed on existing Verizon copper entrance cable and Positron high

voltage protection equipment. Therefore, at this time, it is assumed that there will not be a need

for new Verizon fiber service. However, should the Small Generating Facility proceed,

Connecting Transmission Owner will submit a completed HVP data form to Verizon to verify.

To the extent that it is determined the existing facilities cannot be used, then a new Verizon fiber

service shall be required, additional cost for the new fiber shall be incurred.

The Connecting Transmission Owner will order one (1) Verizon DS1 circuit from the

Mohican Substation to the Dolan Solar Collector Station to support DTT teleprotection. The

DS1 will be extended from the Verizon fiber demarcation point to the Gard 8000 rack location in

the control house.

(Note: Verizon may retire T1 services in the future. If T1 circuits are not available at the

time of project implementation, alternative technologies will be required which could change the

overall cost of the telecom solution.)

2. Battenkill Substation

All modifications shall be completed in the Battenkill Substation yard and control house.

a) Line 15 Protection Packages

The existing Line 15 protection is a POTT for the ‘A’ package and step distance for the

‘B’ package. The existing relays (SEL-311C and ERL Phase LPRO) will be reused and reset to

accommodate the generation. DTT transmit and receive to the Dolan Solar Collector Station will

6-2

SERVICE AGREEMENT NO. 2720

be added. DTT will be sent to the Dolan Solar Collector Station for a line relay operation and for

R15 breaker failure. DTT for breaker failure will be received from the Dolan Solar Collector

Station. The ‘A’ package line relay shall be used for DTT receive supervision and will be used

to trip and drive reclosing to lockout. An on/off switch for the DTT scheme shall be installed

and a GARD8000 will be added for DTT to and from the Dolan Solar Collector Station.

b) Controls and Integration

The existing RTU is sufficient for the scope of this project. Spare I/O points will be used

to accommodate the additions required.

c) Telecommunications

The Battenkill Substation has an existing Verizon copper facility terminated in a High

Voltage Protection (“HVP”) Positron shelf. Preliminary analysis indicates that it is possible that

the new T1 circuit can be installed on existing Verizon copper entrance cable and Positron high

voltage protection equipment. Therefore, at this time, it is assumed that there will not be a need

for new Verizon fiber service. However, should the Small Generating Facility proceed,

Connecting Transmission Owner will submit a completed HVP data form to Verizon to verify.

To the extent that it is determined the existing facilities cannot be used, then a new Verizon fiber

service shall be required, additional cost for the new fiber shall be incurred.

The Connecting Transmission Owner will order one (1) Verizon DS1 circuit from the

Battenkill Substation to the Dolan Solar Collector Station to support DTT teleprotection. The

DS1 will be extended from the Verizon fiber demarcation point to the Gard 8000 rack location in

the control house.

(Note: Verizon may retire T1 services in the future. If T1 circuits are not available at the

time of project implementation, alternative technologies will be required which could change the

overall cost of the telecom solution.)

Due to the addition of the Small Generating Facility an area coordination study will be

completed during final engineering and may result in resetting of relays in the area. The

Interconnection Customer shall be responsible for all costs associated with this.

D.

AFFECTED SYSTEM UPGRADES

The Interconnection Facilities Study for the Somers Solar Project (Q1015) identified the

Dolan Solar Collector Substation as an Affected System. The Somers Solar Project is owned by

Somers Solar, LLC (“Somers”), which is an affiliate of the Interconnection Customer. In

particular, the interconnection of the Somers Solar Project will require the need for DTT between

the collector substation for the Somers Solar project (the “Somers Solar Collector Substation”)

and the Dolan Solar Collector Substation. The related Affected System Upgrades at the Dolan

Solar Collector Substation include:

- engineering of the relay upgrade required for the DTT;

6-3

SERVICE AGREEMENT NO. 2720

- procurement of the relay and minor wiring materials required;

- installation and testing of the relay at the Dolan Solar Collector Substation site; and

- review by Connecting Transmission Owner.

The Interconnection Customer has agreed with Somers that it will perform the Affected

System Upgrades work associated with the Somers Solar Project at the Dolan Solar Collector

Substation under the terms of this Agreement, that it will reimburse the Connecting Transmission

Owner for any oversight costs concerning the Affected System Upgrades work under the terms

of this Agreement, and that Interconnection Customer will separately address with Somers any

cost reimbursement as between the two entities concerning the Affected System Upgrades work.

If the Small Generating Facility or the Somers Solar Project is terminated or is delayed in a

manner that impacts the scope or timing of the Affected System Upgrades work, the

Interconnection Customer shall coordinate with the NYISO, National Grid, and Somers

concerning any required modifications to the Affected System Upgrades, and the NYISO,

Connecting Transmission Owner, and Interconnection Customer shall amend this Agreement to

reflect any changes.

Interconnection Customer shall be responsible for the design, engineering, procurement,

and installation of the Affected System Upgrades, subject to Connecting Transmission Owner’s

oversight. The cost estimate (+30%/-15%, in 2023 dollars) of the Affected System Upgrades is

$180,000.

E.

COST ESTIMATES RELATED TO DISTRIBUTION UPGRADES AND SYSTEM

UPGRADE FACILITIES

The total estimated costs (+30%/-15%) of the work associated with the System Upgrade

Facilities required for the interconnection of the Small Generating Facility are presented in the

table below.

System Upgrade Facilities (SUFs)

Engineering, design, construction, testing and commissioning for

remote stations upgrade facilities.

Mohican Station

Battenkill Station

$246,100

$95,500

SUF Subtotal

$341,600

SUF Subtotal

Contingency

SUF TOTAL

$341,600

$90,900

$432,500

6-4

SERVICE AGREEMENT NO. 2720

As described in the Facilities Study for the Small Generating Facility, the estimates

provided herein:

Assume:

• 5X10 construction work week;

• outages are available;

• all major material is delivered to site (i.e., no costs are included for transport from

storage); and

• existing equipment to remain is functional.

Exclude (as applicable):

• discussions and negotiations of issued interconnection study;

• application fees;

• applicable surcharges;

• overall project sales tax;

• property taxes;

• line switching;

• property/easement acquisitions;

• access roads and associated matting;

• future operation and maintenance costs;

• recurring monthly communications circuits’ charges, if any, responsible by the

Interconnection Customer to the communications utility;

• soil testing;

• adverse field conditions such as rock, water, weather, and Interconnection Customer

electrical equipment obstructions;

• environmental mitigation;

• extended engineering to minimize outage time or Connecting Transmission Owner’s

public duty to serve;

• extended craft labor hours, to minimize outage and/or construction time;

• property transactions reviews associated with Interconnection Customer’s requests to

occupy the Connecting Transmission Owner’s rights-of-way and/or fee owned property;

or

• any required permits.

Cost adders estimated for overtime will be based on 1.5 and 2 times labor rates if

required for work beyond normal business hours. Meals and equipment are also extra costs

incurred for overtime labor.

6-5

SERVICE AGREEMENT NO. 2720

Attachment 7

Insurance Coverage

Interconnection Customer shall, at its own expense, maintain in force throughout the

period of this Agreement, the following minimum insurance coverage, with insurers authorized

to do business in the State of New York.

Commercial General Liability Insurance including, but not limited to, bodily injury,

property damage, products/completed operations, contractual and personal injury liability with a

combined single limit of $2 million per occurrence, $5 million annual aggregate.

7-1

SERVICE AGREEMENT NO. 2720

Attachment 8

Initial Synchronization Date

[Date]

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid

Attention: Kevin Reardon

40 Sylvan Road

Waltham, MA 02541-1120

Re: Dolan Solar Project Small Generating Facility

Dear

:

On [Date] [Interconnection Customer] initially synchronized the Small Generating Facility

[specify units, if applicable]. This letter confirms that [Interconnection Customer]’s Initial

Synchronization Date was [specify].

Thank you.

[Signature]

[Interconnection Customer Representative]

8-1

SERVICE AGREEMENT NO. 2720

Attachment 9

Commercial Operation Date

[Date]

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid

Attention: Kevin Reardon

40 Sylvan Road

Waltham, MA 02541-1120

Re:

Dolan Solar Project Small Generating Facility

Dear __________________:

On [Date] [Interconnection Customer] has completed Trial Operation of Unit No. ___. This

letter confirms that [Interconnection Customer] commenced Commercial Operation of the

Small Generating Facility [specify units, as applicable], effective as of [Date plus one day].

Thank you.

[Signature]

[Interconnection Customer Representative]

9-1