SERVICE AGREEMENT NO. 2913

SERVICE AGREEMENT NO. 2913

STANDARD SMALL GENERATOR

INTERCONNECTION AGREEMENT

AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.,

NIAGARA MOHAWK POWER CORPORATION

D/B/A NATIONAL GRID,

AND

BR PROJECT 1 LLC

Dated as of October 1, 2025

(BR Benson Mines Solar)

SERVICE AGREEMENT NO. 2913

TABLE OF CONTENTS

Article 1 Scope and Limitations of Agreement ...................................................................2
 1.1 Applicability ........................................................................................................... 2
 1.2 Purpose.................................................................................................................... 2
 1.3 Scope of Interconnection Service ........................................................................... 2
 1.4 Limitations.............................................................................................................. 2
 1.5 Responsibilities of the Parties................................................................................. 2
 1.6 Parallel Operation Obligations................................................................................ 4
 1.7 Metering.................................................................................................................. 5
 1.8 Reactive Power and Primary Frequency Response ................................................ 5
 1.9 Capitalized Terms ................................................................................................... 8

Article 2 Inspection, Testing, Authorization, and Right of Access ...................................9
 2.1 Equipment Testing and Inspection.......................................................................... 9
 2.2 Authorization Required Prior to Parallel Operation ............................................... 9
 2.3 Right of Access..................................................................................................... 10

Article 3 Effective Date, Term, Termination, and Disconnection...................................11
 3.1 Effective Date ....................................................................................................... 11
 3.2 Term of Agreement............................................................................................... 11
 3.3 Termination........................................................................................................... 11
 3.4 Temporary Disconnection..................................................................................... 12

Article 4 Cost Responsibility for Interconnection Facilities and Distribution
 Upgrades...............................................................................................................14
 4.1 Interconnection Facilities...................................................................................... 14
 4.2 Distribution Upgrades........................................................................................... 14

Article 5 Cost Responsibility for System Upgrade Facilities and System
 Deliverability Upgrades.......................................................................................15
 5.1 Applicability ......................................................................................................... 15
 5.2 System Upgrades .................................................................................................. 15
 5.3 Special Provisions for Affected Systems.............................................................. 15
 5.4 Limited Operation................................................................................................. 15

Article 6 Billing, Payment, Milestones, and Financial Security ......................................17
 6.1 Billing and Payment Procedures and Final Accounting ....................................... 17
 6.2 Milestones............................................................................................................. 17
 6.3 Financial Security Arrangements.......................................................................... 18

Article 7 Assignment, Liability, Indemnity, Force Majeure, Consequential
 Damages, and Default..........................................................................................19
 7.1 Assignment ........................................................................................................... 19
 7.2 Limitation of Liability........................................................................................... 19
 7.3 Indemnity.............................................................................................................. 19
 7.4 Consequential Damages........................................................................................ 20

i

SERVICE AGREEMENT NO. 2913

7.5 Force Majeure ....................................................................................................... 21

7.6 Breach and Default ............................................................................................... 21

Article 8 Insurance ..............................................................................................................23
Article 9 Confidentiality......................................................................................................24
Article 10 Disputes.................................................................................................................26
Article 11 Taxes......................................................................................................................27

Article 12 Miscellaneous........................................................................................................28
 12.1 Governing Law, Regulatory Authority, and Rules ............................................... 28
 12.2 Amendment........................................................................................................... 28
 12.3 No Third-Party Beneficiaries................................................................................ 28
 12.4 Waiver................................................................................................................... 28
 12.5 Entire Agreement.................................................................................................. 28
 12.6 Multiple Counterparts........................................................................................... 29
 12.7 No Partnership ...................................................................................................... 29
 12.8 Severability ........................................................................................................... 29
 12.9 Security Arrangements.......................................................................................... 29
 12.10 Environmental Releases........................................................................................ 29
 12.11 Subcontractors....................................................................................................... 29
 12.12 Reservation of Rights............................................................................................ 30
 12.13 Modifications Related to NYISO’s Compliance with Order No. 2023................ 30

Article 13 Notices ...................................................................................................................31
 13.1 General.................................................................................................................. 31
 13.2 Billing and Payment.............................................................................................. 32
 13.3 Alternative Forms of Notice ................................................................................. 32
 13.4 Designated Operating Representative................................................................... 33
 13.5 Changes to the Notice Information....................................................................... 34

Article 14 Signatures .............................................................................................................35

Attachment 1 Glossary of Terms

Attachment 2 Detailed Scope of Work, Including Description and Costs of the Small Generating
Facility, Interconnection Facilities, and Metering Equipment

Attachment 3 One-line Diagram Depicting the Small Generating Facility, Interconnection
Facilities, Metering Equipment, and Upgrades

Attachment 4 Milestones

Attachment 5 Additional Operating Requirements for the New York State Transmission System,
the Distribution System and Affected Systems Needed to Support the Interconnection
Customer’s Needs

ii

SERVICE AGREEMENT NO. 2913

Attachment 6 Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of Upgrade Costs

Attachment 7 Insurance Coverage

Attachment 8 Initial Synchronization Date

Attachment 9 Commercial Operation Date

iii

SERVICE AGREEMENT NO. 2913

This Standard Small Generator Interconnection Agreement (“Agreement” or “SGIA”) is made
and entered into this 1st day of October, 2025, by and among the New York Independent System
Operator, Inc., a not-for-profit corporation organized and existing under the laws of the State of
New York (“NYISO”) and Niagara Mohawk Power Corporation d/b/a National Grid a
corporation organized and existing under the laws of the State of New York (“Connecting
Transmission Owner”), and BR Project 1 LLC, a limited liability company organized and
existing under the laws of the State of New York (“Interconnection Customer”) each hereinafter
sometimes referred to individually as “Party” or referred to collectively as the “Parties.”

In consideration of the mutual covenants set forth herein, the Parties agree as follows:

1

SERVICE AGREEMENT NO. 2913

Article 1 Scope and Limitations of Agreement

1.1 Applicability

This Agreement shall be used for all Interconnection Requests submitted under the Small
Generator Interconnection Procedures (SGIP) except for those submitted under the 10 kW
Inverter Process contained in SGIP Attachment 5.

1.2 Purpose

This Agreement governs the terms and conditions under which the Interconnection
Customer’s Small Generating Facility will interconnect with, and operate in parallel with, the
New York State Transmission System or the Distribution System.

1.3 Scope of Interconnection Service

1.3.1 The NYISO will provide Energy Resource Interconnection Service to
 Interconnection Customer at the Point of Interconnection.

1.3.2 This Agreement does not constitute an agreement to purchase or deliver the
 Interconnection Customer’s power. The purchase or delivery of power and other
 services that the Interconnection Customer may require will be covered under
 separate agreements, if any, or applicable provisions of NYISO’s or Connecting
 Transmission Owner’s tariffs. The Interconnection Customer will be responsible
 for separately making all necessary arrangements (including scheduling) for
 delivery of electricity in accordance with the applicable provisions of the ISO
 OATT and Connecting Transmission Owner’s tariff. The execution of this
 Agreement does not constitute a request for, nor agreement to, provide Energy,
 any Ancillary Services or Installed Capacity under the NYISO Services Tariff or
 any Connecting Transmission Owner’s tariff. If Interconnection Customer wishes
 to supply or purchase Energy, Installed Capacity or Ancillary Services, then
 Interconnection Customer will make application to do so in accordance with the
 NYISO Services Tariff or Connecting Transmission Owner’s tariff.

1.4 Limitations

Nothing in this Agreement is intended to affect any other agreement by and among the
NYISO, Connecting Transmission Owner and the Interconnection Customer, except as otherwise
expressly provided herein.

1.5 Responsibilities of the Parties

1.5.1 The Parties shall perform all obligations of this Agreement in accordance with all
 Applicable Laws and Regulations, Operating Requirements, and Good Utility
 Practice.

1.5.2 The Interconnection Customer shall construct, interconnect, operate and maintain
 its Small Generating Facility and construct, operate, and maintain its

2

SERVICE AGREEMENT NO. 2913

Interconnection Facilities in accordance with the applicable manufacturer’s
recommended maintenance schedule, and in accordance with this Agreement, and
with Good Utility Practice.

1.5.3 The Connecting Transmission Owner shall construct, operate, and maintain its
 Interconnection Facilities and Upgrades covered by this Agreement in accordance
 with this Agreement, and with Good Utility Practice. If all the Parties agree, the
 Interconnection Customer may construct the Connecting Transmission Owner’s
 Interconnection Facilities and Upgrades as specified in Attachment 2 and
 Attachment 6.

1.5.4 The Interconnection Customer agrees to construct its facilities or systems in
 accordance with applicable specifications that meet or exceed those provided by
 the National Electrical Safety Code, the American National Standards Institute,
 IEEE, Underwriter’s Laboratory, and Operating Requirements in effect at the time
 of construction and other applicable national and state codes and standards. The
 Interconnection Customer agrees to design, install, maintain, and operate its Small
 Generating Facility so as to reasonably minimize the likelihood of a disturbance
 adversely affecting or impairing the system or equipment of the Connecting
 Transmission Owner or Affected Systems.

1.5.5 The Connecting Transmission Owner and Interconnection Customer shall operate,
 maintain, repair, and inspect, and shall be fully responsible for the facilities that it
 now or subsequently may own unless otherwise specified in the Attachments to
 this Agreement. Each of those Parties shall be responsible for the safe
 installation, maintenance, repair and condition of their respective lines and
 appurtenances on their respective sides of the point of change of ownership. The
 Connecting Transmission Owner and the Interconnection Customer, as
 appropriate, shall provide Interconnection Facilities that adequately protect the
 Connecting Transmission Owner’s electric system, personnel, and other persons
 from damage and injury. The allocation of responsibility for the design,
 installation, operation, maintenance and ownership of Interconnection Facilities
 shall be delineated in the Attachments to this Agreement.

1.5.6 The NYISO shall coordinate with all Affected Systems to support the
 interconnection. The Connecting Transmission Owner shall cooperate with the
 NYISO in these efforts.

1.5.7 The Interconnection Customer shall ensure “frequency ride through” capability
 and “voltage ride through” capability of its Small Generating Facility. The
 Interconnection Customer shall enable these capabilities such that its Small
 Generating Facility shall not disconnect automatically or instantaneously from the
 system or equipment of the Connecting Transmission Owner and any Affected
 Systems for a defined under-frequency or over-frequency condition, or an under-
 voltage or over-voltage condition, as tested pursuant to Section 2.1 of this
 agreement. The defined conditions shall be in accordance with Good Utility
 Practice and consistent with any standards and guidelines that are applied to other

3

SERVICE AGREEMENT NO. 2913

generating facilities in the Balancing Authority Area on a comparable basis. The
Small Generating Facility’s protective equipment settings shall comply with the
Transmission Owner’s automatic load-shed program. The Transmission Owner
shall review the protective equipment settings to confirm compliance with the
automatic load-shed program. The term “ride through” as used herein shall mean
the ability of a Small Generating Facility to stay connected to and synchronized
with the system or equipment of the Transmission Owner and any Affected
Systems during system disturbances within a range of conditions, in accordance
with Good Utility Practice and consistent with any standards and guidelines that
are applied to other generating facilities in the Balancing Authority on a
comparable basis. The term “frequency ride through” as used herein shall mean
the ability of a Small Generating Facility to stay connected to and synchronized
with the system or equipment of the Transmission Owner and any Affected
Systems during system disturbances within a range of under-frequency and over-
frequency conditions, in accordance with Good Utility Practice and consistent
with any standards and guidelines that are applied to other generating facilities in
the Balancing Authority Area on a comparable basis. The term “voltage ride
through” as used herein shall mean the ability of a Small Generating Facility to
stay connected to and synchronized with the system or equipment of the
Transmission Owner and any Affected Systems during system disturbances
within a range of under-voltage and over-voltage conditions, in accordance with
Good Utility Practice and consistent with any standards and guidelines that are
applied to other generating facilities in the Balancing Authority Area on a
comparable basis unless the Transmission Owner in whose Transmission District
the Small Generating Facility interconnects has established different requirements
that apply on a comparable basis in accordance with Good Utility Practice. For
abnormal frequency conditions and voltage conditions within the “no trip zone”
as that term is defined by ERO Reliability Standard PRC-024-3, any successor
mandatory ride through ERO standards, or any more stringent NPCC or NYSRC
requirements applicable to Generating Facilities in the Balancing Authority Area
on a comparable basis, the non-synchronous Small Generating Facility must
ensure that, within any physical limitations of the Small Generating Facility, its
control and protection settings are configured or set to (1) continue active power
production during disturbance and post disturbance periods at pre-disturbance
levels unless reactive power priority mode is enabled or unless providing primary
frequency response or fast frequency response; (2) minimize reductions in active
power and remain within dynamic voltage and current limits, if reactive power
priority mode is enabled, unless providing primary frequency response or fast
frequency response; (3) not artificially limit dynamic reactive power capability
during disturbances and (4) return to pre-disturbance active power levels without
artificial ramp rate limits if active power is reduced, unless providing primary
frequency response or fast frequency response.

1.6 Parallel Operation Obligations

Once the Small Generating Facility has been authorized to commence parallel operation,
the Interconnection Customer shall abide by all rules and procedures pertaining to the parallel

4

SERVICE AGREEMENT NO. 2913

operation of the Small Generating Facility in the applicable New York Control Area, including,
but not limited to: (1) the rules and procedures concerning the operation of generation set forth in
the NYISO tariffs or ISO Procedures or the Connecting Transmission Owner’s tariff; (2) any
requirements consistent with Good Utility Practice or that are necessary to ensure the safe and
reliable operation of the Transmission System or Distribution System; and (3) the Operating
Requirements set forth in Attachment 5 of this Agreement.

1.7 Metering

The Interconnection Customer shall be responsible for the Connecting Transmission
Owner’s reasonable and necessary cost for the purchase, installation, operation, maintenance,
testing, repair, and replacement of metering and data acquisition equipment specified in
Attachments 2 and 3 of this Agreement. The Interconnection Customer’s metering (and data
acquisition, as required) equipment shall conform to applicable industry rules and Operating
Requirements.

1.8 Reactive Power and Primary Frequency Response

1.8.1 Power Factor Design Criteria

1.8.1.1 Synchronous Generation. The Interconnection Customer shall design its
Small Generating Facility to maintain a composite power delivery at continuous
rated power output at the Point of Interconnection at a power factor within the
range of 0.95 leading to 0.95 lagging, unless the NYISO or the Transmission
Owner in whose Transmission District the Small Generating Facility interconnects has established different requirements that apply to all similarly
situated generators in the New York Control Area or Transmission District (as
applicable) on a comparable basis, in accordance with Good Utility Practice.

1.8.1.2 Non-Synchronous Generation. The Interconnection Customer shall
design its Small Generating Facility to maintain a composite power delivery at
continuous rated power output at the high-side of the generator substation at a
power factor within the range of 0.95 leading to 0.95 lagging, unless the NYISO
or the Transmission Owner in whose Transmission District the Small Generating
Facility interconnects has established a different power factor range that applies to
all similarly situated non-synchronous generators in the New York Control Area
or Transmission District (as applicable) on a comparable basis, in accordance with
Good Utility Practice. This power factor range standard shall be dynamic and can
be met using, for example, power electronics designed to supply this level of
reactive capability (taking into account any limitations due to voltage level, real
power output, etc.) or fixed and switched capacitors, or a combination of the two.
This requirement shall only apply to newly interconnecting non-synchronous
generators that have not yet executed a Facilities Study Agreement as of
September 21, 2016.

1.8.2 The NYISO is required to pay the Interconnection Customer for reactive power,
 or voltage support service, that the Interconnection Customer provides from the

5

SERVICE AGREEMENT NO. 2913

Small Generating Facility in accordance with Rate Schedule 2 of the NYISO
Services Tariff.

1.8.3 Primary Frequency Response. Interconnection Customer shall ensure the primary
 frequency response capability of its Small Generating Facility by installing,
 maintaining, and operating a functioning governor or equivalent controls. The
 term “functioning governor or equivalent controls” as used herein shall mean the
 required hardware and/or software that provides frequency responsive real power
 control with the ability to sense changes in system frequency and autonomously
 adjust the Small Generating Facility’s real power output in accordance with the
 droop and deadband parameters and in the direction needed to correct frequency
 deviations. Interconnection Customer is required to install a governor or
 equivalent controls with the capability of operating: (1) with a maximum 5
 percent droop and ±0.036 Hz deadband; or (2) in accordance with the relevant
 droop, deadband, and timely and sustained response settings from an approved
 Applicable Reliability Standard providing for equivalent or more stringent
 parameters. The droop characteristic shall be: (1) based on the nameplate
 capacity of the Small Generating Facility, and shall be linear in the range of
 frequencies between 59 to 61 Hz that are outside of the deadband parameter; or
 (2) based on an approved Applicable Reliability Standard providing for an
 equivalent or more stringent parameter. The deadband parameter shall be: the
 range of frequencies above and below nominal (60 Hz) in which the governor or
 equivalent controls is not expected to adjust the Small Generating Facility’s real
 power output in response to frequency deviations. The deadband shall be
 implemented: (1) without a step to the droop curve, that is, once the frequency
 deviation exceeds the deadband parameter, the expected change in the Small
 Generating Facility’s real power output in response to frequency deviations shall
 start from zero and then increase (for under-frequency deviations) or decrease (for
 over-frequency deviations) linearly in proportion to the magnitude of the
 frequency deviation; or (2) in accordance with an approved Applicable Reliability
 Standard providing for an equivalent or more stringent parameter.

Interconnection Customer shall notify NYISO that the primary frequency
response capability of the Small Generating Facility has been tested and
confirmed during commissioning. Once Interconnection Customer has
synchronized the Small Generating Facility with the New York State
Transmission System, Interconnection Customer shall operate the Small
Generating Facility consistent with the provisions specified in Articles 1.8.3.1 and

1.8.3.2 of this Agreement. The primary frequency response requirements
contained herein shall apply to both synchronous and non-synchronous Small
Generating Facilities.

1.8.3.1 Governor or Equivalent Controls. Whenever the Small Generating Facility
is operated in parallel with the New York State Transmission System,
Interconnection Customer shall operate the Small Generating Facility with its
governor or equivalent controls in service and responsive to frequency.
Interconnection Customer shall: (1) in coordination with NYISO, set the
deadband parameter to: (1) a maximum of ±0.036 Hz and set the droop parameter

6

SERVICE AGREEMENT NO. 2913

to a maximum of 5 percent; or (2) implement the relevant droop and deadband
settings from an approved Applicable Reliability Standard that provides for
equivalent or more stringent parameters. Interconnection Customer shall be
required to provide the status and settings of the governor and equivalent controls
to NYISO and/or the Connecting Transmission Owner upon request. If
Interconnection Customer needs to operate the Small Generating Facility with its
governor or equivalent controls not in service, Interconnection Customer shall
immediately notify NYISO and the Connecting Transmission Owner, and provide
both with the following information: (1) the operating status of the governor or
equivalent controls (i.e., whether it is currently out of service or when it will be
taken out of service); (2) the reasons for removing the governor or equivalent
controls from service; and (3) a reasonable estimate of when the governor or
equivalent controls will be returned to service. Interconnection Customer shall
make Reasonable Efforts to return its governor or equivalent controls into service
as soon as practicable. Interconnection Customer shall make Reasonable Efforts
to keep outages of the Small Generating Facility’s governor or equivalent controls
to a minimum whenever the Small Generating Facility is operated in parallel with
the New York State Transmission System.

1.8.3.2 Timely and Sustained Response. Interconnection Customer shall ensure
that the Small Generating Facility’s real power response to sustained frequency
deviations outside of the deadband setting is automatically provided and shall
begin immediately after frequency deviates outside of the deadband, and to the
extent the Small Generating Facility has operating capability in the direction
needed to correct the frequency deviation. Interconnection Customer shall not
block or otherwise inhibit the ability of the governor or equivalent controls to
respond and shall ensure that the response is not inhibited, except under certain
operational constraints including, but not limited to, ambient temperature
limitations, physical energy limitations, outages of mechanical equipment, or
regulatory requirements. The Small Generating Facility shall sustain the real
power response at least until system frequency returns to a value within the
deadband setting of the governor or equivalent controls. An Applicable
Reliability Standard with equivalent or more stringent requirements shall
supersede the above requirements.

1.8.3.3 Exemptions. Small Generating Facilities that are regulated by the United
States Nuclear Regulatory Commission shall be exempt from Articles 1.8.3,

1.8.3.1, and 1.8.3.2 of this Agreement. Small Generating Facilities that are
behind the meter generation that is sized-to-load (i.e., the thermal load and the
generation are near-balanced in real-time operation and the generation is primarily
controlled to maintain the unique thermal, chemical, or mechanical output
necessary for the operating requirements of its host facility) shall be required to
install primary frequency response capability requirements in accordance with the
droop and deadband capability requirements specified in Article 1.8.3, but shall
be otherwise exempt from the operating requirements in Articles 1.8.3, 1.8.3.1,

1.8.3.2, and 1.8.3.4 of this Agreement.

7

SERVICE AGREEMENT NO. 2913

1.8.3.4 Electric Storage Resources. Interconnection Customer interconnecting an
electric storage resource shall establish an operating range in Attachment 5 of its
SGIA that specifies a minimum state of charge and a maximum state of charge
between which the electric storage resource will be required to provide primary
frequency response consistent with the conditions set forth in Articles 1.8.3,

1.8.3.1, 1.8.3.2, and 1.8.3.3 of this Agreement. Attachment 5 shall specify
whether the operating range is static or dynamic, and shall consider (1) the
expected magnitude of frequency deviations in the interconnection; (2) the
expected duration that system frequency will remain outside of the deadband
parameter in the interconnection; (3) the expected incidence of frequency
deviations outside of the deadband parameter in the interconnection; (4) the
physical capabilities of the electric storage resource; (5) operational limitations of
the electric storage resources due to manufacturer specification; and (6) any other
relevant factors agreed to by the NYISO, Connecting Transmission Owner, and
Interconnection Customer. If the operating range is dynamic, then Attachment 5
must establish how frequently the operating range will be reevaluated and the
factors that may be considered during its reevaluation.

Interconnection Customer’s electric storage resource is required to provide timely
and sustained primary frequency response consistent with Article 1.8.3.2 of this
Agreement when it is online and dispatched to inject electricity to the New York
State Transmission System and/or receive electricity from the New York State
Transmission System. This excludes circumstances when the electric storage
resource is not dispatched to inject electricity to the New York State Transmission
System and/or dispatched to receive electricity from the New York State
Transmission System. If Interconnection Customer’s electric storage resource is
charging at the time of a frequency deviation outside of its deadband parameter, it
is to increase (for over-frequency deviations) or decrease (for under-frequency
deviations) the rate at which it is charging in accordance with its droop parameter.
Interconnection Customer’s electric storage resource is not required to change
from charging to discharging, or vice versa, unless the response necessitated by
the droop and deadband settings requires it to do so and it is technically capable
of making such a transition.

1.9 Capitalized Terms

Capitalized terms used herein shall have the meanings specified in the Glossary of Terms
in Attachment 1 or the body of this Agreement. Capitalized terms used herein that are not so
defined shall have the meanings specified in Appendix 1 of Attachment Z, Section 25.1.2 of
Attachment S, or Section 30.1 of Attachment X of the ISO OATT.

8

SERVICE AGREEMENT NO. 2913

Article 2 Inspection, Testing, Authorization, and Right of Access

2.1 Equipment Testing and Inspection

2.1.1 The Interconnection Customer shall test and inspect its Small Generating Facility
 and Interconnection Facilities prior to interconnection. The Interconnection
 Customer shall notify the NYISO and the Connecting Transmission Owner of
 such activities no fewer than five (5) Business Days (or as may be agreed to by
 the Parties) prior to such testing and inspection. Testing and inspection shall
 occur on a Business Day. The Connecting Transmission Owner may, at its own
 expense, send qualified personnel to the Small Generating Facility site to inspect
 the interconnection and observe the testing. The Interconnection Customer shall
 provide the NYISO and Connecting Transmission Owner a written test report
 when such testing and inspection is completed. The Small Generating Facility
 may not commence parallel operations if the NYISO, in consultation with the
 Connecting Transmission Owner, finds that the Small Generating Facility has not
 been installed as agreed upon or may not be operated in a safe and reliable
 manner.

2.1.2 The NYISO and Connecting Transmission Owner shall each provide the
 Interconnection Customer written acknowledgment that it has received the
 Interconnection Customer’s written test report. Such written acknowledgment
 shall not be deemed to be or construed as any representation, assurance,
 guarantee, or warranty by the NYISO or Connecting Transmission Owner of the
 safety, durability, suitability, or reliability of the Small Generating Facility or any
 associated control, protective, and safety devices owned or controlled by the
 Interconnection Customer or the quality of power produced by the Small
 Generating Facility.

2.2 Authorization Required Prior to Parallel Operation

2.2.1 The NYISO, in consultation with the Connecting Transmission Owner, shall use
 Reasonable Efforts to list applicable parallel Operating Requirements in

Attachment 5 of this Agreement. Additionally, the NYISO, in consultation with
the Connecting Transmission Owner, shall notify the Interconnection Customer of
any changes to these requirements as soon as they are known. The NYISO and
Connecting Transmission Owner shall make Reasonable Efforts to cooperate with
the Interconnection Customer in meeting requirements necessary for the Interconnection Customer to commence parallel operations by the in-service date.

2.2.2 The Interconnection Customer shall not operate its Small Generating Facility in
 parallel with the New York State Transmission System or the Distribution System
 without prior written authorization of the NYISO. The NYISO, in consultation
 with the Connecting Transmission Owner, will provide such authorization once
 the NYISO receives notification that the Interconnection Customer has complied
 with all applicable parallel Operating Requirements. Such authorization shall not
 be unreasonably withheld, conditioned, or delayed.

9

SERVICE AGREEMENT NO. 2913

2.3 Right of Access

2.3.1 Upon reasonable notice, the NYISO and/or Connecting Transmission Owner may
 send a qualified person to the premises of the Interconnection Customer at or
 immediately before the time the Small Generating Facility first produces energy
 to inspect the interconnection, and observe the commissioning of the Small
 Generating Facility (including any required testing), startup, and operation for a
 period of up to three (3) Business Days after initial start-up of the unit. In
 addition, the Interconnection Customer shall notify the NYISO and Connecting
 Transmission Owner at least five (5) Business Days prior to conducting any on-
 site verification testing of the Small Generating Facility.

2.3.2 Following the initial inspection process described above, at reasonable hours, and
 upon reasonable notice, or at any time without notice in the event of an
 emergency or hazardous condition, the NYISO and Connecting Transmission
 Owner each shall have access to the Interconnection Customer’s premises for any
 reasonable purpose in connection with the performance of the obligations
 imposed on them by this Agreement or if necessary to meet their legal obligation
 to provide service to their customers.

2.3.3 Each Party shall be responsible for its own costs associated with following this
 article.

10

SERVICE AGREEMENT NO. 2913

Article 3 Effective Date, Term, Termination, and Disconnection

3.1 Effective Date

This Agreement shall become effective upon execution by the Parties subject to
acceptance by FERC (if applicable), or if filed unexecuted, upon the date specified by the FERC.
The NYISO and Connecting Transmission Owner shall promptly file, or cause to be filed, this
Agreement with FERC upon execution, if required. If the Agreement is disputed and the
Interconnection Customer requests that it be filed with FERC in an unexecuted form, the NYISO
shall file, or cause to be filed, this Agreement and the NYISO shall identify the disputed
language.

3.2 Term of Agreement

This Agreement shall become effective on the Effective Date and shall remain in effect
for a period of thirty (30) years from the Effective Date and shall be automatically renewed for
each successive one-year period thereafter, unless terminated earlier in accordance with article

3.3 of this Agreement.

3.3 Termination

No termination shall become effective until the Parties have complied with all Applicable
Laws and Regulations applicable to such termination, including the filing with FERC of a notice
of termination of this Agreement (if required), which notice has been accepted for filing by
FERC.

3.3.1 The Interconnection Customer may terminate this Agreement at any time by
 giving the NYISO and Connecting Transmission Owner twenty (20) Business
 Days written notice. The NYISO may terminate this Agreement after the Small
 Generating Facility is Retired.

3.3.2 Any Party may terminate this Agreement after Default pursuant to article 7.6.

3.3.3 Upon termination of this Agreement, the Small Generating Facility will be
 disconnected from the New York State Transmission System or the Distribution
 System, as applicable. All costs required to effectuate such disconnection shall be
 borne by the terminating Party, unless such termination resulted from the non-
 terminating Party’s Default of this SGIA or such non-terminating Party otherwise
 is responsible for these costs under this SGIA.

3.3.4 The termination of this Agreement shall not relieve any Party of its liabilities and
 obligations, owed or continuing at the time of the termination. The

Interconnection Customer shall pay all amounts in excess of any deposit or other
security without interest within thirty (30) calendar days after receipt of the
invoice for such amounts. If the deposit or other security exceeds the invoice, the
Connecting Transmission Owner shall refund such excess within thirty (30)
calendar days of the invoice without interest. If the Interconnection Customer
disputes an amount to be paid the Interconnection Customer shall pay the disputed

11

SERVICE AGREEMENT NO. 2913

amount to the Connecting Transmission Owner or into an interest bearing escrow
account, pending resolution of the dispute in accordance with Article 10 of this
Agreement. To the extent the dispute is resolved in the Interconnection
Customer’s favor, that portion of the disputed amount will be returned to the
Interconnection Customer with interest at rates applicable to refunds under the
Commission’s regulations. To the extent the dispute is resolved in the
Connecting Transmission Owner’s favor, that portion of any escrowed funds and
interest will be released to the Connecting Transmission Owner.

3.3.5 The limitations of liability, indemnification and confidentiality provisions of this
 Agreement shall survive termination or expiration of this Agreement.

3.4 Temporary Disconnection

Temporary disconnection shall continue only for so long as reasonably necessary under
Good Utility Practice.

3.4.1 Emergency Conditions

“Emergency Condition” shall mean a condition or situation: (1) that in the judgment of
the Party making the claim is imminently likely to endanger life or property; or (2) that, in the
case of the NYISO or Connecting Transmission Owner, is imminently likely (as determined in a
non-discriminatory manner) to cause a material adverse effect on the security of, or damage to
the New York State Transmission System or Distribution System, the Connecting Transmission
Owner’s Interconnection Facilities or the electric systems of others to which the New York State
Transmission System or Distribution System is directly connected; or (3) that, in the case of the
Interconnection Customer, is imminently likely (as determined in a non-discriminatory manner)
to cause a material adverse effect on the security of, or damage to, the Small Generating Facility
or the Interconnection Customer’s Interconnection Facilities. Under Emergency Conditions, the
NYISO or Connecting Transmission Owner may immediately suspend interconnection service
and temporarily disconnect the Small Generating Facility. The NYISO or Connecting
Transmission Owner shall notify the Interconnection Customer promptly when it becomes aware
of an Emergency Condition that may reasonably be expected to affect the Interconnection
Customer’s operation of the Small Generating Facility. The Interconnection Customer shall
notify the NYISO and Connecting Transmission Owner promptly when it becomes aware of an
Emergency Condition that may reasonably be expected to affect the New York State
Transmission System or Distribution System or any Affected Systems. To the extent
information is known, the notification shall describe the Emergency Condition, the extent of the
damage or deficiency, the expected effect on the operation of each Party’s facilities and
operations, its anticipated duration, and the necessary corrective action.

3.4.2 Routine Maintenance, Construction, and Repair

The NYISO or Connecting Transmission Owner may interrupt interconnection service or
curtail the output of the Small Generating Facility and temporarily disconnect the Small
Generating Facility from the New York State Transmission System or Distribution System when
necessary for routine maintenance, construction, and repairs on the New York State

12

SERVICE AGREEMENT NO. 2913

Transmission System or Distribution System. The NYISO or the Connecting Transmission
Owner shall provide the Interconnection Customer with five (5) Business Days notice prior to
such interruption. The NYISO and Connecting Transmission Owner shall use Reasonable
Efforts to coordinate such reduction or temporary disconnection with the Interconnection
Customer.

3.4.3 Forced Outages

During any forced outage, the NYISO or Connecting Transmission Owner may suspend
interconnection service to the Interconnection Customer to effect immediate repairs on the New
York State Transmission System or the Distribution System. The NYISO shall use Reasonable
Efforts to provide the Interconnection Customer with prior notice. If prior notice is not given,
the NYISO shall, upon request, provide the Interconnection Customer written documentation
after the fact explaining the circumstances of the disconnection.

3.4.4 Adverse Operating Effects

The NYISO or Connecting Transmission Owner shall notify the Interconnection
Customer as soon as practicable if, based on Good Utility Practice, operation of the Small
Generating Facility may cause disruption or deterioration of service to other customers served
from the same electric system, or if operating the Small Generating Facility could cause damage
to the New York State Transmission System, the Distribution System or Affected Systems, or if
disconnection is otherwise required under Applicable Reliability Standards or the ISO OATT.
Supporting documentation used to reach the decision to disconnect shall be provided to the
Interconnection Customer upon request. If, after notice, the Interconnection Customer fails to
remedy the adverse operating effect within a reasonable time, the NYISO or Connecting
Transmission Owner may disconnect the Small Generating Facility. The NYISO or Connecting
Transmission Owner shall provide the Interconnection Customer with five Business Day notice
of such disconnection, unless the provisions of article 3.4.1 apply.

3.4.5 Modification of the Small Generating Facility

The Interconnection Customer must receive written authorization from the NYISO and
Connecting Transmission Owner before making any change to the Small Generating Facility that
may have a material impact on the safety or reliability of the New York State Transmission
System or the Distribution System. Such authorization shall not be unreasonably withheld.
Modifications shall be done in accordance with Good Utility Practice. If the Interconnection
Customer makes such modification without the prior written authorization of the NYISO and
Connecting Transmission Owner, the Connecting Transmission Owner shall have the right to
temporarily disconnect the Small Generating Facility. If disconnected, the Small Generating
Facility will not be reconnected until the unauthorized modifications are authorized or removed.

3.4.6 Reconnection

The Parties shall cooperate with each other to restore the Small Generating Facility,
Interconnection Facilities, and the New York State Transmission System and Distribution
System to their normal operating state as soon as reasonably practicable following a temporary
disconnection.

13

SERVICE AGREEMENT NO. 2913

Article 4 Cost Responsibility for Interconnection Facilities and Distribution Upgrades

4.1 Interconnection Facilities

4.1.1 The Interconnection Customer shall pay for the cost of the Interconnection
 Facilities itemized in Attachment 2 of this Agreement. The NYISO, in
 consultation with the Connecting Transmission Owner, shall provide a best
 estimate cost, including overheads, for the purchase and construction of its
 Interconnection Facilities and provide a detailed itemization of such costs. Costs
 associated with Interconnection Facilities may be shared with other entities that
 may benefit from such facilities by agreement of the Interconnection Customer,
 such other entities, the NYISO, and the Connecting Transmission Owner.

4.1.2 The Interconnection Customer shall be responsible for its share of all reasonable
 expenses, including overheads, associated with (1) owning, operating,
 maintaining, repairing, and replacing its own Interconnection Facilities, and
 (2) operating, maintaining, repairing, and replacing the Connecting Transmission
 Owner’s Interconnection Facilities, as set forth in Attachment 2 to this
 Agreement.

4.2 Distribution Upgrades

The Connecting Transmission Owner shall design, procure, construct, install, and own
the Distribution Upgrades described in Attachment 6 of this Agreement. If the Connecting
Transmission Owner and the Interconnection Customer agree, the Interconnection Customer may
construct Distribution Upgrades. The actual cost of the Distribution Upgrades, including
overheads, shall be directly assigned to the Interconnection Customer. The Interconnection
Customer shall be responsible for its share of all reasonable expenses, including overheads,
associated with owning, operating, maintaining, repairing, and replacing the Distribution
Upgrades, as set forth in Attachment 6 to this Agreement.

14

SERVICE AGREEMENT NO. 2913

Article 5 Cost Responsibility for System Upgrade Facilities and System Deliverability
 Upgrades

5.1 Applicability

No portion of this article 5 shall apply unless the interconnection of the Small Generating
Facility requires System Upgrade Facilities or System Deliverability Upgrades.

5.2 System Upgrades

The Connecting Transmission Owner shall procure, construct, install, and own the
System Upgrade Facilities and System Deliverability Upgrades described in Attachment 6 of this
Agreement. To the extent that design work is necessary in addition to that already accomplished
in the Class Year Interconnection Facilities Study for the Interconnection Customer, the
Connecting Transmission Owner shall perform or cause to be performed such work. If all the
Parties agree, the Interconnection Customer may construct System Upgrade Facilities and
System Deliverability Upgrades.

5.2.1 As described in Section 32.3.5.3 of the SGIP in Attachment Z of the ISO OATT,
 the responsibility of the Interconnection Customer for the cost of the System
 Upgrade Facilities and System Deliverability Upgrades described in Attachment 6
 of this Agreement shall be determined in accordance with Attachment S of the
 ISO OATT, as required by Section 32.3.5.3.2 of Attachment Z. The
 Interconnection Customer shall be responsible for all System Upgrade Facility
 costs as required by Section 32.3.5.3.2 of Attachment Z or its share of any System
 Upgrade Facilities and System Deliverability Upgrades costs resulting from the
 final Attachment S process, as applicable, and Attachment 6 to this Agreement
 shall be revised accordingly.

5.2.2 Pending the outcome of the Attachment S cost allocation process, if applicable,
 the Interconnection Customer may elect to proceed with the interconnection of its
 Small Generating Facility in accordance with Section 32.3.5.3 of the SGIP.

5.3 Special Provisions for Affected Systems

For the repayment of amounts advanced to the Affected System Operator for System
Upgrade Facilities or System Deliverability Upgrades, the Interconnection Customer and
Affected System Operator shall enter into an agreement that provides for such repayment, but
only if responsibility for the cost of such System Upgrade Facilities is not to be allocated in
accordance with Attachment S of the ISO OATT. The agreement shall specify the terms
governing payments to be made by the Interconnection Customer to the Affected System
Operator as well as the repayment by the Affected System Operator.

5.4 Limited Operation

If any of the Connecting Transmission Owner’s Interconnection Facilities or System
Upgrade Facilities or System Deliverability Upgrades are not reasonably expected to be
completed prior to the Commercial Operation Date of the Interconnection Customer’s Small

15

SERVICE AGREEMENT NO. 2913

Generating Facility, NYISO shall, upon the request and at the expense of Interconnection
Customer, in conjunction with the Connecting Transmission Owner, perform operating studies
on a timely basis to determine the extent to which the Interconnection Customer’s Small
Generating Facility and the Interconnection Customer’s Interconnection Facilities may operate
prior to the completion of the Connecting Transmission Owner’s Interconnection Facilities or
System Upgrade Facilities or System Deliverability Upgrades consistent with Applicable Laws
and Regulations, Applicable Reliability Standards, Good Utility Practice, and this Agreement.
Connecting Transmission Owner and NYISO shall permit Interconnection Customer to operate
the Interconnection Customer’s Small Generating Facility and the Interconnection Customer’s
Interconnection Facilities in accordance with the results of such studies.

16

SERVICE AGREEMENT NO. 2913

Article 6 Billing, Payment, Milestones, and Financial Security

6.1 Billing and Payment Procedures and Final Accounting

6.1.1 The Connecting Transmission Owner shall bill the Interconnection Customer for
 the design, engineering, construction, and procurement costs of Interconnection
 Facilities and Upgrades contemplated by this Agreement on a monthly basis, or as
 otherwise agreed by those Parties and as set forth in Section 2 of Attachment 4.
 The Interconnection Customer shall pay all invoice amounts within thirty (30)
 calendar days after receipt of the invoice.

6.1.2 Within three months of completing the construction and installation of the
 Connecting Transmission Owner’s Interconnection Facilities and/or Upgrades
 described in the Attachments to this Agreement, the Connecting Transmission
 Owner shall provide the Interconnection Customer with a final accounting report
 of any difference between (1) the Interconnection Customer’s cost responsibility
 for the actual cost of such facilities or Upgrades, and (2) the Interconnection
 Customer’s previous aggregate payments to the Connecting Transmission Owner
 for such facilities or Upgrades. If the Interconnection Customer’s cost
 responsibility exceeds its previous aggregate payments, the Connecting
 Transmission Owner shall invoice the Interconnection Customer for the amount
 due and the Interconnection Customer shall make payment to the Connecting
 Transmission Owner within thirty (30) calendar days. If the Interconnection
 Customer’s previous aggregate payments exceed its cost responsibility under this
 Agreement, the Connecting Transmission Owner shall refund to the

Interconnection Customer an amount equal to the difference within thirty (30)
calendar days of the final accounting report.

6.1.3 If the Interconnection Customer disputes an amount to be paid, the
 Interconnection Customer shall pay the disputed amount to the Connecting
 Transmission Owner or into an interest bearing escrow account, pending
 resolution of the dispute in accordance with Article 10 of this Agreement. To the
 extent the dispute is resolved in the Interconnection Customer’s favor, that portion
 of the disputed amount will be credited or returned to the Interconnection
 Customer with interest at rates applicable to refunds under the Commission’s
 regulations. To the extent the dispute is resolved in the Connecting Transmission
 Owner’s favor, that portion of any escrowed funds and interest will be released to
 the Connecting Transmission Owner.

6.2 Milestones

Subject to the provisions of the SGIP, the Parties shall agree on milestones for which
each Party is responsible and list them in Attachment 4 of this Agreement. A Party’s obligations
under this provision may be extended by agreement. If a Party anticipates that it will be unable
to meet a milestone for any reason other than a Force Majeure event, it shall immediately notify
the other Parties of the reason(s) for not meeting the milestone and: (1) propose the earliest
reasonable alternate date by which it can attain this and future milestones, and (2) requesting

17

SERVICE AGREEMENT NO. 2913

appropriate amendments to Attachment 4. The Party affected by the failure to meet a milestone
shall not unreasonably withhold agreement to such an amendment unless: (1) it will suffer
significant uncompensated economic or operational harm from the delay, (2) attainment of the
same milestone has previously been delayed, or (3) it has reason to believe that the delay in
meeting the milestone is intentional or unwarranted notwithstanding the circumstances explained
by the Party proposing the amendment.

6.3 Financial Security Arrangements

At least twenty (20) Business Days prior to the commencement of the design,
procurement, installation, or construction of a discrete portion of the Connecting Transmission
Owner’s Interconnection Facilities, the Interconnection Customer shall provide the Connecting
Transmission Owner, at the Interconnection Customer’s option, a guarantee, a surety bond, letter
of credit or other form of security that is reasonably acceptable to the Connecting Transmission
Owner and is consistent with the Uniform Commercial Code of the jurisdiction where the Point
of Interconnection is located. Such security for payment shall be in an amount sufficient to
cover the costs for constructing, designing, procuring, and installing the applicable portion of the
Connecting Transmission Owner’s Interconnection Facilities and shall be reduced on a dollar-
for-dollar basis for payments made to the Connecting Transmission Owner under this Agreement
during its term. The Connecting Transmission Owner may draw on any such security to the
extent that the Interconnection Customer fails to make any payments due under this Agreement.
In addition:

6.3.1 The guarantee must be made by an entity that meets the creditworthiness
 requirements of the Connecting Transmission Owner, and contain terms and
 conditions that guarantee payment of any amount that may be due from the
 Interconnection Customer, up to an agreed-to maximum amount.

6.3.2 The letter of credit or surety bond must be issued by a financial institution or
 insurer reasonably acceptable to the Connecting Transmission Owner and must
 specify a reasonable expiration date.

6.3.3 Attachment Z to the ISO OATT shall govern the security that an Interconnection
 Customer provides for System Upgrade Facilities identified through

Interconnection Studies under the Small Generator Interconnection Procedures.

6.3.4 Notwithstanding the above, Security posted for System Upgrade Facilities for a
 Small Generating Facility required to enter the Class Year process, or cash or
 Security provided for System Deliverability Upgrades, shall meet the

requirements for Security contained in Attachment S to the ISO OATT.

18

SERVICE AGREEMENT NO. 2913

Article 7 Assignment, Liability, Indemnity, Force Majeure, Consequential Damages,
 and Default

7.1 Assignment

This Agreement, and each and every term and condition hereof, shall be binding upon
and inure to the benefit of the Parties hereto and their respective successors and assigns. This
Agreement may be assigned by any Party upon fifteen (15) Business Days prior written notice
and opportunity to object by the other Parties; provided that:

7.1.1 A Party may assign this Agreement without the consent of the other Parties to any
 affiliate of the assigning Party with an equal or greater credit rating and with the
 legal authority and operational ability to satisfy the obligations of the assigning
 Party under this Agreement, provided that the Interconnection Customer promptly
 notifies the NYISO and the Connecting Transmission Owner of any such
 assignment. A Party may assign this Agreement without the consent of the other
 Parties in connection with the sale, merger, restructuring, or transfer of a
 substantial portion of all of its assets, including the Interconnection Facilities it
 owns, so long as the assignee in such a transaction directly assumes all rights,
 duties and obligation arising under this Agreement.

7.1.2 The Interconnection Customer shall have the right to assign this Agreement,
 without the consent of the NYISO or Connecting Transmission Owner, for
 collateral security purposes to aid in providing financing for the Small Generating
 Facility.

7.1.3 Any attempted assignment that violates this article is void and ineffective.
 Assignment shall not relieve a Party of its obligations, nor shall a Party’s
 obligations be enlarged, in whole or in part, by reason thereof. An assignee is
 responsible for meeting the same financial, credit, and insurance obligations as
 the Interconnection Customer. Where required, consent to assignment will not be
 unreasonably withheld, conditioned or delayed.

7.2 Limitation of Liability

Each Party’s liability to the other Parties for any loss, cost, claim, injury, liability, or
expense, including reasonable attorney’s fees, relating to or arising from any act or omission in
its performance of this Agreement, shall be limited to the amount of direct damage actually
incurred. In no event shall any Party be liable to the other Parties for any indirect, special,
consequential, or punitive damages.

7.3 Indemnity

7.3.1 This provision protects each Party from liability incurred to third parties as a
 result of carrying out the provisions of this Agreement. Liability under this
 provision is exempt from the general limitations on liability found in article 7.2.

19

SERVICE AGREEMENT NO. 2913

7.3.2 Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and
 hold harmless the other Parties (each an “ Indemnified Party”) from, any and all
 damages, losses, claims, including claims and actions relating to injury to or death
 of any person or damage to property, the alleged violation of any Environmental
 Law, or the release or threatened release of any Hazardous Substance, demand,
 suits, recoveries, costs and expenses, court costs, attorney fees, and all other
 obligations by or to third parties (any and all of these a “Loss”), arising out of or
 resulting from: (i) the Indemnified Party’s performance under this Agreement on
 behalf of the Indemnifying Party, except in cases where the Indemnifying Party
 can demonstrate that the Loss of the Indemnified Party was caused by the gross
 negligence or intentional wrongdoing by the Indemnified Party, or (ii) the
 violation by the Indemnifying Party of any Environmental Law or the release by
 the Indemnifying Party of a Hazardous Substance.

7.3.3 If a Party is entitled to indemnification under this article as a result of a claim by a
 third party, and the Indemnifying Party fails, after notice and reasonable
 opportunity to proceed under this article, to assume the defense of such claim,
 such Indemnified Party may at the expense of the Indemnifying Party contest,
 settle or consent to the entry of any judgment with respect to, or pay in full, such
 claim.

7.3.4 If an Indemnifying Party is obligated to indemnify and hold any Indemnified
 Party harmless under this article, the amount owing to the Indemnified Party shall
 be the amount of such Indemnified Party’s actual loss, net of any insurance or
 other recovery.

7.3.5 Promptly after receipt by an Indemnified Party of any claim or notice of the
 commencement of any action or administrative or legal proceeding or

investigation as to which the indemnity provided for in this article may apply, the
Indemnified Party shall notify the Indemnifying Party of such fact. Any failure of
or delay in such notification shall not affect a Party’s indemnification obligation
unless such failure or delay is materially prejudicial to the Indemnifying Party.

7.4 Consequential Damages

Other than as expressly provided for in this Agreement, no Party shall be liable under any
provision of this Agreement for any losses, damages, costs or expenses for any special, indirect,
incidental, consequential, or punitive damages, including but not limited to loss of profit or
revenue, loss of the use of equipment, cost of capital, cost of temporary equipment or services,
whether based in whole or in part in contract, in tort, including negligence, strict liability, or any
other theory of liability; provided, however, that damages for which a Party may be liable to
another Party under another agreement will not be considered to be special, indirect, incidental,
or consequential damages hereunder.

20

SERVICE AGREEMENT NO. 2913

7.5 Force Majeure

7.5.1 As used in this article, a “Force Majeure Event” shall mean “any act of God, labor
 disturbance, act of the public enemy, war, insurrection, riot, fire, storm or flood,
 explosion, breakage or accident to machinery or equipment, any order, regulation
 or restriction imposed by governmental, military or lawfully established civilian
 authorities, or any other cause beyond a Party’s control. A Force Majeure Event
 does not include an act of negligence or intentional wrongdoing.” For the
 purposes of this article, this definition of Force Majeure shall supersede the
 definitions of Force Majeure set out in Section 32.10.1 of the ISO OATT.

7.5.2 If a Force Majeure Event prevents a Party from fulfilling any obligations under
 this Agreement, the Party affected by the Force Majeure Event (“Affected Party”)
 shall promptly notify the other Parties, either in writing or via the telephone, of
 the existence of the Force Majeure Event. The notification must specify in
 reasonable detail the circumstances of the Force Majeure Event, its expected
 duration, and the steps that the Affected Party is taking to mitigate the effects of
 the event on its performance. The Affected Party shall keep the other Parties
 informed on a continuing basis of developments relating to the Force Majeure
 Event until the event ends. The Affected Party will be entitled to suspend or
 modify its performance of obligations under this Agreement (other than the
 obligation to make payments) only to the extent that the effect of the Force
 Majeure Event cannot be mitigated by the use of Reasonable Efforts. The
 Affected Party will use Reasonable Efforts to resume its performance as soon as
 possible.

7.6 Breach and Default

7.6.1 No Breach of this Agreement shall exist where such failure to discharge an
 obligation (other than the payment of money) is the result of a Force Majeure
 Event or the result of an act or omission of the other Parties. Upon a Breach, the
 non-breaching Party shall give written notice of such Breach to the Breaching
 Party. Except as provided in article 7.6.2, the Breaching Party shall have sixty
 (60) calendar days from receipt of the Breach notice within which to cure such
 Breach; provided however, if such Breach is not capable of cure within sixty (60)
 calendar days, the Breaching Party shall commence such cure within twenty (20)
 calendar days after notice and continuously and diligently complete such cure
 within six months from receipt of the Breach notice; and, if cured within such
 time, the Breach specified in such notice shall cease to exist.

7.6.2 If a Breach is not cured as provided in this article, or if a Breach is not capable of
 being cured within the period provided for herein, a Default shall exist and the
 non-defaulting Parties acting together shall thereafter have the right to terminate
 this Agreement, in accordance with article 3.3 hereof, by written notice to the
 defaulting Party at any time until cure occurs, and be relieved of any further
 obligation hereunder and, whether or not those Parties terminate this Agreement,
 to recover from the defaulting Party all amounts due hereunder, plus all other

21

SERVICE AGREEMENT NO. 2913

damages and remedies to which they are entitled at law or in equity. The
provisions of this article shall survive termination of this Agreement.

7.6.3 In cases where the Interconnection Customer has elected to proceed under
 Section 32.3.5.3 of the SGIP, if the Interconnection Request is withdrawn or
 deemed withdrawn pursuant to the SGIP during the term of this Agreement, this
 Agreement shall terminate.

22

SERVICE AGREEMENT NO. 2913

Article 8 Insurance

8.1 The Interconnection Customer shall, at its own expense, maintain in force general
 liability insurance without any exclusion for liabilities related to the interconnection
 undertaken pursuant to this Agreement. The amount of such insurance shall be sufficient
 to insure against all reasonably foreseeable direct liabilities given the size and nature of
 the generating equipment being interconnected, the interconnection itself, and the
 characteristics of the system to which the interconnection is made. Such insurance
 coverage is specified in Attachment 7 to this Agreement. The Interconnection Customer
 shall obtain additional insurance only if necessary as a function of owning and operating
 a generating facility. Such insurance shall be obtained from an insurance provider
 authorized to do business in New York State where the interconnection is located.
 Certification that such insurance is in effect shall be provided upon request of the
 Connecting Transmission Owner, except that the Interconnection Customer shall show
 proof of insurance to the Connecting Transmission Owner no later than ten (10) Business
 Days prior to the anticipated commercial operation date. An Interconnection Customer
 of sufficient creditworthiness may propose to self-insure for such liabilities, and such a
 proposal shall not be unreasonably rejected.

8.2 The NYISO and Connecting Transmission Owner agree to maintain general liability
 insurance or self-insurance consistent with the existing commercial practice. Such
 insurance or self-insurance shall not exclude the liabilities undertaken pursuant to this
 Agreement.

8.3 The Parties further agree to notify one another whenever an accident or incident occurs
 resulting in any injuries or damages that are included within the scope of coverage of
 such insurance, whether or not such coverage is sought.

23

SERVICE AGREEMENT NO. 2913

Article 9 Confidentiality

9.1 Confidential Information shall mean any confidential and/or proprietary information
 provided by one Party to the other Party that is clearly marked or otherwise designated
 “Confidential.” For purposes of this Agreement all design, operating specifications, and
 metering data provided by the Interconnection Customer shall be deemed Confidential
 Information regardless of whether it is clearly marked or otherwise designated as such.
 Confidential Information shall include, without limitation, information designated as
 such by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

9.2 Confidential Information does not include information previously in the public domain,
 required to be publicly submitted or divulged by Governmental Authorities (after notice
 to the other Party and after exhausting any opportunity to oppose such publication or
 release), or necessary to be divulged in an action to enforce this Agreement. Each Party
 receiving Confidential Information shall hold such information in confidence and shall
 not disclose it to any third party nor to the public without the prior written authorization
 from the Party providing that information, except to fulfill obligations under this
 Agreement, or to fulfill legal or regulatory requirements.

9.2.1 Each Party shall employ at least the same standard of care to protect Confidential
 Information obtained from the other Parties as it employs to protect its own
 Confidential Information.

9.2.2 Each Party is entitled to equitable relief, by injunction or otherwise, to enforce its
 rights under this provision to prevent the release of Confidential Information
 without bond or proof of damages, and may seek other remedies available at law
 or in equity for breach of this provision.

9.3 Notwithstanding anything in this article to the contrary, and pursuant to 18 CFR §
 lb.20, if FERC, during the course of an investigation or otherwise, requests
 information from one of the Parties that is otherwise required to be maintained in
 confidence pursuant to this Agreement, the Party shall provide the requested
 information to FERC, within the time provided for in the request for information.
 In providing the information to FERC, the Party may, consistent with 18 CFR §
 388.112, request that the information be treated as confidential and non-public by
 FERC and that the information be withheld from public disclosure. Each Party is
 prohibited from notifying the other Parties to this Agreement prior to the release
 of the Confidential Information to FERC. The Party shall notify the other Parties
 to this Agreement when it is notified by FERC that a request to release
 Confidential Information has been received by FERC, at which time either of the
 Parties may respond before such information would be made public, pursuant to
 18 CFR § 388.112. Requests from a state regulatory body conducting a
 confidential investigation shall be treated in a similar manner if consistent with
 the applicable state rules and regulations.

9.4 Consistent with the provisions of this article 9, the Parties to this Agreement will
 cooperate in good faith to provide each other, Affected Systems, Affected System

24

SERVICE AGREEMENT NO. 2913

Operators, and state and federal regulators the information necessary to carry out
the terms of the SGIP and this Agreement.

25

SERVICE AGREEMENT NO. 2913

Article 10 Disputes

10.1 The NYISO, Connecting Transmission Owner and Interconnection Customer agree to
 attempt to resolve all disputes arising out of the interconnection process according to the
 provisions of this article.

10.2 In the event of a dispute, the Parties will first attempt to promptly resolve it on an
 informal basis. The NYISO will be available to the Interconnection Customer and
 Connecting Transmission Owner to help resolve any dispute that arises with respect to
 performance under this Agreement. If the Parties cannot promptly resolve the dispute on
 an informal basis, then any Party shall provide the other Parties with a written Notice of
 Dispute. Such notice shall describe in detail the nature of the dispute.

10.3 If the dispute has not been resolved within two (2) Business Days after receipt of the
 notice, any Party may contact FERC’s Dispute Resolution Service (“DRS”) for assistance
 in resolving the dispute.

10.4 The DRS will assist the Parties in either resolving their dispute or in selecting an
 appropriate dispute resolution venue (e.g., mediation, settlement judge, early neutral
 evaluation, or technical expert) to assist the Parties in resolving their dispute. The result
 of this dispute resolution process will be binding only if the Parties agree in advance.
 DRS can be reached at 1-877-337-2237 or via the internet at

http://www.ferc.gov/legal/adr.asp.

10.5 Each Party agrees to conduct all negotiations in good faith and will be responsible for
 one-third of any costs paid to neutral third-parties.

10.6 If any Party elects to seek assistance from the DRS, or if the attempted dispute resolution
 fails, then any Party may exercise whatever rights and remedies it may have in equity or
 law consistent with the terms of this Agreement.

26

SERVICE AGREEMENT NO. 2913

Article 11 Taxes

11.1 The Parties agree to follow all applicable tax laws and regulations, consistent with FERC
 policy and Internal Revenue Service requirements.

11.2 Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.
 Nothing in this Agreement is intended to adversely affect the tax status of any Party
 including the status of NYISO, or the status of any Connecting Transmission Owner with
 respect to the issuance of bonds including, but not limited to, Local Furnishing Bonds.
 Notwithstanding any other provisions of this Agreement, LIPA, NYPA and Consolidated
 Edison Company of New York, Inc. shall not be required to comply with any provisions
 of this Agreement that would result in the loss of tax-exempt status of any of their Tax-
 Exempt Bonds or impair their ability to issue future tax-exempt obligations. For
 purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long
 Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc.,
 the interest on which is not included in gross income under the Internal Revenue Code.

11.3 LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA,
 from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s
 general ratemaking authority.

11.4 Any payments due to the Connecting Transmission Owner under this Agreement shall be
 adjusted to include any tax liability incurred by the Connecting Transmission Owner with
 respect to the interconnection request which is the subject of this Agreement. Such
 adjustments shall be made in accordance with the provisions of Article 5.17 of the LGIA
 in Attachment X of the ISO OATT. Except where otherwise noted, all costs, deposits,
 financial obligations and the like specified in this Agreement shall be assumed not to
 reflect the impact of applicable taxes.

27

SERVICE AGREEMENT NO. 2913

Article 12 Miscellaneous

12.1 Governing Law, Regulatory Authority, and Rules

The validity, interpretation and enforcement of this Agreement and each of its provisions
shall be governed by the laws of the state of New York, without regard to its conflicts of law
principles. This Agreement is subject to all Applicable Laws and Regulations. Each Party
expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, or
regulations of a Governmental Authority.

12.2 Amendment

The Parties may amend this Agreement by a written instrument duly executed by the
Parties, or under article 12.12 of this Agreement.

12.3 No Third-Party Beneficiaries

This Agreement is not intended to and does not create rights, remedies, or benefits of any
character whatsoever in favor of any persons, corporations, associations, or entities other than the
Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their
successors in interest and where permitted, their assigns. Notwithstanding the foregoing, any
subcontractor of the Connecting Transmission Owner or NYISO assisting either of those Parties
with the Interconnection Request covered by this Agreement shall be entitled to the benefits of
indemnification provided for under Article 7.3 of this Agreement and the limitation of liability
provided for in Article 7.2 of this Agreement.

12.4 Waiver

12.4.1 The failure of a Party to this Agreement to insist, on any occasion, upon strict
 performance of any provision of this Agreement will not be considered a waiver
 of any obligation, right, or duty of, or imposed upon, such Party.

12.4.2 Any waiver at any time by a Party of its rights with respect to this Agreement
 shall not be deemed a continuing waiver or a waiver with respect to any other
 failure to comply with any other obligation, right, duty of this Agreement.
 Termination or default of this Agreement for any reason by Interconnection
 Customer shall not constitute a waiver of the Interconnection Customer’s legal
 rights to obtain an interconnection from the NYISO. Any waiver of this
 Agreement shall, if requested, be provided in writing.

12.5 Entire Agreement

This Agreement, including all Attachments, constitutes the entire agreement between the
Parties with reference to the subject matter hereof, and supersedes all prior and contemporaneous
understandings or agreements, oral or written, between the Parties with respect to the subject
matter of this Agreement. There are no other agreements, representations, warranties, or
covenants which constitute any part of the consideration for, or any condition to, any Party’s
compliance with its obligations under this Agreement.

28

SERVICE AGREEMENT NO. 2913

12.6 Multiple Counterparts

This Agreement may be executed in two or more counterparts, each of which is deemed
an original but all constitute one and the same instrument.

12.7 No Partnership

This Agreement shall not be interpreted or construed to create an association, joint
venture, agency relationship, or partnership between the Parties or to impose any partnership
obligation or partnership liability upon any Party. No Party shall have any right, power or
authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an
agent or representative of, or to otherwise bind, another Party.

12.8 Severability

If any provision or portion of this Agreement shall for any reason be held or adjudged to
be invalid or illegal or unenforceable by any court of competent jurisdiction or other
Governmental Authority, (1) such portion or provision shall be deemed separate and
independent, (2) the Parties shall negotiate in good faith to restore insofar as practicable the
benefits to each Party that were affected by such ruling, and (3) the remainder of this Agreement
shall remain in full force and effect.

12.9 Security Arrangements

Infrastructure security of electric system equipment and operations and control hardware
and software is essential to ensure day-to-day reliability and operational security. FERC expects
the NYISO, the Connecting Transmission Owner, Market Participants, and Interconnection
Customers interconnected to electric systems to comply with the recommendations offered by
the President’s Critical Infrastructure Protection Board and, eventually, best practice
recommendations from the electric reliability authority. All public utilities are expected to meet
basic standards for system infrastructure and operational security, including physical,
operational, and cyber-security practices.

12.10 Environmental Releases

Each Party shall notify the other Parties, first orally and then in writing, of the release of
any hazardous substances, any asbestos or lead abatement activities, or any type of remediation
activities related to the Small Generating Facility or the Interconnection Facilities, each of which
may reasonably be expected to affect the other Parties. The notifying Party shall: (1) provide the
notice as soon as practicable, provided such Party makes a good faith effort to provide the notice
no later than 24 hours after such Party becomes aware of the occurrence, and (2) promptly
furnish to the other Parties copies of any publicly available reports filed with any governmental
authorities addressing such events.

12.11 Subcontractors

Nothing in this Agreement shall prevent a Party from utilizing the services of any subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,

29

SERVICE AGREEMENT NO. 2913

however, that each Party shall require its subcontractors to comply with all applicable terms and
conditions of this Agreement in providing such services and each Party shall remain primarily
liable to the other Parties for the performance of such subcontractor.

12.11.1 The creation of any subcontract relationship shall not relieve the hiring
 Party of any of its obligations under this Agreement. The hiring Party
 shall be fully responsible to the other Parties to the extent provided for in
 Articles 7.2 and 7.3 above for the acts or omissions of any subcontractor
 the hiring Party hires as if no subcontract had been made; provided,
 however, that in no event shall the NYISO or Connecting Transmission
 Owner be liable for the actions or inactions of the Interconnection
 Customer or its subcontractors with respect to obligations of the
 Interconnection Customer under this Agreement. Any applicable
 obligation imposed by this Agreement upon the hiring Party shall be
 equally binding upon, and shall be construed as having application to, any
 subcontractor of such Party.

12.11.2 The obligations under this article will not be limited in any way by any

limitation of subcontractor’s insurance.

12.12 Reservation of Rights

Nothing in this Agreement shall alter the right of the NYISO or Connecting Transmission
Owner to make unilateral filings with FERC to modify this Agreement with respect to any rates,
terms and conditions, charges, classifications of service, rule or regulation under Section 205 or
any other applicable provision of the Federal Power Act and FERC’s rules and regulations
thereunder which rights are expressly reserved herein, and the existing rights of the Interconnection Customer to make a unilateral filing with FERC to modify this Agreement under
any applicable provision of the Federal Power Act and FERC’s rules and regulations are also
expressly reserved herein; provided that each Party shall have the right to protest any such filing
by another Party and to participate fully in any proceeding before FERC in which such
modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties
or of FERC under Sections 205 or 206 of the Federal Power Act and FERC’s rules and
regulations, except to the extent that the Parties otherwise agree as provided herein.

12.13 Modifications Related to NYISO’s Compliance with Order No. 2023

If, as part of the NYISO’s compliance proceeding at the Commission in response to
Order No. 2023, the Commission directs that the NYISO modify the pro forma Standard Small
Generator Interconnection Agreement located in Appendix 7 of Attachment Z of the ISO OATT,
the Parties shall amend and restate this Agreement to incorporate the modifications; provided,
however, the Parties may agree to include in the amended and restated agreement non-
conforming changes to any terms of the pro forma Standard Small Generator Interconnection
Agreement that have been modified to comply with the Commission’s order, which non-
conforming modifications must be filed with the Commission for its acceptance.

30

SERVICE AGREEMENT NO. 2913

Article 13 Notices

13.1 General

Unless otherwise provided in this Agreement, any written notice, demand, or request
required or authorized in connection with this Agreement shall be deemed properly given if
delivered in person, delivered by recognized national courier service, or sent by first class mail,
postage prepaid, to the person specified below:

If to the Interconnection Customer:

BR Project 1 LLC

Attention: CleanCapital Interconnection Project Manager
Address: 228 Park Ave S

PMB 23351

City: New York State: NY Zip: 10003-1502
Phone: (845)594-7629

Email: ascott@cleancapital.com
 interconnection@cleancapital.com

If to the Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration & Commercial Services NY
Address: 2 Hanson Place

City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171

Email: Vishal.Ahirrao@nationalgrid.com

If to the NYISO:

Before Commercial Operation of the Small Generating Facility

New York Independent System Operator, Inc.
Attention: Vice President, System and Resource Planning
Address: 10 Krey Boulevard

City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000

After Commercial Operation

New York Independent System Operator, Inc.
Attention: Vice President, Operations
Address: 10 Krey Boulevard

City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000

31

SERVICE AGREEMENT NO. 2913

13.2 Billing and Payment

Billings and payments shall be sent to the addresses set out below:

Interconnection Customer:

BR Project 1 LLC

Attention: CleanCapital Interconnection Project Manager
Address: 228 Park S

PMB 23351

City: New York State: NY Zip: 10003-1502
Phone: (845) 594-7629

Email: ascott@cleancapital.com

Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration & Commercial Services NY
Address: 2 Hanson Place

City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171

Email: Vishal.Ahirrao@nationalgrid.com

13.3 Alternative Forms of Notice

Any notice or request required or permitted to be given by either Party to the other and
not required by this Agreement to be given in writing may be so given by telephone or e-mail to
the telephone numbers and e-mail addresses set out below:

If to the Interconnection Customer:

BR Project 1 LLC

Attention: CleanCapital, Legal
Address: 228 Park Ave S

PMB 23351

City: New York State: NY Zip: 10003-1502
Phone: (845) 594-7629

E-mail: legal@cleancapital.com

If to the Connecting Transmission Owner:

Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration & Commercial Services NY
Address: 2 Hanson Place

City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171

32

SERVICE AGREEMENT NO. 2913

Email: Vishal.Ahirrao@nationalgrid.com

If to the NYISO:

New York Independent System Operator, Inc.
Attention: Vice President, Operations
Address: 10 Krey Boulevard

City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000

E-mail: interconnectionsupport@nyiso.com

13.4 Designated Operating Representative

The Parties may also designate operating representatives to conduct the communications
which may be necessary or convenient for the administration of this Agreement. This person
will also serve as the point of contact with respect to operations and maintenance of the Party’s
facilities.

Interconnection Customer’s Operating Representative:

BR Project 1 LLC

Attention: CleanCapital, Technical Asset Management
Address: 228 Park Ave S

PMB 23351

City: New York State: NY Zip: 10003-1502
Phone: (646)-992-3607

E-mail: amtech@cleancapital.com

Connecting Transmission Owner’s Operating Representative:

Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration & Commercial Services NY
Address: 2 Hanson Place

City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171

Email: Vishal.Ahirrao@nationalgrid.com

NYISO’s Operating Representative:

New York Independent System Operator, Inc.
Attention: Vice President, Operations
Address: 10 Krey Boulevard

City: Rensselaer State: NY Zip: 12144
Phone: (518) 356-6000

E-mail: interconnectionsupport@nyiso.com

33

SERVICE AGREEMENT NO. 2913

13.5 Changes to the Notice Information

Either Party may change this information by giving five (5) Business Days written notice
prior to the effective date of the change.

34

SERVICE AGREEMENT NO. 2913

Article 14 Signatures

IN WITNESS WHEREOF, the Parties have caused this Agreement to be executed by their
respective duly authorized representatives.

For the New York Independent System Operator, Inc.

By:

Name: _________________________

Title: __________________________

Date: __________________________

For Niagara Mohawk Power Corporation d/b/a National Grid

By:

Name: _________________________

Title: __________________________

Date: __________________________

For BR Project 1 LLC

By:

Name: __________________________

Title: ___________________________

Date: ___________________________

35

SERVICE AGREEMENT NO. 2913

Attachment 1

Glossary of Terms

Affected System – An electric system other than the transmission system owned, controlled or
operated by the Connecting Transmission Owner that may be affected by the proposed
interconnection.

Affected System Operator – Affected System Operator shall mean the operator of any Affected System.

Affected Transmission Owner – The New York public utility or authority (or its designated
agent) other than the Connecting Transmission Owner that: (i) owns facilities used for the
transmission of Energy in interstate commerce and provides Transmission Service under the
Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State
Transmission System where System Deliverability Upgrades or System Upgrade Facilities are
installed pursuant to Attachment Z and Attachment S to the ISO OATT.

Applicable Laws and Regulations – All duly promulgated applicable federal, state and local
laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or
administrative orders, permits and other duly authorized actions of any Governmental Authority,
including but not limited to Environmental Law.

Applicable Reliability Standards – The criteria, requirements and guidelines of the North
American Electric Reliability Council, the Northeast Power Coordinating Council, the New York
State Reliability Council and related and successor organizations, or the Transmission District to
which the Interconnection Customer’s Small Generating Facility is directly interconnected, as
those criteria, requirements and guidelines are amended and modified and in effect from time to
time; provided that no Party shall waive its right to challenge the applicability of or validity of
any criterion, requirement or guideline as applied to it in the context of Attachment Z to the ISO
OATT and this Agreement. For the purposes of this Agreement, this definition of Applicable
Reliability Standards shall supersede the definition of Applicable Reliability Standards set out in
Attachment X to the ISO OATT.

Balancing Authority – An entity that integrates resource plans ahead of time, maintains demand
and resource balance within a Balancing Authority Area, and supports interconnection frequency
in real time.

Balancing Authority Area – The collection of generation, transmission, and loads within the
metered boundaries of the Balancing Authority. The Balancing Authority maintains load-
resource balance within this area.

Base Case – The base case power flow, short circuit, and stability data bases used for the
Interconnection Studies by NYISO, Connecting Transmission Owner or Interconnection
Customer; described in Section 32.2.3 of the Large Facility Interconnection Procedures, and
updated consistent with the rules set forth in Section 25.5.5.1 of Attachment S to the OATT at
the start of each Interconnection Study under the Small Generator Interconnection Procedures.

1-1

SERVICE AGREEMENT NO. 2913

Breach - The failure of a Party to perform or observe any material term or condition of this Agreement.

Business Day – Monday through Friday, excluding federal holidays.

Capacity Resource Interconnection Service – The service provided by NYISO to
Interconnection Customers that satisfy the NYISO Deliverability Interconnection Standard or
that are otherwise eligible to receive CRIS in accordance with Attachment S to the ISO OATT;
such service being one of the eligibility requirements for participation as a NYISO Installed
Capacity Supplier.

Commercial Operation shall mean the status of the Small Generating Facility that has
commenced generating electricity for sale, excluding electricity generated during Trial
Operation, notice of which must be provided to the NYISO in the form of Attachment 9 to this
Agreement.

Commercial Operation Date of a Small Generating Facility shall mean the date on which the
Large Generating Facility commences Commercial Operation as agreed to by the Parties, notice
of which must be provided to the NYISO in the form of Attachment 9 to this Agreement.

Connecting Transmission Owner – The New York public utility or authority (or its designated
agent) that: (i) owns facilities used for the transmission of Energy in interstate commerce and
provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an
interest in the portion of the New York State Transmission System or Distribution System at the
Point of Interconnection, and (iii) is a Party to the Standard Small Generator Interconnection
Agreement.

Default – The failure of a Party in Breach of this Agreement to cure such Breach under the Small Generator Interconnection Agreement.

Distribution System – The Transmission Owner’s facilities and equipment used to distribute
electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s Large Facility
Interconnection Procedures in Attachment X to the ISO OATT or Small Generator
Interconnection Procedures in Attachment Z to the ISO OATT under FERC Order Nos. 2003
and/or 2006. For the purpose of this Agreement, the term Distribution System shall not include
LIPA’s distribution facilities.

Distribution Upgrades – The additions, modifications, and upgrades to the Connecting
Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate
interconnection of the Small Generating Facility and render the transmission service necessary to
effect the Interconnection Customer’s wholesale sale of electricity in interstate commerce.
Distribution Upgrades do not include Interconnection Facilities or System Upgrade Facilities or
System Deliverability Upgrades.

Energy Resource Interconnection Service – The service provided by NYISO to interconnect
the Interconnection Customer’s Small Generating Facility to the New York State Transmission
System or Distribution System in accordance with the NYISO Minimum Interconnection

1-2

SERVICE AGREEMENT NO. 2913

Standard, to enable the New York State Transmission System to receive Energy and Ancillary
Services from the Small Generating Facility, pursuant to the terms of the ISO OATT.

Force Majeure – Any act of God, labor disturbance, act of the public enemy, war, insurrection,
riot, fire, storm or flood, explosion, breakage or accident to machinery or equipment, any order,
regulation or restriction imposed by governmental, military or lawfully established civilian
authorities, or any other cause beyond a Party’s control. A Force Majeure event does not include
an act of negligence or intentional wrongdoing. For the purposes of this Agreement, this
definition of Force Majeure shall supersede the definitions of Force Majeure set out in Section

32.2.11 of the NYISO Open Access Transmission Tariff.

Good Utility Practice – Any of the practices, methods and acts engaged in or approved by a
significant portion of the electric industry during the relevant time period, or any of the practices,
methods and acts which, in the exercise of reasonable judgment in light of the facts known at the
time the decision was made, could have been expected to accomplish the desired result at a
reasonable cost consistent with good business practices, reliability, safety and expedition. Good
Utility Practice is not intended to be limited to the optimum practice, method, or act to the
exclusion of all others, but rather to be acceptable practices, methods, or acts generally accepted
in the region.

Governmental Authority – Any federal, state, local or other governmental regulatory or
administrative agency, court, commission, department, board, or other governmental subdivision,
legislature, rulemaking board, tribunal, or other governmental authority having jurisdiction over
the Parties, their respective facilities, or the respective services they provide, and exercising or
entitled to exercise any administrative, executive, police, or taxing authority or power; provided,
however, that such term does not include the Interconnection Customer, NYISO, Affected
Transmission Owner, Connecting Transmission Owner or any Affiliate thereof.

Initial Synchronization Date shall mean the date upon which the Small Generating Facility is
initially synchronized and upon which Trial Operation begins, notice of which must be provided
to the NYISO in the form of Attachment 9.

In-Service Date shall mean the date upon which the Developer reasonably expects it will be
ready to begin use of the Connecting Transmission Owner’s Interconnection Facilities to obtain
back feed power.

Interconnection Customer – Any entity, including the Transmission Owner or any of the
affiliates or subsidiaries, that proposes to interconnect its Small Generating Facility with the New
York State Transmission System or the Distribution System.

Interconnection Facilities – The Connecting Transmission Owner’s Interconnection Facilities
and the Interconnection Customer’s Interconnection Facilities. Collectively, Interconnection
Facilities include all facilities and equipment between the Small Generating Facility and the
Point of Interconnection, including any modification, additions or upgrades that are necessary to
physically and electrically interconnect the Small Generating Facility to the New York State
Transmission System or the Distribution System. Interconnection Facilities are sole use facilities
and shall not include Distribution Upgrades or System Upgrade Facilities.

1-3

SERVICE AGREEMENT NO. 2913

Interconnection Request – The Interconnection Customer’s request, in accordance with the
Tariff, to interconnect a new Small Generating Facility, or to materially increase the capacity of,
or make a material modification to the operating characteristics of, an existing Small Generating
Facility that is interconnected with the New York State Transmission System or the Distribution
System. For the purposes of this Agreement, this definition of Interconnection Request shall
supersede the definition of Interconnection Request set out in Attachment X to the ISO OATT.

Interconnection Study – Any study required to be performed under Sections 32.2 or 32.3 of the SGIP.

Material Modification – A modification that has a material impact on the cost or timing of any Interconnection Request with a later queue priority date.

New York State Transmission System – The entire New York State electric transmission
system, which includes: (i) the Transmission Facilities under ISO Operational Control; (ii) the
Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities
within the New York Control Area.

NYISO Deliverability Interconnection Standard – The standard that must be met, unless
otherwise provided for by Attachment S to the ISO OATT, by any of the following requesting
CRIS: (i) any generation facility larger than 2MW in order for that facility to obtain CRIS; (ii)
any Class Year Transmission Project proposing to interconnect to the New York State
Transmission System and receive Unforced Capacity Delivery Rights; (iii) any entity requesting
External CRIS Rights, and (iv) any entity requesting a CRIS transfer pursuant to Section 25.9.5
of Attachment S to the ISO OATT. To meet the NYISO Deliverability Interconnection
Standard, the Interconnection Customer must, in accordance with the rules in Attachment S to
the ISO OATT, fund or commit to fund any System Deliverability Upgrades identified for its
Project in the Class Year Deliverability Study.

NYISO Minimum Interconnection Standard – The reliability standard that must be met by
any Large Facility that is subject to NYISO’s Large Facility Interconnection Procedures in
Attachment X to the ISO OATT or Small Generating Facility that is subject to the NYISO’s
Small Generator Interconnection Procedures in this Attachment Z, that is proposing to connect to
the New York State Transmission System or Distribution System, to obtain ERIS. The
Minimum Interconnection Standard is designed to ensure reliable access by the proposed Project
to the New York State Transmission System or to the Distribution System. The Minimum
Interconnection Standard does not impose any deliverability test or deliverability requirement on
the proposed interconnection.

Operating Requirements – Any operating and technical requirements that may be applicable
due to Regional Transmission Organization, Independent System Operator, control area,
Balancing Authority Area, or the Connecting Transmission Owner’s requirements, including
those set forth in the Small Generator Interconnection Agreement. Operating Requirements shall
include Applicable Reliability Standards.

Party or Parties – The NYISO, Connecting Transmission Owner, Interconnection Customer or any combination of the above.

1-4

SERVICE AGREEMENT NO. 2913

Point of Interconnection – The point where the Interconnection Facilities connect with the New York State Transmission System or the Distribution System.

Reasonable Efforts – With respect to an action required to be attempted or taken by a Party
under this Agreement, efforts that are timely and consistent with Good Utility Practice and are
otherwise substantially equivalent to those a Party would use to protect its own interests.

Small Generating Facility – The Interconnection Customer’s facility, no larger than 20 MW for
the production and/or storage for later injection of electricity identified in the Interconnection
Request if proposing to interconnect to the New York State Transmission System or Distribution
System, but shall not include (i) facilities proposing to simply receive power from the New York
State Transmission System or the Distribution System; (ii) facilities proposing to interconnect to the
New York State Transmission System or the Distribution System made solely for the purpose of
generation with no wholesale sale for resale nor to net metering; (iii) facilities proposing to the New
York State Transmission System or the Distribution System made solely for the purpose of net
metering; (iv) facilities proposing to interconnect to LIPA’s distribution facilities; and (v) the
Interconnection Customer’s Interconnection Facilities. A facility will be treated as a single Small
Generating Facility if all Generators within the facility are behind a single Point of Interconnection,
even if such units are different technology types.

System Deliverability Upgrades – The least costly configuration of commercially available
components of electrical equipment that can be used, consistent with Good Utility Practice and
Applicable Reliability Requirements, to make the modifications or additions to the existing New
York State Transmission System that are required for the proposed Project to connect reliably to
the system in a manner that meets the NYISO Deliverability Interconnection Standard for
Capacity Resource Interconnection Service.

System Upgrade Facilities – The least costly configuration of commercially available
components of electrical equipment that can be used, consistent with Good Utility Practice and
Applicable Reliability Requirements to make the modifications to the existing transmission
system that are required to maintain system reliability due to: (i) changes in the system,
including such changes as load growth and changes in load pattern, to be addressed in the form
of generic generation or transmission projects; and (ii) proposed interconnections. In the case of
proposed interconnections, System Upgrade Facilities are the modification or additions to the
existing New York State Transmission System that are required for the proposed Project to
connect reliably to the system in a manner that meets the NYISO Minimum Interconnection
Standard.

Tariff – The NYISO’s Open Access Transmission Tariff, as filed with the FERC, and as amended or supplemented from time to time, or any successor tariff.

Trial Operation shall mean the period during which Interconnection Customer is engaged in on-
site test operations and commissioning of the Small Generating Facility prior to Commercial
Operation.

Upgrades – The required additions and modifications to the Connecting Transmission Owner’s portion of the New York State Transmission System or the Distribution System at or beyond the

1-5

SERVICE AGREEMENT NO. 2913

Point of Interconnection. Upgrades may be System Upgrade Facilities or System Deliverability
Upgrades Distribution Upgrades. Upgrades do not include Interconnection Facilities.

1-6

SERVICE AGREEMENT NO. 2913

Attachment 2

Detailed Scope of Work, Including Description and Costs of the Small Generating Facility,
 Interconnection Facilities, and Metering Equipment

Equipment, including the Small Generating Facility, Interconnection Facilities, and
metering equipment shall be itemized and identified as being owned by the Interconnection
Customer, or the Connecting Transmission Owner. The NYISO, in consultation with the
Connecting Transmission Owner, will provide a best estimate itemized cost, including
overheads, of its Interconnection Facilities and metering equipment, and a best estimate itemized
cost of the annual operation and maintenance expenses associated with its Interconnection
Facilities and metering equipment.

A. PROJECT DESCRIPTION

The Interconnection Customer is constructing a 12.1MW solar generation facility (“Small
Generating Facility”) at Benson Mines in Star Lake, New York. The Small Generating Facility
will be comprised of five (5) 2.8 MW SMA SC-2800-UP-US inverters. The five inverters are
paired with a pad mounted 2.8 MVA transformer (34.5 kV Delta, 630V wye-ungrounded, 6.0%
impedance, X/R 8.0).

Each of the five (5) step-up transformers are daisy chained together using 34.5 kV
medium voltage collection circuit (“Collection Feeder Lines”). The home run of cable is then
run to the Interconnection Customer’s collector station (“Benson Mines Collector Station”)
comprised of ground-mounted metal-clad switchgear.

(Note: The Collection Feeder Lines shall be designed, constructed, operated, and
maintained by the Interconnection Customer in accordance with Good Utility Practice,
Connecting Transmission Owner’s electric system bulletins (“ESBs”), and the Project Specific
Specifications (as defined below).

The Point of Interconnection (“POI”) for the Small Generating Facility is Connecting
Transmission Owner’s 34.5 kV Star Lake Tap off the Browns Falls–Newtown Falls Line 22,
approximately 6.95 miles from Browns Falls Station, 3.34 miles from Newton Falls Station, and

0.3 miles from Star Lake Station. The Small Generating Facility will interconnect to the
Connecting Transmission Owner’s system via a single breaker tap that will be constructed at Star
Lake Station.

The Point of Change of Ownership (“PCO”) shall be the line side connection of the
Interconnection Customer’s disconnect switch located on the Interconnection Customer’s riser
outside of Star Lake Station. The Connecting Transmission Owner shall own the insulators,
whips and hardware connections to the Interconnection Customer’s disconnect switch.

The POI and PCO are detailed in the one-line diagram in Attachment 3.

To the extent Small Generating Facility’s feeder lines, communication circuits, access roads, and/or driveways cross Connecting Transmission Owner-owned transmission or

2-1

SERVICE AGREEMENT NO. 2913

distribution circuits or corridors, such crossings must be reviewed by the Connecting Transmission
Owner in accordance with the Connecting Transmission Owner’s Land Use Application &
Requirements which are located on the Connecting Transmission Owner’s Wholesale
Interconnections-New York website (https://www.nationalgridus.com/Wholesale-
Interconnections/New-York/) under “Land Use Application Form: Wholesale
Generation/Transmission Projects” (“Land Use Requirements”). As stated in the Land Use
Requirements, no longitudinal occupancies are permitted for third party owned non-utility
facilities (i.e., generator tie lines, feeder lines, access roads, etc.). All feeder line and
telecommunication circuit crossings must be underground so as to maintain system reliability and
safety and should be perpendicular. Please refer to the Land Use Requirements for additional
information regarding prohibited encroachments.

As a regulated company, the Connecting Transmission Owner has the responsibility to
ensure that it can continue to deliver safe and reliable power as well as maintain and modernize its
facilities to meet present and future demands. Submission of an application does not authorize use
of the Connecting Transmission Owner’s property and/or rights-of-way. Final approval is
contingent upon a full engineering review of the application materials, impacts to the Connecting
Transmission Owner’s granted rights and negotiation of the applicable formal agreements.

No work on Connecting Transmission Owner property may proceed until the
Interconnection Customer is in receipt of a fully executed occupation agreement and authorization
is obtained from the Connecting Transmission Owner’s contact. To the extent construction is
performed prior to the completion of the reviews and execution of applicable agreements, the
Interconnection Customer may be required to halt construction and/or remove or modify the
facilities constructed.

B. INTERCONNECTION CUSTOMER’S INTERCONNECTION FACILITIES

The Interconnection Customer’s Interconnection Facilities (“ICIF”) include all of the
facilities between the Interconnection Customer’s side of the PCO and the Small Generating
Facilities. The ICIF will be located on property owned or leased by the Interconnection
Customer. As depicted on the one-line diagram in Attachment 3, the ICIF will consist of the
following:

1. Benson Mines Collector Station

The Benson Mines Collector Station will be comprised of metal-clad switchgear located
at the Small Generating Facility site on the south side of State Route 3 Olympic Trail in Star
Lake, New York and will be comprised of the following major equipment:

• one (1) set of three (3) single phase 31 kV maximum continuously operating

voltage (“MCOV”) station class surge arresters;

• one (1) 34.5 kV, 1200A, 150 kV basic insulation level (“BIL”), 38 kAIC

disconnect switch;

• one (1) 38 kV, 1200A, 150 kV BIL, 25 kAIC draw-out breaker;

2-2

SERVICE AGREEMENT NO. 2913

• one (1) 19.9 kV / 120V 5kVA control power transformer;

• customer metering; and

• various instrument transformers and equipment for controls and protection.

2. Generator Tie Line

The Benson Mines Collector Station will connect to the single breaker tap via ~1,776-feet
of 34.5 kV underground line (“Generator Tie Line”). The last structure of the Generator Tie
Line must include a disconnect switch and be located on the south side of Star Lake Station. The
Interconnection Customer-owned Generator Tie Line, including the last structure and switch,
must be located off Connecting Transmission Owner’s property.

The Generator Tie Line consists of:

• one (1) 1,776-foot 795kC MIL aluminum (“AL”) underground cable in conduit;

• one (1) riser pole;

• one (1) 38 kV, 200 kV BIL fused cut-out;

• one (1) 38 kV, 600A, 20 kV BIL group operated air break switch; and

• one (1) set of three 31 kV MCOV station class surge arresters.

3. System Protection Requirements

The Small Generating Facility can only be in service under normal system conditions
(i.e., when Brown Falls 34.5 kV network is in normal configuration). When the tie switches
between Line 22 and Line 21 are closed or the tie switches between Mine Road and Browns
Falls are closed, the Small Generating Facility must be taken offline.

The following protection and telecom systems are required for interconnection of the
Small Generating Facility under normal operating conditions:

a) Generator Tie Line (Line XX)

The Generator Tie Line will be protected by redundant line differential packages. The
Generator Tie Line number will be determined during final engineering. The ‘A’ package will
use a Schweitzer Engineering Laboratories (“SEL”)-411L relay and the ‘B’ package will use a
GE-L90. These two packages will require use of redundant geographically physically separate
dedicated fiber cables. Direct Transfer Trip (“DTT”) will be used between the Benson Mines
Collector Station and Star Lake to ensure removal of the generation. This will require
installation of one (1) RFL GARD Pro (or equivalent) tele-protection sets at the Benson Mines
Collector Station. The line relays will provide DTT supervision and breaker failure protections.

2-3

SERVICE AGREEMENT NO. 2913

(Note: The GARD Pro will be procured, installed, owned, operated and maintained by the
Interconnection Customer.)

The Interconnection Customer is to provide redundant 34.5 kV line protection to remove
the generation for line faults. Two sets of C400 multi-ratio current transformers (“CTs”) shall be
provided for these schemes.

b) Breaker

Breaker failure protection shall be provided for the 34.5 kV breaker; this protection must
trip the Interconnection Customer’s 34.5 kV breaker and send DTT to Star Lake Substation
which will be relayed on to Browns Falls. DTT receive from Star Lake and Browns Falls
substations will be required to trip the Interconnection Customer’s 34.5 kV circuit breaker for a
line relay operation or breaker failure at Browns Falls or Star Lake stations. The Interconnection
Customer shall provide separate on/off switches for the DTT schemes.

The Interconnection Customer must provide on/off switches for the line protection and
DTT schemes.

Protection scheme drawings and relay settings shall be prepared by the Interconnection
Customer’s NYS licensed professional engineer and submitted to the Connecting Transmission
Owner for review, comment and acceptance, a minimum of six (6) weeks prior to application
and testing.

4. Telecommunications Circuits

For Generator Tie Line protection, DTT, and data transmittal, the Interconnection Customer
shall install one (1) 48-strand, single mode, fiber optic communication cable between the Benson
Mines Collector Station and the PCO, in accordance with the Connecting Transmission Owner’s
specifications.

In accordance with the Connecting Transmission Owner’s ESBs, the Interconnection
Customer is required to provide generator status to the Connecting Transmission Owner’s energy
management system (“EMS”). As such, the Interconnection Customer shall provide a distributed
network protocol (“DNP”) enabled port on the Interconnection Customer-owned remote terminal unit
(“RTU”) at the Benson Mines Collector Station.

To the extent not inconsistent with this Agreement, the NYISO Tariffs, and ISO
Procedures, the ICIFs shall be designed, constructed, operated and maintained by the
Interconnection Customer in accordance with the standards and specifications defined in section
I.B. of the Facilities Study for the Small Generating Facility (“Facilities Study”), the Project
Specific Specifications (as defined below), and National Grid Environmental Standards and
Requirements which are located on the Connecting Transmission Owner’s Wholesale
Interconnections-New York website: https://www.nationalgridus.com/Wholesale-
Interconnections/New-York/  as amended or superseded prior to the start of final engineering.

2-4

SERVICE AGREEMENT NO. 2913

All protection scheme design drawings and relay settings shall be prepared by the
Interconnection Customer’s NYS licensed professional engineer, and the design and equipment
specifications shall be provided to the Connecting Transmission Owner for review, comment and
acceptance, prior to application and testing in accordance with the ESBs and the Project Specific
Specifications (as defined below).

C. CONNECTING TRANSMISSION OWNER’S INTERCONNECTION FACILITIES

As depicted in the one-line diagram in Attachment 3, the Connecting Transmission
Owner’s Interconnection Facilities (“CTOIF”) consist of the following constructed or installed
between the POI and PCO:

1. Star Lake Station

To interconnect the Small Generating Facility to the Star Lake tap off Line 22, a single
breaker tap station is required. The existing Star Lake distribution station will be expanded to
include the single breaker tap facilities as further described below. The station will need to be
extended by a minimum of forty feet to the east. The Interconnection Customer is responsible
for all land acquisition all clearing and removal of structures on the new property required for the
station expansion. Clearing and removals must be completed at least 3 months in advance of
construction start and ownership of the property must be transferred to Connecting Transmission
Owner at least 2 months in advance of construction start.

The Interconnection Customer shall acquire all required real estate in accordance with
National Grid Real Estate Standards & Requirements and Environmental Standards &
Requirements which are located on the Connecting Transmission Owner’s Wholesale
Interconnections-New York website (https://www.nationalgridus.com/Wholesale-
Interconnections/New-York/).

a) Site Work

Star Lake Station will be expanded to the east to accommodate the addition of take-off
structures, lightning mast structures, a control enclosure, foundations and other major equipment.
The expansion will require removal of approximately sixty (60) linear feet of fence and installation
of: (i) approximately 100 linear feet of fence, and (ii) a twenty-foot gate. A second driveway will
also need to be installed.

b) Civil/Structural Work

The following structures and foundations shall be installed:

• two (2) galvanized steel A-frame take-off structures with concrete caisson/spread

footers;

• two (2) galvanized steel lightning mast structures w/ concrete caisson/spread

footers; and

2-5

SERVICE AGREEMENT NO. 2913

• concrete slab foundations for the breaker and control enclosure.

c) Major Equipment

The following major equipment must be installed in the station yard:

• one (1) 38 kV, 1250A, 200 kV BIL, control 125 VDC motor 125 dead tank vacuum

circuit breaker;

• two (2) 34.5 kV, 200 kV BIL, 1250A gang-operated disconnect switches with

arcing horns;

• one (1) 34.5 kV, 200 kV BIL, 1250A single phase disconnect fuse for AC station

service isolation;

• two (2) 34.5 kV, 200 kV BIL, 175/300.1 voltage transformers (“VTs”);

• two (2) 34.5 kV rated dual bushing voltage transformers and three (3) 34.5 kV rated

CTs for revenue metering;

• two (2) 31.5 kV MCOV station class surge arresters;

• one (1) 120/240 25kVA station service voltage transformer (“SSVT”); and

• one (1) control enclosure with:

o protection panels;

o relays & control switchboards;

o indoor over-head cable trays;

o AC & DC power panels;

o one (1) 125VDC battery systems;

o one (1) battery chargers;

o HVAC system with AC panels;

o RTU;

o communication equipment;

o fire & security equipment;

o indoor lighting; and

o revenue metering.

2-6

SERVICE AGREEMENT NO. 2913

d) Ground Grid

A complete grounding system for the station expansion shall be installed (approximately
2000 square feet).

e) Protection

The Small Generating Facility can only be in service under normal system conditions
(i.e., when Browns Falls 34.5 kV network is in normal configuration). When the tie switches
between Line 22 and Line 21 are closed or the tie switches between Mine Road and Browns
Falls are closed, the Small Generating Facility must be taken offline. The protection and telecom
systems requirements and modifications contain in this section are for interconnection of the
Small Generating Facility under normal operating conditions.

The line between the Benson Mines Collector Station and Star Lake shall be protected
redundant digital line differential protection with bi-directional DTT. The ‘A’ package will use a
SEL-411L relay which will directly connect to the ‘A’ package fiber installed between Benson
Mines Collector Station and the Star Lake Station. The ‘B’ package will use a GE L90 relay that
will directly connect to the ‘B’ package fiber installed between Benson Mines Collector Station
and the Star Lake Station. Breaker failure will be provided by the line protection relays.

DTT transmit and receive (single package) between Browns Falls and Star Lake stations
is required and will require installation of one (1) GARD Pro relay and one (1) 43TT control
handle.

Due to the addition of the Small Generating Facility, an area coordination study will be
completed during final engineering design stage and may result in resetting of relays in the area.
The cost of the coordination study is included in the cost estimates provided in the Facilities
Study. If the area coordination study determines that additional relays in the area must be reset,
the costs associated with resetting the relays will be the responsibility of the Interconnection
Customer.

f) Controls & Integration

An RTU/communications processor shall be installed in the control enclosure for status,
control and analog data, and one (1) I/O unit will be installed to accommodate hardwired control
and status of the new breaker and equipment alarms. One (1) RE-01 control switch relay
(“CSR”) and one (1) RE-43A/M latching switch relay (“LSR”) will be installed for the new
breaker. One (1) Ruggedcom RX1536 gateway router will be installed to provide a secure
connection to the EMS network for supervisory control and data acquisition (“SCADA”) data
and revenue metering. The gateway will connect to a multiprotocol label switching (“MPLS”)
circuit extended to Star Lake from Browns Falls.

g) Telecommunications

2-7

SERVICE AGREEMENT NO. 2913

For the tie line protection schemes, one (1) dedicated fiber connection will be required
between the Benson Mines Collector Station and Star Lake Station. The Interconnection
Customer is responsible for installing one (1) 48-strand, single mode, fiber optic communication
cable between the Benson Mines Collector Station and the PCO, in accordance with the
Connecting Transmission Owner’s specifications. The Connecting Transmission Owner will
then install one (1) 48-strand fiber cable in a 4” schedule 80 conduits from the PCO into the
control house. The Connecting Transmission Owner will coordinate an end-to-end optical time
domain reflectometer (“OTDR”) test of all fibers from the termination/patch panel at Star Lake
Station to the termination/patch panel in the Benson Mines Collector Station.

For protection systems and EMS RTU data transmittal, Connecting Transmission Owner
anticipates the use of the dark fiber for a connection from the Star Lake to Browns Falls. This
will require installation of floor mount telecom racks with an optical node, directional
comparison blocking (“DCB”) loop channel bank, 48 VDC telecom power plant system and DPS
NG-420 RTU. After the dark fiber is installed and turned up, Connecting Transmission Owner
will provision one (1) telecom C37.94 from Star Lake to Browns Falls and one (1) telecom
circuit for the RTU.

(Note: Since the indefeasible right to use (“IRU”) cannot be signed at the time of
execution of this Agreement, it is assumed that the dark fiber will be available should this project
proceed to engineering, procurement and construction. The estimated cost of the dark fiber at
the time of the Facilities Study is $250k. The actual cost of the dark fiber IRU will be
determined during final engineering and could increase significantly. The Interconnection
Customer is responsible for the actual cost.)

2. Station and Line Taps

To interconnect the Small Generating Facility to the Star Lake Tap offline 22, a tap must
be constructed from the tap point on Star Lake Tap between Structures 52 and 53 to the line side
take-off structure inside the Star Lake Station fence. In addition, a small section of conductor
must be installed between the Interconnection Customer’s disconnect switch located on its riser
structure directly adjacent to Star Lake Station and the Small Generating Facility side take-off
structure in the fence line.

The following removals and installations are required:

Removal of:

• one (1) horizontal upright loadbreak wood pole structure and loadbreak switch;

• one (1) stub pole;

• approximately 30 circuit feet of 1/0 aluminum-conductor steel-reinforced

(“ACSR”) 6/1 “Raven” conductor; and

• approximately 40 linear feet of 16M span guy wire.

2-8

SERVICE AGREEMENT NO. 2913

Installation of:

• two (2) wood pole structures;

• one (1) horizontal upright loadbreak wood pole structure and loadbreak switch;

• three (3) 3-disc insulators; and

• approximately 231circuit feet of 336.4 ACSR 18/1 “Merlin” conductor.

Take off structure heights and phase spacing will need to be established between
Interconnection Customer and Connecting Transmission Owner before final design and material
specifications are prepared. Soil borings for the line tap will be completed by the Connecting
Transmission Owner and all line phasing shall match the existing Star Lake Tap line.

The Interconnection Customer’s takeoff structure shall be designed in accordance with the Project Specific Specifications (defined below).

The National Pipeline Mapping System does not identify gas lines located in the site
location. However, the Interconnection Customer is responsible for obtaining gas line
information and determining if there are any other underground facilities that were not identified
on the drawings provided by the Interconnection Customer for the Facilities Study.

New right-of-way (“ROW”) will be required for the construction, operation, and
maintenance of the tap line and must accommodate the 125’ x 125’ work pads (temporary)
required for the installation of the new structures. All ROW widths shall adhere to the most
current Connecting Transmission Owner standards at the time of final engineering. Final ROW
width requirements cannot be determined until after final design is complete. Permanent access
roads are required for switches whether they are motor operated disconnects or manually
operated switches.

The Interconnection Customer shall obtain all real estate/easements and environmental
permits for Connecting Transmission Owner to construct, operate and maintain the transmission
infrastructure including all permanent and temporary real estate for construction of the facilities
and all access roads (permanent and temporary). The Interconnection Customer shall acquire all
required real estate and permitting in accordance with National Grid Real Estate Standards &
Requirements and Environmental Standards and Requirements which are located on the
Connecting Transmission Owner’s Wholesale Interconnections-New York website
(https://www.nationalgridus.com/Wholesale-Interconnections/New-York/).

Property rights for the line tap and transmission line facilities, and associated access
roads, must be transferred to Connecting Transmission Owner at least two (2) months in advance
of construction initiation.

D. SCOPE OF WORK AND RESPONSIBILITIES

1. Interconnection Customer’s Scope of Work and Responsibilities

2-9

SERVICE AGREEMENT NO. 2913

The Interconnection Customer shall construct, operate and maintain the ICIF in
accordance with the following requirements, to the extent not inconsistent with the terms of this
Agreement, the ISO OATT, or the applicable NYISO procedures: the NYISO’s requirements;
industry standards and specifications; regulatory requirements; the Connecting Transmission
Owner’s applicable ESBs located on the Connecting Transmission Owner’s Wholesale
Interconnections-New York website (https://www.nationalgridus.com/Wholesale-
Interconnections/New-York/) under “Electric Specifications”; the Connecting Transmission
Owner’s System Protection and Interconnection Customer Attachment Facilities Electric
Installation Specification for Benson Mines Solar Project (“Project Specific Specifications”),
provided in Appendix C to the Facilities Study for the Small Generating Facility; Real Estate
Standards & Requirements and Environmental Standards and Requirements which are located
on the Connecting Transmission Owner’s Wholesale Interconnections-New York website
(https://www.nationalgridus.com/Wholesale-Interconnections/New-York/) under “Third Party
Acquisitions and Transfer of Real Property and Good Utility Practice. The Interconnection
Customer shall submit all engineering design and electrical specifications associated with
Interconnection Customer’s Interconnection Facilities to the Connecting Transmission Owner for
its review and acceptance in accordance with the Connecting Transmission Owner’s ESBs and
Project Specific Specifications.

The Project Specific Specifications may require modification, after receipt and review of
the Interconnection Customer’s final design and equipment specifications for the Small
Generating Facility, subsequent to: (i) execution of the Agreement, (ii) receipt of the notice to
proceed under the terms of the Agreement, and (iii) posting of security in accordance with the
terms of the Agreement; provided however, that the Project Specific Specifications shall not be
modified due to changes in the Connecting Transmission Owner’s ESBs that occur after
completion of the Facility Study, except as required to comply with all Applicable Laws and
Regulations and the requirements and guidelines of the Applicable Reliability Councils.

2. Connecting Transmission Owner’s Scope of Work and Responsibilities

The Connecting Transmission Owner will construct all CTOIFs, except as otherwise states above and in the Project Specific Specifications. Connecting Transmission Owner will:

• install one (1) 48-strand fiber cable in a 4” schedule 80 conduits from the PCO into

the control house;

• coordinate an end-to-end OTDR test of all fibers from the termination/patch panel at
 Star Lake Station to the termination/patch panel in the Benson Mines Collector
 Station); and

• provision one (1) telecom C37.94 from Star Lake to Browns Falls and one (1)

telecom circuit for the RTU after the dark fiber is installed and turned up.

E. ESTIMATED COSTS OF INTERCONNECTION FACILITIES

2-10

SERVICE AGREEMENT NO. 2913

The estimated costs (+30%/-15%) (in 2024 dollars) of the work associated with the
Interconnection Facilities required for the interconnection of the Small Generating Facility are
presented in the table below.

As described in the Facilities Study for the Small Generating Facility, the estimates
provided herein:

Assume:

• 5X10 construction work week;

• outages are available;

• all major material is delivered to site (i.e., no costs are included for transport from

storage);

• existing equipment to remain is functional; and

• no mobile generation or additional facilities are required for outages.

Exclude:

• discussions and negotiations of issued interconnection study;

• application fees;

2-11

SERVICE AGREEMENT NO. 2913

• applicable surcharges;

• overall project sales tax;

• property taxes;

• line switching;

• property/easement acquisitions;

• access roads and associated matting;

• future operation and maintenance costs;

• recurring monthly communications circuits’ charges, if any, responsible by the

Interconnection Customer to the communications utility;

• soil testing;

• adverse field conditions such as rock, water, weather, and Interconnection Customer

electrical equipment obstructions;

• additional facilities/equipment (temporary or permanent) required for outages to

maintain system reliability and safety, and service to customers;

• environmental mitigation;

• extended engineering to minimize outage time or Connecting Transmission Owner’s

public duty to serve;

• extended craft labor hours, to minimize outage and/or construction time; or

• any required permits.

F. O&M EXPENSES FOR INTERCONNECTION FACILITIES

In accordance with Article 4.1.2 of this Agreement, the Interconnection Customer shall
be responsible for all reasonable expenses associated with the operation, maintenance, repair and
replacement of the Connecting Transmission Owner’s Interconnection Facilities, as such
facilities are detailed in this Attachment 2 (“O&M Expenses”).

The Interconnection Customer shall have the option to pay such O&M Expenses either
under the procedure described in Option 1 or in Option 2 below.

Option 1: Fixed On-Going Charge Payment:

The Connecting Transmission Owner will invoice and Interconnection Customer
shall pay an annual payment to the Connecting Transmission Owner equal to the

2-12

SERVICE AGREEMENT NO. 2913

product of the Gross Plant Investment associated with the Connecting
Transmission Owner’s Interconnection Facilities and the Annual Transmission
Ongoing Charge Factor, for the term of this Agreement.

For purposes of this Agreement, Gross Plant Investment shall mean the
investment from the plant account records associated with the Connecting
Transmission Owner’s Interconnection Facilities for the Small Generating
Facility.

All payments due to be made by the Interconnection Customer shall be made
within thirty (30) days after receiving an invoice from the Connecting
Transmission Owner. Connecting Transmission Owner will bill Interconnection
Customer for the O&M Expenses on a quarterly basis.

The Project’s Gross Plant Investment associated with the Connecting
Transmission Owner’s Interconnection Facilities shall be established in writing by
the Connecting Transmission Owner no later than 90 days following commercial
operation.

The Annual Transmission On-Going Charge Factor shall be calculated annually
each July based on the Connecting Transmission Owner’s most recent FERC
Form 1 data and will equal the sum of the Revenue Requirement Components as
identified in O&M Attachment 1 divided by the Total Gross Plant of the
Connecting Transmission Owner. Total Gross Plant shall equal the sum of Item
Nos. A (1)(a)(b)(c) in O&M Attachment 1.

Option 2: Quarterly Actual O&M Expenses

The Interconnection Customer shall pay for all actual O&M Expenses incurred by
the Connecting Transmission Owner, which expenses shall be billed by the
Connecting Transmission Owner quarterly as accumulated during the quarter for
which they were incurred.

All payments due to be made by the Interconnection Customer shall be made
within thirty (30) days after receiving an invoice from the Connecting
Transmission Owner, which invoice shall be issued after the end of each quarter
for the most recent quarter.

Selection by Interconnection Customer

The Interconnection Customer shall select which option for paying such O&M Expenses
by providing written notice to the Connecting Transmission Owner within thirty (30) days after
the Gross Connecting Transmission Owner’s Interconnection Facilities Plant Investment cost and
the most recent Annual Transmission Ongoing Charge Factor have been provided to the
Interconnection Customer. If the Interconnection Customer fails to provide timely notice to the
Connecting Transmission Owner of the option selected, the Interconnection Customer will be
deemed to have selected Option 2: Quarterly Actual O&M Expenses.

2-13

SERVICE AGREEMENT NO. 2913

O&M ATTACHMENT 1

Capitalized terms used in this calculation will have the following definitions:

Allocation Factor

(1) General Plant Allocation Factor shall equal Electric General Plant divided by the sum of
Electric General Plant plus gas general plant as reported in the Annual Report filed with the New
York State Public Service Commission.

(2) Gross Transmission Plant Allocation Factor shall equal the total investment in
Transmission Plant in Service divided by the sum of the total Transmission Plant in Service plus
the total Distribution Plant in Service, excluding Intangible Plant, General Plant and Common
Plant.

(3) Transmission Wages and Salaries Allocation Factor shall equal the ratio of Connecting
Transmission Owner Transmission-related direct electric wages and salaries including any direct
wages or salaries charged to Connecting Transmission Owner by a Connecting Transmission
Owner Affiliate to Connecting Transmission Owner’s total electric direct wages and salaries
including any wages charged to Connecting Transmission Owner by a Connecting Transmission
Owner Affiliate excluding any electric administrative and general wages and salaries.

Ratebase and Expense items

(1) Administrative and General Expense shall equal electric expenses as recorded in FERC
Account Nos. 920-935.

(2) Amortization of Investment Tax Credits shall equal electric credits as recorded in FERC
Account No. 411.4.

(3) Distribution Plant in Service shall equal the gross plant balance as recorded in FERC Account Nos. 360 – 374.

(4) Electric Common Plant shall equal the balance of Common Plant recorded in FERC
Account Nos. 389-399 multiplied by the General Plant Allocation Factor.

(5) General Plant shall equal electric gross general plant balance recorded in FERC Account
Nos. 389-399.

(6) Materials and Supplies shall equal electric materials and supplies balance as recorded in
FERC Account No. 154.

(7) Payroll Taxes shall equal those electric payroll tax expenses as recorded in FERC
Account Nos. 408.100, 408.110 and 408.130.

(8) Prepayments shall equal electric prepayment balance as recorded in FERC Account
No. 165.

2-14

SERVICE AGREEMENT NO. 2913

(9) Real Estate Tax Expenses shall equal electric transmission-related real estate tax expense
as recorded in FERC Account No. 408.140 and 408.180.

(10) Transmission Operation and Maintenance Expense shall equal electric expenses as
recorded in FERC Account Nos. 560, 562-573.

(11) Transmission Plant in Service shall equal the gross plant balance as recorded in FERC
Account Nos. 350-359.

(12) Transmission Revenue Credits shall equal the revenue reported in Account 456.

(13) Transmission Related Bad Debt Expense shall equal Bad Debt Expense as reported in
Account 904 related to transmission billing.

(14) Wholesale Metering Cost shall equal any costs associated with any Revenue or Remote
Terminal Unit (RTU) meters and associated equipment located at an internal or external tie at
voltages equal to or greater than 23V. The cost shall be determined by multiplying the number of
wholesale meters in FERC Account No. 370.3 by the average cost of the meters plus the average
costs of installation.

In the event that the above-referenced FERC accounts are renumbered, renamed, or
otherwise modified, the above sections shall be deemed amended to incorporate such
renumbered, renamed, modified or additional accounts.

Revenue Requirement Components

The Revenue Requirement Components shall be the sum of Connecting Transmission
Owner’s (A) Return and Associated Income Taxes, (B) Transmission Related Real Estate Tax
Expense, (C) Transmission Related Amortization of Investment Tax Credits, (D) Transmission
Related Payroll Tax Expense (E) Transmission Operation and Maintenance Expense, (F)
Transmission Related Administrative and General Expenses, less (G) Revenue Credits, plus (H)
Bad Debt Expense.

A. Return and Associated Income Taxes shall equal the product of the Transmission
Investment Base as identified in A(1) below and the Cost of Capital Rate.

1. Transmission Investment Base shall be defined as

Transmission Related General Plant plus Transmission Related Common
Plant plus Transmission Related Regulatory Assets plus Transmission
Related Prepayments plus Transmission Related Materials and Supplies
plus Transmission Related Cash Working Capital.

(a) Transmission Plant in Service shall equal the balance of Total
 investment in Transmission Plant plus Wholesale Metering Cost.

(b) Transmission Related General Plant shall equal the balance of
 investment in General Plant multiplied by the Transmission Wages
 and Salaries Allocation Factor.

2-15

SERVICE AGREEMENT NO. 2913

(c) Transmission Related Common Plant shall equal Electric Common
 Plant multiplied by the Gross Transmission Plant Allocation Factor
 and multiplied by the Transmission Wages and Salaries Allocation
 Factor.

(d) Transmission Related Regulatory Assets shall equal balances in
 FERC Account Nos. 182.3 and 254 for state and federal regulatory
 assets and liabilities related to FAS109, and excess AFUDC
 multiplied by the Gross Transmission Plant Allocation Factor

(e) Transmission Related Prepayments shall equal the electric balance
 of Prepayments multiplied by the Gross Transmission Plant
 Allocation Factor.

(f) Transmission Related Materials and Supplies shall equal the balance
 of Materials and Supplies assigned to Transmission added to the
 remainder of Material and Supplies not directly assigned to either
 Transmission or Distribution multiplied by the Gross Transmission
 Plant Allocation Factor.

(g) Transmission Related Cash Working Capital shall be a 12.5%
 allowance (45 days/360 days) of the Transmission Operation and
 Maintenance Expense (less FERC Account 565: Transmission of
 Electricity by Others) and Transmission-Related Administrative and
 General Expense.

2. Cost of Capital Rate

The Cost of Capital Rate shall equal the proposed Weighted Costs of Capital
plus Federal Income Taxes and State Income Taxes.

(a) The Weighted Costs of Capital will be calculated for the
 Transmission Investment Base using Connecting Transmission
 Owner’s actual capital structure and will equal the sum of (i), (ii),
 and (iii) below:

(i) the long-term debt component, which equals the product of
 the actual weighted average embedded cost to maturity of
 Connecting Transmission Owner’s long-term debt then
 outstanding and the actual long-term debt capitalization
 ratio.

(ii) the preferred stock component, which equals the product of
 the actual weighted average embedded cost to maturity of
 Connecting Transmission Owner’s preferred stock then
 outstanding and the actual preferred stock capitalization
 ratio;

2-16

SERVICE AGREEMENT NO. 2913

(iii) the return on equity component, shall be the product of the
 allowed ROE of 10.30% or such value as most recently
 approved by the Commission plus a 50 basis point adder (per
 FERC Order 697 and 697-A, if authorized by the
 Commission for the Connecting Transmission Owner) and
 Connecting Transmission Owner’s actual common equity
 capitalization ratio.

(b) Federal Income Tax shall equal

A x Federal Income Tax Rate
(1 - Federal Income Tax Rate)

where A is the sum of the preferred stock component and the return
on equity component, each as determined in Sections 2.(a)(ii) and
for the ROE set forth in 2.(a)(iii) above

(c) State Income Tax shall equal

(A + Federal Income Tax) x State Income Tax Rate

(1 – State Income Tax Rate)

Where A is the sum of the preferred stock component and the return on
equity component as determined in A.2.(a)(ii) and A.2.(a)(iii) above and
Federal income Tax is determined in 2.(b) above.

B. Transmission Related Real Estate Tax Expense shall equal the Real Estate Tax
Expenses multiplied by the Gross Plant Allocation Factor.

C. Transmission Related Amortization of Investment Tax Credits shall equal the
electric Amortization of Investment Tax Credits multiplied by the Gross Transmission Plant
Allocation Factor.

D. Transmission Related Payroll Tax Expense shall equal Payroll Taxes multiplied by
the Transmission Wages and Salaries Allocation Factor.

E. Transmission Operation and Maintenance Expense shall equal the Transmission
Operation and Maintenance Expense as previously defined.

F. Transmission Related Administrative and General Expenses shall equal the sum
of the electric Administrative and General Expenses multiplied by the Transmission Wages and
Salaries Allocation Factor.

G. Revenue Credits shall equal all Transmission revenue recorded in FERC account 456.

H. Transmission Related Bad Debt Expense shall equal Transmission Related Bad
Debt Expense as previously defined.

2-17

SERVICE AGREEMENT NO. 2913

Attachment 3

One-line Diagram Depicting the Small Generating Facility, Interconnection Facilities, Metering Equipment, and
 Upgrades

|  | 34.5 kV Line 22 ~ 6.95 miles to Browns Falls Station |  | 34.5 kV Line 22 ~ 3.34 miles to Newton Falls Station |
| --- | --- | --- | --- |

Station
 Service
120/240V

SST
1 ph 25kVA

Interconnection
 Customer

Attachment
 Facilities

|  | MV90 |  | EMS- RTU |  | CTO Interconnection Facilities |  | Point of Interconnection (POI) |
| --- | --- | --- | --- | --- | --- | --- | --- |

3

12.1MW R50

(~1,776 ft ) 3

|  | INVERTERS (5) SMA Sunny Central 2800 UP-US 2.8 MVA |  |  | PT s (3) |  | PT s (3) |  |  |  | Star Lake Station (Note: This is not a representation of the entire station.) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Benson Mines Solar Collector Station |  |  |  |  |  | Point of Change of Ownership (PCO) (Note: PCO is at the connection to the IC s Disconnect Switch. National Grid will own the insulators, whips, and connection hardware.) |  |  |  | Relocated mobile sub tap (System Upgrade Facility (SUF) |

34.5 kV Star Lake Tap
 ~0.3 miles to

Star Lake Station

3-1

SERVICE AGREEMENT NO. 2913

Attachment 4

Milestones

1. Milestones

In-Service Date: October 2027

Critical milestones and responsibility as agreed to by the Parties:

MILESTONE DATES RESPONSIBLE
 PARTY

Interconnection

1. Execute Interconnection Agreement 09/2025
 Customer/CTO/NYISO

2. Provide security for CTOIF 09/2025 Interconnection Customer

3. Start engineering on Interconnection 09/2025 Interconnection Customer

Customer’s Interconnection Facilities

4. Complete Project Initiation 09/2025 Connecting Transmission
 Owner

10/2025 Connecting Transmission

Project Management level kickoff

5. Owner/Interconnection

meeting

Customer

6. Provide survey map and initial property 10/2025 Interconnection Customer
 rights confirming site control for CTOIFs

Provide initial property rights 10/2025 documentation (i.e., options, deeds,

7. Interconnection Customer
 easements, etc.) for CTOIFs to CTO for

review

Provide final civil plans for Benson 10/2025
Mines Collector Station with surveyed location and height of termination

8. Interconnection Customer
 structure, grading plan, access roads, and

wetlands delineation maps (in CAD format)

Start engineering on System Upgrade 11/2025 Connecting Transmission

9. Facilities and Connecting Transmission Owner, Interconnection
 Owner’s Interconnection Facilities Customer
 Initiate ICIF engineering design

10. submittals to Connecting Transmission 11/2025 Interconnection Customer
 Owner

Submit ROW crossings for access roads, 11/2025

11. feeder lines, etc.) for property transaction Interconnection Customer
 review

12. Start procurement for Interconnection

11/2025 Interconnection Customer

Customer’s Interconnection Facilities

4-1

SERVICE AGREEMENT NO. 2913

MILESTONE DATES RESPONSIBLE
 PARTY

Complete review of site control 12/2025 Connecting Transmission

13.

documents Owner

Start procurement for System Upgrade 05/2026 Connecting Transmission

14. Facilities and Connecting Transmission Owner, Interconnection
 Owner’s Interconnection Facilities Customer Determination that all necessary permits

06/2026 Connecting Transmission

15. and approvals have been obtained for

Owner

CTOIFs

16. Start construction of generation facilities 02/2026 Interconnection Customer

Complete engineering on Interconnection

06/2026 Connecting Transmission

Customer’s Interconnection Facilities

17. Owner/Interconnection

(including Connecting Transmission
 Customer

Owner approvals)

Start construction of Interconnection 07/2026

18. Interconnection Customer
 Customer’s Interconnection Facilities

Complete engineering on System 10/2026

Connecting Transmission

Upgrade Facilities and Connecting

19. Owner, Interconnection

Transmission Owner’s Interconnection

Customer
Facilities

Deliver property rights to CTO for SUFs 10/2026

20. (must be provided at least 60 days prior Interconnection Customer
 to construction start)

Complete procurement for 11/2026

21. Interconnection Customer’s Interconnection Customer

Interconnection Facilities

Start construction of System Upgrade 11/2026 Connecting Transmission

22. Facilities and Connecting Transmission Owner, Interconnection
 Owner’s Interconnection Facilities Customer
 Complete construction of Interconnection

05/2027 Customer’s Interconnection Facilities (including all telecom circuits

23. Interconnection Customer

installation and provisioning, as well as all make ready work for revenue metering and RTU )

Connecting Transmission

Start field verification of Interconnection

24. Customer Interconnection Facilities 06/2027 Owner/Interconnection
 Customer

Complete procurement for System 07/2027 Connecting Transmission

Upgrade Facilities and Connecting

25. Owner, Interconnection

Transmission Owner’s Interconnection

Customer
Facilities

Provide Connecting Transmission Owner

26. the NYISO assigned PTID number and 07/2027 Interconnection Customer
 associated project name (must be

4-2

SERVICE AGREEMENT NO. 2913

MILESTONE DATES RESPONSIBLE

PARTY provided at least 2 months in advance of

backfeed)

10/2027 Interconnection

27. Initial Backfeed Date Customer/Connecting
 Transmission Owner

Complete construction and testing of

10/2027 Connecting Transmission

System Upgrade Facilities and

28. Owner, Interconnection

Connecting Transmission Owner’s

Customer

Interconnection Facilities

Complete field verification and witness 10/2027 Connecting Transmission

29. testing of Interconnection Customer’s Owner/Interconnection
 Interconnection Facilities Customer
 11/2027

30. Complete testing and commissioning of
 Small Generating Facility

Interconnection Customer

31. Synchronization Date 11/2027 Interconnection Customer

32. Commercial Operations Date 12/2027 Interconnection Customer

Submit Interconnection Customer’s 12/2027

33. Interconnection Customer
 Interconnection Facilities as builts

Complete System Upgrade Facilities and Connecting Transmission

34. Connecting Transmission Owner’s 03/2028 Owner, Interconnection
 Interconnection Facilities as builts Customer
 Complete review / acceptance of

35. Interconnection Customer’s

03/2028 Connecting Transmission

Owner

Interconnection Facilities as builts

36. Complete project closeout 05/2028 Connecting Transmission
 Owner

37. Issue final invoicing 06/2028 Connecting Transmission
 Owner

To the extent procurement lead times increase, and/or additional system modifications
(temporary or permanent) are required, the schedule must be adjusted accordingly. Furthermore,
the schedule does not account for potential delays or disruptions caused by any Force Majeure
event. Finally, these milestones are contingent upon, but not limited to, outage requirements and
scheduling and the Interconnecting Customer’s successful compliance with all interconnection
requirements and timely completion of its obligations in accordance with this Agreement.

2. Security Arrangement

Interconnection Customer has provided security in the form of cash to the Connecting
Transmission Owner in the amount of $633,500 to satisfy its Project Cost Allocation determined
for its share of the required System Upgrade Facilities.

4-3

SERVICE AGREEMENT NO. 2913

As agreed upon by Connecting Transmission Owner and Interconnection Customer
pursuant to Article 6.1.1 of this Agreement, the Interconnection Customer shall, at the
Interconnection Customer’s discretion, either (i) make prepayments (in lieu of posting the
security contemplated by Article 6.3 of this Agreement), or (ii) provide security installments to
Connecting Transmission Owner in the form contemplated by Article 6.3 of this Agreement, in
each case for its estimated costs to design, engineer, procure, construct, and install Connecting
Transmission Owner’s Interconnection Facilities and Upgrades. Interconnection Customer shall
make such prepayment or security installments in accordance with the following schedule:

(1) $3,997,900.00 such prepayment amount or security amount to be provided at
 least twenty (20) Business Days prior to Interconnection Customer’s issuance of
 the written authorization to proceed with engineering, procurement and
 construction. Such amount to be provided as contemplated by Milestones 2 and 3
 in the table contained in Section 1 of this Attachment 4;

The actual amount of the prepayment or security to be provided by Interconnection
Customer may be adjusted by Connecting Transmission Owner following completion of
engineering for Connecting Transmission Owner’s Interconnection Facilities and System
Upgrade Facilities; Connecting Transmission Owner shall provide written notice to
Interconnection Customer of the adjusted prepayment or security amount, together with
reasonable supporting documentation of the related cost estimates.

If at any time after Interconnection Customer has made a prepayment of amounts due in
accordance with this Section 2 of Attachment 4, Interconnection Customer provides Connecting
Transmission Owner with security satisfying the requirements of Article 6.3 in an amount at
least equal to the amount required to be provided as of such date by this Section 2, Connecting
Transmission Owner will refund to Interconnection Customer any prepayment or portion thereof
that Interconnection Customer has made prior to the date such alternate security is provided and
that has not been applied against Interconnection Customer’s payment obligations as of such
date.

The Connecting Transmission Owner shall not be obligated to commence engineering,
procurement, or construction, as applicable, unless the Connecting Transmission Owner has
received the corresponding prepayment or security installment as contemplated above.

As agreed to, by Interconnection Customer and Connecting Transmission Owner, the
Connecting Transmission Owner shall issue Interconnection Customer an invoice on a monthly
basis detailing Interconnection Customer’s cost responsibility under this Agreement and
providing the net amount, if any, due to Connecting Transmission Owner after Connecting
Transmission Owner has applied any prepayment amounts towards settlement of the invoice. For
the avoidance of doubt, Connecting Transmission Owner shall apply the full amount of any
prepayment amount held by Connecting Transmission Owner against Interconnection
Customer’s cost responsibility under this Agreement before Interconnection Customer is
required to pay any amount in excess of such prepayment amount. If any amount is due from
Interconnection Customer, it shall make such payments pursuant to Article 6.1.1 of this
Agreement. The amount of any security provided by Interconnection Customer under this

4-4

SERVICE AGREEMENT NO. 2913

Section 2 shall be reduced for payments made by Interconnection Customer as provided in
Article 6.3 of this Agreement.

4-5

SERVICE AGREEMENT NO. 2913

Attachment 5

Additional Operating Requirements for the New York State Transmission System, the
 Distribution System and Affected Systems Needed to Support the Interconnection
 Customer’s Needs

The NYISO, in consultation with the Connecting Transmission Owner, shall also provide
requirements that must be met by the Interconnection Customer prior to initiating parallel
operation with the New York State Transmission System or the Distribution System.

(a) The Interconnection Customer must comply with all applicable NYISO tariffs and
procedures, as amended from time to time.

(b) To the extent not inconsistent with the terms of this Agreement, the ISO OATT, or applicable
NYISO procedures, Interconnection Customer must comply with Connecting Transmission
Owner’s operating instructions and requirements, which requirements shall include the dedicated
data circuits, including system protection circuits, to be maintained by Interconnection Customer
in accordance with Article 1.5 of this Agreement. Interconnection Customer must also comply
with the applicable requirements as set out in the Connecting Transmission Owner’s ESBs,
which have been identified and provided to the Interconnection Customer as amended from time
to time to the extent not inconsistent with the terms of this Agreement or applicable NYISO
tariffs and procedures. Upon the Connecting Transmission Owner’s notice to the Interconnection
Customer of amendments to the ESBs, the Interconnection Customer has 30 days to comply with
such amendments.

(c) Line 22 outages will be required for installation of the protection schemes and construction of
the line tap. The specific outage requirements shall be identified, and detailed outage plans
developed, during final engineering. If additional facilities/equipment (temporary or permanent)
are identified during detailed outage planning as being required for the outage to maintain system
reliability and safety, and service to customers, the Interconnection Customer will be responsible
for the costs of such facilities/equipment.

(i) Connecting Transmission Owner’s power control order 7.3, Coordination
of Transmission Outages and In-Service Work requires thirty (30) days advance lead time
for Transmission Outage Application (TOA) submission for any line outage with a
duration longer than three (3) days, and ten (10) days’ notice for outages less than or
equal to three (3) days. Summer scheduling criteria will prohibit any outages on the
transmission lines between June 1 and August 31. However, if high grid loading occurs
(due to hot weather) or severe storms are forecasted in late in September, as has happened
historically, outages in September can be cancelled by the NYISO.

(ii) If additional facilities/equipment (temporary or permanent) are identified
during detailed outage planning as being required for the outage to maintain system
reliability and safety, and service to customers, the Interconnection Customer will be
responsible for the costs of such facilities/equipment.

(d) Limited Operation

5-1

SERVICE AGREEMENT NO. 2913

As detailed in Section A of Attachment 2 to this Agreement, the Interconnection
Customer plans to construct a 12.1 MW solar farm with a proposed In-Service Date of October

2027.

The Connecting Transmission Owner’s Interconnection Facilities described in
Attachment 2 and the System Upgrade Facilities described in Attachment 6 are required to
enable the Small Generating Facility to operate at its maximum generating capability. To the
extent any of the required Interconnection Facilities or Upgrades (“Required Facilities”) will not
be completed prior to the Interconnection Customer’s completion of its Small Generating
Facility, Interconnection Customer may request, pursuant to Section 5.4, no later than 12 months
prior to the Commercial Operations Date of the Small Generating Facility that the NYISO, in
coordination with the Connecting Transmission Owner, perform, at Interconnection Customer’s
expense, certain analyses to determine the extent to which the Small Generating Facility can
operate at its maximum generating capacity prior to the completion of the Required
Facilities. The Interconnection Customer agrees to be responsible for the costs of any work
required to implement the results of the study.

The Parties shall amend this Agreement, pursuant to Article 12.2, to reflect the
requirements or conditions on the Small Generating Facility’s ability to operate in limited
operation.

5-2

SERVICE AGREEMENT NO. 2913

Attachment 6

Connecting Transmission Owner’s Description of its Upgrades and Best Estimate of

Upgrade Costs

The NYISO, in consultation with the Connecting Transmission Owner, shall describe
Upgrades and provide an itemized best estimate of the cost, including overheads, of the
Upgrades and annual operation and maintenance expenses associated with such Upgrades. The
Connecting Transmission Owner shall functionalize Upgrade costs and annual expenses as either
transmission or distribution related.

The cost estimate for System Upgrade Facilities and System Deliverability Upgrades
shall be taken from the ISO OATT Attachment S cost allocation process or applicable
Interconnection Study, as required by Section 32.3.5.3.2 of Attachment Z. The cost estimate for
Distribution Upgrades shall include the costs of Distribution Upgrades that are reasonably
allocable to the Interconnection Customer at the time the estimate is made, and the costs of any
Distribution Upgrades not yet constructed that were assumed in the Interconnection Studies for
the Interconnection Customer but are, at the time of the estimate, an obligation of an entity other
than the Interconnection Customer.

The cost estimates for Distribution Upgrades, System Upgrade Facilities, and System
Deliverability Upgrades are estimates. The Interconnection Customer is ultimately responsible
for the actual cost of the Distribution Upgrades, System Upgrade Facilities, and System
Deliverability Upgrades needed for its Small Generating Facility, as that is determined under
Attachments S, X, and Z of the ISO OATT.

A. DISTRIBUTION UPGRADES

None.

B. STAND-ALONE SYSTEM UPGRADE FACILITIES (“SUF”)

None.

C. OTHER SYSTEM UPGRADE FACILITIES (“SUF”)

Interconnection of the Small Generating Facility to the Star Lake Tap of Line 22 will
require modifications at Browns Falls Stations, removal of the existing mobile tap, and an
upgrade to the station service at Star Lake Station as further described below.

1. Browns Falls Substation

Browns Falls Station is in the process of being rebuilt as part of an asset separation
project and the Connecting Transmission Owner anticipates that there will be adequate space in
the new control enclosure to accommodate the protection modifications required for the Small
Generating Facility. All modifications shall be completed in the Browns Falls Station yard and
control enclosure.

6-1

SERVICE AGREEMENT NO. 2913

a) Protection

The Small Generating Facility can only be in service under normal system conditions
(i.e., when Browns Falls 34.5 kV network is in normal configuration). When the tie switches
between Line 22 and Line 21 are closed or the tie switches between Mine Road and Browns
Falls are closed, the Small Generating Facility must be taken offline. The protection and telecom
systems requirements and modifications contain in this section are for interconnection of the
Small Generating Facility under normal operating conditions.

Relay settings changes will be required at Browns Falls to coordinate with the infeed
from the Small Generating Facility and the new protection schemes at Star Lake Station.

DTT transmit and receive (single package) between Browns Falls and Star Lake stations
is required and will require installation of one (1) GARD Pro relay and one (1) 43TT control
handle.

Due to the addition of the Small Generating Facility, an area coordination study will be
completed during final engineering design stage and may result in resetting of relays in the area.
The cost of the coordination study is included in the cost estimates provided in the Facilities
Study for the Small Generating Facility. If the study determines that additional relays in the area
must be reset, the costs associated with resetting the relays will be the responsibility of the
Interconnection Customer.

b) Controls and Integration

A new RTU is being installed as part of the Browns Falls rebuild project and it is
anticipated that it will only need to be reprogrammed for this project. The human-machine-
interface (“HMI”), sequence of events recording (“SER”), and fault recorder will also need to be
reprogrammed to accommodate the additions required for the project.

c) Telecommunications

For protection systems and EMS RTU data transmittal, the Connecting Transmission
Owner anticipates the use of the dark fiber for a connection from the Star Lake to Browns Falls.
This will require installation of floor mount telecom racks with an optical node, DCB loop
channel bank, 48 VDC telecom power plant system and DPS NG-420 RTU. After the dark fiber
is installed and turned up, the Connecting Transmission Owner will provision one (1) telecom
C37.94 and one (1) telecom circuit for the RTU between Star Lake and Browns Falls.

(Note: Since the indefeasible right to use (“IRU”) cannot be signed at the time of
execution of this Agreement, it is assumed that the dark fiber will be available should this project
proceed to engineering, procurement and construction. The estimated cost of the dark fiber at
the time of the Facilities Study is $250k and is included in the Star Lake cost estimate. The
actual cost of the dark fiber IRU will be determined during final engineering and could increase
significantly. The Interconnection Customer is responsible for the actual cost.)

2. Mobile Tap

6-2

SERVICE AGREEMENT NO. 2913

The existing mobile tap located outside Star Lake Station must be removed to
accommodate construction of the line tap. As such, a new mobile tap must be constructed to
replace it. The new mobile tap will require installation of:

• one (1) horizontal upright load break wood pole structure and load break switch; and

• approximately 63 circuit feet of 336.4 ACSR 18/1 “Merlin” conductor.

3. Star Lake Station Service

To accommodate the additional facilities at Star Lake Station, the station service must be
upgraded to 25kVA.

D. AFFECTED SYSTEM UPGRADES

None.

E. COST ESTIMATES RELATED TO DISTIRBUTION UPGRADES AND SYSTEM
 UPGRADE FACILITIES

The estimated (+30%/-15%) of the work associated with the interconnection of the Facility
are presented in the table below. The cost estimates are in 2024 dollars and are based on the
Facilities Study and assumptions listed below.

As described in the Facilities Study for the Small Generating Facility, the estimates provided
herein:

Assume:

6-3

SERVICE AGREEMENT NO. 2913

• 5X10 construction work week;

• outages are available;

• all major material is delivered to site (i.e., no costs are included for transport from storage);

• existing equipment to remain is functional; and

• no mobile generation or additional facilities are required for outages.

Exclude:

• discussions and negotiations of issued interconnection study;

• application fees;

• applicable surcharges;

• overall project sales tax;

• property taxes;

• line switching;

• property/easement acquisitions;

• access roads and associated matting;

• future operation and maintenance costs;

• recurring monthly communications circuits’ charges, if any, responsible by the

Interconnection Customer to the communications utility;

• soil testing;

• adverse field conditions such as rock, water, weather, and Interconnection Customer

electrical equipment obstructions;

• additional facilities/equipment (temporary or permanent) required for outages to maintain

system reliability and safety, and service to customers;

• environmental mitigation;

• extended engineering to minimize outage time or Connecting Transmission Owner’s

public duty to serve;

• extended craft labor hours, to minimize outage and/or construction time; or

6-4

SERVICE AGREEMENT NO. 2913

• any required permits.

6-5

SERVICE AGREEMENT NO. 2913

Attachment 7

Insurance Coverage

Interconnection Customer shall, at its own expense, maintain in force throughout the
period of this Agreement, the following minimum insurance coverage, with insurers authorized
to do business in the State of New York.

Commercial General Liability Insurance including, but not limited to, bodily injury,
property damage, products/completed operations, contractual and personal injury liability with a
combined single limit of $2 million per occurrence, $5 million annual aggregate.

7-1

SERVICE AGREEMENT NO. 2913

Attachment 8

Initial Synchronization Date

[Date]

New York Independent System Operator, Inc.
Attn: Vice President, Operations
10 Krey Boulevard Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration and Commercial Services
Address: 2 Hanson Place, 12th Floor

City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171

E-mail: Vishal.Ahirrao@nationalgrid.com

Re: BR Benson Mines Solar Small Generating Facility

Dear __________________:

On [Date] [Interconnection Customer] initially synchronized the Small Generating Facility
[specify units, if applicable]. This letter confirms that [Interconnection Customer]’s Initial
Synchronization Date was [specify].

Thank you.

[Signature]

[Interconnection Customer Representative]

8-1

SERVICE AGREEMENT NO. 2913

Attachment 9

Commercial Operation Date

[Date]

New York Independent System Operator, Inc.
Attn: Vice President, Operations
10 Krey Boulevard Rensselaer, NY 12144

Niagara Mohawk Power Corporation d/b/a National Grid
Attention: Director, Customer Energy Integration and Commercial Services
Address: 2 Hanson Place, 12th Floor

City: Brooklyn State: NY Zip: 11217
Phone: 516-448-7171

E-mail: Vishal.Ahirrao@nationalgrid.com

Re: BR Benson Mines Solar Small Generating Facility

Dear __________________:

On [Date] [Interconnection Customer] has completed Trial Operation of Unit No. ___. This
letter confirms that [Interconnection Customer] commenced Commercial Operation of the
Small Generating Facility [specify units, as applicable], effective as of [Date plus one day].

Thank you.

[Signature]

[Interconnection Customer Representative]

9-1