**SERVICE AGREEMENT NO. 2734**

**SERVICE AGREEMENT NO. 2734**

**AMENDED AND RESTATED**

**TRANSMISSION PROJECT**

**INTERCONNECTION AGREEMENT**

**AMONG THE**

**NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.**

**AND**

**CONSOLIDATED EDISON COMPANY OF NEW YORK, INC.**

**AND**

**NEW YORK TRANSCO, LLC**

**Dated as of August 2, 2024**

**(Dover PAR Substation for**

**New York Energy Solution Segment B Transmission Project)**

**SERVICE AGREEMENT NO. 2734**

**TABLE OF CONTENTS**

Page Number

[ARTICLE 1. DEFINITIONS.........................................................................................................2](#br7)

[ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION .............................................8](#br13)

[Effective Date..................................................................................................... 8](#br13)

[Term of Agreement............................................................................................ 8](#br13)

[Termination........................................................................................................ 8](#br13)

[Termination Costs............................................................................................ 10](#br15)

[Disconnection................................................................................................... 11](#br16)

[Survival. ........................................................................................................... 11](#br16)

[ARTICLE 3. REGULATORY FILINGS....................................................................................11](#br16)

[ARTICLE 4. SCOPE OF SERVICE ...........................................................................................11](#br16)

[Interconnection of Transmission Facilities...................................................... 11](#br16)

[No Transmission Delivery Service. ................................................................. 12](#br17)

[No Other Services. ........................................................................................... 12](#br17)

[ARTICLE 5. NETWORK UPGRADE FACILITIES ENGINEERING, PROCUREMENT,](#br17)

[AND CONSTRUCTION...............................................................................................................12](#br17)

[Network Upgrade Facilities ............................................................................. 12](#br17)

[General Conditions Applicable to Network Upgrade Facilities Constructed by](#br17)

[Transmission Developer. .......................................................................................................... 12](#br17)

[Equipment Procurement................................................................................... 14](#br19)

[Construction Commencement.......................................................................... 14](#br19)

[Work Progress.................................................................................................. 14](#br19)

[Information Exchange...................................................................................... 15](#br20)

[Network Upgrade Facilities ............................................................................. 15](#br20)

[Access Rights................................................................................................... 15](#br20)

[Lands of Other Property Owners. .................................................................... 16](#br21)

[Permits. ............................................................................................................ 16](#br21)

[Suspension. ...................................................................................................... 16](#br21)

[Taxes. ............................................................................................................... 17](#br22)

[Tax Status; Non-Jurisdictional Entities............................................................ 22](#br27)

[Modification..................................................................................................... 22](#br27)

[ARTICLE 6. TESTING AND INSPECTION.............................................................................23](#br28)

[Pre-In-Service Date Testing and Modifications............................................... 23](#br28)

[Post-In-Service Date Testing and Modifications............................................. 23](#br28)

[Right to Observe Testing. ................................................................................ 23](#br28)

[Right to Inspect. ............................................................................................... 24](#br29)

[ARTICLE 7. METERING...........................................................................................................24](#br29)

[General............................................................................................................. 24](#br29)

[Check Meters. .................................................................................................. 24](#br29)

[Standards.......................................................................................................... 24](#br29)

[Testing of Metering Equipment. ...................................................................... 25](#br30)

[Metering Data................................................................................................... 25](#br30)

[ARTICLE 8. COMMUNICATIONS ..........................................................................................25](#br30)

[Transmission Developer Obligations............................................................... 25](#br30)

i



**SERVICE AGREEMENT NO. 2734**

[Remote Terminal Unit...................................................................................... 26](#br31)

[No Annexation. ................................................................................................ 26](#br31)

[ARTICLE 9. OPERATIONS.......................................................................................................26](#br31)

[General............................................................................................................. 26](#br31)

[NYISO and Connecting Transmission Owner Obligations. ............................ 26](#br31)

[Transmission Developer Obligations............................................................... 27](#br32)

[Outages and Interruptions. ............................................................................... 27](#br32)

[Switching and Tagging Rules. ......................................................................... 30](#br35)

[Disturbance Analysis Data Exchange. ............................................................. 30](#br35)

[ARTICLE 10. MAINTENANCE ..................................................................................................30](#br35)

[Connecting Transmission Owner Obligations. ................................................ 30](#br35)

[Transmission Developer Obligations............................................................... 30](#br35)

[Coordination..................................................................................................... 30](#br35)

[Secondary Systems. ......................................................................................... 30](#br35)

[Operating and Maintenance Expenses. ............................................................ 31](#br36)

[ARTICLE 11. PERFORMANCE OBLIGATION ........................................................................31](#br36)

[Transmission Project........................................................................................ 31](#br36)

[Network Upgrade Facilities. ............................................................................ 31](#br36)

[Special Provisions for Affected Systems. ........................................................ 31](#br36)

[Provision of Security........................................................................................ 31](#br36)

[Forfeiture of Security....................................................................................... 32](#br37)

[Network Upgrade Facility Costs...................................................................... 33](#br38)

[Line Outage Costs............................................................................................ 33](#br38)

[ARTICLE 12. INVOICE ...............................................................................................................33](#br38)

[General............................................................................................................. 33](#br38)

[Final Invoice and Refund of Remaining Security............................................ 34](#br39)

[Payment............................................................................................................ 34](#br39)

[Disputes............................................................................................................ 34](#br39)

[ARTICLE 13. EMERGENCIES....................................................................................................34](#br39)

[Obligations....................................................................................................... 34](#br39)

[Notice............................................................................................................... 35](#br40)

[Immediate Action............................................................................................. 35](#br40)

[NYISO, Transmission Developer, and Connecting Transmission Owner](#br40)

[Authority.](#br40)

[35](#br40)

[Limited Liability. ............................................................................................. 35](#br40)

[ARTICLE 14. REGULATORY REQUIREMENTS AND GOVERNING LAW........................35](#br40)

[Regulatory Requirements................................................................................. 35](#br40)

[Governing Law................................................................................................. 36](#br41)

[ARTICLE 15. NOTICES...............................................................................................................36](#br41)

[General............................................................................................................. 36](#br41)

[Billings and Payments...................................................................................... 36](#br41)

[Alternative Forms of Notice. ........................................................................... 36](#br41)

[Operations and Maintenance Notice. ............................................................... 36](#br41)

[ARTICLE 16. FORCE MAJEURE ...............................................................................................37](#br42)

[ARTICLE 17. DEFAULT .............................................................................................................37](#br42)

[General............................................................................................................. 37](#br42)

ii



**SERVICE AGREEMENT NO. 2734**

[Right to Terminate. .......................................................................................... 37](#br42)

[ARTICLE 18. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE ...............37](#br42)

[Indemnity. ........................................................................................................ 37](#br42)

[No Consequential Damages............................................................................. 39](#br44)

[Insurance. ......................................................................................................... 39](#br44)

[ARTICLE 19. ASSIGNMENT......................................................................................................41](#br46)

[ARTICLE 20. SEVERABILITY...................................................................................................42](#br47)

[ARTICLE 21. COMPARABILITY...............................................................................................42](#br47)

[ARTICLE 22. CONFIDENTIALITY............................................................................................42](#br47)

[Confidentiality. ................................................................................................ 42](#br47)

[Term................................................................................................................. 42](#br47)

[Confidential Information.................................................................................. 42](#br47)

[Scope................................................................................................................ 43](#br48)

[Release of Confidential Information................................................................ 43](#br48)

[Rights. .............................................................................................................. 43](#br48)

[No Warranties. ................................................................................................. 43](#br48)

[Standard of Care............................................................................................... 44](#br49)

[Order of Disclosure.......................................................................................... 44](#br49)

[Termination of Agreement............................................................................... 44](#br49)

[Remedies.......................................................................................................... 44](#br49)

[Disclosure to FERC, its Staff, or a State.......................................................... 45](#br50)

[Required Notices Upon Requests or Demands for Confidential Information . 45](#br50)

[ARTICLE 23. TRANSMISSION DEVELOPER AND CONNECTING TRANSMISSION](#br50)

[OWNER NOTICES OF ENVIRONMENTAL RELEASES ........................................................45](#br50)

[ARTICLE 24. INFORMATION REQUIREMENT......................................................................46](#br51)

[Information Acquisition................................................................................... 46](#br51)

[Information Submission Concerning the Network Upgrade Facilities............ 46](#br51)

[Updated Information Submission Concerning the Transmission Project........ 46](#br51)

[Information Supplementation........................................................................... 47](#br52)

[ARTICLE 25. INFORMATION ACCESS AND AUDIT RIGHTS.............................................47](#br52)

[Information Access. ......................................................................................... 47](#br52)

[Reporting of Non-Force Majeure Events......................................................... 47](#br52)

[Audit Rights. .................................................................................................... 48](#br53)

[Audit Rights Periods. ....................................................................................... 48](#br53)

[Audit Results.................................................................................................... 48](#br53)

[ARTICLE 26. SUBCONTRACTORS ..........................................................................................48](#br53)

[General............................................................................................................. 48](#br53)

[Responsibility of Principal............................................................................... 49](#br54)

[No Limitation by Insurance. ............................................................................ 49](#br54)

[ARTICLE 27. DISPUTES.............................................................................................................49](#br54)

[Submission....................................................................................................... 49](#br54)

[External Arbitration Procedures....................................................................... 49](#br54)

[Arbitration Decisions. ...................................................................................... 50](#br55)

[Costs................................................................................................................. 50](#br55)

[Termination...................................................................................................... 50](#br55)

[ARTICLE 28. REPRESENTATIONS, WARRANTIES AND COVENANTS ...........................50](#br55)

iii



**SERVICE AGREEMENT NO. 2734**

[General............................................................................................................. 50](#br55)

[ARTICLE 29. MISCELLANEOUS ..............................................................................................51](#br56)

[Binding Effect.................................................................................................. 51](#br56)

[Conflicts........................................................................................................... 51](#br56)

[Rules of Interpretation...................................................................................... 51](#br56)

[Compliance. ..................................................................................................... 52](#br57)

[Joint and Several Obligations. ......................................................................... 52](#br57)

[Entire Agreement. ............................................................................................ 52](#br57)

[No Third Party Beneficiaries. .......................................................................... 52](#br57)

[Waiver.............................................................................................................. 53](#br58)

[Headings........................................................................................................... 53](#br58)

[Multiple Counterparts. ..................................................................................... 53](#br58)

[Amendment...................................................................................................... 53](#br58)

[Modification by the Parties.............................................................................. 53](#br58)

[Reservation of Rights....................................................................................... 53](#br58)

[No Partnership.................................................................................................. 54](#br59)

[Other Transmission Rights............................................................................... 54](#br59)

Appendices

iv



**SERVICE AGREEMENT NO. 2734**

**AMENDED AND RESTATED TRANSMISSION PROJECT INTERCONNECTION**

**AGREEMENT**

**THIS AMENDED AND RESTATED TRANSMISSION PROJECT**

**INTERCONNECTION AGREEMENT** (“Agreement”) is made and entered into this 2nd day

of August, 2024, by and among New York Transco, LLC, a limited liability company organized

and existing under the laws of the State of New York (“Transmission Developer” with a

Transmission Project), the New York Independent System Operator, Inc., a not-for-profit

corporation organized and existing under the laws of the State of New York (“NYISO”), and

Consolidated Edison Company of New York, Inc. a transportation corporation organized and

existing under the laws of the State of New York (“Connecting Transmission Owner”).

Transmission Developer, the NYISO, or Connecting Transmission Owner each may be referred

to as a “Party” or collectively referred to as the “Parties.”

**RECITALS**

**WHEREAS**, NYISO operates the New York State Transmission System, and Connecting

Transmission Owner owns certain facilities included in the New York State Transmission

System;

**WHEREAS**, Transmission Developer intends to construct, own, and operate a Transmission

Project described in Appendix C to this Agreement that will interconnect to the New York State

Transmission System;

**WHEREAS,** the NYISO selected the Transmission Project proposed by Transmission

Developer and Niagara Mohawk Power Corporation d/b/a National Grid (“National Grid”) as the

more efficient or cost effective transmission solution to address a Public Policy Transmission

Need in accordance with the NYISO’s Public Policy Transmission Planning Process located in

Attachment Y of the ISO OATT;

**WHEREAS**, Transmission Developer and National Grid entered into the Development

Agreement (as defined herein) with the NYISO for purposes of constructing the Transmission

Project and placing it in-service to satisfy the Public Policy Transmission Need;

**WHEREAS**, National Grid assigned its rights, duties, and obligations under the Development

Agreement to Transmission Developer on March 10, 2020, giving Transmission Developer sole

rights to the development of the Transmission Project;

**WHEREAS,** the Parties acknowledge that Connecting Transmission Owner is not a party to the

Development Agreement and is not bound by any of the terms or conditions contained therein;

**WHEREAS**, the Transmission Project was evaluated pursuant to the NYISO’s Transmission

Interconnection Procedures located in Attachment P of the ISO OATT;

**WHEREAS**, portions of the Transmission Project will interconnect to the New York State

Transmission System at several different facilities owned and operated by the Connecting

Transmission Owner;

1

**SERVICE AGREEMENT NO. 2734**

**WHEREAS**, Transmission Interconnection Studies determined that certain Network Upgrade

Facilities were required on the Connecting Transmission Owner’s and the Transmission

Developer’s systems for the Transmission Project to connect reliably to the systems in a manner

that meets the NYISO Transmission Interconnection Standard;

**WHEREAS,** the Parties agreed to enter into two separate Transmission Project Interconnection

Agreements to address the interconnection of the Transmission Project at different facilities

owned and operated by Connecting Transmission Owner, as described in Appendix A; and

**WHEREAS**, Transmission Developer, NYISO, and Connecting Transmission Owner have

agreed to enter into this Agreement for the purpose of interconnecting a certain portion of the

Transmission Project as specified in Appendix A with the Connecting Transmission Owner’s

Line 398 345 kV transmission line included in the New York State Transmission System and

constructing and placing in-service the Network Upgrade Facilities that will be owned and

operated by the Connecting Transmission Owner as specified in Appendix A;

**NOW, THEREFORE,** in consideration of and subject to the mutual covenants contained herein,

it is agreed:

**ARTICLE 1. DEFINITIONS**

Whenever used in this Agreement with initial capitalization, the following terms shall have the

meanings specified in thi[s Article 1. Te](#br7)rms used in this Agreement with initial capitalization that

are not defined in t[his Article 1](#br7) shall have the meanings specified in Section 1 of the ISO OATT,

Section 22.1 of Attachment P of the ISO OATT, Section 25.1.2 of Attachment S of the ISO

OATT, the body of the Transmission Interconnection Procedures or the body of this Agreement.

**Affected System** shall mean an electric system other than the transmission system owned,

controlled or operated by the Connecting Transmission Owner that may be affected by the

proposed interconnection.

**Affected System Operator** shall mean the entity that operates an Affected System.

**Affected Transmission Owner** shall mean the New York public utility or authority (or its

designated agent) other than the Connecting Transmission Owner that (i) owns facilities used for

the transmission of Energy in interstate commerce and provides Transmission Service under the

Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State

Transmission System where System Deliverability Upgrades, System Upgrade Facilities, or

Network Upgrade Facilities are or will be installed pursuant to Attachment P, Attachment X,

Attachment Z, or Attachment S to the ISO OATT.

**Affiliate** shall mean, with respect to a person or entity, any individual, corporation, partnership,

firm, joint venture, association, joint-stock company, trust or unincorporated organization,

directly or indirectly controlling, controlled by, or under common control with, such person or

entity. The term “control” shall mean the possession, directly or indirectly, of the power to

2

**SERVICE AGREEMENT NO. 2734**

direct the management or policies of a person or an entity. A voting interest of ten percent or

more shall create a rebuttable presumption of control.

**Applicable Laws and Regulations** shall mean all duly promulgated applicable federal, state and

local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or

administrative orders, permits and other duly authorized actions of any Governmental Authority,

including but not limited to Environmental Law.

**Applicable Reliability Councils** shall mean the NERC, the NPCC and the NYSRC.

**Applicable Reliability Standards** shall mean the requirements and guidelines of the Applicable

Reliability Councils, and the Transmission District to which the Transmission Developer’s

Transmission Project is directly interconnected, as those requirements and guidelines are

amended and modified and in effect from time to time; provided that no Party shall waive its

right to challenge the applicability or validity of any requirement or guideline as applied to it in

the context of this Agreement.

**Base Case** shall mean the base case power flow, short circuit, and stability data bases used for

the Transmission Interconnection Studies by the NYISO, Connecting Transmission Owner, or

the Transmission Developer, as described in Section 22.6.1 of the Transmission Interconnection

Procedures.

**Breach** shall mean the failure of a Party to perform or observe any material term or condition of

this Agreement.

**Breaching Party** shall mean a Party that is in Breach of this Agreement.

**Business Day** shall mean Monday through Friday, excluding federal holidays.

**Calendar Day** shall mean any day including Saturday, Sunday or a federal holiday.

**Confidential Information** shall mean any information that is defined as confidentia[l by Article](#br47)

[22](#br47) of this Agreement.

**Connecting Transmission Owner** shall mean the New York public utility or authority (or its

designated agent) that (i) owns facilities used for the transmission of Energy in interstate

commerce and provides Transmission Service under the Tariff, (ii) owns, leases or otherwise

possesses an interest in the portion of the New York State Transmission System or Distribution

System at the Point(s) of Interconnection, and (iii) is a Party to this Agreement. For purposes of

this Agreement, the Connecting Transmission Owner is defined in the introductory paragraph.

**Control Area** shall mean an electric power system or combination of electric power systems to

which a common automatic generation control scheme is applied in order to: (1) match, at all

times, the power output of the Generators within the electric power system(s) and capacity and

energy purchased from entities outside the electric power system(s), with the Load within the

electric power system(s); (2) maintain scheduled interchange with other Control Areas, within

the limits of Good Utility Practice; (3) maintain the frequency of the electric power system(s)

within reasonable limits in accordance with Good Utility Practice; and (4) provide sufficient

3

**SERVICE AGREEMENT NO. 2734**

generating capacity to maintain Operating Reserves in accordance with Good Utility Practice. A

Control Area must be certified by the NPCC.

**Default** shall mean the failure of a Party in Breach of this Agreement to cure such Breach in

accordance [with Article 17](#br42) of this Agreement.

**Development Agreement** shall mean the agreement executed between the NYISO,

Transmission Developer, and Niagara Mohawk Power Corporation d/b/a National Grid

concerning the development of the Transmission Project, dated January 10, 2020, and assigned

by National Grid to Transmission Developer on March 10, 2020, as it may be amended from

time to time.

**Effective Date** shall mean the date on which this Agreement becomes effective upon execution

by the Parties, subject to acceptance by the Commission, or if filed unexecuted, upon the date

specified by the Commission.

**Emergency** shall mean any abnormal condition or situation which the Connecting Transmission

Owner, Transmission Developer, or NYISO, in their sole discretion, deems imminently likely to

endanger life or property, or adversely affect or impair the New York State Transmission

System, Connecting Transmission Owner’s electrical system, the Transmission Project, or the

electrical or transmission systems of others to which they are directly or indirectly connected,

which requires immediate automatic or manual action to correct. Such an abnormal system

condition or situation includes, without limitation, overloading or potential overloading

(exceeding thermal limits of pre- and post-contingency), excessive voltage drop, exceeding

voltage limits as defined by the NYISO, Transmission Developer, or Connecting Transmission

Owner, load shedding, voltage reduction, operating reserve deficiencies, frequency deviations,

over-generation or other non-normal conditions. Economic hardship of a Party will not

constitute an “Emergency.”

**Emergency State** shall mean the condition or state that the New York State Power System is in

when an abnormal condition occurs that requires automatic or immediate manual action to

prevent or limit loss of the New York State Transmission System or Generators that could

adversely affect the reliability of the New York State Power System.

**Environmental Law** shall mean Applicable Laws and Regulations relating to pollution or

protection of the environment or natural resources.

**Facilities Study** shall mean the study conducted pursuant to Section 22.9 of Attachment P of the

ISO OATT to determine a list of facilities required to reliably interconnect the Transmission

Project (including Network Upgrade Facilities) as identified in the System Impact Study, the cost

of those facilities, and the time required to interconnect the Transmission Project with the New

York State Transmission System.

**Facilities Study Agreement** shall mean the agreement described in Section 22.9.1 of

Attachment P of the ISO OATT for conducting the Facilities Study.

**Federal Power Act** shall mean the Federal Power Act, as amended, 16 U.S.C. §§ 791a *et seq.*

(“FPA”).

4

**SERVICE AGREEMENT NO. 2734**

**FERC** shall mean the Federal Energy Regulatory Commission (“Commission”) or its successor.

**Force Majeure** shall mean any act of God, labor disturbance, act of the public enemy, war,

insurrection, riot, fire, storm or flood, explosion, breakage or accident to machinery or

equipment, any order, regulation or restriction imposed by governmental, military or lawfully

established civilian authorities, or any other cause beyond a Party’s control. A Force Majeure

event does not include acts of negligence or intentional wrongdoing by the Party claiming Force

Majeure.

**Good Utility Practice** shall mean any of the practices, methods and acts engaged in or approved

by a significant portion of the electric industry during the relevant time period, or any of the

practices, methods and acts which, in the exercise of reasonable judgment in light of the facts

known at the time the decision was made, could have been expected to accomplish the desired

result at a reasonable cost consistent with good business practices, reliability, safety and

expedition. Good Utility Practice is not intended to be limited to the optimum practice, method,

or act to the exclusion of all others, but rather to delineate acceptable practices, methods, or acts

generally accepted in the region.

**Governmental Authority** shall mean any federal, state, local or other governmental regulatory

or administrative agency, court, commission, department, board, or other governmental

subdivision, legislature, rulemaking board, tribunal, or other governmental authority having

jurisdiction over any of the Parties, their respective facilities, or the respective services they

provide, and exercising or entitled to exercise any administrative, executive, police, or taxing

authority or power; provided, however, that such term does not include Transmission Developer,

NYISO, Affected Transmission Owner, Connecting Transmission Owner, or any Affiliate

thereof.

**Hazardous Substances** shall mean any chemicals, materials or substances defined as or

included in the definition of “hazardous substances,” “hazardous wastes,” “hazardous materials,”

“hazardous constituents,” “restricted hazardous materials,” “extremely hazardous substances,”

“toxic substances,” “radioactive substances,” “contaminants,” “pollutants,” “toxic pollutants” or

words of similar meaning and regulatory effect under any applicable Environmental Law, or any

other chemical, material or substance, exposure to which is prohibited, limited or regulated by

any applicable Environmental Law.

**Initial Synchronization Date(s)** shall mean the date(s) upon which the Transmission Project and

Network Upgrade Facilities, as applicable, are initially synchronized with the New York State

Transmission System and upon which Trial Operation begins, which date(s) shall be set forth in

the milestones table in Appendix B. The Connecting Transmission Owner or Transmission

Developer, as applicable, must provide notice of the Initial Synchronization Date(s) to the other

Parties in the form of Appendix E-1 to this Agreement.

**In-Service Date(s)** shall mean the date(s) upon which the Transmission Project and Network

Upgrade Facilities, as applicable, are energized consistent with the provisions of this Agreement

and available to provide Transmission Service under the NYISO’s Tariffs, which date(s) shall be

set forth in the milestones table in Appendix B. The Connecting Transmission Owner or

5

**SERVICE AGREEMENT NO. 2734**

Transmission Developer, as applicable, must provide notice of the In-Service Date(s) to the other

Parties in the form of Appendix E-2 to this Agreement.

**IRS** shall mean the Internal Revenue Service.

**Metering Equipment** shall mean all metering equipment installed or to be installed at the

Transmission Project pursuant to this Agreement, including but not limited to instrument

transformers, MWh-meters, data acquisition equipment, transducers, remote terminal unit,

communications equipment, phone lines, and fiber optics.

**Metering Points** shall mean the location(s) identified by the NYISO for any Metering

Equipment associated with the Transmission Project that are required for the Transmission

Project to provide zonal or subzonal metering data.

**NERC** shall mean the North American Electric Reliability Council or its successor organization.

**Network Upgrade Facilities** shall mean the least costly configuration of commercially available

components of electrical equipment that can be used, consistent with Good Utility Practice and

Applicable Reliability Requirements, to make the modifications or additions to the New York

State Transmission System that are required for the proposed Transmission Project to connect

reliably to the system in a manner that meets the NYISO Transmission Interconnection Standard.

For purposes of this Agreement, the Network Upgrade Facilities are described in Appendix A of

this Agreement.

**New York State Transmission System** shall mean the entire New York State electric

transmission system, which includes (i) the Transmission Facilities Under ISO Operational

Control; (ii) the Transmission Facilities Requiring ISO Notification; and (iii) all remaining

transmission facilities within the New York Control Area.

**Notice of Dispute** shall mean a written notice of a dispute or claim that arises out of or in

connection with this Agreement or its performance.

**NPCC** shall mean the Northeast Power Coordinating Council or its successor organization.

**NYISO Transmission Interconnection Standard** shall mean the reliability standard that must

be met by any Transmission Project proposing to connect to the New York State Transmission

System. The standard is designed to ensure reliable access by the proposed project to the New

York State Transmission System.

**NYSRC** shall mean the New York State Reliability Council or its successor organization.

**Operating Agreement** shall mean the operating agreement for non-incumbent transmission

owners between the NYISO and Transmission Developer with Service Agreement No. 2271 of

the ISO OATT, with an effective date of May 23, 2016, as the agreement may be amended from

time to time.

**Party or Parties** shall mean NYISO, Connecting Transmission Owner, or Transmission

Developer or any combination of the above.

6

**SERVICE AGREEMENT NO. 2734**

**Point(s) of Change of Ownership** shall mean the point(s), as set forth in Appendix C to this

Agreement, where the Transmission Developer’s Transmission Project connects to the

Connecting Transmission Owner’s system.

**Point(s) of Interconnection** shall mean the point(s), as set forth in Appendix C to this

Agreement, where the Transmission Developer’s Transmission Project connects to the New

York State Transmission System.

**Reasonable Efforts** shall mean, with respect to an action required to be attempted or taken by a

Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and

are otherwise substantially equivalent to those a Party would use to protect its own interests.

**Security** shall mean a bond, irrevocable letter of credit, parent company guarantee or other form

of security from an entity with an investment grade rating, executed for the benefit of the

Connecting Transmission Owner, meeting the commercially reasonable requirements of the

Connecting Transmission Owner with which it is required to be posted pursuant to Artic[le 11.3,](#br36)

and consistent with the Uniform Commercial Code of the jurisdiction identified in Artic[le 14.2.1](#br41)

of this Agreement.

**Services Tariff** shall mean the NYISO Market Administration and Control Area Tariff, as filed

with the Commission, and as amended or supplemented from time to time, or any successor tariff

thereto.

**System Impact Study** shall mean the study conducted pursuant to Section 22.8 of Attachment P

of the ISO OATT that evaluates the impact of the proposed Transmission Project on the safety

and reliability of the New York State Transmission System and, if applicable, and Affected

System, to determine what Network Upgrade Facilities are needed for the proposed

Transmission Project to connect reliably to the New York State Transmission System in a

manner that meets the NYISO Transmission Interconnection Standard.

**System Impact Study Agreement** shall mean the agreement described in Section 22.8.1 of

Attachment P of the ISO OATT for conducting the System Impact Study.

**System Protection Facilities** shall mean the equipment, including necessary protection signal

communications equipment, required to (1) protect the New York State Transmission System

from faults or other electrical disturbances occurring at the Transmission Project and (2) protect

the Transmission Project from faults or other electrical system disturbances occurring on the

New York State Transmission System or on other delivery systems or other generating systems

to which the New York State Transmission System is directly connected.

**Tariff** shall mean the NYISO Open Access Transmission Tariff (“OATT”), as filed with the

Commission, and as amended or supplemented from time to time, or any successor tariff.

**Transmission Developer** shall mean an entity that proposes to interconnect its Transmission

Project to the New York State Transmission System in compliance with the NYISO

Transmission Interconnection Standard. For purposes of this Agreement, the Transmission

Developer is defined in the introductory paragraph.

7

**SERVICE AGREEMENT NO. 2734**

**Transmission Interconnection Application** shall mean the Transmission Developer’s request,

in the form of Appendix 1 to the Transmission Interconnection Procedures, to interconnect a

Transmission Project to the New York State Transmission System.

**Transmission Interconnection Procedures (“TIP”)** shall mean the interconnection procedures

applicable to a Transmission Interconnection Application pertaining to a Transmission Project

that are included in Attachment P of the ISO OATT.

**Transmission Interconnection Study** shall mean any of the following studies: the Optional

Feasibility Study, the System Impact Study, and the Facilities Study described in the

Transmission Interconnection Procedures.

**Transmission Project** shall mean the Transmission Developer’s proposed transmission facility

or facilities that collectively satisfy the definition of Transmission Project in Section 22.3.1 of

Attachment P of the ISO OATT. For purposes of this Agreement, the Transmission Project is

described in Appendix C of this Agreement.

**Transmission Project Interconnection Agreement** shall mean this interconnection agreement

applicable to the interconnection of the Transmission Project to the New York State

Transmission System.

**Trial Operation** shall mean the period(s) during which Connecting Transmission Owner or

Transmission Developer, as applicable, is engaged in on-site test operations and commissioning

of the Transmission Project or Network Upgrade Facilities prior to the In-Service Date.

**ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION**

**Effective Date.**

This Agreement shall become effective upon execution by the Parties, subject to

acceptance by FERC, or if filed unexecuted, upon the date specified by FERC. The NYISO and

Connecting Transmission Owner shall promptly file this Agreement with FERC upon execution

in accordance with Article 3.

**Term of Agreement.**

Subject to the provisions of Article [2.3, thi](#br13)s Agreement shall remain in effect for a period

of forty (40) years from the Effective Date and shall be automatically renewed for each

successive one-year period thereafter.

**Termination.**

**2.3.1 Written Notice.**

**2.3.1.1**

**Written Notice of Termination**

This Agreement may be terminated: (i) by any Party after giving the other Parties ninety

(90) Calendar Days advance written notice following the termination of the Development

8



**SERVICE AGREEMENT NO. 2734**

Agreement prior to the completion of its term, subject to the suspension requirements in

Article [2.3.1.2](#br14) below; or (ii) by the mutual agreement in writing of all Parties.

**2.3.1.2**

**Suspension Period for Project Transfer**

2.3.1.2.1 If the Development Agreement is terminated prior to the completion of its

term and the NYISO exercises its right under the Development Agreement and the Tariff to

request that a developer other than the Transmission Developer complete the Transmission

Project, this Agreement shall be suspended. The suspension period will last until either: (i) the

NYISO issues a written determination that the Transmission Project cannot be transferred to

another developer and will not proceed, or (ii) the Transmission Developer completes the

assignment of this Agreement to a new developer selected by the NYISO as set forth in

Article [2.3.1.2.3. Dur](#br14)ing the suspension period, the running of any advanced notice of

termination time period pursuant to Article [2.3.1.1](#br13) will be paused. The Agreement shall not be

terminated during the suspension period without the written agreement of all Parties.

2.3.1.2.2 During the suspension period, the Transmission Developer and

Connecting Transmission Owner shall suspend all work associated with the construction and

installation of the Network Upgrade Facilities required for only that Transmission Developer

under this Agreement with the condition that the New York State Transmission System shall be

left in a safe and reliable condition in accordance with Good Utility Practice and the safety and

reliability criteria of Connecting Transmission Owner and NYISO. In such event, Transmission

Developer shall be responsible for all reasonable and necessary costs and/or obligations in

accordance with this Agreement, including those which Connecting Transmission Owner (i) has

incurred pursuant to this Agreement prior to the suspension and (ii) incurs in suspending such

work, including any costs incurred to perform such work as may be necessary to ensure the

safety of persons and property and the integrity of the New York State Transmission System

during such suspension and, if applicable, any costs incurred in connection with the cancellation

or suspension of material, equipment and labor contracts which Connecting Transmission Owner

cannot reasonably avoid; provided, however, that prior to canceling or suspending any such

material, equipment or labor contract, Connecting Transmission Owner shall obtain

Transmission Developer’s authorization to do so, which authorization shall not unreasonably be

withheld, conditioned or delayed.

2.3.1.2.3 If, pursuant to its Tariff, the NYISO selects a new developer to complete

the Transmission Project, Transmission Developer shall coordinate with the new developer

concerning the assignment of this Agreement to the new developer pursuant to the assignment

requirements i[n Article 19](#br46) of this Agreement. All liabilities under this Agreement existing prior

to such transfer shall remain with the Transmission Developer, unless otherwise agreed upon by

the Transmission Developer and the new developer as part of their good faith negotiations

regarding the transfer.

**2.3.2 Default.**

Any Party may terminate this Agreement in accordance [with Article 17.](#br42)

9

**SERVICE AGREEMENT NO. 2734**

**2.3.3 Compliance.**

Notwithstanding Artic[les 2.3.1](#br13) a[nd 2.3.2, no ter](#br14)mination of this Agreement shall become

effective until the Parties have complied with all Applicable Laws and Regulations applicable to

such termination, including the filing with FERC of a notice of termination of this Agreement,

which notice has been accepted for filing by FERC.

**Termination Costs.**

If a Party elects to terminate this Agreement pursuant to Artic[le 2.3.1](#br13) above, the

Transmission Developer shall be responsible for all costs that are the responsibility of the

Transmission Developer under this Agreement that are incurred by the Transmission Developer

or the other Parties through the date, as applicable, of the other Parties’ receipt of a Party’s notice

of termination or of the Parties’ mutual agreement to terminate the agreement. Such costs

include any cancellation costs relating to orders or contracts. In the event of termination by the

Transmission Developer, all Parties shall use commercially Reasonable Efforts to mitigate the

costs, damages and charges arising as a consequence of termination. Upon termination of this

Agreement, unless otherwise ordered or approved by FERC:

**2.4.1** With respect to any portion of the Network Upgrade Facilities that have not yet

been constructed or installed, but that is being relied upon by other projects in the manner

described in Artic[le 11.5](#br37) of this Agreement, Transmission Developer shall forfeit any remaining

Security in accordance with the requirements in Artic[le 11.5.](#br37)

**2.4.2** With respect to any portion of the Network Upgrade Facilities that has not yet

been constructed or installed and is not being relied upon by other projects in the manner

described in Article 11.5 of this Agreement, the Connecting Transmission Owner shall to the

extent possible and with Transmission Developer’s authorization and the consent of the NYISO

cancel any pending orders of, or return, any materials or equipment for, or contracts for

construction of, such facilities; provided that in the event Transmission Developer elects not to

authorize such cancellation, Transmission Developer shall assume all payment obligations with

respect to such materials, equipment, and contracts, and the Connecting Transmission Owner

shall deliver such material and equipment, and, if necessary, assign such contracts, to

Transmission Developer as soon as practicable, at Transmission Developer’s expense. To the

extent that Transmission Developer has already paid Connecting Transmission Owner for any or

all such costs of materials or equipment not taken by Transmission Developer, Connecting

Transmission Owner shall promptly refund such amounts to Transmission Developer, less any

costs, including penalties incurred by the Connecting Transmission Owner to cancel any pending

orders of or return such materials, equipment, or contracts.

**2.4.3** Connecting Transmission Owner may, at its option, retain any portion of such

materials, equipment, or facilities that Transmission Developer chooses not to accept delivery of,

in which case Connecting Transmission Owner shall be responsible for all costs associated with

procuring such materials, equipment, or facilities.

**2.4.4** With respect to any portion of the Network Upgrade Facilities, and any other

facilities already installed or constructed pursuant to the terms of this Agreement, Transmission

10



**SERVICE AGREEMENT NO. 2734**

Developer shall be responsible for all costs associated with the removal, relocation or other

disposition or retirement of such materials, equipment, or facilities.

**Disconnection.**

Upon termination of this Agreement, Transmission Developer and Connecting

Transmission Owner will take all appropriate steps to disconnect the Transmission Developer’s

Transmission Project from the New York State Transmission System and to perform such work

as may be necessary to ensure that the New York State Transmission System shall be left in a

safe and reliable condition in accordance with Good Utility Practice and the safety and reliability

criteria of Connecting Transmission Owner and NYISO. All costs required to effectuate such

disconnection shall be borne by the Transmission Developer, unless such termination resulted

from the Connecting Transmission Owner’s Default of this Agreement.

**Survival.**

This Agreement shall continue in effect after termination to the extent necessary to

provide for final billings and payments and for costs incurred hereunder; including billings and

payments pursuant to this Agreement and Transmission Developer’s satisfaction of the Security

requirements in Article 11.5; to permit the determination and enforcement of liability and

indemnification obligations arising from acts or events that occurred while this Agreement was

in effect; and to permit Transmission Developer and Connecting Transmission Owner each to

have access to the lands of the other pursuant to this Agreement or other applicable agreements,

to disconnect, remove or salvage its own facilities and equipment.

**ARTICLE 3. REGULATORY FILINGS**

NYISO and Connecting Transmission Owner shall file this Agreement (and any

amendment hereto) with the appropriate Governmental Authority, if required. Any information

related to studies for interconnection asserted by Transmission Developer to contain Confidential

Information shall be treated in accordance [with Article 22](#br47) of this Agreement and Attachment F

to the ISO OATT. If the Transmission Developer has executed this Agreement, or any

amendment thereto, the Transmission Developer shall reasonably cooperate with NYISO and

Connecting Transmission Owner with respect to such filing and to provide any information

reasonably requested by NYISO and Connecting Transmission Owner needed to comply with

Applicable Laws and Regulations.

**ARTICLE 4. SCOPE OF SERVICE**

**Interconnection of Transmission Facilities.**

The Transmission Developer’s Transmission Project and the Connecting Transmission

Owner’s transmission system shall interconnect at the Points of Interconnection set forth in

Appendix C of this Agreement in accordance with the terms and conditions of this Agreement.

11



**SERVICE AGREEMENT NO. 2734**

**No Transmission Delivery Service.**

The execution of this Agreement does not constitute a request for, nor agreement to

provide, any Transmission Service under the ISO OATT, and does not convey any right to

deliver electricity to any specific customer or Point of Delivery.

**No Other Services.**

The execution of this Agreement does not constitute a request for, nor agreement to

provide Energy, any Ancillary Services or Installed Capacity under the NYISO Market

Administration and Control Area Services Tariff (“Services Tariff”).

**ARTICLE 5. NETWORK UPGRADE FACILITIES ENGINEERING,**

**PROCUREMENT, AND CONSTRUCTION**

**Network Upgrade Facilities**

Unless otherwise mutually agreed to by Transmission Developer and Connecting

Transmission Owner, Transmission Developer shall select the In-Service Date and Initial

Synchronization Date of the Network Upgrade Facilities, and such dates shall be set forth in

Appendix B hereto. The Connecting Transmission Owner’s and Transmission Developer’s

respective obligations to design, procure, construct, install, and own the Network Upgrade

Facilities, as applicable, shall be set forth in Appendix A hereto. The Connecting Transmission

Owner and Transmission Developer shall each use Reasonable Efforts to complete the Network

Upgrade Facilities for which it has construction responsibility by the dates set forth in Appendix

B hereto. The Connecting Transmission Owner shall not be required to undertake any action

which is inconsistent with its standard safety practices, its material and equipment specifications,

its design criteria and construction procedures, its labor agreements, and Applicable Laws and

Regulations. In the event the Connecting Transmission Owner reasonably expects that it will not

be able to complete the Network Upgrade Facilities for which it has construction responsibility,

by the specified dates, the Connecting Transmission Owner shall promptly provide written notice

to the Transmission Developer and NYISO, and shall undertake Reasonable Efforts to meet the

earliest dates thereafter.

**General Conditions Applicable to Network Upgrade Facilities**

**Constructed by Transmission Developer.**

Where Transmission Developer has assumed responsibility for the design, procurement

and/or construction of the Network Upgrade Facilities as set forth in Appendix A, the following

conditions apply:

**5.2.1** Transmission Developer shall engineer, procure equipment, and/or construct the

Network Upgrade Facilities (or portions thereof) using Good Utility Practice and using standards

and specifications provided in advance by the Connecting Transmission Owner;

**5.2.2** Transmission Developer’s engineering, procurement and/or construction of the

Network Upgrade Facilities shall comply with all requirements of law to which Connecting

12



**SERVICE AGREEMENT NO. 2734**

Transmission Owner would be subject in the engineering, procurement or construction of the

Network Upgrade Facilities.

**5.2.3** Connecting Transmission Owner shall review and approve the engineering

design, equipment acceptance tests, and the construction of the Network Upgrade Facilities;

**5.2.4** Prior to commencement of construction, Transmission Developer shall provide to

Connecting Transmission Owner and NYISO a schedule for construction of the Network

Upgrade Facilities, and shall promptly respond to requests for information from Connecting

Transmission Owner or NYISO;

**5.2.5** At any time during construction, Connecting Transmission Owner shall have the

right to gain unrestricted access to the Network Upgrade Facilities and to conduct inspections of

the same;

**5.2.6** At any time during construction, should any phase of the engineering, equipment

procurement, or construction of the Network Upgrade Facilities not meet the standards and

specifications provided by Connecting Transmission Owner, the Transmission Developer shall

be obligated to remedy deficiencies in that portion of the Network Upgrade Facilities;

**5.2.7** Transmission Developer shall indemnify Connecting Transmission Owner and

NYISO for claims arising from the Transmission Developer’s construction of Network Upgrade

Facilities under procedures applicable to Artic[le 18.1](#br42) Indemnity;

**5.2.8** Transmission Developer shall transfer control of Network Upgrade Facilities to

the Connecting Transmission Owner as set forth in Appendix A hereto;

**5.2.9** Transmission Developer shall transfer ownership of the Network Upgrade

Facilities to Connecting Transmission Owner as set forth in Appendix A hereto;

**5.2.10** Connecting Transmission Owner shall approve and accept for operation and

maintenance the Network Upgrade Facilities to the extent engineered, procured, and constructed

in accordance with this Article [5.2;](#br17)

**5.2.11** Transmission Developer shall deliver to NYISO and Connecting Transmission

Owner “as built” drawings, information, and any other documents that are reasonably required

by NYISO or Connecting Transmission Owner to assure that the Network Upgrade Facilities are

built to the standards and specifications required by Connecting Transmission Owner; and

**5.2.12** The Transmission Developer shall be responsible for the costs that Connecting

Transmission Owner incurs in executing the responsibilities enumerated to Connecting

Transmission Owner under Article [5.2. Th](#br17)e Connecting Transmission Owner shall invoice

Transmission Developer for such costs pursuant t[o Article 12.](#br38)

13

**SERVICE AGREEMENT NO. 2734**

**Equipment Procurement.**

The Connecting Transmission Owner shall commence design of the Network Upgrade

Facilities for which it has construction responsibility and procure necessary equipment as soon as

practicable after all of the following conditions are satisfied, unless the Transmission Developer

and Connecting Transmission Owner otherwise agree in writing:

**5.3.1** NYISO and Connecting Transmission Owner have completed the Facilities Study

pursuant to the Facilities Study Agreement;

**5.3.2** The NYISO has completed the required cost allocation analyses, and

Transmission Developer has provided Security to the Connecting Transmission Owner in

accordance with Artic[le 11.3](#br36) by the date specified in Appendix B hereto; and

**5.3.3** The Connecting Transmission Owner has received written authorization to

proceed with design and procurement from the Transmission Developer by the date specified in

Appendix B hereto.

**Construction Commencement.**

The Connecting Transmission Owner shall commence construction of the Network

Upgrade Facilities for which it has construction responsibility as set forth in Appendix A as soon

as practicable after the following additional conditions are satisfied:

**5.4.1** Approval of the appropriate Governmental Authority has been obtained for any

facilities requiring regulatory approval;

**5.4.2** Necessary real property rights and rights-of-way have been obtained by the

Transmission Developer, to the extent required for the construction of a discrete aspect of the

Network Upgrade Facilities; and

**5.4.3** The Connecting Transmission Owner has received written authorization to

proceed with construction from the Transmission Developer by the date specified in Appendix B

hereto; and

**5.4.4** The Transmission Developer has provided Security to the Connecting

Transmission Owner in accordance with Article 11.4 by the dates specified in Appendix B

hereto.

**Work Progress.**

The Transmission Developer and Connecting Transmission Owner will keep each other

and the NYISO advised periodically as to the progress of their respective design, procurement

and construction efforts of the Transmission Project and the Network Upgrade Facilities. Any

Party may, at any time, request a progress report from the Transmission Developer or

Connecting Transmission Owner.

14



**SERVICE AGREEMENT NO. 2734**

**Information Exchange.**

As soon as reasonably practicable after the Effective Date, the Transmission Developer

and Connecting Transmission Owner shall exchange information, and provide NYISO the same

information, regarding the design and compatibility of the Transmission Project and Network

Upgrade Facilities and the compatibility of the Transmission Project and Network Upgrade

Facilities with the New York State Transmission System, and shall work diligently and in good

faith to make any necessary design changes.

**Network Upgrade Facilities**

Transmission Developer shall submit initial specifications for the Network Upgrade

Facilities for which it is responsible pursuant to Appendix A to Connecting Transmission Owner

and NYISO at least one hundred eighty (180) Calendar Days prior to the Initial Synchronization

Date; and final specifications for review and comment at least ninety (90) Calendar Days prior to

the Initial Synchronization Date. Connecting Transmission Owner and NYISO shall review

such specifications to ensure that the Network Upgrade Facilities are compatible with the

technical specifications, operational control, and safety requirements of the Connecting

Transmission Owner and NYISO and comment on such specifications within thirty (30)

Calendar Days of Transmission Developer’s submission. All specifications provided hereunder

shall be deemed to be Confidential Information.

The review of Transmission Developer’s final specifications by Connecting Transmission

Owner and NYISO shall not be construed as confirming, endorsing, or providing a warranty as

to the design, fitness, safety, durability or reliability of the Transmission Project or Network

Upgrade Facilities. Transmission Developer shall make such changes to the Network Upgrade

Facilities as may reasonably be required by Connecting Transmission Owner or NYISO, in

accordance with Good Utility Practice, to ensure that the Network Upgrade Facilities are

compatible with the technical specifications, operational control, and safety requirements of the

Connecting Transmission Owner and NYISO.

Transmission Developer and Connecting Transmission Owner shall design and construct

the Network Upgrade Facilities for which each is responsible pursuant to Appendix A in

accordance with Good Utility Practice and the Connecting Transmission Owner’s standards and

specifications. Transmission Developer and Connecting Transmission Owner shall each deliver

to the other Parties pursuant to the dates set forth in Appendix B “as-built” drawings, information

and documents for the Network Upgrade Facilities.

The Connecting Transmission Owner shall transfer operational control of Network

Upgrade Facilities at a voltage of 230 kV or greater upon completion of such facilities, but shall

not transfer operational control of Network Upgrade Facilities of a voltage of less than 230 kV.

**Access Rights.**

Upon reasonable notice and supervision by a Granting Party, and subject to any required

or necessary regulatory approvals, the Connecting Transmission Owner and Transmission

Developer (each a “Granting Party”) shall each furnish to the other Parties (“Access Party”) at no

15



**SERVICE AGREEMENT NO. 2734**

cost any rights of use, licenses, rights of way and easements with respect to lands owned or

controlled by the Granting Party, its agents (if allowed under the applicable agency agreement),

or any Affiliate, that are necessary to enable the Access Party to obtain ingress and egress at the

Point(s) of Interconnection, or any other necessary point to construct, operate, maintain, repair,

test (or witness testing), inspect, replace or remove facilities and equipment to: (i) interconnect

the Transmission Project and Network Upgrade Facilities with the New York State Transmission

System; (ii) operate and maintain the Transmission Project, Network Upgrade Facilities, and the

New York State Transmission System; and (iii) disconnect or remove the Access Party’s

facilities and equipment upon termination of this Agreement. In exercising such licenses, rights

of way and easements, the Access Party shall not unreasonably disrupt or interfere with normal

operation of the Granting Party’s business and shall adhere to the safety rules and procedures

established in advance, as may be changed from time to time, by the Granting Party and provided

to the Access Party. The Access Party shall indemnify the Granting Party against all claims of

injury or damage from third parties resulting from the exercise of the access rights provided for

herein.

**Lands of Other Property Owners.**

If any part of the Network Upgrade Facilities is to be installed on property owned by

persons other than Transmission Developer or Connecting Transmission Owner, the Connecting

Transmission Owner shall at Transmission Developer’s expense use efforts, similar in nature and

extent to those that it typically undertakes for its own or affiliated generation, including use of its

eminent domain authority, and to the extent consistent with state law, to procure from such

persons any rights of use, licenses, rights of way and easements that are necessary to construct,

operate, maintain, test, inspect, replace or remove the Network Upgrade Facilities upon such

property.

**Permits.**

NYISO, Connecting Transmission Owner and the Transmission Developer shall

cooperate with each other in good faith in obtaining all permits, licenses and authorizations that

are necessary to accomplish the interconnection in compliance with Applicable Laws and

Regulations. With respect to this paragraph, Connecting Transmission Owner shall provide

permitting assistance to the Transmission Developer comparable to that provided to the

Connecting Transmission Owner’s own, or an Affiliate’s, generation or transmission facilities, if

any.

**Suspension.**

Transmission Developer reserves the right, upon written notice to Connecting

Transmission Owner and NYISO, to suspend at any time all work by Transmission Developer

and Connecting Transmission Owner associated with the construction and installation of the

Network Upgrade Facilities required for only that Transmission Developer under this Agreement

with the condition that the New York State Transmission System shall be left in a safe and

reliable condition in accordance with Good Utility Practice and the safety and reliability criteria

of Connecting Transmission Owner and NYISO. If the suspension will impact the Transmission

Developer’s ability to meet any Advisory Milestones or Critical Path Milestones in the

16



**SERVICE AGREEMENT NO. 2734**

Development Agreement, Transmission Developer shall notify the NYISO in accordance with

the requirements in Article 3.3 of the Development Agreement. NYISO reserves the right, upon

written notice to Transmission Developer and Connecting Transmission Owner, to require the

suspension of all work by Transmission Developer and Connecting Transmission Owner

associated with the engineering, procurement, and/or construction services under this Agreement

if the NYISO terminates the Development Agreement pursuant to Article 8 of the Development

Agreement.

In the event of suspension under this Artic[le 5.11,](#br21) Transmission Developer shall be

responsible for all reasonable and necessary costs and/or obligations in accordance with the ISO

OATT and the Facilities Study report including those which Connecting Transmission Owner

(i) has incurred pursuant to this Agreement prior to the suspension and (ii) incurs in suspending

such work, including any costs incurred to perform such work as may be necessary to ensure the

safety of persons and property and the integrity of the New York State Transmission System

during such suspension and, if applicable, any costs incurred in connection with the cancellation

or suspension of material, equipment and labor contracts which Connecting Transmission Owner

cannot reasonably avoid; provided, however, that prior to canceling or suspending any such

material, equipment or labor contract, Connecting Transmission Owner shall obtain

Transmission Developer’s authorization to do so.

Connecting Transmission Owner shall invoice Transmission Developer for such costs

pursuant t[o Article 12](#br38) and shall use due diligence to minimize its costs. In the event

Transmission Developer suspends work by the Transmission Developer and Connecting

Transmission Owner required under this Agreement pursuant to this Article [5.11, a](#br21)nd has not

informed the Parties that it is recommencing its work and requested Connecting Transmission

Owner to recommence its work required under this Agreement on or before the expiration of

three (3) years following commencement of such suspension, this Agreement shall be deemed

terminated. The three-year period shall begin on the date of the written notice required under

this Artic[le 5.11](#br21) or the date specified in the written notice of suspension.

**Taxes.**

**5.12.1 Developer Payments Not Taxable.**

The Transmission Developer and Connecting Transmission Owner intend that all

payments or property transfers made by Transmission Developer to Connecting Transmission

Owner for the installation of the Network Upgrade Facilities shall be non-taxable, either as

contributions to capital, or as an advance, in accordance with the Internal Revenue Code and any

applicable state income tax laws and shall not be taxable as contributions in aid of construction

or otherwise under the Internal Revenue Code and any applicable state income tax laws.

**5.12.2 Representations and Covenants.**

In accordance with IRS Notice 2016-36, Transmission Developer represents and

covenants that (i) ownership of the electricity generated at the Large Generating Facility will

pass to another party prior to the transmission of the electricity on the New York State

Transmission System, (ii) for income tax purposes, the amount of any payments and the cost of

17



**SERVICE AGREEMENT NO. 2734**

any property transferred to the Connecting Transmission Owner for the Network Upgrade

Facilities will be capitalized by Transmission Developer as an intangible asset and recovered

using the straight-line method over a useful life of twenty (20) years, and (iii) any portion of the

Connecting Transmission Owner’s Network Upgrade Facility that is a “dual-use intertie,” within

the meaning of IRS Notice 2016-36, is reasonably expected to carry only a de minimis amount of

electricity in the direction of the Large Generating Facility. For this purpose, “de minimis

amount” means no more than 5 percent of the total power flows in both directions, calculated in

accordance with the “5 percent test” set forth in IRS Notice 2016-36. This is not intended to be

an exclusive list of the relevant conditions that must be met to conform to IRS requirements for

non-taxable treatment.

At Connecting Transmission Owner’s request, Transmission Developer shall provide

Connecting Transmission Owner with a report from an independent engineer confirming its

representation in clause (iii), above. Connecting Transmission Owner represents and covenants

that the cost of the Network Upgrade Facilities paid for by Transmission Developer will have no

net effect on the base upon which rates are determined.

**5.12.3 Indemnification for the Cost Consequences of Current Tax Liability**

**Imposed Upon the Connecting Transmission Owner.**

Notwithstanding Artic[le 5.12.1,](#br22) Transmission Developer shall protect, indemnify and

hold harmless Connecting Transmission Owner from the cost consequences of any current tax

liability imposed against Connecting Transmission Owner as the result of payments or property

transfers made by Transmission Developer to Connecting Transmission Owner under this

Agreement, as well as any interest and penalties, other than interest and penalties attributable to

any delay caused by Connecting Transmission Owner.

Connecting Transmission Owner shall not include a gross-up for the cost consequences

of any current tax liability in the amounts it charges Transmission Developer under this

Agreement unless (i) Connecting Transmission Owner has determined, in good faith, that the

payments or property transfers made by Transmission Developer to Connecting Transmission

Owner should be reported as income subject to taxation or (ii) any Governmental Authority

directs Connecting Transmission Owner to report payments or property as income subject to

taxation; provided, however, that Connecting Transmission Owner may require Transmission

Developer to provide security, in a form reasonably acceptable to Connecting Transmission

Owner (such as a parental guarantee or a letter of credit), in an amount equal to the cost

consequences of any current tax liability under this Artic[le 5.12.](#br22) Transmission Developer shall

reimburse Connecting Transmission Owner for such costs on a fully grossed-up basis, in

accordance with Artic[le 5.12.4, withi](#br24)n thirty (30) Calendar Days of receiving written notification

from Connecting Transmission Owner of the amount due, including detail about how the amount

was calculated.

This indemnification obligation shall terminate at the earlier of (1) the expiration of the

ten-year testing period and the applicable statute of limitation, as it may be extended by the

Connecting Transmission Owner upon request of the IRS, to keep these years open for audit or

adjustment, or (2) the occurrence of a subsequent taxable event and the payment of any related

indemnification obligations as contemplated by this Artic[le 5.12.](#br22)

18

**SERVICE AGREEMENT NO. 2734**

**5.12.4 Tax Gross-Up Amount.**

Transmission Developer’s liability for the cost consequences of any current tax liability

under this Artic[le 5.12](#br22) shall be calculated on a fully grossed-up basis. Except as may otherwise

be agreed to by the parties, this means that Transmission Developer will pay Connecting

Transmission Owner, in addition to the amount paid for the Network Upgrade Facilities, an

amount equal to (1) the current taxes imposed on Connecting Transmission Owner (“Current

Taxes”) on the excess of (a) the gross income realized by Connecting Transmission Owner as a

result of payments or property transfers made by Transmission Developer to Connecting

Transmission Owner under this Agreement (without regard to any payments under this

Article [5.12) (](#br22)the “Gross Income Amount”) over (b) the present value of future tax deductions

for depreciation that will be available as a result of such payments or property transfers (the

“Present Value Depreciation Amount”), plus (2) an additional amount sufficient to permit the

Connecting Transmission Owner to receive and retain, after the payment of all Current Taxes, an

amount equal to the net amount described in clause (1).

For this purpose, (i) Current Taxes shall be computed based on Connecting Transmission

Owner’s composite federal and state tax rates at the time the payments or property transfers are

received and Connecting Transmission Owner will be treated as being subject to tax at the

highest marginal rates in effect at that time (the “Current Tax Rate”), and (ii) the Present Value

Depreciation Amount shall be computed by discounting Connecting Transmission Owner’s

anticipated tax depreciation deductions as a result of such payments or property transfers by

Connecting Transmission Owner’s current weighted average cost of capital. Thus, the formula

for calculating Transmission Developer’s liability to Connecting Transmission Owner pursuant

to this Article [5.12.4](#br24) can be expressed as follows: (Current Tax Rate x (Gross Income Amount -

Present Value Depreciation Amount))/(1 - Current Tax Rate). Transmission Developer’s

estimated tax liability in the event taxes are imposed shall be stated in Appendix A.

**5.12.5 Reserved.**

**5.12.6 Subsequent Taxable Events.**

If, within 10 years from the date on which the relevant Network Upgrade Facilities are

placed in service, (i) Transmission Developer Breaches the covenants contained in

Article [5.12.2, (ii) a](#br22) “disqualification event” occurs within the meaning of IRS Notice 2016-36,

or (iii) this Agreement terminates and Connecting Transmission Owner retains ownership of the

Network Upgrade Facilities, the Transmission Developer shall pay a tax gross-up for the cost

consequences of any current tax liability imposed on Connecting Transmission Owner,

calculated using the methodology described in Article [5.12.4](#br24) and in accordance with IRS Notice

2016-36.

**5.12.7 Contests.**

In the event any Governmental Authority determines that Connecting Transmission

Owner’s receipt of payments or property constitutes income that is subject to taxation,

19

**SERVICE AGREEMENT NO. 2734**

Connecting Transmission Owner shall notify Transmission Developer, in writing, within thirty

(30) Calendar Days of receiving notification of such determination by a Governmental

Authority. Upon the timely written request by Transmission Developer and at Transmission

Developer’s sole expense, Connecting Transmission Owner may appeal, protest, seek abatement

of, or otherwise oppose such determination. Upon Transmission Developer’s written request and

sole expense, Connecting Transmission Owner may file a claim for refund with respect to any

taxes paid under this Artic[le 5.12, whe](#br22)ther or not it has received such a determination.

Connecting Transmission Owner reserves the right to make all decisions with regard to the

prosecution of such appeal, protest, abatement or other contest, including the selection of counsel

and compromise or settlement of the claim, but Connecting Transmission Owner shall keep

Transmission Developer informed, shall consider in good faith suggestions from Transmission

Developer about the conduct of the contest, and shall reasonably permit Transmission Developer

or a Transmission Developer representative to attend contest proceedings.

Transmission Developer shall pay to Connecting Transmission Owner on a periodic

basis, as invoiced by Connecting Transmission Owner, Connecting Transmission Owner’s

documented reasonable costs of prosecuting such appeal, protest, abatement or other contest,

including any costs associated with obtaining the opinion of independent tax counsel described

in this Article [5.12.7. The](#br24) Connecting Transmission Owner may abandon any contest if the

Transmission Developer fails to provide payment to the Connecting Transmission Owner within

thirty (30) Calendar Days of receiving such invoice. At any time during the contest, Connecting

Transmission Owner may agree to a settlement either with Transmission Developer’s consent or

after obtaining written advice from nationally-recognized tax counsel, selected by Connecting

Transmission Owner, but reasonably acceptable to Transmission Developer, that the proposed

settlement represents a reasonable settlement given the hazards of litigation. Transmission

Developer’s obligation shall be based on the amount of the settlement agreed to by Transmission

Developer, or if a higher amount, so much of the settlement that is supported by the written

advice from nationally-recognized tax counsel selected under the terms of the preceding

sentence. The settlement amount shall be calculated on a fully grossed-up basis to cover any

related cost consequences of the current tax liability. The Connecting Transmission Owner may

also settle any tax controversy without receiving the Transmission Developer’s consent or any

such written advice; however, any such settlement will relieve the Transmission Developer from

any obligation to indemnify Connecting Transmission Owner for the tax at issue in the contest

(unless the failure to obtain written advice is attributable to the Transmission Developer’s

unreasonable refusal to the appointment of independent tax counsel).

**5.12.8 Refund.**

In the event that (a) any legislative change or administrative announcement, notice, ruling

or other determination makes it reasonably clear to Connecting Transmission Owner in good

faith that any amount paid or the value of any property transferred by Transmission Developer to

Connecting Transmission Owner under the terms of this Agreement is not taxable to Connecting

Transmission Owner, (b) any abatement, appeal, protest, or other contest results in a

determination that any payments or transfers made by Transmission Developer to Connecting

Transmission Owner are not subject to federal income tax, or (c) if Connecting Transmission

Owner receives a refund from any taxing authority for any overpayment of tax attributable to any

20

**SERVICE AGREEMENT NO. 2734**

payment or property transfer made by Transmission Developer to Connecting Transmission

Owner pursuant to this Agreement, Connecting Transmission Owner shall promptly refund to

Transmission Developer the following:

(i)

Any payment made by Transmission Developer under this Artic[le 5.12](#br22) for taxes

that is attributable to the amount determined to be non-taxable, together with interest thereon,

(ii)

Interest on any amounts paid by Transmission Developer to Connecting

Transmission Owner for such taxes which Connecting Transmission Owner did not submit to the

taxing authority, calculated in accordance with the methodology set forth in FERC’s regulations

at 18 C.F.R. §35.19a(a)(2)(iii) from the date payment was made by Transmission Developer to

the date Connecting Transmission Owner refunds such payment to Transmission Developer, and

(iii) With respect to any such taxes paid by Connecting Transmission Owner, any

refund or credit Connecting Transmission Owner receives or to which it may be entitled from

any Governmental Authority, interest (or that portion thereof attributable to the payment

described in clause (i), above) owed to the Connecting Transmission Owner for such

overpayment of taxes (including any reduction in interest otherwise payable by Connecting

Transmission Owner to any Governmental Authority resulting from an offset or credit);

provided, however, that Connecting Transmission Owner will remit such amount promptly to

Transmission Developer only after and to the extent that Connecting Transmission Owner has

received a tax refund, credit or offset from any Governmental Authority for any applicable

overpayment of income tax related to the Network Upgrade Facilities.

The intent of this provision is to leave both the Transmission Developer and Connecting

Transmission Owner, to the extent practicable, in the event that no taxes are due with respect to

any payment for Network Upgrade Facilities hereunder, in the same position they would have

been in had no such tax payments been made.

**5.12.9 Taxes Other Than Income Taxes.**

Upon the timely request by Transmission Developer, and at Transmission Developer’s

sole expense, Connecting Transmission Owner shall appeal, protest, seek abatement of, or

otherwise contest any tax (other than federal or state income tax) asserted or assessed against

Connecting Transmission Owner for which Transmission Developer may be required to

reimburse Connecting Transmission Owner under the terms of this Agreement. Transmission

Developer shall pay to Connecting Transmission Owner on a periodic basis, as invoiced by

Connecting Transmission Owner, Connecting Transmission Owner’s documented reasonable

costs of prosecuting such appeal, protest, abatement, or other contest. Transmission Developer

and Connecting Transmission Owner shall cooperate in good faith with respect to any such

contest. Unless the payment of such taxes is a prerequisite to an appeal or abatement or cannot

be deferred, no amount shall be payable by Transmission Developer to Connecting Transmission

Owner for such taxes until they are assessed by a final, non-appealable order by any court or

agency of competent jurisdiction. In the event that a tax payment is withheld and ultimately due

and payable after appeal, Transmission Developer will be responsible for all taxes, interest and

21

**SERVICE AGREEMENT NO. 2734**

penalties, other than penalties attributable to any delay caused by Connecting Transmission

Owner.

**Tax Status; Non-Jurisdictional Entities.**

**5.13.1 Tax Status.**

Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.

Nothing in this Agreement is intended to adversely affect the tax status of any Party including

the status of NYISO, or the status of any Connecting Transmission Owner with respect to the

issuance of bonds including, but not limited to, Local Furnishing Bonds. Notwithstanding any

other provisions of this Agreement, Connecting Transmission Owner shall not be required to

comply with any provisions of this Agreement that would result in the loss of tax-exempt status

of any of their Tax-Exempt Bonds or impair its ability to issue future tax-exempt obligations. For

purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Connecting

Transmission Owner, the interest on which is not included in gross income under the Internal

Revenue Code.

**Modification.**

**5.14.1 General.**

If, prior to the In-Service Date of the Transmission Project or Network Upgrade

Facilities, either the Transmission Developer or Connecting Transmission Owner proposes to

modify the Transmission Project or Network Upgrade Facilities, they must inform the other

Parties of the proposed modification and must satisfy the requirements for such modifications in

(i) Section 22.5.4 of Attachment P to the ISO OATT, and (ii) the Development Agreement. The

Transmission Developer shall be responsible for the cost of any such additional modifications,

including the cost of studying the materiality and impact of the modification.

Following the In-Service Date of the Transmission Project or Network Upgrade

Facilities, either the Transmission Developer or Connecting Transmission Owner may undertake

modifications to its facilities covered by this Agreement. If either the Transmission Developer

or Connecting Transmission Owner plans to undertake a modification that reasonably may be

expected to affect the other Party’s facilities, that Party shall provide to the other Party, and to

NYISO, sufficient information regarding such modification so that the other Party and NYISO

may evaluate the potential impact of such modification prior to commencement of the work.

Such information shall be deemed to be Confidential Information hereunder and shall include

information concerning the timing of such modifications and whether such modifications are

expected to interrupt the transmission of electricity at the Point(s) of Interconnection. The Party

desiring to perform such work shall provide the relevant drawings, plans, and specifications to

the other Party and NYISO at least ninety (90) Calendar Days in advance of the commencement

of construction regarding such work or such shorter period upon which the Parties may agree,

which agreement shall not unreasonably be withheld, conditioned or delayed.

22



**SERVICE AGREEMENT NO. 2734**

**5.14.2 Standards.**

Any additions, modifications, or replacements made to a Party’s facilities shall be

designed, constructed and operated in accordance with this Agreement, NYISO requirements and

Good Utility Practice.

**5.14.3 Modification Costs.**

Transmission Developer or Connecting Transmission Owner, as applicable, shall not be

assigned the costs of any additions, modifications, or replacements that the other Party makes to

the New York State Transmission System to facilitate the interconnection of a third party to the

New York State Transmission System, or to provide Transmission Service to a third party under

the ISO OATT, except in accordance with the cost allocation procedures in Attachment S of the

ISO OATT.

**ARTICLE 6. TESTING AND INSPECTION**

**Pre-In-Service Date Testing and Modifications.**

Prior to the In-Service Date of the Transmission Project or Network Upgrade Facilities,

as applicable, the Connecting Transmission Owner or Transmission Developer shall, as specified

in Appendix A, test the Transmission Project and Network Upgrade Facilities to ensure their safe

and reliable operation. Similar testing may be required after initial operation. Transmission

Developer and Connecting Transmission Owner shall each make any modifications to its

facilities that are found to be necessary as a result of such testing. Transmission Developer shall

bear the cost of all such testing and modifications. Transmission Developer and Connecting

Transmission Owner shall coordinate with NYISO prior to performing the testing of the

Transmission Project and Network Upgrade Facilities and prior to the facilities entering into

service.

**Post-In-Service Date Testing and Modifications.**

Transmission Developer and Connecting Transmission Owner shall each at its own

expense perform routine inspection and testing of its facilities and equipment in accordance with

Good Utility Practice and Applicable Reliability Standards as may be necessary to ensure the

continued interconnection of the Transmission Project with the New York State Transmission

System in a safe and reliable manner. Transmission Developer and Connecting Transmission

Owner shall each have the right, upon advance written notice, to require reasonable additional

testing of the other Party’s facilities, at the requesting Party’s expense, as may be in accordance

with Good Utility Practice.

**Right to Observe Testing.**

Transmission Developer and Connecting Transmission Owner shall each notify the other

Party, and the NYISO, in advance of its performance of tests of the Transmission Project and

Network Upgrade Facilities. The other Party, and the NYISO, shall each have the right, at its

own expense, to observe such testing.

23



**SERVICE AGREEMENT NO. 2734**

**Right to Inspect.**

Transmission Developer and Connecting Transmission Owner shall each have the right,

but shall have no obligation to: (i) observe the other Party’s tests and/or inspection of any of its

System Protection Facilities and other protective equipment; (ii) review the settings of the other

Party’s System Protection Facilities and other protective equipment; and (iii) review the other

Party’s maintenance records relative to the System Protection Facilities and other protective

equipment. NYISO shall have these same rights of inspection as to the facilities and equipment

of Transmission Developer and Connecting Transmission Owner. A Party may exercise these

rights from time to time as it deems necessary upon reasonable notice to the other Party. The

exercise or non-exercise by a Party of any such rights shall not be construed as an endorsement

or confirmation of any element or condition of the System Protection Facilities or other

protective equipment or the operation thereof, or as a warranty as to the fitness, safety,

desirability, or reliability of same. Any information that a Party obtains through the exercise of

any of its rights under this Artic[le 6.4](#br29) shall be treated in accordance [with Article 22](#br47) of this

Agreement and Attachment F to the ISO OATT.

**ARTICLE 7. METERING**

**General.**

Connecting Transmission Owner shall be responsible for the metering at any Metering

Points identified by the NYISO in connection with the interconnection of the Transmission

Project with Connecting Transmission Owner’s system in accordance with the requirements in

thi[s Article 7. C](#br29)onnecting Transmission Owner and/or Transmission Developer shall, as such

responsibilities are specified in Appendix A of this Agreement, procure and install any required

Metering Equipment prior to any operation of the Transmission Project. Connecting

Transmission Owner shall own, operate, test, maintain, and, if directed by the NYISO, relocate

such Metering Equipment in accordance with ISO Procedures, as such requirements are amended

from time to time. Connecting Transmission Owner shall provide the NYISO and Transmission

Developer with metering data in accordance with the metering requirements set forth in this

Agreement, the NYISO Tariffs, and ISO Procedures, as such requirements are amended from

time to time. Transmission Developer shall bear all reasonable documented costs associated

with the purchase and installation of the Metering Equipment.

**Check Meters.**

Transmission Developer, at its option and expense, may install and operate, on its

premises and on its side of the Points of Interconnection, one or more check meters to check

Connecting Transmission Owner’s meters. Such check meters shall be for check purposes only

and shall not be used for the measurement of power flows for purposes of this Agreement, except

as provided in Artic[le 7.4](#br30) below. The installation, operation and maintenance thereof shall be

performed entirely by Transmission Developer in accordance with Good Utility Practice

**Standards.**

Connecting Transmission Owner and Transmission Developer shall, as such

responsibilities are specified in Appendix A of this Agreement, install, calibrate, and test revenue

24



**SERVICE AGREEMENT NO. 2734**

quality Metering Equipment including potential transformers and current transformers in

accordance with ISO Procedures, as such requirements are amended from time to time.

**Testing of Metering Equipment.**

Connecting Transmission Owner shall inspect and test all of its Metering Equipment

upon installation and at least once every two (2) years thereafter. If required by ISO Procedures,

Connecting Transmission Owner shall, at its own expense, inspect or test Metering Equipment

more frequently than every two (2) years. Connecting Transmission Owner shall give reasonable

notice of the time when any inspection or test shall take place, and NYISO and Transmission

Developer may have representatives present at the test or inspection. If at any time Metering

Equipment is found to be inaccurate or defective, it shall be adjusted, repaired or replaced at

Connecting Transmission Owner’s expense in order to provide accurate metering. Connecting

Transmission Owner and NYISO shall address the loss of meter data or meter data anomalies in

accordance with ISO Procedures. The NYISO shall reserve the right to review all associated

metering equipment installation on the Transmission Developer’s or Connecting Transmission

Owner’s property at any time.

**Metering Data.**

At Transmission Developer’s expense, the metered data shall be telemetered to one or

more locations designated by NYISO. Such telemetered data shall be used, under normal

operating conditions, as the official measurement of the amount of energy at the Metering Points.

**ARTICLE 8. COMMUNICATIONS**

**Transmission Developer Obligations.**

Transmission Developer shall maintain satisfactory operating communications, including

providing analog and digital real-time telemetry, with Connecting Transmission Owner and

NYISO in accordance with the requirements in this Agreement, the Operating Agreement

(including Section 2.05, *Local Control Center, Metering and Telemetry*), NYISO Tariffs, and

ISO Procedures, as such requirements are amended from time to time. Transmission Developer

shall provide standard voice line, dedicated voice line and facsimile communications at its

control center for the Transmission Project through use of either the public telephone system, or

a voice communications system that does not rely on the public telephone system. Transmission

Developer shall also provide the dedicated data circuit(s) necessary to provide Transmission

Developer data to Connecting Transmission Owner and NYISO as set forth in Appendix D

hereto. The data circuit(s) shall extend from the Transmission Project to the location(s) specified

by Connecting Transmission Owner and NYISO. Any required maintenance of such

communications equipment shall be performed by Transmission Developer. Operational

communications shall be activated and maintained under, but not be limited to, the following

events: system paralleling or separation, scheduled and unscheduled shutdowns, equipment

clearances, and hourly and daily load data.

25



**SERVICE AGREEMENT NO. 2734**

**Remote Terminal Unit.**

Prior to the Initial Synchronization Date of the Transmission Project, a Remote Terminal

Unit, or equivalent data collection and transfer equipment acceptable to the Parties, shall be

installed by Transmission Developer, or by Connecting Transmission Owner at Transmission

Developer’s expense, to gather accumulated and instantaneous data to be telemetered to the

location(s) designated by Connecting Transmission Owner and NYISO through use of a

dedicated point-to-point data circuit(s) as indicated in Artic[le 8.1. The](#br30) communication protocol

for the data circuit(s) shall be specified by Connecting Transmission Owner and NYISO.

Instantaneous bi-directional analog real power and reactive power flow information must be

telemetered directly to the location(s) specified by Connecting Transmission Owner and NYISO.

Each Party will promptly advise the appropriate other Party if it detects or otherwise

learns of any metering, telemetry or communications equipment errors or malfunctions that

require the attention and/or correction by that other Party. The Party owning such equipment

shall correct such error or malfunction as soon as reasonably feasible.

**No Annexation.**

Any and all equipment placed on the premises of a Party shall be and remain the property

of the Party providing such equipment regardless of the mode and manner of annexation or

attachment to real property, unless otherwise mutually agreed by the Party providing such

equipment and the Party receiving such equipment.

**ARTICLE 9. OPERATIONS**

**General.**

Each Party shall comply with Applicable Laws and Regulations and Applicable

Reliability Standards. Each Party shall provide to the other Parties all information that may

reasonably be required by the other Parties to comply with Applicable Laws and Regulations and

Applicable Reliability Standards. Connecting Transmission Owner or Transmission Developer,

as applicable, shall provide the NYISO with notifications of all of its power system equipment

additions or modifications in accordance with ISO Procedures, including the NYISO’s

Reliability Analysis Data Manual (Manual 24).

**NYISO and Connecting Transmission Owner Obligations.**

Connecting Transmission Owner and NYISO shall cause the New York State

Transmission System to be operated, maintained and controlled in a safe and reliable manner in

accordance with this Agreement and the NYISO Tariffs. Connecting Transmission Owner and

NYISO may provide operating instructions to Transmission Developer consistent with this

Agreement, NYISO procedures and Connecting Transmission Owner’s operating protocols and

procedures as they may change from time to time. Connecting Transmission Owner and NYISO

will consider changes to their respective operating protocols and procedures proposed by

Transmission Developer.

26



**SERVICE AGREEMENT NO. 2734**

**Transmission Developer Obligations.**

Transmission Developer shall at its own expense operate, maintain and control the

Transmission Project in a safe and reliable manner and in accordance with this Agreement, the

NYISO Tariffs, ISO Procedures, and the Operating Agreement. Transmission Developer shall

operate the Transmission Project in accordance with NYISO and Connecting Transmission

Owner requirements, as such requirements are set forth or referenced in Appendix C hereto.

Appendix C will be modified to reflect changes to the requirements as they may change from

time to time. Any Party may request that the appropriate other Party or Parties provide copies of

the requirements set forth or referenced in Appendix C hereto.

**Outages and Interruptions.**

**9.4.1 Outages.**

**9.4.1.1 Outage Authority and Coordination**.

Transmission Developer and Connecting Transmission Owner may each, in accordance

with NYISO procedures and Good Utility Practice and in coordination with the other Party,

remove from service any of its Transmission Project facilities or Network Upgrade Facilities that

may impact the other Party’s facilities as necessary to perform maintenance or testing or to

install or replace equipment. Absent an Emergency or Emergency State, the Party scheduling a

removal of such facility(ies) from service will use Reasonable Efforts to schedule such removal

on a date and time mutually acceptable to both the Transmission Developer and the Connecting

Transmission Owner. In all circumstances either Party planning to remove such facility(ies)

from service shall use Reasonable Efforts to minimize the effect on the other Party of such

removal.

**9.4.1.2 Outage Schedules**.

The Transmission Developer or Connecting Transmission Owner, as applicable, and

pursuant to ISO Procedures, shall post scheduled outages of its respective transmission facilities

on the NYISO OASIS.

**9.4.1.3 Outage Restoration**.

If an outage on the Transmission Project or Network Upgrade Facilities adversely affects

the other Party’s operations or facilities, the Party that owns the facility that is out of service

shall use Reasonable Efforts to promptly restore such facility(ies) to a normal operating

condition consistent with the nature of the outage. The Party that owns the facility that is out of

service shall provide the other Party and NYISO, to the extent such information is known,

information on the nature of the Emergency or Emergency State, an estimated time of

restoration, and any corrective actions required. Initial verbal notice shall be followed up as

soon as practicable with written notice explaining the nature of the outage.

**9.4.2 Interruption of Service**. If required by Good Utility Practice or Applicable

Reliability Standards to do so, the NYISO, Connecting Transmission Owner, or Transmission

27



**SERVICE AGREEMENT NO. 2734**

Developer may require the Connecting Transmission Owner or Transmission Developer to

interrupt the transmission of electricity if such transmission of electricity could adversely affect

the ability of NYISO and, as applicable, Connecting Transmission Owner or Transmission

Developer to perform such activities as are necessary to safely and reliably operate and maintain

the New York State Transmission System. The following provisions shall apply to any

interruption permitted under this Artic[le 9.4.2:](#br32)

**9.4.2.1** The interruption shall continue only for so long as reasonably necessary

under Good Utility Practice;

**9.4.2.2** When the interruption must be made under circumstances which do not

allow for advance notice, NYISO, Connecting Transmission Owner, or Transmission Developer

shall notify, as applicable, Transmission Developer or Connecting Transmission Owner by

telephone as soon as practicable of the reasons for the curtailment or interruption, and, if known,

its expected duration. Telephone notification shall be followed by written notification as soon as

practicable;

**9.4.2.3** Except during the existence of an Emergency or Emergency State, when

the interruption can be scheduled without advance notice, NYISO, Connecting Transmission

Owner, or Transmission Developer shall notify, as applicable, Transmission Developer or

Connecting Transmission Owner in advance regarding the timing of such scheduling and of the

expected duration. The Parties shall coordinate with each other using Good Utility Practice to

schedule the interruption during periods of least impact to the Transmission Developer, the

Connecting Transmission Owner and the New York State Transmission System;

**9.4.2.4** The Parties shall cooperate and coordinate with each other to the extent

necessary in order to restore the Transmission Project, Network Upgrade Facilities, and the New

York State Transmission System to their normal operating state, consistent with system

conditions and Good Utility Practice.

**9.4.3 System Protection and Other Control Requirements.**

**9.4.3.1 System Protection Facilities**. Transmission Developer shall, at its

expense, install, operate and maintain System Protection Facilities as a part of the Transmission

Project. Connecting Transmission Owner shall install at Transmission Developer’s expense any

System Protection Facilities that may be required on the New York State Transmission System

as a result of the interconnection of the Transmission Project.

**9.4.3.2** The protection facilities of both the Transmission Developer and

Connecting Transmission Owner shall be designed and coordinated with other systems in

accordance with Good Utility Practice and Applicable Reliability Standards.

**9.4.3.3** The Transmission Developer and Connecting Transmission Owner shall

each be responsible for protection of its respective facilities consistent with Good Utility Practice

and Applicable Reliability Standards.

28

**SERVICE AGREEMENT NO. 2734**

**9.4.3.4** The protective relay design of the Transmission Developer and

Connecting Transmission Owner shall each incorporate the necessary test switches to perform

the tests required in Article [6](#br28) of this Agreement. The required test switches will be placed such

that they allow operation of lockout relays while preventing breaker failure schemes from

operating and causing unnecessary breaker operations and/or the tripping of the Transmission

Developer’s Transmission Project.

**9.4.3.5** The Transmission Developer and Connecting Transmission Owner will

each test, operate and maintain System Protection Facilities in accordance with Good Utility

Practice, NERC and NPCC criteria.

**9.4.3.6** Prior to the In-Service Dates of the Network Upgrade Facilities and

Transmission Project, the Transmission Developer and Connecting Transmission Owner shall

each perform, or their agents shall perform, a complete calibration test and functional trip test of

the System Protection Facilities. At intervals suggested by Good Utility Practice and following

any apparent malfunction of the System Protection Facilities, the Transmission Developer and

Connecting Transmission Owner shall each perform both calibration and functional trip tests of

its System Protection Facilities. These tests do not require the tripping of any in-service

generation unit. These tests do, however, require that all protective relays and lockout contacts

be activated.

**9.4.4 Requirements for Protection.**

In compliance with NPCC requirements and Good Utility Practice, Transmission

Developer shall provide, install, own, and maintain relays, circuit breakers and all other devices

necessary to remove any fault contribution of the Transmission Project to any short circuit

occurring on the New York State Transmission System not otherwise isolated by Connecting

Transmission Owner’s equipment, such that the removal of the fault contribution shall be

coordinated with the protective requirements of the New York State Transmission System. Such

protective equipment shall include, without limitation, a disconnecting device or switch with

load-interrupting capability located between the Transmission Project and the New York State

Transmission System at a site selected upon mutual agreement (not to be unreasonably withheld,

conditioned or delayed) of the Transmission Developer and Connecting Transmission Owner.

Transmission Developer shall be responsible for protection of the Transmission Project and

Transmission Developer’s other equipment from such conditions as negative sequence currents,

over- or under-frequency, sudden load rejection, over- or under-voltage, and generator loss-of-

field. Transmission Developer shall be solely responsible to disconnect the Transmission Project

and Transmission Developer’s other equipment if conditions on the New York State

Transmission System could adversely affect the Transmission Project.

**9.4.5 Power Quality.**

Neither the facilities of Transmission Developer nor the facilities of Connecting

Transmission Owner shall cause excessive voltage flicker nor introduce excessive distortion to

the sinusoidal voltage or current waves as defined by ANSI Standard C84.1-1989, in accordance

with IEEE Standard 519, or any applicable superseding electric industry standard. In the event

of a conflict between ANSI Standard C84.1-1989, or any applicable superseding electric industry

29

**SERVICE AGREEMENT NO. 2734**

standard, ANSI Standard C84.1-1989, or the applicable superseding electric industry standard,

shall control.

**Switching and Tagging Rules.**

The Transmission Developer and Connecting Transmission Owner shall each provide the

other Party a copy of its switching and tagging rules that are applicable to the other Party’s

activities. Such switching and tagging rules shall be developed on a nondiscriminatory basis.

The Parties shall comply with applicable switching and tagging rules, as amended from time to

time, in obtaining clearances for work or for switching operations on equipment.

**Disturbance Analysis Data Exchange.**

The Parties will cooperate with one another and the NYISO in the analysis of

disturbances to either the Transmission Project or the New York State Transmission System by

gathering and providing access to any information relating to any disturbance, including

information from disturbance recording equipment, protective relay targets, breaker operations

and sequence of events records, and any disturbance information required by Good Utility

Practice.

**ARTICLE 10. MAINTENANCE**

**Connecting Transmission Owner Obligations.**

Connecting Transmission Owner shall maintain its transmission facilities, including the

Network Upgrade Facilities, in a safe and reliable manner and in accordance with this

Agreement.

**Transmission Developer Obligations.**

Transmission Developer shall maintain its Transmission Project in a safe and reliable

manner and in accordance with this Agreement.

**Coordination.**

The Transmission Developer and Connecting Transmission Owner shall confer regularly

to coordinate the planning, scheduling and performance of preventive and corrective

maintenance on the Transmission Project and Network Upgrade Facilities. The Transmission

Developer and Connecting Transmission Owner shall keep NYISO fully informed of the

preventive and corrective maintenance that is planned, and shall schedule all such maintenance

in accordance with NYISO procedures.

**Secondary Systems.**

The Transmission Developer and Connecting Transmission Owner shall each cooperate

with the other in the inspection, maintenance, and testing of control or power circuits that operate

below 600 volts, AC or DC, including, but not limited to, any hardware, control or protective

devices, cables, conductors, electric raceways, secondary equipment panels, transducers,

30



**SERVICE AGREEMENT NO. 2734**

batteries, chargers, and voltage and current transformers that directly affect the operation of

Transmission Developer or Connecting Transmission Owner’s facilities and equipment which

may reasonably be expected to impact the other Party. The Transmission Developer and

Connecting Transmission Owner shall each provide advance notice to the other Party, and to

NYISO, before undertaking any work on such circuits, especially on electrical circuits involving

circuit breaker trip and close contacts, current transformers, or potential transformers.

**Operating and Maintenance Expenses.**

Subject to the provisions herein addressing the use of facilities by others, and except for

operations and maintenance expenses associated with modifications made for providing

interconnection or transmission service to a third party and such third party pays for such

expenses, Transmission Developer shall be responsible for all reasonable expenses including

overheads, associated with owning, operating, maintaining, repairing, and replacing the

Transmission Project. The Connecting Transmission Owner shall be responsible for all

reasonable expenses including overheads, associated with owning, operating, maintaining,

repairing, and replacing the Network Upgrade Facilities.

**ARTICLE 11. PERFORMANCE OBLIGATION**

**Transmission Project.**

Transmission Developer shall design, procure, construct, install, own and/or control the

Transmission Project described in Appendix C hereto, at its sole expense.

**Network Upgrade Facilities.**

Connecting Transmission Owner and Transmission Developer shall design, procure,

construct, and install the Network Upgrade Facilities as specified in Appendix A hereto.

Connecting Transmission Owner shall have ownership and control of the Network Upgrade

Facilities.

**Special Provisions for Affected Sy**s**tems.**

For the re-payment of amounts advanced to Affected System Operator for Network

Upgrade Facilities, the Transmission Developer and Affected System Operator shall enter into an

agreement that provides for such re-payment, but only if responsibility for the cost of such

Network Upgrade Facilities is not to be allocated in accordance with the Facilities Study report.

The agreement shall specify the terms governing payments to be made by the Transmission

Developer to the Affected System Operator as well as the re-payment by the Affected System

Operator.

**Provision of Security.**

Simultaneously with the execution of this Agreement, the Transmission Developer: (i)

shall deliver to the Connecting Transmission Owner a signed security agreement, by and

between the Transmission Developer and the Connecting Transmission Owner, in a form that is

acceptable to the Connecting Transmission Owner in its sole discretion, securing the

31



**SERVICE AGREEMENT NO. 2734**

performance of the Transmission Developer’s obligations under this Agreement, and (ii) shall

provide the Connecting Transmission Owner with an irrevocable, transferrable standby letter of

credit in the form required by the aforementioned security agreement in the amount of the cost

estimate for the Network Upgrade Facilities, as documented in the Facilities Study report, in

accordance with Section 22.9.3 of Attachment P of the ISO OATT. This amount of Security is

set forth in Appendix A of this Agreement. Upon the successful turnover, commissioning, and

energization of any Network Upgrade Facility, the Security shall be reduced on a dollar-for-

dollar basis for payments made to Connecting Transmission Owner for the purpose of

performing engineering design, constructing, procuring, and installing of such Network Upgrade

Facility.

In addition:

**11.4.1** Reserved.

**11.4.2** The letter of credit must be issued by a financial institution reasonably

acceptable to Connecting Transmission Owner and must specify a reasonable expiration date.

**11.4.3** Reserved.

**Forfeiture of Security**

The Security that the Transmission Developer provides the Connecting Transmission

Owner in accordance with Artic[le 11.4](#br36) of this Agreement shall be irrevocable and shall be

subject to forfeiture in the event that the Transmission Developer subsequently terminates or

abandons development of the Transmission Project. Any Security provided by the Transmission

Developer to the Connecting Transmission Owner shall be subject to forfeiture to the extent

necessary to defray the cost of: (1) Network Upgrade Facilities required for other Transmission

Developers whose Transmission Project interconnection studies included the Transmission

Developer’s Transmission Project and Network Upgrade Facilities in their base cases; and (2)

System Upgrade Facilities and System Deliverability Upgrade Facilities required for projects for

which the Transmission Project and Network Upgrade Facilities were included in their Annual

Transmission Reliability Assessment and/or Class Year Deliverability Study, as applicable. If

Transmission Developer’s Security is subject to forfeiture to defray the costs of an affected

upgrade pursuant to this Artic[le 11.5](#br37) and the Security is not in a form that can be readily drawn

on by the Connecting Transmission Owner to defray the costs of the affected upgrade,

Transmission Developer shall negotiate in good faith with the Connecting Transmission Owner

to replace the Security with cash or an alternative form of Security that can be readily drawn on

by Connecting Transmission Owner up to the amount required to satisfy Transmission

Developer’s Security obligations under this Agreement, including defraying the costs of the

affected upgrade. Connecting Transmission Owner shall only be responsible for using

Transmission Developer’s Security to defray the costs of an affected upgrade to the extent

Transmission Developer has provided cash or Security in a form that the Connecting

Transmission Owner can readily draw on to defray such costs.

32



**SERVICE AGREEMENT NO. 2734**

**Network Upgrade Facility Costs**

**11.6.1** If the actual cost of Network Upgrade Facilities is less than the agreed-to and

secured amount, Transmission Developer is responsible only for the actual cost figure.

**11.6.2** If the actual cost of Network Upgrade Facilities is greater than the agreed-to and

secured amount because other projects have been expanded, accelerated, otherwise modified or

terminated, Transmission Developer is responsible only for the agreed-to and secured amount for

the Network Upgrade Facilities. The additional cost is covered by the developers of the

modified projects, or by the drawing on the cash that has been paid and the Security that has

been posted for terminated projects, depending on the factors that caused the additional cost.

Such forfeitable Security from other developers will be drawn on only as needed for this

purpose, and only to the extent that the terminated project associated with that Security has

caused additional cost and that the developer of the terminated project has provided cash or

Security in a form that the Connecting Transmission Owner can readily draw on.

**11.6.3** If the actual cost of the Network Upgrade Facilities is greater than the agreed-to

and secured amount for reasons other than those set forth in Artic[le 11.6.2,](#br38) Transmission

Developer will pay all prudently incurred additional costs to Connecting Transmission Owner as

such costs are incurred; *provided, however*, that if practicable, the Connecting Transmission

Owner shall provide Transmission Developer with thirty (30) days advance, written notice

detailing any costs that Connecting Transmission Owner reasonably anticipates will exceed the

agreed to and secured amount. Disputes between Transmission Developer and Connecting

Transmission Owner concerning costs in excess of the agreed-to and secured amount will be

resolved by the parties in accordance with the terms and conditions o[f Article 27.](#br54)

**Line Outage Costs.**

Notwithstanding anything in the ISO OATT to the contrary, the Connecting Transmission

Owner may propose to recover line outage costs associated with the installation of Network

Upgrade Facilities on a case-by-case basis.

**ARTICLE 12. INVOICE**

**General.**

The Transmission Developer and Connecting Transmission Owner shall each submit to

the other Party, on a monthly basis, invoices of amounts due for the preceding month or as

otherwise agreed by such Parties and as set forth in Section 2 of Appendix B. Each invoice shall

state the month to which the invoice applies and fully describe the services and equipment

provided. The Transmission Developer and Connecting Transmission Owner may discharge

mutual debts and payment obligations due and owing to each other on the same date through

netting, in which case all amounts one Party owes to the other Party under this Agreement,

including interest payments or credits, shall be netted so that only the net amount remaining due

shall be paid by the owing Party.

33



**SERVICE AGREEMENT NO. 2734**

**Final Invoice and Refund of Remaining Security.**

Within six months after completion of the construction of Network Upgrade Facilities,

Connecting Transmission Owner shall provide an invoice of the final cost of the construction of

the Network Upgrade Facilities and shall set forth such costs in sufficient detail to enable

Transmission Developer to compare the actual costs with the estimates and to ascertain

deviations, if any, from the cost estimates. Connecting Transmission Owner shall refund to

Transmission Developer any amount by which the actual payment by Transmission Developer

for estimated costs exceeds the actual costs of construction within thirty (30) Calendar Days of

the issuance of such final construction invoice. Following the later of (i) the completion of the

construction of the Network Upgrade Facilities and Connecting Transmission Owner’s

acceptance of the Network Upgrade Facilities or (ii) Transmission Developer’s payment of any

final invoice issued under this Artic[le 12.2, C](#br39)onnecting Transmission Owner shall refund to the

Transmission Developer any remaining portions of its Security, except as set forth in

Article [11.5. C](#br37)onnecting Transmission Owner shall provide Transmission Developer with the

refunded amount within thirty (30) Calendar Days of the Parties’ satisfaction of the requirements

in this Article 12.2.

**Payment.**

Invoices shall be rendered to the paying Party at the address specified in Appendix F

hereto. The Party receiving the invoice shall pay the invoice within thirty (30) Calendar Days of

receipt. All payments shall be made in immediately available funds payable to the other Party,

or by wire transfer to a bank named and account designated by the invoicing Party. Payment of

invoices will not constitute a waiver of any rights or claims the paying Party may have under this

Agreement.

**Disputes.**

In the event of a billing dispute between Connecting Transmission Owner and

Transmission Developer, Connecting Transmission Owner shall continue to perform under this

Agreement as long as Transmission Developer: (i) continues to make all payments not in dispute;

and (ii) pays to Connecting Transmission Owner or into an independent escrow account the

portion of the invoice in dispute, pending resolution of such dispute. If Transmission Developer

fails to meet these two requirements for continuation of service, then Connecting Transmission

Owner may provide notice to Transmission Developer of a Default pursuant t[o Article 17.](#br42)

Within thirty (30) Calendar Days after the resolution of the dispute, the Party that owes money to

the other Party shall pay the amount due with interest calculated in accord with the methodology

set forth in FERC’s Regulations at 18 C.F.R. § 35.19a(a)(2)(iii).

**ARTICLE 13. EMERGENCIES**

**Obligations.**

Each Party shall comply with the Emergency State procedures of NYISO, the applicable

Reliability Councils, Applicable Laws and Regulations, and any emergency procedures agreed to

by the NYISO Operating Committee. Transmission Developer and Connecting Transmission

34



**SERVICE AGREEMENT NO. 2734**

Owner agree to coordinate with NYISO to develop procedures that will address the operations of

the Transmission Project during Emergency conditions.

**Notice.**

Each Party shall notify the other Parties promptly when it becomes aware of an

Emergency or Emergency State that affects, or may reasonably be expected to affect, the

Transmission Project or the New York State Transmission System. To the extent information is

known, the notification shall describe the Emergency or Emergency State, the extent of the

damage or deficiency, the expected effect on the operation of Transmission Developer’s or

Connecting Transmission Owner’s facilities and operations, its anticipated duration and the

corrective action taken and/or to be taken. The initial notice shall be followed as soon as

practicable with written notice.

**Immediate Action.**

Unless, in Transmission Developer’s reasonable judgment, immediate action is required,

Transmission Developer shall obtain the consent of Connecting Transmission Owner, such

consent to not be unreasonably withheld, prior to performing any manual switching operations at

the Transmission Project in response to an Emergency or Emergency State either declared by

NYISO, Connecting Transmission Owner or otherwise regarding New York State Transmission

System.

**NYISO, Transmission Developer, and Connecting Transmission Owner**

**Authority.**

Consistent with ISO Procedures, Good Utility Practice, and this Agreement, any Party

may take whatever actions with regard to the New York State Transmission System it deems

necessary during an Emergency or Emergency State in order to (i) preserve public health and

safety, (ii) preserve the reliability of the New York State Transmission System, (iii) limit or

prevent damage, and (iv) expedite restoration of service. Transmission Developer and

Connecting Transmission Owner shall use Reasonable Efforts to assist the other in such actions.

**Limited Liability.**

No Party shall be liable to another Party for any action it takes in responding to an

Emergency or Emergency State so long as such action is made in good faith and is consistent

with Good Utility Practice and the NYISO Tariffs.

**ARTICLE 14. REGULATORY REQUIREMENTS AND GOVERNING LAW**

**Regulatory Requirements.**

Each Party’s obligations under this Agreement shall be subject to its receipt of any

required approval or certificate from one or more Governmental Authorities in the form and

substance satisfactory to the applying Party, or the Party making any required filings with, or

providing notice to, such Governmental Authorities, and the expiration of any time period

associated therewith. Each Party shall in good faith seek and use its Reasonable Efforts to obtain

35



**SERVICE AGREEMENT NO. 2734**

such other approvals. Nothing in this Agreement shall require Transmission Developer to take

any action that could result in its inability to obtain, or its loss of, status or exemption under the

Federal Power Act or the Public Utility Holding Company Act of 2005 or the Public Utility

Regulatory Policies Act of 1978, as amended.

**Governing Law.**

**14.2.1** The validity, interpretation and performance of this Agreement and each of its

provisions shall be governed by the laws of the state of New York, without regard to its conflicts

of law principles.

**14.2.2** This Agreement is subject to all Applicable Laws and Regulations.

**14.2.3** Each Party expressly reserves the right to seek changes in, appeal, or otherwise

contest any laws, orders, rules, or regulations of a Governmental Authority.

**ARTICLE 15. NOTICES**

**General.**

Unless otherwise provided in this Agreement, any notice, demand or request required or

permitted to be given by a Party to the other Parties and any instrument required or permitted to

be tendered or delivered by a Party in writing to the other Parties shall be effective when

delivered and may be so given, tendered or delivered, by recognized national courier, or by

depositing the same with the United States Postal Service with postage prepaid, for delivery by

certified or registered mail, addressed to the Party, or personally delivered to the Party, at the

address set out in Appendix F hereto.

A Party may change the notice information in this Agreement by giving five (5) Business

Days written notice prior to the effective date of the change.

**Billings and Payments.**

Billings and payments shall be sent to the addresses set out in Appendix F hereto.

**Alternative Forms of Notice.**

Any notice or request required or permitted to be given by a Party to the other Parties and

not required by this Agreement to be given in writing may be so given by telephone, facsimile or

email to the telephone numbers and email addresses set out in Appendix F hereto.

**Operations and Maintenance Notice.**

Transmission Developer and Connecting Transmission Owner shall each notify the other

Party, and NYISO, in writing of the identity of the person(s) that it designates as the point(s) of

contact with respect to the implementation of Articles 9 and 10 of this Agreement.

36



**SERVICE AGREEMENT NO. 2734**

**ARTICLE 16. FORCE MAJEURE**

**16.1** Economic hardship is not considered a Force Majeure event.

**16.2** A Party shall not be responsible or liable, or deemed, in Default with respect to

any obligation hereunder, other than the obligation to pay money when due, to the extent the

Party is prevented from fulfilling such obligation by Force Majeure. A Party unable to fulfill any

obligation hereunder (other than an obligation to pay money when due) by reason of Force

Majeure shall give notice and the full particulars of such Force Majeure to the other Parties in

writing or by telephone as soon as reasonably possible after the occurrence of the cause relied

upon. Telephone notices given pursuant to this Article shall be confirmed in writing as soon as

reasonably possible and shall specifically state full particulars of the Force Majeure, the time and

date when the Force Majeure occurred and when the Force Majeure is reasonably expected to

cease. The Party affected shall exercise due diligence to remove such disability with reasonable

dispatch, but shall not be required to accede or agree to any provision not satisfactory to it in

order to settle and terminate a strike or other labor disturbance.

**ARTICLE 17. DEFAULT**

**General.**

No Breach shall exist where such failure to discharge an obligation (other than the

payment of money) is the result of Force Majeure as defined in this Agreement or the result of an

act or omission of the other Parties. Upon a Breach, the non-Breaching Parties shall give written

notice of such to the Breaching Party. The Breaching Party shall have thirty (30) Calendar Days

from receipt of the Breach notice within which to cure such Breach; provided however, if such

Breach is not capable of cure within thirty (30) Calendar Days, the Breaching Party shall

commence such cure within thirty (30) Calendar Days after notice and continuously and

diligently complete such cure within ninety (90) Calendar Days from receipt of the Breach

notice; and, if cured within such time, the Breach specified in such notice shall cease to exist.

**Right to Terminate.**

If a Breach is not cured as provided in t[his Article 17, or if](#br42) a Breach is not capable of

being cured within the period provided for herein, the non-Breaching Parties acting together shall

thereafter have the right to declare a Default and terminate this Agreement by written notice at

any time until cure occurs, and be relieved of any further obligation hereunder and, whether or

not those Parties terminate this Agreement, to recover from the defaulting Party all amounts due

hereunder, plus all other damages and remedies to which they are entitled at law or in equity.

The provisions of this Article will survive termination of this Agreement.

**ARTICLE 18. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE**

**Indemnity.**

Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and save

harmless, as applicable, the other Parties (each an “Indemnified Party”) from, any and all

damages, losses, claims, including claims and actions relating to injury to or death of any person

37



**SERVICE AGREEMENT NO. 2734**

or damage to property, the alleged violation of any Environmental Law, or the release or

threatened release of any Hazardous Substance, demand, suits, recoveries, costs and expenses,

court costs, attorney fees, and all other obligations by or to third parties (any and all of these a

“Loss”), arising out of or resulting from (i) the Indemnified Party’s performance of its

obligations under this Agreement on behalf of the Indemnifying Party, except in cases where the

Indemnifying Party can demonstrate that the Loss of the Indemnified Party was caused by the

gross negligence or intentional wrongdoing of the Indemnified Party or (ii) the violation by the

Indemnifying Party of any Environmental Law or the release by the Indemnifying Party of any

Hazardous Substance.

**18.1.1**

**Indemnified Party.**

If a Party is entitled to indemnification unde[r this Article 18](#br42) as a result of a claim by a

third party, and the Indemnifying Party fails, after notice and reasonable opportunity to proceed

under Artic[le 18.1.3, to](#br43) assume the defense of such claim, such Indemnified Party may at the

expense of the Indemnifying Party contest, settle or consent to the entry of any judgment with

respect to, or pay in full, such claim.

**18.1.2**

**Indemnifying Party.**

If an Indemnifying Party is obligated to indemnify and hold any Indemnified Party

harmless under thi[s Article 18, the a](#br42)mount owing to the Indemnified Party shall be the amount of

such Indemnified Party’s actual Loss, net of any insurance or other recovery.

**18.1.3**

**Indemnity Procedures.**

Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or investigation as to which

the indemnity provided for in Artic[le 18.1](#br42) may apply, the Indemnified Party shall notify the

Indemnifying Party of such fact. Any failure of or delay in such notification shall not affect a

Party’s indemnification obligation unless such failure or delay is materially prejudicial to the

Indemnifying Party.

Except as stated below, the Indemnifying Party shall have the right to assume the defense

thereof with counsel designated by such Indemnifying Party and reasonably satisfactory to the

Indemnified Party. If the defendants in any such action include one or more Indemnified Parties

and the Indemnifying Party and if the Indemnified Party reasonably concludes that there may be

legal defenses available to it and/or other Indemnified Parties which are different from or

additional to those available to the Indemnifying Party, the Indemnified Party shall have the right

to select separate counsel to assert such legal defenses and to otherwise participate in the defense

of such action on its own behalf. In such instances, the Indemnifying Party shall only be

required to pay the fees and expenses of one additional attorney to represent an Indemnified

Party or Indemnified Parties having such differing or additional legal defenses.

The Indemnified Party shall be entitled, at its expense, to participate in any such action,

suit or proceeding, the defense of which has been assumed by the Indemnifying Party.

38

**SERVICE AGREEMENT NO. 2734**

Notwithstanding the foregoing, the Indemnifying Party (i) shall not be entitled to assume and

control the defense of any such action, suit or proceedings if and to the extent that, in the opinion

of the Indemnified Party and its counsel, such action, suit or proceeding involves the potential

imposition of criminal liability on the Indemnified Party, or there exists a conflict or adversity of

interest between the Indemnified Party and the Indemnifying Party, in such event the

Indemnifying Party shall pay the reasonable expenses of the Indemnified Party, and (ii) shall not

settle or consent to the entry of any judgment in any action, suit or proceeding without the

consent of the Indemnified Party, which shall not be unreasonably withheld, conditioned or

delayed.

**No Consequential Damages.**

Other than the indemnity obligations set forth in Artic[le 18.1, in no eve](#br42)nt shall any Party

be liable under any provision of this Agreement for any losses, damages, costs or expenses for

any special, indirect, incidental, consequential, or punitive damages, including but not limited to

loss of profit or revenue, loss of the use of equipment, cost of capital, cost of temporary

equipment or services, whether based in whole or in part in contract, in tort, including

negligence, strict liability, or any other theory of liability; provided, however, that damages for

which a Party may be liable to another Party under separate agreement will not be considered to

be special, indirect, incidental, or consequential damages hereunder.

**Insurance.**

Transmission Developer and Connecting Transmission Owner shall each, at its own

expense, procure and maintain in force throughout the period of this Agreement and until

released by the other Parties, the following minimum insurance coverages, with insurance

companies licensed to write insurance or approved eligible surplus lines carriers in the state of

New York with a minimum A.M. Best rating of A or better for financial strength, and an A.M.

Best financial size category of VIII or better:

**18.3.1** Employers’ Liability and Workers’ Compensation Insurance providing statutory

benefits in accordance with the laws and regulations of New York State.

**18.3.2** Commercial General Liability (“CGL”) Insurance including premises and

operations, personal injury, broad form property damage, broad form blanket contractual liability

coverage products and completed operations coverage, coverage for explosion, collapse and

underground hazards, independent contractors coverage, coverage for pollution to the extent

normally available and punitive damages to the extent normally available using Insurance

Services Office, Inc. Commercial General Liability Coverage (“ISO CG”) Form CG 00 01 04 13

or a form equivalent to or better than CG 00 01 04 13, with minimum limits of Two Million

Dollars ($2,000,000) per occurrence and Two Million Dollars ($2,000,000) aggregate combined

single limit for personal injury, bodily injury, including death and property damage.

**18.3.3** Comprehensive Automobile Liability Insurance for coverage of owned and non-

owned and hired vehicles, trailers or semi-trailers designed for travel on public roads, with a

minimum, combined single limit of One Million Dollars ($1,000,000) per occurrence for bodily

injury, including death, and property damage.

39



**SERVICE AGREEMENT NO. 2734**

**18.3.4** If applicable, the Commercial General Liability and Comprehensive Automobile

Liability Insurance policies should include contractual liability for work in connection with

construction or demolition work on or within 50 feet of a railroad, or a separate Railroad

Protective Liability Policy should be provided.

**18.3.5** Excess Liability Insurance over and above the Employers’ Liability, Commercial

General Liability and Comprehensive Automobile Liability Insurance coverages, with a

minimum combined single limit of Twenty Million Dollars ($20,000,000) per occurrence and

Twenty Million Dollars ($20,000,000) aggregate. The Excess policies should contain the same

extensions listed under the Primary policies.

**18.3.6** The Commercial General Liability Insurance, Comprehensive Automobile

Insurance and Excess Liability Insurance policies of Transmission Developer and Connecting

Transmission Owner shall name the other Party, its parent, associated and Affiliate companies

and their respective directors, officers, agents, servants and employees (“Other Party Group”) as

additional insureds using ISO CG Endorsements: CG 20 33 04 13, and CG 20 37 04 13 or CG 20

10 04 13 and CG 20 37 04 13 or equivalent to or better forms. All policies shall contain

provisions whereby the insurers waive all rights of subrogation in accordance with the provisions

of this Agreement against the Other Party Group and provide thirty (30) Calendar days advance

written notice to the Other Party Group prior to anniversary date of cancellation or any material

change in coverage or condition.

**18.3.7** The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Liability Insurance policies shall contain provisions that specify

that the policies are primary and non-contributory. Transmission Developer and Connecting

Transmission Owner shall each be responsible for its respective deductibles or retentions.

**18.3.8** The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Liability Insurance policies, if written on a Claims First Made

Basis, shall be maintained in full force and effect for at least three (3) years after termination of

this Agreement, which coverage may be in the form of tail coverage or extended reporting period

coverage if agreed by the Transmission Developer and Connecting Transmission Owner.

**18.3.9** If applicable, Pollution Liability Insurance in an amount no less than $7,500,000

per occurrence and $7,500,000 in the aggregate. The policy will provide coverage for claims

resulting from pollution or other environmental impairment arising out of or in connection with

work performed on the premises by the other party, its contractors and and/or subcontractors.

Such insurance is to include coverage for, but not be limited to, cleanup, third party bodily injury

and property damage and remediation and will be written on an occurrence basis. The policy

shall name the Other Party Group as additional insureds, be primary and contain a waiver of

subrogation.

**18.3.10**

The requirements contained herein as to the types and limits of all

insurance to be maintained by the Transmission Developer and Connecting Transmission Owner

40

**SERVICE AGREEMENT NO. 2734**

are not intended to and shall not in any manner, limit or qualify the liabilities and obligations

assumed by those Parties under this Agreement.

**18.3.11**

Within ten (10) days following execution of this Agreement, and as soon

as practicable after the end of each fiscal year or at the renewal of the insurance policy and in

any event within ninety (90) days thereafter, Transmission Developer and Connecting

Transmission Owner shall provide certificate of insurance for all insurance required in this

Agreement, executed by each insurer or by an authorized representative of each insurer.

**18.3.12**

Notwithstanding the foregoing, Transmission Developer and Connecting

Transmission Owner may each self-insure to meet the minimum insurance requirements of

Artic[les 18.3.1](#br44) [through 18.3.9](#br45) to the extent it maintains a self-insurance program; provided that,

such Party’s senior debt is rated at investment grade, or better, by Standard & Poor’s and that its

self-insurance program meets the minimum insurance requirements of Article[s 18.3.1](#br44) through

[18.3.9. I](#br45)n the event that a Party is permitted to self-insure pursuant to this Artic[le 18.3.12, it](#br46)

shall notify the other Party that it meets the requirements to self-insure and that its self-insurance

program meets the minimum insurance requirements in a manner consistent with that specified

in Artic[les 18.3.1](#br44) [through 18.3.9](#br45) and provide evidence of such coverages. For any period of

time that a Party’s senior debt is unrated by Standard & Poor’s or is rated at less than investment

grade by Standard & Poor’s, such Party shall comply with the insurance requirements applicable

to it under Artic[les 18.3.1](#br44) [through 18.3.9.](#br45)

**18.3.13**

Transmission Developer and Connecting Transmission Owner agree to

report to each other in writing as soon as practical all accidents or occurrences resulting in

injuries to any person, including death, and any property damage arising out of this Agreement.

**18.3.14**

Subcontractors of each party must maintain the same insurance

requirements stated under Artic[les 18.3.1through](#br44) [18.3.9](#br45) and comply with the Additional Insured

requirements herein. In addition, their policies must state that they are primary and non-

contributory and contain a waiver of subrogation.

**ARTICLE 19. ASSIGNMENT**

This Agreement may be assigned by a Party only with the written consent of the other

Parties; provided that a Party may assign this Agreement without the consent of the other Parties

to any Affiliate of the assigning Party with an equal or greater credit rating and with the legal

authority and operational ability to satisfy the obligations of the assigning Party under this

Agreement; provided further that a Party may assign this Agreement without the consent of the

other Parties in connection with the sale, merger, restructuring, or transfer of a substantial

portion or all of its assets, so long as the assignee in such a transaction directly assumes in

writing all rights, duties and obligations arising under this Agreement; and provided further that

the Transmission Developer shall have the right to assign this Agreement, without the consent of

the NYISO or Connecting Transmission Owner, for collateral security purposes to aid in

providing financing for the Transmission Project, provided that the Transmission Developer will

promptly notify the NYISO and Connecting Transmission Owner of any such assignment. Any

financing arrangement entered into by the Transmission Developer pursuant to this Article will

provide that prior to or upon the exercise of the secured party’s, trustee’s or mortgagee’s

41

**SERVICE AGREEMENT NO. 2734**

assignment rights pursuant to said arrangement, the secured creditor, the trustee or mortgagee

will notify the NYISO and Connecting Transmission Owner of the date and particulars of any

such exercise of assignment right(s) and will provide the NYISO and Connecting Transmission

Owner with proof that it meets the requirements of Artic[les 11.3](#br36) a[nd 18.3.](#br44) Any attempted

assignment that violates this Article is void and ineffective. Any assignment under this

Agreement shall not relieve a Party of its obligations, nor shall a Party’s obligations be enlarged,

in whole or in part, by reason thereof. Where required, consent to assignment will not be

unreasonably withheld, conditioned or delayed.

**ARTICLE 20. SEVERABILITY**

If any provision in this Agreement is finally determined to be invalid, void or

unenforceable by any court or other Governmental Authority having jurisdiction, such

determination shall not invalidate, void or make unenforceable any other provision, agreement or

covenant of this Agreement.

**ARTICLE 21. COMPARABILITY**

The Parties will comply with all applicable comparability and code of conduct laws, rules

and regulations, as amended from time to time.

**ARTICLE 22. CONFIDENTIALITY**

**Confidentiality.**

Certain information exchanged by the Parties during the term of this Agreement shall

constitute confidential information (“Confidential Information”) and shall be subject to this

Article 22.

If requested by a Party receiving information, the Party supplying the information shall

provide in writing, the basis for asserting that the information referred to in this Article warrants

confidential treatment, and the requesting Party may disclose such writing to the appropriate

Governmental Authority. Each Party shall be responsible for the costs associated with affording

confidential treatment to its information.

**Term.**

During the term of this Agreement, and for a period of three (3) years after the expiration

or termination of this Agreement, except as otherwise provided in thi[s Article 22, e](#br47)ach Party

shall hold in confidence and shall not disclose to any person Confidential Information.

**Confidential Information.**

The following shall constitute Confidential Information: (1) any non-public information

that is treated as confidential by the disclosing Party and which the disclosing Party identifies as

Confidential Information in writing at the time, or promptly after the time, of disclosure; or (2)

information designated as Confidential Information by the NYISO Code of Conduct contained in

Attachment F to the ISO OATT.

42



**SERVICE AGREEMENT NO. 2734**

**Scope.**

Confidential Information shall not include information that the receiving Party can

demonstrate: (1) is generally available to the public other than as a result of a disclosure by the

receiving Party; (2) was in the lawful possession of the receiving Party on a non-confidential

basis before receiving it from the disclosing Party; (3) was supplied to the receiving Party

without restriction by a third party, who, to the knowledge of the receiving Party after due

inquiry, was under no obligation to the disclosing Party to keep such information confidential;

(4) was independently developed by the receiving Party without reference to Confidential

Information of the disclosing Party; (5) is, or becomes, publicly known, through no wrongful act

or omission of the receiving Party or Breach of this Agreement; or (6) is required, in accordance

with Artic[le 22.9](#br49) of this Agreement, Order of Disclosure, to be disclosed by any Governmental

Authority or is otherwise required to be disclosed by law or subpoena, or is necessary in any

legal proceeding establishing rights and obligations under this Agreement. Information

designated as Confidential Information will no longer be deemed confidential if the Party that

designated the information as confidential notifies the other Party that it no longer is

confidential.

**Release of Confidential Information.**

No Party shall release or disclose Confidential Information to any other person, except to

its Affiliates (limited by FERC Standards of Conduct requirements), subcontractors, employees,

consultants, or to parties who may be considering providing financing to or equity participation

with Transmission Developer, or to potential purchasers or assignees of a Party, on a need-to-

know basis in connection with this Agreement, unless such person has first been advised of the

confidentiality provisi[ons of this Article 22](#br47) and has agreed to comply with such provisions.

Notwithstanding the foregoing, a Party providing Confidential Information to any person shall

remain primarily responsible for any release of Confidential Information in contravention of this

Article 22.

**Rights.**

Each Party retains all rights, title, and interest in the Confidential Information that each

Party discloses to the other Party. The disclosure by each Party to the other Parties of

Confidential Information shall not be deemed a waiver by any Party or any other person or entity

of the right to protect the Confidential Information from public disclosure.

**No Warranties.**

By providing Confidential Information, no Party makes any warranties or representations

as to its accuracy or completeness. In addition, by supplying Confidential Information, no Party

obligates itself to provide any particular information or Confidential Information to the other

Parties nor to enter into any further agreements or proceed with any other relationship or joint

venture.

43



**SERVICE AGREEMENT NO. 2734**

**Standard of Care.**

Each Party shall use at least the same standard of care to protect Confidential Information

it receives as it uses to protect its own Confidential Information from unauthorized disclosure,

publication or dissemination. Each Party may use Confidential Information solely to fulfill its

obligations to the other Parties under this Agreement or its regulatory requirements, including the

ISO OATT and ISO Services Tariff. The NYISO shall, in all cases, treat the information it

receives in accordance with the requirements of Attachment F to the ISO OATT.

**Order of Disclosure.**

If a court or a Government Authority or entity with the right, power, and apparent

authority to do so requests or requires any Party, by subpoena, oral deposition, interrogatories,

requests for production of documents, administrative order, or otherwise, to disclose Confidential

Information, that Party shall provide the other Parties with prompt notice of such request(s) or

requirement(s) so that the other Parties may seek an appropriate protective order or waive

compliance with the terms of this Agreement. Notwithstanding the absence of a protective order

or waiver, the Party may disclose such Confidential Information which, in the opinion of its

counsel, the Party is legally compelled to disclose. Each Party will use Reasonable Efforts to

obtain reliable assurance that confidential treatment will be accorded any Confidential

Information so furnished.

**Termination of Agreement.**

Upon termination of this Agreement for any reason, each Party shall, within ten (10)

Calendar Days of receipt of a written request from the other Parties, use Reasonable Efforts to

destroy, erase, or delete (with such destruction, erasure, and deletion certified in writing to the

other Parties) or return to the other Parties, without retaining copies thereof, any and all written

or electronic Confidential Information received from the other Parties pursuant to this

Agreement.

**Remedies.**

The Parties agree that monetary damages would be inadequate to compensate a Party for

another Party’s Breach of its obligations under thi[s Article 22. Ea](#br47)ch Party accordingly agrees

that the other Parties shall be entitled to equitable relief, by way of injunction or otherwise, if the

first Party Breaches or threatens to Breach its obligations under thi[s Article 22, whic](#br47)h equitable

relief shall be granted without bond or proof of damages, and the receiving Party shall not plead

in defense that there would be an adequate remedy at law. Such remedy shall not be deemed an

exclusive remedy for the Breac[h of this Article 22,](#br47) but shall be in addition to all other remedies

available at law or in equity. The Parties further acknowledge and agree that the covenants

contained herein are necessary for the protection of legitimate business interests and are

reasonable in scope. No Party, however, shall be liable for indirect, incidental, or consequential

or punitive damages of any nature or kind resulting from or arising in connection with this

[Article 22.](#br47)

44



**SERVICE AGREEMENT NO. 2734**

**Disclosure to FERC, its Staff, or a State.**

Notwithstanding anything in t[his Article 22](#br47) to the contrary, and pursuant to 18 C.F.R.

section 1b.20, if FERC or its staff, during the course of an investigation or otherwise, requests

information from one of the Parties that is otherwise required to be maintained in confidence

pursuant to this Agreement or the ISO OATT, the Party shall provide the requested information

to FERC or its staff, within the time provided for in the request for information. In providing the

information to FERC or its staff, the Party must, consistent with 18 C.F.R. section 388.112,

request that the information be treated as confidential and non-public by FERC and its staff and

that the information be withheld from public disclosure. Parties are prohibited from notifying

the other Parties to this Agreement prior to the release of the Confidential Information to the

Commission or its staff. The Party shall notify the other Parties to the Agreement when it is

notified by FERC or its staff that a request to release Confidential Information has been received

by FERC, at which time the Parties may respond before such information would be made public,

pursuant to 18 C.F.R. section 388.112. Requests from a state regulatory body conducting a

confidential investigation shall be treated in a similar manner if consistent with the applicable

state rules and regulations. A Party shall not be liable for any losses, consequential or otherwise,

resulting from that Party divulging Confidential Information pursuant to a FERC or state

regulatory body request under this paragraph.

**Required Notices Upon Requests or Demands for Confidential**

**Information**

Except as otherwise expressly provided herein, no Party shall disclose Confidential

Information to any person not employed or retained by the Party possessing the Confidential

Information, except to the extent disclosure is (i) required by law; (ii) reasonably deemed by the

disclosing Party to be required to be disclosed in connection with a dispute between or among

the Parties, or the defense of litigation or dispute; (iii) otherwise permitted by consent of the

other Party, such consent not to be unreasonably withheld; or (iv) necessary to fulfill its

obligations under this Agreement, the ISO OATT or the ISO Services Tariff. Prior to any

disclosures of a Party’s Confidential Information under this subparagraph, or if any third party or

Governmental Authority makes any request or demand for any of the information described in

this subparagraph, the disclosing Party agrees to promptly notify the other Party in writing and

agrees to assert confidentiality and cooperate with the other Party in seeking to protect the

Confidential Information from public disclosure by confidentiality agreement, protective order or

other reasonable measures.

**ARTICLE 23. TRANSMISSION DEVELOPER AND CONNECTING TRANSMISSION**

**OWNER NOTICES OF ENVIRONMENTAL RELEASES**

Transmission Developer and Connecting Transmission Owner shall each notify the other

Party, first orally and then in writing, of the release of any Hazardous Substances, any asbestos

or lead abatement activities, or any type of remediation activities related to the Transmission

Project or Network Upgrade Facilities, each of which may reasonably be expected to affect the

other Party. The notifying Party shall: (i) provide the notice as soon as practicable, provided

such Party makes a good faith effort to provide the notice no later than twenty-four hours after

such Party becomes aware of the occurrence; and (ii) promptly furnish to the other Party copies

45



**SERVICE AGREEMENT NO. 2734**

of any publicly available reports filed with any Governmental Authorities addressing such

events.

**ARTICLE 24. INFORMATION REQUIREMENT**

**Information Acquisition.**

Connecting Transmission Owner and Transmission Developer shall each submit specific

information regarding the electrical characteristics of their respective facilities to the other, and

to NYISO, as described below and in accordance with Applicable Reliability Standards.

**Information Submission Concerning the Network Upgrade Facilities.**

The initial information submission by each of Connecting Transmission Owner and

Transmission Developer for the portion of the Network Upgrade Facilities for which each is

responsible shall occur no later than one hundred eighty (180) Calendar Days prior to Trial

Operation of the Network Upgrade Facilities and shall include New York State Transmission

System information necessary to allow the Transmission Developer to select equipment and meet

any system protection and stability requirements, unless otherwise mutually agreed to by the

Transmission Developer and Connecting Transmission Owner. On a quarterly basis Connecting

Transmission Owner and Transmission Developer shall each provide the other Parties a status

report on the construction and installation of the Network Upgrade Facilities for which it has

construction responsibility pursuant to Appendix A, including, but not limited to, the following

information: (1) progress to date; (2) a description of the activities since the last report; (3) a

description of the action items for the next period; and (4) the delivery status of equipment

ordered.

**Updated Information Submission Concerning the Transmission Project.**

The updated information submission by the Transmission Developer, including

manufacturer information, shall occur no later than one hundred eighty (180) Calendar Days

prior to the Trial Operation of the Transmission Project. Transmission Developer shall submit a

completed copy of the Transmission Project data requirements contained in Appendix 1 to the

Transmission Interconnection Procedures. It shall also include any additional information

provided to Connecting Transmission Owner for the Facilities Study. Information in this

submission shall be the most current Transmission Project design or expected performance data.

Information submitted for stability models shall be compatible with NYISO standard models. If

there is no compatible model, the Transmission Developer will work with a consultant mutually

agreed to by the Parties to develop and supply a standard model and associated information.

If the Transmission Developer’s data is different from what was originally provided to

Connecting Transmission Owner and NYISO pursuant to a Transmission Interconnection Study

agreement among Connecting Transmission Owner, NYISO and Transmission Developer and

this difference may be reasonably expected to affect the other Parties’ facilities or the New York

State Transmission System, but does not require the submission of a new Transmission

Interconnection Application, then NYISO will conduct appropriate studies to determine the

impact on the New York State Transmission System based on the actual data submitted pursuant

46



**SERVICE AGREEMENT NO. 2734**

to this Article [24.3. S](#br51)uch studies will provide an estimate of any additional modifications to the

New York State Transmission System or Network Upgrade Facilities based on the actual data

and a good faith estimate of the costs thereof. The Transmission Developer shall not begin Trial

Operation for the Transmission Project until such studies are completed. The Transmission

Developer shall be responsible for the cost of any modifications required by the actual data,

including the cost of any required studies.

**Information Supplementation.**

Prior to the In-Service Date, the Transmission Developer and Connecting Transmission

Owner shall supplement their information submissions described above in t[his Article 24](#br51) with

any and all “as-built” Transmission Project and Network Upgrade Facilities information or “as-

tested” performance information that differs from the initial submissions or, alternatively, written

confirmation that no such differences exist. The Transmission Developer shall conduct tests on

the Transmission Project as required by Good Utility Practice.

Subsequent to the In-Service Date, the Transmission Developer shall provide Connecting

Transmission Owner and NYISO any information changes concerning the Transmission Project

due to equipment replacement, repair, or adjustment. Connecting Transmission Owner shall

provide the Transmission Developer and NYISO any information changes concerning the

Network Upgrade Facilities due to equipment replacement, repair or adjustment in the directly

connected substation or any adjacent Connecting Transmission Owner substation that may affect

the Transmission Project’s equipment ratings, protection or operating requirements. The

Transmission Developer and Connecting Transmission Owner shall provide such information no

later than thirty (30) Calendar Days after the date of the equipment replacement, repair or

adjustment.

**ARTICLE 25. INFORMATION ACCESS AND AUDIT RIGHTS**

**Information Access.**

Each Party (“Disclosing Party”) shall make available to another Party (“Requesting

Party”) information that is in the possession of the Disclosing Party and is necessary in order for

the Requesting Party to: (i) verify the costs incurred by the Disclosing Party for which the

Requesting Party is responsible under this Agreement; and (ii) carry out its obligations and

responsibilities under this Agreement. The Parties shall not use such information for purposes

other than those set forth in this Article [25.1](#br52) of this Agreement and to enforce their rights under

this Agreement.

**Reporting of Non-Force Majeure Events.**

Each Party (the “Notifying Party”) shall notify the other Parties when the Notifying Party

becomes aware of its inability to comply with the provisions of this Agreement for a reason other

than a Force Majeure event. The Parties agree to cooperate with each other and provide

necessary information regarding such inability to comply, including the date, duration, reason for

the inability to comply, and corrective actions taken or planned to be taken with respect to such

inability to comply. Notwithstanding the foregoing, notification, cooperation or information

47



**SERVICE AGREEMENT NO. 2734**

provided under this Article shall not entitle the Party receiving such notification to allege a cause

for anticipatory breach of this Agreement.

**Audit Rights.**

Subject to the requirements of confidentiality under [Article 22](#br47) of this Agreement, each

Party shall have the right, during normal business hours, and upon prior reasonable notice to

another Party, to audit at its own expense the other Party’s accounts and records pertaining to the

other Party’s performance or satisfaction of its obligations under this Agreement. Such audit

rights shall include audits of the other Party’s costs, calculation of invoiced amounts, and each

Party’s actions in an Emergency or Emergency State. Any audit authorized by this Article shall

be performed at the offices where such accounts and records are maintained and shall be limited

to those portions of such accounts and records that relate to the Party’s performance and

satisfaction of obligations under this Agreement. Each Party shall keep such accounts and

records for a period equivalent to the audit rights periods described in Artic[le 25.4](#br53) of this

Agreement.

**Audit Rights Periods.**

**25.4.1 Audit Rights Period for Construction-Related Accounts and Records.**

Accounts and records related to the design, engineering, procurement, and construction of

the Network Upgrade Facilities shall be subject to audit for a period of twenty-four months

following Connecting Transmission Owner’s issuance of a final invoice in accordance with

Artic[le 12.2](#br39) of this Agreement.

**25.4.2 Audit Rights Period for All Other Accounts and Records.**

Accounts and records related to a Party’s performance or satisfaction of its obligations

under this Agreement other than those described in Artic[le 25.4.1](#br53) of this Agreement shall be

subject to audit as follows: (i) for an audit relating to cost obligations, the applicable audit rights

period shall be twenty-four months after the auditing Party’s receipt of an invoice giving rise to

such cost obligations; and (ii) for an audit relating to all other obligations, the applicable audit

rights period shall be twenty-four months after the event for which the audit is sought.

**Audit Results.**

If an audit by a Party determines that an overpayment or an underpayment has occurred, a

notice of such overpayment or underpayment shall be given to the other Party together with

those records from the audit which support such determination.

**ARTICLE 26. SUBCONTRACTORS**

**General.**

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided,

however, that each Party shall require its subcontractors to comply with all applicable terms and

48



**SERVICE AGREEMENT NO. 2734**

conditions of this Agreement in providing such services and each Party shall remain primarily

liable to the other Parties for the performance of such subcontractor.

**Responsibility of Principal.**

The creation of any subcontract relationship shall not relieve the hiring Party of any of its

obligations under this Agreement. The hiring Party shall be fully responsible to the other Parties

for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been

made; provided, however, that in no event shall the NYISO or Connecting Transmission Owner

be liable for the actions or inactions of the Transmission Developer or its subcontractors with

respect to obligations of the Transmission Developer unde[r Article 5](#br17) of this Agreement. Any

applicable obligation imposed by this Agreement upon the hiring Party shall be equally binding

upon, and shall be construed as having application to, any subcontractor of such Party.

**No Limitation by Insurance.**

The obligations unde[r this Article 26](#br53) will not be limited in any way by any limitation of

subcontractor’s insurance.

**ARTICLE 27. DISPUTES**

**Submission.**

In the event any Party has a dispute, or asserts a claim, that arises out of or in connection

with this Agreement or its performance (a “Dispute”), such Party shall provide the other Parties

with written notice of the Dispute (“Notice of Dispute”). Such Dispute shall be referred to a

designated senior representative of each Party for resolution on an informal basis as promptly as

practicable after receipt of the Notice of Dispute by the other Parties. In the event the designated

representatives are unable to resolve the Dispute through unassisted or assisted negotiations

within thirty (30) Calendar Days of the other Parties’ receipt of the Notice of Dispute, such

Dispute may, upon mutual agreement of the Parties, be submitted to arbitration and resolved in

accordance with the arbitration procedures set forth below. In the event the Parties do not agree

to submit such Dispute to arbitration, each Party may exercise whatever rights and remedies it

may have in equity or at law consistent with the terms of this Agreement.

**External Arbitration Procedures.**

Any arbitration initiated under this Agreement shall be conducted before a single neutral

arbitrator appointed by the Parties. If the Parties fail to agree upon a single arbitrator within ten

(10) Calendar Days of the submission of the Dispute to arbitration, each Party shall choose one

arbitrator who shall sit on a three-member arbitration panel. In each case, the arbitrator(s) shall

be knowledgeable in electric utility matters, including electric transmission and bulk power

issues, and shall not have any current or past substantial business or financial relationships with

any party to the arbitration (except prior arbitration). The arbitrator(s) shall provide each of the

Parties an opportunity to be heard and, except as otherwise provided herein, shall conduct the

arbitration in accordance with the Commercial Arbitration Rules of the American Arbitration

Association (“Arbitration Rules”) and any applicable FERC regulations or RTO rules; provided,

49



**SERVICE AGREEMENT NO. 2734**

however, in the event of a conflict between the Arbitration Rules and the terms of thi[s Article 27,](#br54)

the terms of thi[s Article 27](#br54) shall prevail.

**Arbitration Decisions.**

Unless otherwise agreed by the Parties, the arbitrator(s) shall render a decision within

ninety (90) Calendar Days of appointment and shall notify the Parties in writing of such decision

and the reasons therefor. The arbitrator(s) shall be authorized only to interpret and apply the

provisions of this Agreement and shall have no power to modify or change any provision of this

Agreement in any manner. The decision of the arbitrator(s) shall be final and binding upon the

Parties, and judgment on the award may be entered in any court having jurisdiction. The

decision of the arbitrator(s) may be appealed solely on the grounds that the conduct of the

arbitrator(s), or the decision itself, violated the standards set forth in the Federal Arbitration Act

or the Administrative Dispute Resolution Act. The final decision of the arbitrator must also be

filed with FERC if it affects jurisdictional rates, terms and conditions of service, or Network

Upgrade Facilities.

**Costs.**

Each Party shall be responsible for its own costs incurred during the arbitration process

and for the following costs, if applicable: (1) the cost of the arbitrator chosen by the Party to sit

on the three member panel; or (2) one-third the cost of the single arbitrator jointly chosen by the

Parties.

**Termination.**

Notwithstanding the provisi[ons of this Article 27, a](#br54)ny Party may terminate this

Agreement in accordance with its provisions or pursuant to an action at law or equity. The issue

of whether such a termination is proper shall not be considered a Dispute hereunder.

**ARTICLE 28. REPRESENTATIONS, WARRANTIES AND COVENANTS**

**General.**

Each Party makes the following representations, warranties and covenants:

**28.1.1**

**Good Standing.**

Such Party is duly organized, validly existing and in good standing under the laws of the

state in which it is organized, formed, or incorporated, as applicable; that it is qualified to do

business in the state or states in which the Transmission Project and Network Upgrade Facilities

owned by such Party, as applicable, are located; and that it has the corporate power and authority

to own its properties, to carry on its business as now being conducted and to enter into this

Agreement and carry out the transactions contemplated hereby and perform and carry out all

covenants and obligations on its part to be performed under and pursuant to this Agreement.

50



**SERVICE AGREEMENT NO. 2734**

**28.1.2 Authority.**

Such Party has the right, power and authority to enter into this Agreement, to become a

Party hereto and to perform its obligations hereunder. This Agreement is a legal, valid and

binding obligation of such Party, enforceable against such Party in accordance with its terms,

except as the enforceability thereof may be limited by applicable bankruptcy, insolvency,

reorganization or other similar laws affecting creditors’ rights generally and by general equitable

principles (regardless of whether enforceability is sought in a proceeding in equity or at law).

**28.1.3**

**No Conflict.**

The execution, delivery and performance of this Agreement does not violate or conflict

with the organizational or formation documents, or bylaws or operating agreement, of such

Party, or any judgment, license, permit, order, material agreement or instrument applicable to or

binding upon such Party or any of its assets.

**28.1.4**

**Consent and Approval.**

Such Party has sought or obtained, or, in accordance with this Agreement will seek or

obtain, each consent, approval, authorization, order, or acceptance by any Governmental

Authority in connection with the execution, delivery and performance of this Agreement, and it

will provide to any Governmental Authority notice of any actions under this Agreement that are

required by Applicable Laws and Regulations.

**ARTICLE 29. MISCELLANEOUS**

**Binding Effect.**

This Agreement and the rights and obligations hereof, shall be binding upon and shall

inure to the benefit of the successors and permitted assigns of the Parties hereto.

**Conflicts.**

If there is a discrepancy or conflict between or among the terms and conditions of this

cover agreement and the Appendices hereto, the terms and conditions of this cover agreement

shall be given precedence over the Appendices, except as otherwise expressly agreed to in

writing by the Parties. As permitted by the foregoing, the Parties expressly agree that the terms

and conditions of the Appendices shall take precedence over the provisions of this cover

agreement in case of a discrepancy or conflict between or among the terms and conditions of

same.

**Rules of Interpretation.**

This Agreement, unless a clear contrary intention appears, shall be construed and

interpreted as follows: (1) the singular number includes the plural number and vice versa; (2)

reference to any person includes such person’s successors and assigns but, in the case of a Party,

only if such successors and assigns are permitted by this Agreement, and reference to a person in

51



**SERVICE AGREEMENT NO. 2734**

a particular capacity excludes such person in any other capacity or individually; (3) reference to

any agreement (including this Agreement), document, instrument or tariff means such

agreement, document, instrument, or tariff as amended or modified and in effect from time to

time in accordance with the terms thereof and, if applicable, the terms hereof; (4) reference to

any Applicable Laws and Regulations means such Applicable Laws and Regulations as

amended, modified, codified, or reenacted, in whole or in part, and in effect from time to time,

including, if applicable, rules and regulations promulgated thereunder; (5) unless expressly stated

otherwise, reference to any Article, Section or Appendix means such Article of this Agreement

or such Appendix to this Agreement, or such Section to the Transmission Interconnection

Procedures or such Appendix to the Transmission Interconnection Procedures, as the case may

be; (6) “hereunder”, “hereof’, “herein”, “hereto” and words of similar import shall be deemed

references to this Agreement as a whole and not to any particular Article or other provision

hereof or thereof; (7) “including” (and with correlative meaning “include”) means including

without limiting the generality of any description preceding such term; and (8) relative to the

determination of any period of time, “from” means “from and including”, “to” means “to but

excluding” and “through” means “through and including”.

**Compliance.**

Each Party shall perform its obligations under this Agreement in accordance with

Applicable Laws and Regulations, Applicable Reliability Standards, the ISO OATT and Good

Utility Practice. To the extent a Party is required or prevented or limited in taking any action by

such regulations and standards, such Party shall not be deemed to be in Breach of this Agreement

for its compliance therewith. When any Party becomes aware of such a situation, it shall notify

the other Parties promptly so that the Parties can discuss the amendment to this Agreement that is

appropriate under the circumstances.

**Joint and Several Obligations.**

Except as otherwise stated herein, the obligations of NYISO, Transmission Developer

and Connecting Transmission Owner are several, and are neither joint nor joint and several.

**Entire Agreement.**

Except as described in Section 7 of Appendix C, this Agreement, including all

Appendices and Schedules attached hereto, constitutes the entire agreement between the Parties

with reference to the subject matter hereof, and supersedes all prior and contemporaneous

understandings or agreements, oral or written, between the Parties with respect to the subject

matter of this Agreement. Except as described in Section 7 of Appendix C, there are no other

agreements, representations, warranties, or covenants which constitute any part of the

consideration for, or any condition to, either Party’s compliance with its obligations under this

Agreement.

**No Third Party Beneficiaries.**

This Agreement is not intended to and does not create rights, remedies, or benefits of any

character whatsoever in favor of any persons, corporations, associations, or entities other than the

52



**SERVICE AGREEMENT NO. 2734**

Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their

successors in interest and permitted their assigns.

**Waiver.**

The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver of any

obligation, right, or duty of, or imposed upon, such Party. Any waiver at any time by either

Party of its rights with respect to this Agreement shall not be deemed a continuing waiver or a

waiver with respect to any other failure to comply with any other obligation, right, duty of this

Agreement. Termination or Default of this Agreement for any reason by the Transmission

Developer shall not constitute a waiver of the Transmission Developer’s legal rights to obtain

Capacity Resource Interconnection Service and Energy Resource Interconnection Service from

the NYISO and Connecting Transmission Owner in accordance with the provisions of the ISO

OATT. Any waiver of this Agreement shall, if requested, be provided in writing.

**Headings.**

The descriptive headings of the various Articles of this Agreement have been inserted for

convenience of reference only and are of no significance in the interpretation or construction of

this Agreement.

**Multiple Counterparts.**

This Agreement may be executed in two or more counterparts, each of which is deemed

an original but all constitute one and the same instrument.

**Amendment.**

The Parties may by mutual agreement amend this Agreement, by a written instrument

duly executed by all three of the Parties.

**Modification by the Parties.**

The Parties may by mutual agreement amend the Appendices to this Agreement, by a

written instrument duly executed by all three of the Parties. Such an amendment shall become

effective and a part of this Agreement upon satisfaction of all Applicable Laws and Regulations.

**Reservation of Rights.**

NYISO and Connecting Transmission Owner shall have the right to make unilateral

filings with FERC to modify this Agreement with respect to any rates, terms and conditions,

charges, classifications of service, rule or regulation under section 205 or any other applicable

provision of the Federal Power Act and FERC’s rules and regulations thereunder, and

Transmission Developer shall have the right to make a unilateral filing with FERC to modify this

Agreement pursuant to section 206 or any other applicable provision of the Federal Power Act

and FERC’s rules and regulations thereunder; provided that each Party shall have the right to

protest any such filing by another Party and to participate fully in any proceeding before FERC

53



**SERVICE AGREEMENT NO. 2734**

in which such modifications may be considered. Nothing in this Agreement shall limit the rights

of the Parties or of FERC under sections 205 or 206 of the Federal Power Act and FERC’s rules

and regulations thereunder, except to the extent that the Parties otherwise mutually agree as

provided herein.

**No Partnership.**

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership among the Parties or to impose any partnership

obligation or partnership liability upon any Party. No Party shall have any right, power or

authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an

agent or representative of, or to otherwise bind, any other Party.

**Other Transmission Rights.**

Notwithstanding any other provision of this Agreement, nothing herein shall be construed

as relinquishing or foreclosing any rights, including but not limited to firm transmission rights,

capacity rights, or transmission congestion rights that the Transmission Developer shall be

entitled to, now or in the future under any other agreement or tariff as a result of, or otherwise

associated with, the transmission capacity, if any, created by the Transmission Project and

Network Upgrade Facilities.

54



**SERVICE AGREEMENT NO. 2734**

**IN WITNESS WHEREOF**, the Parties have executed this Agreement in duplicate originals,

each of which shall constitute and be an original effective Agreement between the Parties.

**New York Independent System Operator, Inc.**

By:

Name:

Title:

Date:

**Consolidated Edison Company of New York, Inc.**

By:

Name: Walter Alvarado

Title: Vice President of Systems and Transmission Operations

Date:

**New York Transco, LLC**

By:

By: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name: Paul Haering\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title: Vice President of Capital Investment

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name: Victor Mullin\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title: President\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date:

55



**SERVICE AGREEMENT NO. 2734**

**APPENDICES**

**Appendix A**

Network Upgrade Facilities

**Appendix B**

Milestones

**Appendix C**

Interconnection Details

**Appendix D**

Security Arrangements Details

**Appendix E-1**

Initial Synchronization Date

**Appendix E-2**

In-Service Date

**Appendix F**

Addresses for Delivery of Notices and Billings

**SERVICE AGREEMENT NO. 2734**

**APPENDIX A**

**NETWORK UPGRADE FACILITIES**

**I.**

**Network Upgrade Facilities for Connecting Transmission Owner’s Transmission**

**System**

The Transmission Project, which is described in Appendix C, will interconnect to the

New York State Transmission System at existing transmission facilities owned and operated by

the Connecting Transmission Owner, as shown in Figure A-1 in this Appendix A. A portion of

the Transmission Project will interconnect with the Connecting Transmission Owner’s Line 398

345 kV transmission line (“Line 398”). This portion of the Transmission Project is described in

Section II of this Appendix A and shown in Figure C-2 in Appendix C to this Agreement. The

Facilities Study identified the Network Upgrade Facilities that are described in Section III of this

Appendix A that are required to reliably interconnect the Transmission Project with Line 398.

The Transmission Developer’s and Connecting Transmission Owner’s responsibilities

concerning these Network Upgrade Facilities are set forth in this Appendix A and are in

accordance with the terms of this Agreement.

Pursuant to Section 22.10 of Attachment P to the NYISO OATT, the Connecting

Transmission Owner and Transmission Developer entered into a Master Services Agreement

(MSA) with Transaction Form 3 (TF #3), which addresses the engineering design of the Network

Upgrade Facilities as identified in Section III.1 of this Appendix A. The procurement of the

equipment will be performed by Transmission Developer with Connecting Transmission

Owner’s review and approval in accordance with this Agreement.

Portions of the Transmission Project will separately interconnect to other Connecting

Transmission Owner’s transmission facilities, which interconnection requires certain Network

Upgrade Facilities at the Connecting Transmission Owner’s Pleasant Valley 345 kV Substation

and Transmission Developer’s Knickerbocker Substation, along with relay testing at the

Connecting Transmission Owner’s Pleasant Valley 345 kV and Cricket Valley Substations.

These Network Upgrade Facilities are detailed in the separate Transmission Project

Interconnection Agreement among the NYISO, Connecting Transmission Owner, and

Transmission Developer dated as of October 8, 2021 with Service Agreement No. 2654.

Connecting Transmission Owner’s and Transmission Developer’s responsibilities concerning

this separate interconnection and the related Network Upgrade Facilities are set forth in such

other Transmission Project Interconnection Agreement.

**II.**

**Transmission Project Interconnecting with Connecting Transmission Owner’s Line**

**398**

As part of the Transmission Project described in Appendix C, Transmission Developer is

constructing a phase angle regulator (“PAR”) substation in the Town of Dover, Dutchess

County, New York (“Dover PAR Substation”). The Dover PAR Substation is located less than

one half mile south of Connecting Transmission Owner’s right of way for Connecting

Transmission Owner’s existing transmission Line 398 that runs between Connecting

A-1

**SERVICE AGREEMENT NO. 2734**

Transmission Owner’s Cricket Valley Substation and the Long Mountain Substation (owned by

Eversource) located in Milford, Connecticut.

The impacts of the Network Upgrade Facilities on the relay settings at the Long

Mountain Substation are subject to a separate Facilities Study Report performed by ISO New

England and Eversource. Transmission Developer shall be responsible for complying with ISO

New England requirements to address any impacts identified at the Long Mountain Substation.

Transmission Developer will own and operate the Dover PAR Substation, the PARs at

the Dover PAR Substation, and the line segment between the Dover PAR Substation and the

Point of Interconnection (“POI”)/Point of Change of Ownership (“PCO”), which are defined in

Appendix C. The Dover PAR Substation is a greenfield site, air insulated substation (“AIS”)

arrangement and will operate at 345 kV nominal. The Dover PAR Substation will intercept the

existing 345 kV circuit 398.

**III.**

**Network Upgrade Facilities on Connecting Transmission Owner’s Transmission**

**System Identified for the Transmission Project**

**1. Network Upgrade Facilities on Connecting Transmission Owner’s Line 398**

Transmission Developer will design, procure, construct, and install the Network Upgrade

Facilities described in this Section III.1 of Appendix A in accordance with the requirements in

Article 5.2 of this Agreement and the following requirements to the extent not inconsistent with

the terms of this Agreement, the NYISO OATT, or ISO Procedures: Applicable Laws and

Regulations, the New York State Public Service Commission (“NYPSC”) Order Granting

Certificate of Environmental Compatibility and Public Need, issued and effective, April 20, 2016

(the “Certificate”), and all follow up approvals by the NYPSC, including any approved

Environmental Management and Construction Plan (the “EM&CP”), all approved modifications

to the Certificate and/or the EM&CP, Connecting Transmission Owner’s NERC/CIP risk

management and/or compliance plans, and the applicable requirements and standards of the

Connecting Transmission Owner provided in accordance with Section 6 of Appendix C.

Transmission Developer’s contractor performing this work shall be from the Connecting

Transmission Owner’s list of approved contractors.

Specifically, Transmission Developer will design, procure, construct, and install the

following Network Upgrade Facilities:

A) Line 398 Structures:

• Remove existing lattice tower (L-61) and replace with new steel monopole;

• Install a new double circuit, steel monopole (#L61-1); and

• Reinforce existing H-Frame structures (#62).

A-2



**SERVICE AGREEMENT NO. 2734**

• Splice the existing OPGW from Cricket Valley to Long Mountain at the newly

proposed transmission tower L-61-1 between transmission towers L-61 and L-62;

and

• Connect splices to new Dover PAR Substation, effectively creating 2 fiber paths –

one from Cricket Valley to Dover PAR and one from Dover PAR to Long

Mountain.

B) Bifurcating and Reconductoring Line 398:

• Reconductor segment between L-61 and L-61-1 to be redesignated Y-17;

• Install new segment between L-61-1 and the POI/PCO at the Dover PAR

Substation (West), to be redesignated Y-17;

• Reconductor segment between L-62 and L-61-1;

• Install new segments between L-61-1 and the POI/PCO at the Dover PAR

Substation (East);

• Modify/install OPGW / ADSS fiber as required by final design including, but not

limited to installing ADSS cable from Dover to Cricket Valley Substation and

testing of the cables; and

• Revenue grade metering associated with the PAR’s when in service.

Transmission Developer will be responsible for performing the reconductoring and

replacement of shield wire with optical ground wire (“OPGW”) with 72 fibers of Line 398

identified above (“New York Line 398 Reconductoring”), which line segment will consist of

twin-bundled 795 kcmil ACSS Mallard conductor and one (1) shield wire~~s~~ and one (1) OPGW

with 72 fibers as necessary to connect the Dover PAR Substation.

**2. Network Upgrade Facilities at Cricket Valley Substation – Relay Protection**

Connecting Transmission Owner will design, procure, construct and install, as required,

the Network Upgrade Facilities at the Cricket Valley Substation to accommodate the

modification of the Line 398, which major equipment shall consist of the following:

• The existing SEL-411L (11L-1/398) shall be reused as first line current differential

protection, utilizing OPGW and dark fiber for route 1 and route 2 communications

respectively;

• The existing second line SEL-421 (11L-2/398) relay will be removed and replaced by

a SEL-311L (11L-2/398\*\*) current differential relay, utilizing fiber communication

and OPGW for route 1 and route 2 communications respectively. An SEL field

representative will be required to assist on site;

A-3



**SERVICE AGREEMENT NO. 2734**

\*\* feeder designation subject to change

• The existing SEL-487B (11B-2) shall be reused for second line bus differential

protection;

• Support testing of OPGW and ADSS fiber cables at the Cricket Valley Substation;

and

• Install/test fiber jumpers inside Cricket Valley Substation.

Connecting Transmission Owner shall perform all final acceptance inspections and testing at the

Cricket Valley Substation.

**IV.**

**Interconnection to and Network Upgrade Facilities for Other Connecting**

**Transmission Owners’ Transmission Systems**

**A. Niagara Mohawk Power Corporation d/b/a National Grid**

Portions of the Transmission Project will interconnect to the New York State

Transmission System at existing transmission facilities owned and operated by National Grid,

which is also a Connecting Transmission Owner for the Transmission Project. The Facilities

Study identified certain Network Upgrade Facilities at National Grid’s Schodack 115 kV

Substation, Greenbush 115 kV Substation, Valkin 115 kV Substation, Hudson 115 kV

Substation, New Scotland Substation and Alps Substation, along with upgrades at the Blue

Stores 115 kV tap, Buckley Corners 115 kV tap, Fort Orange 115 kV tap, LaFarge 115 kV Tap,

ADM Milling 115 kV tap, Hudson 115 kV tap, line 14N interconnection point, and Valkin 115

kV tap, which Network Upgrade Facilities are required to reliably interconnect the Transmission

Project to National Grid’s system. The Transmission Developer, National Grid, and the NYISO

have entered into a separate Transmission Project Interconnection Agreement concerning the

interconnection of the Transmission Project to National Grid’s facilities and the construction or

installation of the related Network Upgrade Facilities on National Grid’s facilities.

**B. New York State Electric & Gas Corporation**

Portions of the Transmission Project will interconnect to the New York State

Transmission System at existing transmission facilities owned and operated by New York State

Electric & Gas Corporation (“NYSEG”), which is also a Connecting Transmission Owner for the

Transmission Project. The draft NYSEG Facilities Study identified certain Network Upgrade

Facilities at NYSEG’s Fall Park 115 kV Substation, Craryville 115 kV Substation, Klinekill

115/34.5 kV Substation, and Coopers Corner 345 kV Substation that are required to reliably

interconnect the Transmission Project to NYSEG’s system. The Transmission Developer,

NYSEG, and the NYISO have entered into a separate Transmission Project Interconnection

Agreement concerning the interconnection of the Transmission Project to NYSEG’s facilities

and the construction or installation of the related Network Upgrade Facilities on NYSEG’s

facilities.

**C. Central Hudson Gas & Electric Corporation**

A-4

**SERVICE AGREEMENT NO. 2734**

Portions of the Transmission Project will interconnect to the New York State

Transmission System at existing transmission facilities owned and operated by Central Hudson

Gas & Electric Corporation (“Central Hudson”), which is also a Connecting Transmission

Owner for the Transmission Project. The Facilities Study identified certain Network Upgrade

Facilities at Central Hudson’s Milan 115 kV Substation, North Catskill Substation, Pleasant

Valley 115 kV Substation, Rock Tavern 345 kV and 115 kV Substations, and Roseton 345 kV

Substation that are required to reliably interconnect the Transmission Project to Central

Hudson’s system. The Transmission Developer, Central Hudson, and the NYISO have entered

into a separate Transmission Project Interconnection Agreement concerning the interconnection

of the Transmission Project to Central Hudson’s facilities and the construction or installation of

the related Network Upgrade Facilities on Central Hudson’s facilities.

**D. Orange and Rockland Utilities, Inc.**

Portions of the Transmission Project will interconnect to the New York State

Transmission System at existing transmission facilities owned and operated by Orange and

Rockland Utilities, Inc. (“O&R”), which is also a Connecting Transmission Owner for the

Transmission Project. The Facilities Study identified certain Network Upgrade Facilities at

O&R’s Sugarloaf 138 kV Substation that are required to reliably interconnect the Transmission

Project to O&R’s system. The Transmission Developer, O&R, and the NYISO have entered into

a separate Transmission Project Interconnection Agreement concerning the interconnection of

the Transmission Project to O&R’s facilities and the construction or installation of the related

Network Upgrade Facilities on O&R’s facilities.

**V.**

**Affected System Upgrade Facilities**

The Transmission Interconnection Studies for the Transmission Project identified New

York Power Authority (“NYPA”), Castleton Power, LLC (for the Fort Orange Substation),

Holcim (US) Inc. (for the LaFarge Substation), and ADM Milling Co. (for the ADM Milling

Substation) as Affected System Operators, which systems are impacted by the Transmission

Project. The Facilities Studies conducted for the Transmission Project identified certain

Network Upgrade Facilities required for these Affected Systems.

**A. NYPA**

The Transmission Interconnection Studies for the Transmission Project identified that

certain Network Upgrade Facilities at NYPA’s Dolson Ave. 345 kV Substation are required in

connection with the Transmission Project. This work will be performed in accordance with the

terms of an engineering, procurement, and construction agreement by and among the NYISO,

Transmission Developer, and NYPA. However, the NYISO reviewed a non-material

determination of Transmission Developer and determined that certain feeder re-ratings would not

result in any Network Upgrade Facilities at the NYPA substations, other than a relay setting

evaluation.

**B. Fort Orange Substation**

A-5

**SERVICE AGREEMENT NO. 2734**

The Transmission Interconnection Studies for the Transmission Project identified that

modifications to the relay settings at the Fort Orange Substation are required in connection with

the Transmission Project. The relay resetting and drawing updates will be performed for the Fort

Orange Substation to reflect the new Line 14N Tap location in accordance with the terms of an

engineering, procurement, and construction agreement by and among the Transmission

Developer, Castleton Power, LLC, and the NYISO.

**C. LaFarge Substation**

The Transmission Interconnection Studies for the Transmission Project identified that

certain Network Upgrade Facilities at the LaFarge Substation are required in connection with the

Transmission Project. This work including, but not limited to, relay resetting, and drawing

updates will be performed for the LaFarge Substation to reflect the new Line 8 Tap location in

accordance with the terms of an engineering, procurement, and construction agreement by and

among the Transmission Developer, LaFarge, and the NYISO.

**D. ADM Milling**

The Transmission Interconnection Studies for the Transmission Project identified that

certain Network Upgrade Facilities at the ADM Milling Substation are required in connection

with the Transmission Project. This work will be performed in accordance with the terms of an

engineering, procurement, and construction agreement by and among the NYISO, Transmission

Developer, and ADM Milling. The work will include performance of calculations for the

resetting of relays, and the update to drawings to reflect the new line nomenclature.

**VI. Work Responsibilities.**

Transmission Developer shall design, procure, construct, and install the Network Upgrade

Facilities for which it is responsible as specified in Section III.1 of this Appendix A.

Transmission Developer will also complete testing and commissioning for the Dover PAR

Substation equipment and for the segment of conductor up to and including the POI /PCO.

Connecting Transmission Owner shall design, procure, construct, and install the Network

Upgrade Facilities for which it is responsible as specified in Section III.2 of this Appendix A.

Connecting Transmission Owner shall also provide electrical isolation on 345kV feeder #398 to

allow all work to safety proceed (isolation/grounds, wiring) for all work associated with

Connecting Transmission Owner’s equipment. In addition, Connecting Transmission Owner’s

System Operations Department shall coordinate with NYISO and Eversource and other

transmission operators, as may be necessary, to provide required isolation/protection at remote

ends. Connecting Transmission Owner will also complete pre-in-service testing and

commissioning for the NUFs that are to be transferred to the Connecting Transmission Owner,

and for the relays that may require resetting.

**VII. Cost Estimates**

**Description**

**Estimated Cost**

A-6



**SERVICE AGREEMENT NO. 2734**

Network Upgrade Facilities

$13,550,000.00

**Total $13.550,000.00**

The following labor and material are **excluded** from the Facility Study cost estimates:

1. All environmental costs associated with the Transmission Developer’s Transmission Project,

including but not limited to any environmental remediation and environmental cleanup.

2. All costs associated with subsurface conditions.

3. Cost for tower stringing by Transmission Developer.

4. Any and all work inside the fence line of the Dover PAR Substation.

5. Permitting required for installation and/or replacement of new transmission towers.

**Connecting Transmission Owner’s Cost Estimate Assumptions**

1. Connecting Transmission Owner will remain the transmission owner for the entire length of

Feeder 398, excluding the portion within the fence line of Dover PAR Substation.

2. Transmission Developer will be the transmission owner of Dover PAR Substation.

3. Interconnection into Dover PAR Substation will not impact the existing established Feeder

398 ratings (normal, STE and LTE) and reliability criteria.

4. Costs to clear approximately 2.29 moderately wooded acres from the right-of-way for Feeder

398 to the fence line of Dover PAR Substation are included.

5. New right-of-way grading costs are included.

6. New access roads for new tower installations are included.

7. Relay protection man hours are based on the original relay installation work at the Cricket

Valley Substation and recent relay upgrade projects of similar nature.

8. New transmission tower are based on preliminary concept designs by Power Engineers dated

Jan. 25, 2021. Costs are based on recent installations during the construction of the Cricket

Valley Substation.


9. Transmission tower costs include grounding.

10. Transmission tower costs include construction of a work pad for future maintenance work.

11. Transmission tower costs include foundations, based on Connecting Transmission Owner’s

standards.

A-7



**SERVICE AGREEMENT NO. 2734**

12. Contractor rates are based on prevailing wage rates for trades in Dutchess County.

13. Connecting Transmission Owner’s rates are based on the 2020 Accommodation Billing Rates

Schedule are subject to change.

14. Contractor Oversight Project Management and Inspection (“PM&I”) is based on 15% of total

contract man hours.

15. Two full time Substation Operators are included for the duration of the project to handle

work permits, site access and ops support.

**IX.**

**Security**

Pursuant to Article 11.4 of this Agreement, Transmission Developer will provide

Connecting Transmission Owner with Security, in the form of a Letter of Credit, in the amount

of $13,550,000.00, which reflects the estimated costs for the Network Upgrade Facilities.

**Description**

**Estimated Cost**

*Network Upgrade Facilities per Facility Study Report* $13,550,000.00


**Required Security Deposit to be Posted**

**$13,550,000.00**

**Figure A-1 Post Project Diagram**

**[CONTAINS CEII – THIS PAGE REMOVED FROM PUBLIC VERSION]**

A-8



**SERVICE AGREEMENT NO. 2734**

**1. Milestones**

**APPENDIX B**

The following milestones shall apply to the engineering, procurement, and construction

activities related to the interconnection of the Transmission Project. With the exception of the

In-Service Dates and Commercial Operation Date, the timeframes projected for the milestones

are non-binding estimates; *provided, however*, that pursuant to Article 5.1 of the Agreement, the

Transmission Developer and the Connecting Transmission Owner shall each use Reasonable

Efforts to complete the Network Upgrade Facilities for which it has construction responsibility

by the dates set forth such milestones. The In-Service Dates and Commercial Operations Date

can only be extended in accordance with the requirements set forth in the NYISO OATT. The

actual dates for completion of the milestones are highly dependent upon system reliability, lead

times for the procurement of equipment and material, release of engineering packages by the

Transmission Developer and approval of the “issued for construction” packages by Connecting

Transmission Owner, the availability of labor, approved outage scheduling, receipt of regulatory

approvals, and the results of equipment testing.

**MILESTONES**

**Milestone**

**Date**

**Responsible Party**

1.

2.

Award order for Procurement of Complete

the Phase Angle Regulator

Transmission Developer

Transmission Developer

Start engineering of Dover PAR Complete

Substation and Transmission

Line to ROW

3.

Execute Interconnection

Agreement

Complete

Connecting

Transmission

Owner/Transmission

Developer/ NYISO

4.

5.

Post Security Deposit

Complete

Complete

Transmission Developer

Transmission Developer

Complete engineering for

Transmission Project principal

components \*

6.


Complete 60% Transmission

Line design for submittal

Complete

Transmission Developer

B-1



**SERVICE AGREEMENT NO. 2734**

**Milestone**

**Date**

**Responsible Party**

7.

8.

9.

Complete 90% Transmission

Line design for submittal

Complete

Complete

Complete

Transmission Developer

Complete 60% Design Package

- Relay Upgrades

Connecting

Transmission Owner

Complete Issued for

Construction Transmission Line

submittal

Transmission Developer

10.

11.

Commence substation and

transmission line site prep

August 2024

Complete

Transmission Developer

Transmission Developer

Complete Issued for

Construction Primary design

Substation submittal

12.

13.

Mobilize crews for the substation June 2024

build

Transmission Developer

Commence testing of the OPGW November 2024

after the installation of the new

tower L-61

Connecting

Transmission Owner/

Transmission Developer

14.

15.

16.

Complete 90% Design Package December 2024

- Relay Upgrades

Connecting

Transmission Owner

Complete Issue for Construction December 2024

Package - Relays Protection

Connecting

Transmission Owner

Commence testing of the

interception of Line 398 to create

Y17 and commission the Dover

PAR substation.

March 2025

May 2025

Connecting

Transmission Owner/

Transmission Developer

17.

Complete construction of


Network Upgrade Facilities as

defined in Appendix A Section

III

Transmission Developer

B-2



**SERVICE AGREEMENT NO. 2734**

**Milestone**

**Date**

**Responsible Party**

18.

Complete any required relay

May 2025

Connecting

resetting as defined in Appendix

A

Transmission Owner

19.

20.

Complete testing and

commissioning

June 2025

June 2025

Connecting

Transmission Owner/

Transmission Developer

Dover In-Service Date

Connecting

Transmission

Owner/Transmission

Developer

21.

Completion of As Builts

September 2025

Connecting

Transmission

Owner/Transmission

Developer

22.

23.

Project closeout completed

Final invoicing

December 2025

December 2025

Connecting

Transmission Owner

Connecting

Transmission Owner

**2. Prepayment for Work Performed by Connecting Transmission Owner**

Included within the total cost estimates provided in Section VII of Appendix A are the

cost estimates for the Connecting Transmission Owner’s engineering, procurement, construction,

and associated services related to the Network Upgrades Facilities described in Section III of

Appendix A.

As required by Transaction Form #3, Transmission Developer has already paid to

Connecting Transmission Owner a deposit in the amount of two hundred fifty thousand dollars

($250,000.00). This amount is held by Connecting Transmission Owner in immediately

available funds in an account established by Connecting Transmission Owner in accordance with


its internal procedures (the “Engineering Disbursement Account”). The funds in the Engineering

Disbursement Account have been and shall continue to be drawn upon by Connecting

Transmission Owner to pay Connecting Transmission Owner for its performance of the

engineering services identified in Transaction Form #3 in accordance with the terms of that form.

B-3



**SERVICE AGREEMENT NO. 2734**

The Connecting Transmission Owner’s procurement and construction services pursuant

to Section III of Appendix A to this Agreement and the related charges and costs under this

Agreement shall be treated in a similar fashion as the engineering services and will be

compensated through a separate disbursement account as set forth below.

The price for the services described in Section III of Appendix A shall be based on the

applicable hourly rates and other charges and costs set forth in the document entitled

*Consolidated Edison Company of New York, Inc. 2022 Accommodation Billing Rates* (“2022

Accommodation Billing Schedule”). Transmission Developer acknowledges and agrees that the

rates, charges, and costs set forth in the 2022 Accommodation Billing Schedule are subject to

periodic revision by Connecting Transmission Owner upon written notice to Transmission

Developer and that, after the date of the notice, the revised rates, charges, and costs referenced in

the notice shall be applicable to the provided services. The rates, charges, and costs set forth in

the 2022 Accommodation Billing Schedule, and any successor billing schedule, do not include

any charge or fee for any governmental or non-governmental permits, authorization, consents or

approvals that may be required in connection with the provided services. Transmission

Developer agrees to pay any such charges and fees and to reimburse Connecting Transmission

Owner for any such charges and fees that Connecting Transmission Owner is required to pay.

Transmission Developer will be required to provide to Connecting Transmission Owner a

deposit for Connecting Transmission Owner’s services under this Agreement in the amount of

two hundred fifty thousand dollars ($250,000.00) to be held by Connecting Transmission Owner

in immediately available funds in an account established by Connecting Transmission Owner in

accordance with its internal procedures (the “IA Disbursement Account”).

Connecting Transmission Owner shall issue invoices monthly and shall describe the

period covered by the invoice, the hours of services furnished during such period, and the

applicable hourly rates and reimbursable charges and costs. For purposes of the provided

services described in Section III of Appendix A, Connecting Transmission Owner is authorized

to withdraw the amount of each such invoice from the IA Disbursement Account as payment for

such invoice. If, at any time, the balance in the IA Disbursement Account falls below one

hundred thousand dollars ($100,000.00) or is insufficient to cover the amount of any invoice,

Transmission Developer shall replenish the IA Disbursement Account within five (5) Calendar

Days of receiving notice thereof by the payment of an additional amount equal to the greater of

(i) one hundred thousand dollars ($100,000.00) and (ii) the amount of any such insufficiency

plus an additional one hundred thousand dollars ($100,000.00).

Following the completion of the provided services, Connecting Transmission Owner

shall issue a final statement (the “Final Statement”) pursuant to Article 12.2 of this Agreement to

Transmission Developer showing the payments made by Transmission Developer concerning the

provided services and the amount of the invoices applied against the aggregate amount of such

payments. In the event that the balance of the IA Disbursement Account remaining after

application of all prior invoices is not sufficient to cover the amount of any outstanding invoice,

Transmission Developer shall, within thirty (30) Calendar Days of receipt of notice from the

Connecting Transmission Owner, pay the Connecting Transmission Owner the amount of such

insufficiency. To the extent that such remaining balance of the escrow fund exceeds the amount

B-4

**SERVICE AGREEMENT NO. 2734**

necessary to cover all invoices payable to the Connecting Transmission Owner for purposes of

the provided services performed in accordance with Section III of Appendix A, Connecting

Transmission Owner shall, within thirty (30) Calendar Days of issuing the Final Statement to

Transmission Developer, pay Transmission Developer the amount of such balance.

B-5

**SERVICE AGREEMENT NO. 2734**

**APPENDIX C**

**INTERCONNECTION DETAILS**

**Description of the Transmission Project**

The Transmission Project Q543 – the New York Energy Solution Project – was

**1.**

submitted by the Transmission Developer and National Grid and evaluated in the NYISO's

Public Policy Transmission Planning Process to address Segment B of the AC Transmission

Needs identified by the New York Public Service Commission in its December 17, 2015 order in

its Case No. 12-T-0502. The NYISO Board of Directors selected the Transmission Project as the

more efficient and cost-effective transmission solution to Segment B of the AC Transmission

Needs on April 8, 2019. Transmission Developer and National Grid entered into the

Development Agreement with the NYISO for purposes of constructing the Transmission Project

and placing it in-service to satisfy the Public Policy Transmission Need. National Grid

subsequently assigned its rights, duties, and obligations under the Development Agreement to

Transmission Developer on March 10, 2020, giving Transmission Developer sole rights to the

development of the Transmission Project. The Transmission Developer will develop the

Transmission Project in accordance with the terms of the Development Agreement.

The Transmission Project will be mainly located in three counties (Rensselaer, Columbia

and Dutchess) in the northern and mid-Hudson Valley, New York and includes the following

new facilities that will be constructed, owned, and operated by the Transmission Developer:

• A new 345 kV/115 kV double-circuit transmission line from a new Knickerbocker

switching station to the existing Pleasant Valley substation, and the rebuild of

approximately 2.1 miles of the 115 kV Blue Stores Tap;

• A new 345 kV Knickerbocker switching station at the proposed, greenfield site in

Schodack, New York, which will house a bypassable two step 16.67%, 33.33%, and 50%

series compensator for the new 345 kV Knickerbocker to Pleasant Valley transmission

line;

• Rebuild of the existing NYSEG Churchtown 115 kV switching station in Claverack, New

York, which will require decommissioning of the existing facility;

• Originally, the replacement of certain limiting element terminal equipment at the 345 kV

Roseton substation to increase the thermal rating of Roseton to East Fishkill 345 kV

transmission line #305 and the 345 kV New Scotland substation to increase the thermal

ratings on the New Scotland to Knickerbocker 345 kV transmission line #2A was

identified. However, a Non-Material Determination request was approved by the NYISO

which eliminated this work; and

• Two new 135 MVAR 345 kV capacitor banks installed at the new Van Wagner

Substation, which will intercept the existing 91 and 92 feeders. These existing feeder

segments between Van Wagner and the existing Pleasant Valley Substations will be

reconductored and redesignated as Y58 and Y59. The reconductored feeder segments

Y58 and Y59 will utilize the same take off structures as did previous feeders 91 and 92.

C-1

**SERVICE AGREEMENT NO. 2734**

The Transmission Project includes additional upgrades to existing transmission facilities

as identified by the NYPSC in its December 17, 2015 order identifying the AC Transmission

Public Policy Transmission Needs.

• Terminal upgrades of certain limiting elements to the Rock Tavern 345 kV substation and

Coopers Corners substation;

• Note these originally identified upgrades to the Dolson Ave Station, NYPA East and

West Transition Stations, Rock Tavern 345kV, Roseton 345kV and Coopers Corners

Substations have been modified, which modifications the NYISO determined were not

material. This portion of the Transmission Project now involves a limited scope of NUFs

as compared to the original scope of work. These NUFs and modifications will be/ are

addressed in each of the Connecting Transmission Owner’s Transmission Project

Interconnection Agreements or EPC Agreements;

• Upgrades to the Shoemaker to Sugarloaf 138 kV facilities. These originally identified

upgrades to the Shoemaker to Sugarloaf 138kV facilities have been modified, which

modifications the NYISO determined were not material. This portion of the

Transmission Project now involves certain modifications to the Central Hudson 115 kV

Rock Tavern Substation connecting to the Orange & Rockland 138 kV Sugarloaf

Substation. These modifications will be addressed in each of the Connecting

Transmission Owner’s interconnection agreements; and

• Dover PAR Substation as described in Section II of Appendix A.

Additional details concerning the Transmission Project are set forth in Appendices A and

B of the Development Agreement.

**2.**

**Description of the Points of Interconnection and Points of Change of Ownership**

The Points of Interconnection (“POI”) and Points of Change in Ownership (“PCO”) are

identified in the table below and are also shown in the POI one line diagrams that follow. The

POI and PCO are the same location since the Transmission Project will not require any

Connecting Transmission Owner’s Attachment Facilities, as the transfer of ownership of the

feeders occurs at the tower insulator hardware. The POI/PCO locations are:

**Transmission**

**Line**

**Line #**

**Designation**

**Structure**

**Number**

**where**

**Structure**

**Description**

**where**

**Description of Change in**

**Ownership**

**POI/PCO Is POI/PCO Is**

**Located Located**

L61-2 Double circuit Transmission Developer

Connecting

Transmission

Owner to

Transmission

Developer

Transition

398 and

Y17

(see note in

Figure C-1

below)

Dead-end

Tower


ownership will include a

portion of the Y17 and 398

conductors within the Dover

PAR Substation, new take

C-2



**SERVICE AGREEMENT NO. 2734**

**Transmission**

**Line**

**Line #**

**Designation**

**Structure**

**Number**

**where**

**Structure**

**Description**

**where**

**Description of Change in**

**Ownership**

**POI/PCO Is POI/PCO Is**

**Located Located**

off structure, Insulators, and

hardware.

Connecting Transmission

Owner will continue to own

the Y17 (the segment

between the POI/PCO and

the Cricket Valley

Substation), and the 398 (the

segment between the POI

/PCO and the NY- CT state

border) feeders and

structures in the right of

way.

Connecting Transmission

Owner will own the OPGW

/ ADSS to the Dover Station

Control Enclosure Patch

Panel associated with both

the 398 (to the NY – CY



state border) and Y17 (the

segment to Cricket Valley

Substation) line segments

Figure C-1

C-3



**SERVICE AGREEMENT NO. 2734**

Figure C-2

**[CONTAINS CEII – THIS PAGE REMOVED FROM PUBLIC VERSION]**

**3. Ownership/Control/Maintenance Responsibilities of Network Upgrade Facilities**

Connecting Transmission Owner and Transmission Developer shall each design, procure,

construct, and install the Network Upgrade Facilities as specified in Section III of Appendix A to

this Agreement. Connecting Transmission Owner shall have physical ownership and control of

the Network Upgrade Facilities. Transmission Developer shall retain financial ownership of the

Network Upgrade Facilities to Connecting Transmission Owner and recover the costs associated

with the Network Upgrade Facilities in accordance with Transmission Developer’s FERC-

approved formula rate under the NYISO OATT.

**4.**

**Transmission Developer Operating Requirements**

Transmission Developer must comply with all applicable NYISO tariffs and procedures,

as amended from time to time.

**5.**

**Special Protection Facilities**

For purposes of Section 9.4.3 of this Agreement, the Connecting Transmission Owner

does not permit the installation of any special protection facilities on its transmission system.

**6.**

**Connecting Transmission Owner’s Specifications**.

Within 10 days of FERC’s acceptance of this Agreement, Connecting Transmission

Owner shall provide Transmission Developer all relevant standards and specifications that must

be complied with by Transmission Developer in the design, engineering, procurement and/or

construction of the Network Upgrade Facilities. Revisions to such specifications and standards

that occur after the 30% design packages have been reviewed and approved by the Connecting

Transmission Owner will not be imposed on the Network Upgrade Facilities to avoid the need

for any redesigns. In the event that a Party becomes aware that a safety standard, regulatory

requirement, and/or industry standard has been modified that could affect the safe or reliable

operations of the NUF, the Party shall notify the other Parties promptly, so that the Parties can

mutually agree upon an amendment, if needed, of this Agreement.

**7.**

**Additional Agreements**

**(1)** The Transmission Developer and the Connecting Transmission Owner will enter into: (i) a

Security Agreement described in subsection 7(2), (ii) agreements concerning the use and

occupancy of Connecting Transmission Owner’s real property described in subsection 7(3)

below, and (iii) a remote operations agreement described in subsection 7(5) (the “Additional

Agreements”). Except as otherwise described below, it is the belief and intention of the

C-4



**SERVICE AGREEMENT NO. 2734**

Transmission Developer and the Connecting Transmission Owner that nothing in the Additional

Agreements conflict in any material way with this Agreement. If the Connecting

Transmission Owner or Transmission Developer becomes aware of a conflict, such party

shall notify the other party promptly so that the Connecting Transmission Owner and

Transmission Developer can mutually agree upon an amendment, if needed, of such

Additional Agreement. The NYISO is not a party to, has no responsibility under, and shall

have no liability in connection with these Additional Agreements or the Master Services

Agreement and transaction forms described in subsection 7(4) below.

**(2) Security Agreement:** The Transmission Developer and the Connecting Transmission Owner

will enter into a Security Agreement, as described in Article 11.4 of this Agreement.

**(3) Other Agreements Concerning the Use and Occupancy of Connecting Transmission**

**Owner’s Real Property:** Prior to any access by Transmission Developer or its

subcontractors onto the real property of Connecting Transmission Owner for the purposes

provided for in this Agreement, including any construction-related activity, Transmission

Developer and the Connecting Transmission Owner have entered or will enter into one or

more agreements acceptable to the Connecting Transmission Owner in its sole discretion, to

provide Transmission Developer access for the use and occupancy of Connecting

Transmission Owner’s real property (“**U&O Agreements**”). The U&O Agreements shall

exclusively govern the rights and obligations of Connecting Transmission Owner and

Transmission Developer arising out of the use of occupancy of the real property described

therein, including, but not limited to, Transmission Developer’s environmental obligations

and indemnity to the Connecting Transmission Owner for Hazardous Substances; *provided,*

*however,* that the U&O Agreements do not and shall not be construed to limit Connecting

Transmission Owner’s or Transmission Developer’s responsibilities, as applicable, under this

Agreement to satisfy applicable Environmental Laws, to provide notification concerning

environmental releases pursuant to Article 23 of this Agreement, and to indemnify the

NYISO pursuant to Article 18.1 in connection with the violation of any Environmental Law

or the release of any Hazardous Substance. As of the date of this Agreement, the following

U&O Agreements are in effect:

(a) License Agreement, dated as of March 16, 2022, between Transmission Developer and

Connecting Transmission Owner

**(4) Transaction Forms**: As described in Section I of Appendix A, the Connecting Transmission

Owner and Transmission Developer entered into a Master Services Agreement (“MSA”) with

Transaction Form 3 (“TF3”) to provide support services which enabled the Transmission

Developer to commence engineering activities related to Network Upgrade Facilities prior to the

Effective Date of this Agreement. For any engineering design work addressed in TF3 that the

Connecting Transmission Owner or Transmission Developer has commenced prior to the

Effective Date of the Agreement, the Connecting Transmission Owner or Transmission

Developer, as applicable, will continue and complete such work in accordance with the terms

specified in the MSA and TF3. For any engineering design work not addressed in TF3 or not

commenced as of the Effective Date of this Agreement, the Connecting Transmission Owner or

Transmission Developer, as applicable, shall perform such work in accordance with the terms of

this Agreement.

C-5

**SERVICE AGREEMENT NO. 2734**

**(5) Remote Operations Agreement**: Connecting Transmission Owner and Transmission

Developer have negotiated an agreement to define the roles, responsibilities, and scope related to

Connecting Transmission Owner’s performance of certain remote operations and metering

responsibilities, which agreement shall not be inconsistent with the terms of this Agreement or

the NYISO OATT. This agreement has not been finalized as of the execution of this Agreement,

and is incorporated as an applicable agreement.

**8.**

**Metering**

The metering for the existing Line #398 is currently located at Connecting Transmission

Owner’s Cricket Valley Substation, and the Connecting Transmission Owner is the Metering

Authority. With the inclusion of the Dover PAR Substation on Line #398, Connecting

Transmission Owner: (i) will retain the existing revenue metering at the Cricket Valley

Substation for whenever the PARs are bypassed (out of service) and (ii) will use the new, to be

installed revenue meters at the Dover PAR Substation described in Section III.1 of Appendix A

whenever the PARs are in-service. The new revenue meter will be on the NYISO list of

approved meters.

Connecting Transmission Owner will remain the Metering Authority for either

configuration with the PARs in service or bypassed. Connecting Transmission Owner shall be

responsible for maintaining and troubleshooting daily communication with the revenue meter(s).

Transmission Developer shall provide access to Metering Equipment located within the Dover

PAR Substation to Connecting Transmission Owner’s metering technician for troubleshooting.

Transmission Developer shall not block, cover, or modify the area surrounding the Connecting

Transmission Owner’s revenue meter located within the Dover PAR Substation. When metering

communication depends on the communication media of the Transmission Developer, the

Transmission Developer shall prioritize the re-establishment of such communication to the

Connecting Transmission Owner’s Metering Authority.

C-6

**SERVICE AGREEMENT NO. 2734**

**APPENDIX D**

**SECURITY ARRANGEMENTS DETAILS**

Infrastructure security of New York State Transmission System equipment and

operations and control hardware and software is essential to ensure day-to-day New York State

Transmission System reliability and operational security. The Commission will expect the

NYISO, all Transmission Owners, all Transmission Developers and all other Market Participants

to comply with the recommendations offered by the President’s Critical Infrastructure Protection

Board and, eventually, best practice recommendations from the electric reliability authority. All

public utilities will be expected to meet basic standards for system infrastructure and operational

security, including physical, operational, and cyber-security practices.

D-1

**SERVICE AGREEMENT NO. 2734**

**APPENDIX E-1**

**INITIAL SYCHRONIZATION DATE**

[**Date**]

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Consolidated Edison Company of New York, Inc.

Attn: Walter Alvarado

Vice President, System and Transmission Operations

4 Irving Place

New York, NY 10004

Phone: (212-460-1210)

Email: alvaradow@coned.com

New York Transco, LLC.

Attn: Paul Haering

Vice President Capital Investments

One Hudson City Center

Hudson, NY 12534

Phone: (518) 444-4880

Email: paul.haering@nytransco.com

Re:

[**Transmission Project/Network Upgrade Facilities**]

Dear

:

On **[Date] [Transmission Developer/Connecting Transmission Owner]** initially synchronized

the [**describe Transmission Project/Network Upgrade Facilities**]. This letter confirms

[**Transmission Developer/Connecting Transmission Owner**]’s Initial Synchronization Date

was [**specify**].

Thank you.

[**Signature**]

[**Transmission Developer/ Connecting Transmission Owner Representative**]

E-1



**SERVICE AGREEMENT NO. 2734**

**APPENDIX E-2**

**IN-SERVICE DATE**

**[Date]**

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Consolidated Edison Company of New York, Inc.

Attn: Walter Alvarado

Vice President, System and Transmission Operations

4 Irving Place

New York, NY 10004

Phone: (212-460-1210)

Email: alvaradow@coned.com

New York Transco, LLC.

Attn: Paul Haering

Vice President Capital Investments

One Hudson City Center

Hudson, NY 12534

Phone: (518) 444-4880

Email: paul.haering@nytransco.com

Re:

\_\_\_\_\_\_\_\_\_\_\_\_\_ [**Transmission Project/Network Upgrade Facilities**]

Dear \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_:

On **[Date] [Transmission Developer/Connecting Transmission Owner]** has completed Trial

Operation of [**describe Transmission Project/Network Upgrade Facilities**]. This letter

confirms that [**describe Transmission Project/Network Upgrade Facilities**] [**has/have**]

commenced service, effective as of **[Date plus one day]**.

Thank you.

**[Signature]**

**[Transmission Developer/Connecting Transmission Owner Representative]**

E-2

**SERVICE AGREEMENT NO. 2734**

**APPENDIX F**

**ADDRESSES FOR DELIVERY OF NOTICES AND BILLINGS**

**Notices:**

NYISO:

Before commercial operation of the Transmission Project:

New York Independent System Operator, Inc.

Attn: Vice President, System and Resource Planning

10 Krey Boulevard

Rensselaer, NY 12144

Phone: (518) 356-6000

Fax: (518) 356-6118

After commercial operation of the Transmission Project:

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Phone: (518) 356-6000

Fax: (518) 356-6118

Connecting Transmission Owner:

Consolidated Edison Company of New York, Inc.

Attn: Walter Alvarado

Vice President, System and Transmission Operations

4 Irving Place

New York, NY 10004

Phone: (212-460-1210)

Email: alvaradow@coned.com

Transmission Developer:

New York Transco, LLC

Attn: Paul Haering

Vice President Capital Investments

One Hudson City Center

Hudson, NY 12534

Phone: (518) 444-4880

Email: paul.haering@nytransco.com

F-1



**SERVICE AGREEMENT NO. 2734**

**Billings and Payments:**

Connecting Transmission Owner:

Consolidated Edison Company of New York, Inc.

Attn: Walter Alvarado

Vice President, System and Transmission Operations

4 Irving Place

New York, NY 10004

Phone: (212-460-1210)

Email: alvaradow@coned.com

Transmission Developer:

New York Transco, LLC

One Hudson City Center

Hudson, NY 12534

Attn: Vice President, Capital Investments

Phone: (518) 444-4880

Email: paul.haering@nytransco.com

**Alternative Forms of Delivery of Notices (telephone, facsimile or email):**

NYISO:

Before commercial operation of the Transmission Project:

New York Independent System Operator, Inc.

Attn: Vice President, System and Resource Planning

10 Krey Boulevard

Rensselaer, NY 12144

Phone: (518) 356-6000

Fax: (518) 356-6118

E-mail: interconnectionsupport@nyiso.com

After commercial operation of the Transmission Project:

New York Independent System Operator, Inc.

Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

Phone: (518) 356-6000

Fax: (518) 356-6118

E-mail: interconnectionsupport@nyiso.com

F-2



**SERVICE AGREEMENT NO. 2734**

Connecting Transmission Owner:

Consolidated Edison Company of New York, Inc.

Attn: Walter Alvarado

Vice President, System and Transmission Operations

4 Irving Place

New York, NY 10004

Phone: (212-460-1210)

Email: alvaradow@coned.com

Transmission Developer:

New York Transco, LLC

One Hudson City Center

Hudson, NY 12534

Attn: Vice President, Capital Investments

Phone: (518) 444-4880

Email: paul.haering@nytransco.com

F-3

