Service Agreement No. 2161

AMENDED AND RESTATED

INTERCONNECTION AGREEMENT

BETWEEN

NIAGARA MOHAWK POWER CORPORATION   
 D/B/A/ NATIONAL GRID

AND

SELKIRK COGEN PARTNERS, LP

TABLE OF CONTENTS

Page Number

ARTICLE 1. DEFINITIONS 1

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION 11

2.1 Effective Date 11

2.2 Term of Agreement 11

2.3 Termination 11

2.4 Termination Costs 11

2.5 Disconnection 12

2.6 Survival 13

ARTICLE 3. REGULATORY FILINGS 13

3.1 Filing 13

ARTICLE 4. SCOPE OF INTERCONNECTION SERVICE 13

4.1 Provision of Service 13

4.2 No Transmission Delivery Service 13

4.3 No Other Services 14

ARTICLE 5. INTERCONNECTION FACILITIES ENGINEERING, PROCUREMENT, AND

CONSTRUCTION 14

5.1 Options 14

5.2 General Conditions Applicable to Option to Build 16

5.3 Liquidated Damages 17

5.4 Power System Stabilizers 18

5.5 Equipment Procurement 18

5.6 Construction Commencement 19

5.7 Work Progress 19

5.8 Information Exchange 20

5.9 Limited Operation 20

5.10 Interconnection Customer’s Attachment Facilities (“ICAF”) 20

5.11 Connecting Transmission Owner’s Attachment Facilities Construction 21

5.12 Access Rights 21

5.13 Lands of Other Property Owners 22

5.14 Permits 22

5.15 Early Construction of Base Case Facilities 22

5.16 Suspension 23

5.17 Taxes 23

5.18 Tax Status; Non-Jurisdictional Entities 28

5.19 Modification 29

i

ARTICLE 6. TESTING AND INSPECTION 30

6.1 Pre-Commercial Operation Date Testing and Modifications 30

6.2 Post-Commercial Operation Date Testing and Modifications 30

6.3 Right to Observe Testing 30

6.4 Right to Inspect 30

ARTICLE 7. METERING 31

7.1 General 31

7.2 Check Meters 31

7.3 Standards 31

7.4 Testing of Metering Equipment 31

7.5 Metering Data 32

ARTICLE 8. COMMUNICATIONS 32

8.1 Interconnection Customer Obligations 32

8.2 Remote Terminal Unit 32

8.3 No Annexation 33

ARTICLE 9. OPERATIONS 33

9.1 General 33

9.2 NYISO and Connecting Transmission Owner Obligations 33

9.3 Interconnection Customer Obligations 33

9.4 Start-Up and Synchronization 34

9.5 Real and Reactive Power Control 34

9.6 Outages and Interruptions 35

9.7 Switching and Tagging Rules 38

9.8 Use of Attachment Facilities by Third Parties 39

9.9 Disturbance Analysis Data Exchange 39

ARTICLE 10. MAINTENANCE 39

10.1 Connecting Transmission Owner Obligations 39

10.2 Interconnection Customer Obligations 40

10.3 Coordination 40

10.4 Secondary Systems 40

10.5 Operating and Maintenance Expenses 40

ARTICLE 11. PERFORMANCE OBLIGATION 40

11.1 Interconnection Customer Attachment Facilities 40

11.2 Connecting Transmission Owner’s Attachment Facilities 41

ii

11.3 System Upgrade Facilities and System Deliverability Upgrades 41

11.4 Special Provisions for Affected Systems 41

11.5 Provision of Security 41

11.6 Interconnection Customer Compensation for Emergency Services 42

11.7 Line Outage Costs 42

ARTICLE 12. INVOICE 42

12.1 General 42

12.2 Final Invoice 42

12.3 Payment 43

12.4 Disputes 43

ARTICLE 13. EMERGENCIES 43

13.1 Obligations 43

13.2 Notice 43

13.3 Immediate Action 44

13.4 NYISO and Connecting Transmission Owner Authority 44

13.5 Interconnection Customer Authority 45

13.6 Limited Liability 45

ARTICLE 14. REGULATORY REQUIREMENTS AND GOVERNING LAW 45

14.1 Regulatory Requirements 45

14.2 Governing Law 45

ARTICLE 15. NOTICES 46

15.1 General 46

15.2 Billings and Payments 46

15.3 Alternative Forms of Notice 46

15.4 Operations and Maintenance Notice 46

ARTICLE 16. FORCE MAJEURE 46

16.1 Force Majeure 46

ARTICLE 17. DEFAULT 47

17.1 Default 47

ARTICLE 18. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE 47

18.1 Indemnity 47

18.2 No Consequential Damages 49

iii

18.3 Insurance 49

ARTICLE 19. ASSIGNMENT 51

19.1 Assignment 51

ARTICLE 20. SEVERABILITY 52

20.1 Severability 52

ARTICLE 21. COMPARABILITY 52

21.1 Comparability 52

ARTICLE 22. CONFIDENTIALITY 52

22.1 Confidentiality 52

ARTICLE 23. ENVIRONMENTAL RELEASES 55

23.1 Interconnection Customer and Connecting Transmission Owner Notice 55

ARTICLE 24. INFORMATION REQUIREMENT 56

24.1 Information Acquisition 56

24.2 Information Submission by Connecting Transmission Owner 56

24.3 Updated Information Submission by Interconnection Customer 56

24.4 Information Supplementation 57

ARTICLE 25. INFORMATION ACCESS AND AUDIT RIGHTS 58

25.1 Information Access 58

25.2 Reporting of Non-Force Majeure Events 58

25.3 Audit Rights 58

25.4 Audit Rights Periods 58

25.5 Audit Results 59

ARTICLE 26. SUBCONTRACTORS 59

26.1 General 59

26.2 Responsibility of Principal 59

26.3 No Limitation by Insurance 59

ARTICLE 27. DISPUTES 59

27.1 Submission 59

iv

27.2 External Arbitration Procedures 60

27.3 Arbitration Decisions 60

27.4 Costs 61

27.5 Termination 61

ARTICLE 28. REPRESENTATIONS, WARRANTIES AND COVENANTS 61

28.1 General 61

ARTICLE 29. MISCELLANEOUS 62

29.1 Binding Effect 62

29.2 Conflicts 62

29.3 Rules of Interpretation 62

29.4 Compliance 63

29.5 Joint and Several Obligations 63

29.6 Entire Agreement 63

29.7 No Third Party Beneficiaries 63

29.8 Waiver 63

29.9 Headings 64

29.10 Multiple Counterparts 64

29.11 Amendment 64

29.12 Modification by the Parties 64

29.13 Reservation of Rights 64

29.14 No Partnership 64

29.15 Other Transmission Rights 65

Appendices

v

LARGE GENERATOR INTERCONNECTION AGREEMENT

THIS AMENDED AND RESTATED LARGE GENERATOR INTERCONNECTION   
AGREEMENT (“Agreement”) is entered into as of the first day of September 2014 (the   
“Effective Date”), by and between Selkirk Cogen Partners, LP, a limited partnership organized and existing under the laws of the State of Delaware (“Interconnection Customer” with a Large Generating Facility) and Niagara Mohawk Power Corporation d/b/a National Grid a corporation organized and existing under the laws of the State of New York (“Connecting Transmission   
Owner”). Interconnection Customer or Connecting Transmission Owner each may be referred to as a “Party” or collectively referred to as the “Parties.”

RECITALS

WHEREAS, the New York Independent System Operator, Inc. (“NYISO”) operates the New York State Transmission System and Connecting Transmission Owner owns certain facilities included in the New York State Transmission System; and

WHEREAS, Interconnection Customer owns, leases and/or controls and operates the Generating Facility identified as a Large Generating Facility in Appendix C to this Agreement; and,

WHEREAS, Interconnection Customer and Connecting Transmission Owner are parties to that certain Interconnection Agreement dated October 20, 1992, (the “1992 Agreement” shall be referred to herein as the “Original Agreement”);

WHEREAS, Interconnection Customer and Connecting Transmission Owner desire to amend and restate the Original Agreement, including, without limitation, for the purpose of extending the term of the Original Agreement; and

WHEREAS, Interconnection Customer and Connecting Transmission Owner have agreed to enter into this Agreement for the purpose of interconnecting the Large Generating Facility with the New York State Transmission System;

NOW, THEREFORE, in consideration of and subject to the mutual covenants contained herein, it is agreed:

ARTICLE 1. DEFINITIONS

Whenever used in this Agreement with initial capitalization, the following terms shall have the

meanings specified in this Article 1. Terms used in this Agreement with initial capitalization that are not defined in this Article 1 shall have the meanings specified in Section 30.1.0 of   
Attachment X or Section 25.1 of Attachment S of the NYISO OATT.

Affected System shall mean an electric system other than the transmission system owned, controlled or operated by the Connecting Transmission Owner that may be affected by the proposed interconnection.

Affected System Operator shall mean the entity that operates an Affected System.

1

Affected Transmission Owner shall mean the New York public utility or authority (or its

designated agent) other than the Connecting Transmission Owner that (i) owns facilities used for the transmission of Energy in interstate commerce and provides Transmission Service under the Tariff, and (ii) owns, leases or otherwise possesses an interest in a portion of the New York State Transmission System where System Deliverability Upgrades or System Upgrade Facilities are installed pursuant to Attachment X and Attachment S of the Tariff.

Affiliate shall mean, with respect to a person or entity, any individual, corporation, partnership, firm, joint venture, association, joint-stock company, trust or unincorporated organization,   
directly or indirectly controlling, controlled by, or under common control with, such person or entity. The term “control” shall mean the possession, directly or indirectly, of the power to direct the management or policies of a person or an entity. A voting interest of ten percent or more shall create a rebuttable presumption of control.

Ancillary Services shall mean those services that are necessary to support the transmission of Capacity and Energy from resources to Loads while maintaining reliable operation of the New York State Transmission System in accordance with Good Utility Practice.

Applicable Laws and Regulations shall mean all duly promulgated applicable federal, state and local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or administrative orders, permits and other duly authorized actions of any Governmental Authority, including but not limited to Environmental Law.

Applicable Reliability Councils shall mean the NERC, the NPCC and the NYSRC.

Applicable Reliability Standards shall mean the requirements and guidelines of the Applicable Reliability Councils, and the Transmission District to which the Interconnection Customer’s   
Large Generating Facility is directly interconnected, as those requirements and guidelines are   
amended and modified and in effect from time to time; provided that no Party shall waive its   
right to challenge the applicability or validity of any requirement or guideline as applied to it in the context of this Agreement.

Attachment Facilities shall mean the Connecting Transmission Owner’s Attachment Facilities   
and the Interconnection Customer’s Attachment Facilities. Collectively, Attachment Facilities   
include all facilities and equipment between the Large Generating Facility and the Point of   
Interconnection, including any modification, additions or upgrades that are necessary to   
physically and electrically interconnect the Large Generating Facility to the New York State   
Transmission System. Attachment Facilities are sole use facilities and shall not include Stand   
Alone System Upgrade Facilities, Distribution Upgrades, System Upgrade Facilities or System   
Deliverability Upgrades.

Base Case shall mean the base case power flow, short circuit, and stability data bases used for   
the Interconnection Studies by NYISO, Connecting Transmission Owner or Interconnection   
Customer; described in Section 30.2.3 of the Large Facility Interconnection Procedures.

Breach shall mean the failure of a Party to perform or observe any material term or condition of this Agreement.

2

Breaching Party shall mean a Party that is in Breach of this Agreement.

Business Day shall mean Monday through Friday, excluding federal holidays.

Byway shall mean all transmission facilities comprising the New York State Transmission

System that are neither Highways nor Other Interfaces. All transmission facilities in Zone J and Zone K are Byways.

Calendar Day shall mean any day including Saturday, Sunday or a federal holiday.

Capacity Region shall mean one of four subsets of the Installed Capacity statewide markets   
comprised of (1) Rest of State (i.e., Load Zones A through F); (2) Lower Hudson Valley (i.e.,   
Load Zones G, H, and I); (3) New York City (i.e., Load Zone J); and (4) Long Island (i.e., Load   
Zone K), except for Class Year Interconnection Facility Studies conducted prior to Class Year   
2012, for which “Capacity Region” shall be defined as set forth in Section 25.7.3 of Attachment   
S to the NYISO OATT.

Capacity Resource Interconnection Service (“CRIS”) shall mean the service provided by   
NYISO to interconnect the Interconnection Customer’s Large Generating Facility to the New   
York State Transmission System or to the Distribution System in accordance with the NYISO   
Deliverability Interconnection Standard, to enable the New York State Transmission System to   
deliver electric capacity from the Large Generating Facility, pursuant to the terms of the NYISO   
OATT.

Class Year Deliverability Study shall mean an assessment, conducted by the NYISO staff in   
cooperation with Market Participants, to determine the System Deliverability Upgrades required   
for each generation and merchant transmission project included in the Class Year   
Interconnection Facilities Study to interconnect to the New York State Transmission System or   
to the Distribution System in compliance with the NYISO Deliverability Interconnection   
Standard.

Clustering shall mean the process whereby a group of Interconnection Requests is studied

together, instead of serially, for the purpose of conducting the Interconnection System Reliability Impact Study.

Commercial Operation shall mean the status of a Large Generating Facility that has   
commenced generating electricity for sale, excluding electricity generated during Trial   
Operation.

Commercial Operation Date of a unit shall mean the date on which the Large Generating

Facility commences Commercial Operation as agreed to by the Parties pursuant to Appendix E to this Agreement.

Confidential Information shall mean any information that is defined as confidential by Article 22 of this Agreement.

Connecting Transmission Owner shall mean the New York public utility or authority (or its designated agent) that (i) owns facilities used for the transmission of Energy in interstate

3

commerce and provides Transmission Service under the Tariff, (ii) owns, leases or otherwise possesses an interest in the portion of the New York State Transmission System or Distribution System at the Point of Interconnection, and (iii) is a Party to this Agreement.

Connecting Transmission Owner’s Attachment Facilities shall mean all facilities and

equipment owned, controlled or operated by the Connecting Transmission Owner from the Point of Change of Ownership to the Point of Interconnection as identified in Appendix A to this   
Agreement, including any modifications, additions or upgrades to such facilities and equipment. Connecting Transmission Owner’s Attachment Facilities are sole use facilities and shall not include Stand Alone System Upgrade Facilities or System Upgrade Facilities.

Control Area shall mean an electric power system or combination of electric power systems to   
which a common automatic generation control scheme is applied in order to: (1) match, at all   
times, the power output of the Generators within the electric power system(s) and capacity and   
energy purchased from entities outside the electric power system(s), with the Load within the   
electric power system(s); (2) maintain scheduled interchange with other Control Areas, within   
the limits of Good Utility Practice; (3) maintain the frequency of the electric power system(s)   
within reasonable limits in accordance with Good Utility Practice; and (4) provide sufficient

generating capacity to maintain Operating Reserves in accordance with Good Utility Practice. A Control Area must be certified by the NPCC.

Default shall mean the failure of a Party in Breach of this Agreement to cure such Breach in accordance with Article 17 of this Agreement.

Deliverability Interconnection Standard shall mean the standard that must be met by any

Large Generating Facility proposing to interconnect to the New York State Transmission System or to the Distribution System and become a qualified Installed Capacity Supplier. To meet the NYISO Deliverability Interconnection Standard, the Interconnection Customer of the proposed Large Generating Facility must, in accordance with the rules in Attachment S to the NYISO   
OATT, fund or commit to fund the System Deliverability Upgrades identified for its project in the Class Year Deliverability Study.

Dispute Resolution shall mean the procedure described in Article 27 of this Agreement for resolution of a dispute between the Parties.

Distribution System shall mean the Transmission Owner’s facilities and equipment used to

distribute electricity that are subject to FERC jurisdiction, and are subject to the NYISO’s LFIP or SGIP under FERC Order Nos. 2003 and/or 2006. The term Distribution System shall not include LIPA’s distribution facilities.

Distribution Upgrades shall mean the additions, modifications, and upgrades to the Connecting   
Transmission Owner’s Distribution System at or beyond the Point of Interconnection to facilitate   
interconnection of a Large Facility or Small Generating Facility and render the transmission   
service necessary to affect the Interconnection Customer’s wholesale sale of electricity in   
interstate commerce. Distribution Upgrades do not include Interconnection Facilities, System   
Upgrade Facilities, or System Deliverability Upgrades. Distribution Upgrades are sole use

4

facilities and shall not include Stand Alone System Upgrade Facilities, System Upgrade Facilities, or System Deliverability Upgrades.

Effective Date shall mean the date on which this Agreement becomes effective upon execution by the Parties, subject to acceptance by the Commission, or if filed unexecuted, upon the date specified by the Commission.

Emergency State shall mean the condition or state that the New York State Power System is in when an abnormal condition occurs that requires automatic or immediate manual action to   
prevent or limit loss of the New York State Transmission System or Generators that could   
adversely affect the reliability of the New York State Power System.

Energy Resource Interconnection Service (“ERIS”) shall mean the service provided by

NYISO to interconnect the Interconnection Customer’s Large Generating Facility to the New   
York State Transmission System or to the Distribution System in accordance with the NYISO   
Minimum Interconnection Standard, to enable the New York State Transmission System to   
receive Energy and Ancillary Services from the Large Generating Facility, pursuant to the terms of the NYISO OATT.

Engineering & Procurement (E&P) Agreement shall mean an agreement that authorizes

Connecting Transmission Owner to begin engineering and procurement of long lead-time items necessary for the establishment of the interconnection in order to advance the implementation of the Interconnection Request.

Environmental Law shall mean Applicable Laws or Regulations relating to pollution or protection of the environment or natural resources.

Federal Power Act shall mean the Federal Power Act, as amended, 16 U.S.C. §§ 791a et seq. (“FPA”).

FERC shall mean the Federal Energy Regulatory Commission (“Commission”) or its successor.

Force Majeure shall mean any act of God, labor disturbance, act of the public enemy, war,   
insurrection, riot, fire, storm or flood, explosion, breakage or accident to machinery or   
equipment, any order, regulation or restriction imposed by governmental, military or lawfully   
established civilian authorities, or any other cause beyond a Party’s control. A Force Majeure   
event does not include acts of negligence or intentional wrongdoing by the Party claiming Force   
Majeure.

Generating Facility shall mean Interconnection Customer’s device for the production of

electricity identified in the Interconnection Request, but shall not include the Interconnection Customer’s Attachment Facilities or Distribution Upgrades.

Generating Facility Capacity shall mean the net seasonal capacity of the Generating Facility and the aggregate net seasonal capacity of the Generating Facility where it includes multiple energy production devices.

5

Good Utility Practice shall mean any of the practices, methods and acts engaged in or approved   
by a significant portion of the electric industry during the relevant time period, or any of the   
practices, methods and acts which, in the exercise of reasonable judgment in light of the facts   
known at the time the decision was made, could have been expected to accomplish the desired   
result at a reasonable cost consistent with good business practices, reliability, safety and   
expedition. Good Utility Practice is not intended to be limited to the optimum practice, method,   
or act to the exclusion of all others, but rather to delineate acceptable practices, methods, or acts   
generally accepted in the region.

Governmental Authority shall mean any federal, state, local or other governmental regulatory   
or administrative agency, court, commission, department, board, or other governmental   
subdivision, legislature, rulemaking board, tribunal, or other governmental authority having   
jurisdiction over any of the Parties, their respective facilities, or the respective services they   
provide, and exercising or entitled to exercise any administrative, executive, police, or taxing   
authority or power; provided, however, that such term does not include Interconnection   
Customer, NYISO, Affected Transmission Owner, Connecting Transmission Owner, or any   
Affiliate thereof.

Hazardous Substances shall mean any chemicals, materials or substances defined as or

included in the definition of “hazardous substances,” “hazardous wastes,” “hazardous materials,” “hazardous constituents,” “restricted hazardous materials,” “extremely hazardous substances,” “toxic substances,” “radioactive substances,” “contaminants,” “pollutants,” “toxic pollutants” or words of similar meaning and regulatory effect under any applicable Environmental Law, or any other chemical, material or substance, exposure to which is prohibited, limited or regulated by any applicable Environmental Law.

Highway shall mean 115 kV and higher transmission facilities that comprise the following

NYCA interfaces: Dysinger East, West Central, Volney East, Moses South, Central East/Total   
East, and UPNY-ConEd, and their immediately connected, in series, Bulk Power System   
facilities in New York State. Each interface shall be evaluated to determine additional “in   
series” facilities, defined as any transmission facility higher than 115 kV that (a) is located in an   
upstream or downstream zone adjacent to the interface and (b) has a power transfer distribution   
factor (DFAX) equal to or greater than five percent when the aggregate of generation in zones or   
systems adjacent to the upstream zone or zones which define the interface is shifted to the   
aggregate of generation in zones or systems adjacent to the downstream zone or zones which   
define the interface. In determining “in series” facilities for Dysinger East and West Central   
interfaces, the 115 kV and 230 kV tie lines between NYCA and PJM located in LBMP Zones A   
and B shall not participate in the transfer. Highway transmission facilities are listed in ISO   
Procedures.

Initial Synchronization Date shall mean the date upon which the Large Generating Facility is initially synchronized and upon which Trial Operation begins.

In-Service Date shall mean the date upon which the Interconnection Customer reasonably expects it will be ready to begin use of the Connecting Transmission Owner’s Attachment Facilities to obtain back feed power.

6

Interconnection Customer shall mean an Eligible Customer developing a Large Generating Facility, proposing to connect to the New York State Transmission System, in compliance with the NYISO Minimum Interconnection Standard.

Interconnection Customer’s Attachment Facilities shall mean all facilities and equipment, as identified in Appendix A of this Agreement, that are located between the Large Generating   
Facility and the Point of Change of Ownership, including any modification, addition, or upgrades to such facilities and equipment necessary to physically and electrically interconnect the Large Generating Facility to the New York State Transmission System. Interconnection Customer’s Attachment Facilities are sole use facilities.

Interconnection Facilities Study shall mean a study conducted by NYISO or a third party   
consultant for the Interconnection Customer to determine a list of facilities (including   
Connecting Transmission Owner’s Attachment Facilities, Distribution Upgrades, System   
Upgrade Facilities and System Deliverability Upgrades as identified in the Interconnection   
System Reliability Impact Study), the cost of those facilities, and the time required to   
interconnect the Large Generating Facility with the New York State Transmission System or   
with the Distribution System. The scope of the study is defined in Section 30.8 of the Standard Large Facility Interconnection Procedures.

Interconnection Facilities Study Agreement shall mean the form of agreement contained in Appendix 4 of the Standard Large Facility Interconnection Procedures for conducting the Interconnection Facilities Study.

Interconnection Feasibility Study shall mean a preliminary evaluation of the system impact and cost of interconnecting the Large Generating Facility to the New York State Transmission System or to the Distribution System, the scope of which is described in Section 30.6 of the Standard Large Facility Interconnection Procedures.

Interconnection Feasibility Study Agreement shall mean the form of agreement contained in Appendix 2 of the Standard Large Facility Interconnection Procedures for conducting the   
Interconnection Feasibility Study.

Interconnection Request shall mean a Interconnection Customer’s request, in the form of

Appendix 1 to the Standard Large Facility Interconnection Procedures, in accordance with the   
Tariff, to interconnect a new Large Generating Facility to the New York State Transmission   
System or to the Distribution System, or to materially increase the capacity of, or make a   
material modification to the operating characteristics of, an existing Large Generating Facility   
that is interconnected with the New York State Transmission System or with the Distribution   
System.

Interconnection Study shall mean any of the following studies: the Interconnection Feasibility Study, the Interconnection System Reliability Impact Study, and the Interconnection Facilities Study described in the Standard Large Facility Interconnection Procedures.

Interconnection System Reliability Impact Study (“SRIS”) shall mean an engineering study,   
conducted in accordance with Section 30.7 of the Large Facility Interconnection Procedures, that   
evaluates the impact of the proposed Large Generating Facility on the safety and reliability of the

7

New York State Transmission System and, if applicable, an Affected System, to determine what Attachment Facilities, Distribution Upgrades and System Upgrade Facilities are needed for the proposed Large Generation Facility of the Interconnection Customer to connect reliably to the New York State Transmission System or to the Distribution System in a manner that meets the NYISO Minimum Interconnection Standard.

Interconnection System Reliability Impact Study Agreement shall mean the form of

agreement contained in Appendix 3 of the Standard Large Facility Interconnection Procedures for conducting the Interconnection System Reliability Impact Study.

IRS shall mean the Internal Revenue Service.

Large Generating Facility shall mean a Generating Facility having a Generating Facility Capacity of more than 20 MW.

Large Generator Interconnection Agreement (“LGIA”) shall mean this Agreement.

Loss shall mean any and all losses relating to injury to or death of any person or damage to

property, demand, suits, recoveries, costs and expenses, court costs, attorney fees, and all other   
obligations by or to third parties, arising out of or resulting from the Indemnified Party’s   
performance or non-performance of its obligations under this Agreement on behalf of the   
Indemnifying Party, except in cases of gross negligence or intentional wrongdoing by the   
Indemnified Party.

Material Modification shall mean those modifications that have a material impact on the cost or timing of any Interconnection Request with a later queue priority date.

Metering Equipment shall mean all metering equipment installed or to be installed at the Large Generating Facility pursuant to this Agreement at the metering points, including but not limited to instrument transformers, MWh-meters, data acquisition equipment, transducers, remote   
terminal unit, communications equipment, phone lines, and fiber optics.

Minimum Interconnection Standard shall mean the reliability standard that must be met by

any Large Generating Facility proposing to connect to the New York State Transmission System or to the Distribution System. The Standard is designed to ensure reliable access by the   
proposed project to the New York State Transmission System. The Standard does not impose any deliverability test or deliverability requirement on the proposed interconnection.

NERC shall mean the North American Electric Reliability Council or its successor organization.

New York State Transmission System shall mean the entire New York State electric

transmission system, which includes (i) the Transmission Facilities under ISO Operational Control; (ii) the Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities within the New York Control Area.

Notice of Dispute shall mean a written notice of a dispute or claim that arises out of or in connection with this Agreement or its performance.

8

NPCC shall mean the Northeast Power Coordinating Council or its successor organization.   
NYSRC shall mean the New York State Reliability Council or its successor organization.

Optional Interconnection Study shall mean a sensitivity analysis based on assumptions

specified by the Interconnection Customer in the Optional Interconnection Study Agreement.

Optional Interconnection Study Agreement shall mean the form of agreement contained in Appendix 5 of the Standard Large Facility Interconnection Procedures for conducting the Optional Interconnection Study.

Other Interfaces shall mean the following interfaces into Capacity Regions: Lower Hudson

Valley [i.e., Rest of State (Load Zones A-F) to Lower Hudson Valley (Load Zones G, H and I)]; New York City [i.e., Lower Hudson Valley (Load Zones G, H and I) to New York City (Load Zone J)]; and Long Island [i.e., Lower Hudson Valley (Load Zones G, H and I) to Long Island (Load Zone K)], and the following Interfaces between the NYCA and adjacent Control Areas: PJM to NYISO, ISO-NE to NYISO, Hydro-Quebec to NYISO, and Norwalk Harbor   
(Connecticut) to Northport (Long Island) Cable.

Party or Parties shall mean Connecting Transmission Owner or Interconnection Customer or any combination of the above.

Point of Change of Ownership shall mean the point, as set forth in Appendix A to this Agreement, where the Interconnection Customer’s Attachment Facilities connect to the Connecting Transmission Owner’s Attachment Facilities.

Point of Interconnection shall mean the point, as set forth in Appendix A to this Agreement, where the Attachment Facilities connect to the New York State Transmission System or to the Distribution System.

Queue Position shall mean the order of a valid Interconnection Request, relative to all other pending valid Interconnection Requests, that is established based upon the date and time of receipt of the valid Interconnection Request by NYISO.

Reasonable Efforts shall mean, with respect to an action required to be attempted or taken by a   
Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and   
are otherwise substantially equivalent to those a Party would use to protect its own interests.

Scoping Meeting shall mean the meeting between representatives of the Interconnection

Customer, NYISO and Connecting Transmission Owner conducted for the purpose of discussing   
alternative interconnection options, to exchange information including any transmission data and   
earlier study evaluations that would be reasonably expected to impact such interconnection   
options, to analyze such information, and to determine the potential feasible Points of   
Interconnection.

Services Tariff shall mean the NYISO Market Administration and Control Area Tariff, as filed   
with the Commission, and as amended or supplemented from time to time, or any successor tariff   
thereto.

9

Site Control shall mean documentation reasonably demonstrating: (1) ownership of, a leasehold   
interest in, or a right to develop a site for the purpose of constructing the Large Generating   
Facility; (2) an option to purchase or acquire a leasehold site for such purpose; or (3) an   
exclusivity or other business relationship between Interconnection Customer and the entity   
having the right to sell, lease or grant Interconnection Customer the right to possess or occupy a   
site for such purpose.

Stand Alone System Upgrade Facilities shall mean System Upgrade Facilities that a

Interconnection Customer may construct without affecting day-to-day operations of the New

York State Transmission System during their construction. Connecting Transmission Owner and the Interconnection Customer must agree as to what constitutes Stand Alone System Upgrade Facilities and identify them in Appendix A to this Agreement.

Standard Large Facility Interconnection Procedures (“LFIP”) shall mean the

interconnection procedures applicable to an Interconnection Request pertaining to a Large Generating Facility that are included in Attachment X of the NYISO OATT.

System Deliverability Upgrades shall mean the least costly configuration of commercially available components of electrical equipment that can be used, consistent with Good Utility Practice and Applicable Reliability Requirements, to make the modifications or additions to Byways and Highways and Other Interfaces on the existing New York State Transmission   
System and Distribution System that are required for the proposed project to connect reliably to the system in a manner that meets the NYISO Deliverability Interconnection Standard at the requested level of Capacity Resource Interconnection Service.

System Protection Facilities shall mean the equipment, including necessary protection signal   
communications equipment, required to (1) protect the New York State Transmission System   
from faults or other electrical disturbances occurring at the Large Generating Facility and (2)   
protect the Large Generating Facility from faults or other electrical system disturbances   
occurring on the New York State Transmission System or on other delivery systems or other   
generating systems to which the New York State Transmission System is directly connected.

System Upgrade Facilities shall mean the least costly configuration of commercially available   
components of electrical equipment that can be used, consistent with Good Utility Practice and   
Applicable Reliability Requirements, to make the modifications to the existing transmission   
system that are required to maintain system reliability due to: (i) changes in the system,   
including such changes as load growth and changes in load pattern, to be addressed in the form   
of generic generation or transmission projects; and (ii) proposed interconnections. In the case of   
proposed interconnection projects, System Upgrade Facilities are the modifications or additions   
to the existing New York State Transmission System that are required for the proposed project to   
connect reliably to the system in a manner that meets the NYISO Minimum Interconnection   
Standard.

Tariff shall mean the NYISO Open Access Transmission Tariff (“OATT”), as filed with the   
Commission, and as amended or supplemented from time to time, or any successor tariff.

10

Trial Operation shall mean the period during which Interconnection Customer is engaged in on-  
site test operations and commissioning of the Large Generating Facility prior to Commercial   
Operation.

Article 2. EFFECTIVE DATE, TERM AND TERMINATION

2.1 Effective Date.

This Agreement shall become effective as of the Effective Date, subject to acceptance by   
FERC, or if filed unexecuted, upon the date specified by FERC. Connecting Transmission   
Owner shall promptly file this Agreement with FERC upon execution in accordance with   
Article 3.1.

2.2 Term of Agreement.

Subject to the provisions of Article 2.3, this Agreement shall remain in effect for a period   
of ten (10) years from the Effective Date or such other longer period as the Interconnection   
Customer may request and shall be automatically renewed for each successive one-year period   
thereafter.

2.3 Termination.

2.3.1 Written Notice.

This Agreement may be terminated by the Interconnection Customer after giving the Connecting Transmission Owner ninety (90) Calendar Days advance written notice, or by the Connecting Transmission Owner notifying FERC after the Large Generating Facility   
permanently ceases Commercial Operations.

2.3.2 Default.

Any Party may terminate this Agreement in accordance with Article 17.

2.3.3 Compliance.

Notwithstanding Articles 2.3.1 and 2.3.2, no termination of this Agreement shall become effective until the Parties have complied with all Applicable Laws and Regulations applicable to such termination, including the filing with FERC of a notice of termination of this Agreement, which notice has been accepted for filing by FERC.

2.4 Termination Costs.

If a Party elects to terminate this Agreement pursuant to Article 2.3.1 above, the

terminating Party shall pay all costs incurred (including any cancellation costs relating to orders   
or contracts for Attachment Facilities and equipment) or charges assessed by the other Party, as   
of the date of the other Party’s receipt of such notice of termination, that is the responsibility of   
the terminating Party under this Agreement. In the event of termination by a Party, both Parties   
shall use commercially Reasonable Efforts to mitigate the costs, damages and charges arising as

11

a consequence of termination. Upon termination of this Agreement, unless otherwise ordered or approved by FERC:

2.4.1 With respect to any portion of the Connecting Transmission Owner’s Attachment   
Facilities that have not yet been constructed or installed, the Connecting Transmission Owner   
shall to the extent possible and with Interconnection Customer’s authorization cancel any   
pending orders of, or return, any materials or equipment for, or contracts for construction of,   
such facilities; provided that in the event Interconnection Customer elects not to authorize such   
cancellation, Interconnection Customer shall assume all payment obligations with respect to such   
materials, equipment, and contracts, and the Connecting Transmission Owner shall deliver such   
material and equipment, and, if necessary, assign such contracts, to Interconnection Customer as   
soon as practicable, at Interconnection Customer’s expense. To the extent that Interconnection   
Customer has already paid Connecting Transmission Owner for any or all such costs of materials   
or equipment not taken by Interconnection Customer, Connecting Transmission Owner shall   
promptly refund such amounts to Interconnection Customer, less any costs, including penalties   
incurred by the Connecting Transmission Owner to cancel any pending orders of or return such   
materials, equipment, or contracts.

If Interconnection Customer terminates this Agreement, it shall be responsible for all   
costs incurred in association with Interconnection Customer’s interconnection, including any   
cancellation costs relating to orders or contracts for Attachment Facilities and equipment, and   
other expenses including any System Upgrade Facilities and System Deliverability Upgrades for which the Connecting Transmission Owner has incurred expenses and has not been reimbursed by the Interconnection Customer.

2.4.2 Connecting Transmission Owner may, at its option, retain any portion of such materials, equipment, or facilities that Interconnection Customer chooses not to accept delivery of, in which case Connecting Transmission Owner shall be responsible for all costs associated with procuring such materials, equipment, or facilities.

2.4.3 With respect to any portion of the Attachment Facilities, and any other facilities already installed or constructed pursuant to the terms of this Agreement, Interconnection   
Customer shall be responsible for all costs associated with the removal, relocation or other disposition or retirement of such materials, equipment, or facilities.

2.5 Disconnection.

Upon termination of this Agreement, Interconnection Customer and Connecting

Transmission Owner will take all appropriate steps to disconnect the Interconnection Customer’s Large Generating Facility from the New York State Transmission System. All costs required to effectuate such disconnection shall be borne by the terminating Party, unless such termination resulted from the non-terminating Party’s Default of this Agreement or such non-terminating Party otherwise is responsible for these costs under this Agreement.

12

2.6 Survival.

This Agreement shall continue in effect after termination to the extent necessary to

provide for final billings and payments and for costs incurred hereunder; including billings and payments pursuant to this Agreement; to permit the determination and enforcement of liability and indemnification obligations arising from acts or events that occurred while this Agreement was in effect; and to permit Interconnection Customer and Connecting Transmission Owner each to have access to the lands of the other pursuant to this Agreement or other applicable   
agreements, to disconnect, remove or salvage its own facilities and equipment.

Article 3. REGULATORY FILINGS

3.1 Filing.

Connecting Transmission Owner shall file this Agreement (and any amendment hereto)   
with the appropriate Governmental Authority, if required. Any information related to studies for   
interconnection asserted by Interconnection Customer to contain Confidential Information shall   
be treated in accordance with Article 22 of this Agreement and Attachment F to the NYISO   
OATT. If the Interconnection Customer has executed this Agreement, or any amendment   
thereto, the Interconnection Customer shall reasonably cooperate with Connecting Transmission   
Owner with respect to such filing and to provide any information reasonably requested by   
Connecting Transmission Owner needed to comply with Applicable Laws and Regulations.

ARTICLE 4. SCOPE OF INTERCONNECTION SERVICE

4.1 Provision of Service.

The Parties understand that the NYISO will provide Interconnection Customer with interconnection service of the following type for the term of this Agreement.

4.1.1 Product.

The Parties understand that the NYISO will provide Capacity Resource Interconnection Service and Energy Resource Interconnection Service to Interconnection Customer at the Point of Interconnection, with Capacity Resource Interconnection Service subject to the provisions set forth in Appendix C-II.

4.1.2 Interconnection Customer is responsible for ensuring that its actual Large

Generating Facility output matches the scheduled delivery from the Large Generating Facility to   
the New York State Transmission System, consistent with the scheduling requirements of the   
NYISO’s FERC-approved market structure, including ramping into and out of such scheduled   
delivery, as measured at the Point of Interconnection, consistent with the scheduling   
requirements of the NYISO OATT and any applicable FERC-approved market structure.

4.2 No Transmission Delivery Service.

The execution of this Agreement does not constitute a request for, nor agreement to

provide, any Transmission Service under the NYISO OATT, and does not convey any right to

13

deliver electricity to any specific customer or Point of Delivery. If Interconnection Customer wishes to obtain Transmission Service on the New York State Transmission System, then Interconnection Customer must request such Transmission Service in accordance with the provisions of the NYISO OATT.

4.3 No Other Services.

The execution of this Agreement does not constitute a request for, nor agreement to

provide Energy, any Ancillary Services or Installed Capacity under the NYISO Market

Administration and Control Area Services Tariff (“Services Tariff”). If Interconnection

Customer wishes to supply Energy, Installed Capacity or Ancillary Services, then

Interconnection Customer will make application to do so in accordance with the NYISO Services   
Tariff.

Article 5. Interconnection Facilities Engineering, Procurement, And Construction

5.1 Options.

Unless otherwise mutually agreed to by Interconnection Customer and Connecting

Transmission Owner, Interconnection Customer shall select the In-Service Date, Initial

Synchronization Date, and Commercial Operation Date; and either Standard Option or Alternate   
Option set forth below for completion of the Connecting Transmission Owner’s Attachment   
Facilities and System Upgrade Facilities and System Deliverability Upgrades as set forth in   
Appendix A hereto, and such dates and selected option shall be set forth in Appendix B hereto.

5.1.1 Standard Option.

The Connecting Transmission Owner shall design, procure, and construct the Connecting   
Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System   
Deliverability Upgrades, using Reasonable Efforts to complete the Connecting Transmission   
Owner’s Attachment Facilities and System Upgrade Facilities and System Deliverability   
Upgrades by the dates set forth in Appendix B hereto. The Connecting Transmission Owner   
shall not be required to undertake any action which is inconsistent with its standard safety   
practices, its material and equipment specifications, its design criteria and construction   
procedures, its labor agreements, and Applicable Laws and Regulations. In the event the   
Connecting Transmission Owner reasonably expects that it will not be able to complete the   
Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades by the specified dates, the Connecting Transmission Owner   
shall promptly provide written notice to the Interconnection Customer and NYISO, and shall   
undertake Reasonable Efforts to meet the earliest dates thereafter.

5.1.2 Alternate Option.

If the dates designated by Interconnection Customer are acceptable to Connecting

Transmission Owner, the Connecting Transmission Owner shall so notify Interconnection

Customer and NYISO within thirty (30) Calendar Days, and shall assume responsibility for the   
design, procurement and construction of the Connecting Transmission Owner’s Attachment

14

Facilities by the designated dates. If Connecting Transmission Owner subsequently fails to

complete Connecting Transmission Owner’s Attachment Facilities by the In-Service Date, to the   
extent necessary to provide back feed power; or fails to complete System Upgrade Facilities or   
System Deliverability Upgrades by the Initial Synchronization Date to the extent necessary to   
allow for Trial Operation at full power output, unless other arrangements are made by the   
Interconnection Customer and Connecting Transmission Owner for such Trial Operation; or fails   
to complete the System Upgrade Facilities and System Deliverability Upgrades by the   
Commercial Operation Date, as such dates are reflected in Appendix B hereto; Connecting   
Transmission Owner shall pay Interconnection Customer liquidated damages in accordance with   
Article 5.3, Liquidated Damages, provided, however, the dates designated by Interconnection   
Customer shall be extended day for day for each day that NYISO refuses to grant clearances to   
install equipment.

5.1.3 Option to Build.

If the dates designated by Interconnection Customer are not acceptable to Connecting   
Transmission Owner, the Connecting Transmission Owner shall so notify the Interconnection   
Customer and NYISO within thirty (30) Calendar Days, and unless the Interconnection   
Customer and Connecting Transmission Owner agree otherwise, Interconnection Customer shall   
have the option to assume responsibility for the design, procurement and construction of   
Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade   
Facilities on the dates specified in Article 5.1.2; provided that if an Attachment Facility or Stand   
Alone System Upgrade Facility is needed for more than one Interconnection Customer’s project,   
Interconnection Customer’s option to build such Facility shall be contingent on the agreement of   
all other affected Interconnection Customers. Connecting Transmission Owner and   
Interconnection Customer must agree as to what constitutes Stand Alone System Upgrade   
Facilities and identify such Stand Alone System Upgrade Facilities in Appendix A hereto.   
Except for Stand Alone System Upgrade Facilities, Interconnection Customer shall have no right   
to construct System Upgrade Facilities under this option.

5.1.4 Negotiated Option.

If the Interconnection Customer elects not to exercise its option under Article 5.1.3,   
Option to Build, Interconnection Customer shall so notify Connecting Transmission Owner   
within thirty (30) Calendar Days, and the Interconnection Customer and Connecting   
Transmission Owner shall in good faith attempt to negotiate terms and conditions (including   
revision of the specified dates and liquidated damages, the provision of incentives or the   
procurement and construction of a portion of the Connecting Transmission Owner’s Attachment   
Facilities and Stand Alone System Upgrade Facilities by Interconnection Customer) pursuant to   
which Connecting Transmission Owner is responsible for the design, procurement and   
construction of the Connecting Transmission Owner’s Attachment Facilities and System   
Upgrade Facilities and System Deliverability Upgrades. If the two Parties are unable to reach   
agreement on such terms and conditions, Connecting Transmission Owner shall assume   
responsibility for the design, procurement and construction of the Connecting Transmission   
Owner’s Attachment Facilities and System Upgrade Facilities and System Deliverability   
Upgrades pursuant to 5.1.1, Standard Option.

15

5.2 General Conditions Applicable to Option to Build.

If Interconnection Customer assumes responsibility for the design, procurement and construction of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities,

(1) Interconnection Customer shall engineer, procure equipment, and construct the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade   
Facilities (or portions thereof) using Good Utility Practice and using standards and specifications provided in advance by the Connecting Transmission Owner;

(2) Interconnection Customer’s engineering, procurement and construction of the   
Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade   
Facilities shall comply with all requirements of law to which Connecting Transmission Owner   
would be subject in the engineering, procurement or construction of the Connecting   
Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities;

(3) Connecting Transmission Owner shall review and approve the engineering design, equipment acceptance tests, and the construction of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities;

(4) Prior to commencement of construction, Interconnection Customer shall provide   
to Connecting Transmission Owner and NYISO a schedule for construction of the Connecting   
Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities, and   
shall promptly respond to requests for information from Connecting Transmission Owner or   
NYISO;

(5) At any time during construction, Connecting Transmission Owner shall have the right to gain unrestricted access to the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities and to conduct inspections of the same;

(6) At any time during construction, should any phase of the engineering, equipment procurement, or construction of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities not meet the standards and specifications provided by Connecting Transmission Owner, the Interconnection Customer shall be obligated to remedy   
deficiencies in that portion of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities;

(7) Interconnection Customer shall indemnify Connecting Transmission Owner for claims arising from the Interconnection Customer’s construction of Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities under procedures applicable to Article 18.1 Indemnity;

(8) Interconnection Customer shall transfer control of Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to the Connecting Transmission Owner;

16

(9) Unless the Interconnection Customer and Connecting Transmission Owner

otherwise agree, Interconnection Customer shall transfer ownership of Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to Connecting   
Transmission Owner;

(10) Connecting Transmission Owner shall approve and accept for operation and maintenance the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to the extent engineered, procured, and constructed in accordance with this Article 5.2; and

(11) Interconnection Customer shall deliver to NYISO and Connecting Transmission Owner “as built” drawings, information, and any other documents that are reasonably required by NYISO or Connecting Transmission Owner to assure that the Attachment Facilities and Stand Alone System Upgrade Facilities are built to the standards and specifications required by   
Connecting Transmission Owner.

5.3 Liquidated Damages.

The actual damages to the Interconnection Customer, in the event the Connecting

Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System

Deliverability Upgrades are not completed by the dates designated by the Interconnection

Customer and accepted by the Connecting Transmission Owner pursuant to subparagraphs 5.1.2 or 5.1.4, above, may include Interconnection Customer’s fixed operation and maintenance costs and lost opportunity costs. Such actual damages are uncertain and impossible to determine at   
this time. Because of such uncertainty, any liquidated damages paid by the Connecting   
Transmission Owner to the Interconnection Customer in the event that Connecting Transmission Owner does not complete any portion of the Connecting Transmission Owner’s Attachment   
Facilities, System Upgrade Facilities or System Deliverability Upgrades by the applicable dates, shall be an amount equal to 1/2 of 1 percent per day of the actual cost of the Connecting   
Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System   
Deliverability Upgrades, in the aggregate, for which Connecting Transmission Owner has   
assumed responsibility to design, procure and construct.

However, in no event shall the total liquidated damages exceed 20 percent of the actual

cost of the Connecting Transmission Owner Attachment Facilities and System Upgrade Facilities   
and System Deliverability Upgrades for which the Connecting Transmission Owner has assumed   
responsibility to design, procure, and construct. The foregoing payments will be made by the   
Connecting Transmission Owner to the Interconnection Customer as just compensation for the   
damages caused to the Interconnection Customer, which actual damages are uncertain and   
impossible to determine at this time, and as reasonable liquidated damages, but not as a penalty   
or a method to secure performance of this Agreement. Liquidated damages, when the   
Interconnection Customer and Connecting Transmission Owner agree to them, are the exclusive   
remedy for the Connecting Transmission Owner’s failure to meet its schedule.

Further, Connecting Transmission Owner shall not pay liquidated damages to

Interconnection Customer if: (1) Interconnection Customer is not ready to commence use of the   
Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System

17

Deliverability Upgrades to take the delivery of power for the Interconnection Customer’s Large   
Generating Facility’s Trial Operation or to export power from the Interconnection Customer’s   
Large Generating Facility on the specified dates, unless the Interconnection Customer would   
have been able to commence use of the Connecting Transmission Owner’s Attachment Facilities   
or System Upgrade Facilities or System Deliverability Upgrades to take the delivery of power for   
Interconnection Customer’s Large Generating Facility’s Trial Operation or to export power from   
the Interconnection Customer’s Large Generating Facility, but for Connecting Transmission   
Owner’s delay; (2) the Connecting Transmission Owner’s failure to meet the specified dates is   
the result of the action or inaction of the Interconnection Customer or any other Interconnection   
Customer who has entered into a Large Generator Interconnection Agreement with the   
Connecting Transmission Owner, or action or inaction by any other Party, or any other cause   
beyond Connecting Transmission Owner’s reasonable control or reasonable ability to cure; (3)   
the Interconnection Customer has assumed responsibility for the design, procurement and   
construction of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone   
System Upgrade Facilities; or (4) the Connecting Transmission Owner and Interconnection   
Customer have otherwise agreed. In no event shall NYISO have any liability whatever to   
Interconnection Customer for liquidated damages associated with the engineering, procurement   
or construction of Attachment Facilities or System Upgrade Facilities or System Deliverability   
Upgrades.

5.4 Power System Stabilizers.

The Interconnection Customer shall procure, install, maintain and operate Power System   
Stabilizers in accordance with the requirements identified in the Interconnection Studies   
conducted for Interconnection Customer’s Large Generating Facility. Connecting Transmission   
Owner reserve the right to reasonably establish minimum acceptable settings for any installed   
Power System Stabilizers, subject to the design and operating limitations of the Large Generating   
Facility. If the Large Generating Facility’s Power System Stabilizers are removed from service   
or not capable of automatic operation, the Interconnection Customer shall immediately notify the   
Connecting Transmission Owner. The requirements of this paragraph shall not apply to wind   
generators.

5.5 Equipment Procurement.

If responsibility for construction of the Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades is to be borne by the Connecting Transmission Owner, then the Connecting Transmission Owner shall commence design of the Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades and procure necessary equipment as soon as   
practicable after all of the following conditions are satisfied, unless the Interconnection   
Customer and Connecting Transmission Owner otherwise agree in writing:

5.5.1 NYISO and Connecting Transmission Owner have completed the Interconnection Facilities Study pursuant to the Interconnection Facilities Study Agreement;

5.5.2 The NYISO has completed the required cost allocation analyses, and

Interconnection Customer has accepted his share of the costs for necessary System Upgrade

18

Facilities and System Deliverability Upgrades in accordance with the provisions of Attachment S of the NYISO OATT;

5.5.3 The Connecting Transmission Owner has received written authorization to

proceed with design and procurement from the Interconnection Customer by the date specified in Appendix B hereto; and

5.5.4 The Interconnection Customer has provided security to the Connecting

Transmission Owner in accordance with Article 11.5 by the dates specified in Appendix B   
hereto.

5.6 Construction Commencement.

The Connecting Transmission Owner shall commence construction of the Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System   
Deliverability Upgrades for which it is responsible as soon as practicable after the following additional conditions are satisfied:

5.6.1 Approval of the appropriate Governmental Authority has been obtained for any facilities requiring regulatory approval;

5.6.2 Necessary real property rights and rights-of-way have been obtained, to the extent   
required for the construction of a discrete aspect of the Connecting Transmission Owner’s   
Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades;

5.6.3 The Connecting Transmission Owner has received written authorization to

proceed with construction from the Interconnection Customer by the date specified in Appendix B hereto; and

5.6.4 The Interconnection Customer has provided security to the Connecting

Transmission Owner in accordance with Article 11.5 by the dates specified in Appendix B   
hereto.

5.7 Work Progress.

The Interconnection Customer and Connecting Transmission Owner will keep each other, and NYISO, advised periodically as to the progress of their respective design, procurement and   
construction efforts. Any Party may, at any time, request a progress report from the   
Interconnection Customer or Connecting Transmission Owner. If, at any time, the   
Interconnection Customer determines that the completion of the Connecting Transmission   
Owner’s Attachment Facilities will not be required until after the specified In-Service Date, the   
Interconnection Customer will provide written notice to the Connecting Transmission Owner and NYISO of such later date upon which the completion of the Connecting Transmission Owner’s   
Attachment Facilities will be required.

19

5.8 Information Exchange.

As soon as reasonably practicable after the Effective Date, the Interconnection Customer and Connecting Transmission Owner shall exchange information, and provide NYISO the same information, regarding the design and compatibility of their respective Attachment Facilities and compatibility of the Attachment Facilities with the New York State Transmission System, and shall work diligently and in good faith to make any necessary design changes.

5.9 Limited Operation.

If any of the Connecting Transmission Owner’s Attachment Facilities or System Upgrade   
Facilities or System Deliverability Upgrades are not reasonably expected to be completed prior   
to the Commercial Operation Date of the Interconnection Customer’s Large Generating Facility,   
NYISO shall, upon the request and at the expense of Interconnection Customer, in conjunction   
with the Connecting Transmission Owner, perform operating studies on a timely basis to   
determine the extent to which the Interconnection Customer’s Large Generating Facility and the   
Interconnection Customer’s Attachment Facilities may operate prior to the completion of the   
Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System   
Deliverability Upgrades consistent with Applicable Laws and Regulations, Applicable   
Reliability Standards, Good Utility Practice, and this Agreement. Connecting Transmission   
Owner shall permit Interconnection Customer to operate the Interconnection Customer’s Large   
Generating Facility and the Interconnection Customer’s Attachment Facilities in accordance with   
the results of such studies.

5.10 Interconnection Customer’s Attachment Facilities (“ICAF”).

Interconnection Customer shall, at its expense, design, procure, construct, own and install the ICAF, as set forth in Appendix A hereto.

5.10.1 ICAF Specifications.

Interconnection Customer shall submit initial specifications for the ICAF, including

System Protection Facilities, to Connecting Transmission Owner and NYISO at least one

hundred eighty (180) Calendar Days prior to the Initial Synchronization Date; and final

specifications for review and comment at least ninety (90) Calendar Days prior to the Initial

Synchronization Date. Connecting Transmission Owner and NYISO shall review such

specifications to ensure that the ICAF are compatible with the technical specifications,

operational control, and safety requirements of the Connecting Transmission Owner and NYISO and comment on such specifications within thirty (30) Calendar Days of Interconnection   
Customer’s submission. All specifications provided hereunder shall be deemed to be   
Confidential Information.

5.10.2 No Warranty.

The review of Interconnection Customer’s final specifications by Connecting

Transmission Owner and NYISO shall not be construed as confirming, endorsing, or providing a   
warranty as to the design, fitness, safety, durability or reliability of the Large Generating Facility,

20

or the ICAF. Interconnection Customer shall make such changes to the ICAF as may reasonably be required by Connecting Transmission Owner or NYISO, in accordance with Good Utility Practice, to ensure that the ICAF are compatible with the technical specifications, operational control, and safety requirements of the Connecting Transmission Owner and NYISO.

5.10.3 ICAF Construction.

The ICAF shall be designed and constructed in accordance with Good Utility Practice.   
Within one hundred twenty (120) Calendar Days after the Commercial Operation Date, unless   
the Interconnection Customer and Connecting Transmission Owner agree on another mutually   
acceptable deadline, the Interconnection Customer shall deliver to the Connecting Transmission   
Owner and NYISO “as-built” drawings, information and documents for the ICAF, such as: a   
one-line diagram, a site plan showing the Large Generating Facility and the ICAF, plan and

elevation drawings showing the layout of the ICAF, a relay functional diagram, relaying AC and DC schematic wiring diagrams and relay settings for all facilities associated with the   
Interconnection Customer’s step-up transformers, the facilities connecting the Large Generating Facility to the step-up transformers and the ICAF, and the impedances (determined by factory   
tests) for the associated step-up transformers and the Large Generating Facility. The   
Interconnection Customer shall provide to, and coordinate with, Connecting Transmission   
Owner and NYISO with respect to proposed specifications for the excitation system, automatic voltage regulator, Large Generating Facility control and protection settings, transformer tap   
settings, and communications, if applicable.

5.11 Connecting Transmission Owner’s Attachment Facilities Construction.

The Connecting Transmission Owner’s Attachment Facilities shall be designed and

constructed in accordance with Good Utility Practice. Upon request, within one hundred twenty (120) Calendar Days after the Commercial Operation Date, unless the Connecting Transmission Owner and Interconnection Customer agree on another mutually acceptable deadline, the   
Connecting Transmission Owner shall deliver to the Interconnection Customer “as-built”   
drawings, relay diagrams, information and documents for the Connecting Transmission Owner’s Attachment Facilities set forth in Appendix A.

The Connecting Transmission Owner shall transfer operational control of the Connecting Transmission Owner’s Attachment Facilities and Stand Alone System Upgrade Facilities to the NYISO upon completion of such facilities.

5.12 Access Rights.

Upon reasonable notice and supervision by the Granting Party, and subject to any

required or necessary regulatory approvals, either the Connecting Transmission Owner or

Interconnection Customer (“Granting Party”) shall furnish to the other of those two Parties

(“Access Party”) at no cost any rights of use, licenses, rights of way and easements with respect   
to lands owned or controlled by the Granting Party, its agents (if allowed under the applicable   
agency agreement), or any Affiliate, that are necessary to enable the Access Party to obtain   
ingress and egress at the Point of Interconnection to construct, operate, maintain, repair, test (or   
witness testing), inspect, replace or remove facilities and equipment to: (i) interconnect the Large

21

Generating Facility with the New York State Transmission System; (ii) operate and maintain the   
Large Generating Facility, the Attachment Facilities and the New York State Transmission   
System; and (iii) disconnect or remove the Access Party’s facilities and equipment upon   
termination of this Agreement. In exercising such licenses, rights of way and easements, the   
Access Party shall not unreasonably disrupt or interfere with normal operation of the Granting   
Party’s business and shall adhere to the safety rules and procedures established in advance, as   
may be changed from time to time, by the Granting Party and provided to the Access Party. The   
Access Party shall indemnify the Granting Party against all claims of injury or damage from   
third parties resulting from the exercise of the access rights provided for herein.

5.13 Lands of Other Property Owners.

If any part of the Connecting Transmission Owner’s Attachment Facilities and/or System Upgrade Facilities and/or System Deliverability Upgrades is to be installed on property owned   
by persons other than Interconnection Customer or Connecting Transmission Owner, the   
Connecting Transmission Owner shall at Interconnection Customer’s expense use efforts, similar in nature and extent to those that it typically undertakes for its own or affiliated generation,   
including use of its eminent domain authority, and to the extent consistent with state law, to   
procure from such persons any rights of use, licenses, rights of way and easements that are   
necessary to construct, operate, maintain, test, inspect, replace or remove the Connecting   
Transmission Owner’s Attachment Facilities and/or System Upgrade Facilities and/or System   
Deliverability Upgrades upon such property.

5.14 Permits.

Connecting Transmission Owner and the Interconnection Customer shall cooperate with each other in good faith in obtaining all permits, licenses and authorizations that are necessary to accomplish the interconnection in compliance with Applicable Laws and Regulations. With respect to this paragraph, Connecting Transmission Owner shall provide permitting assistance to the Interconnection Customer comparable to that provided to the Connecting Transmission   
Owner’s own, or an Affiliate’s generation, if any.

5.15 Early Construction of Base Case Facilities.

Interconnection Customer may request Connecting Transmission Owner to construct, and Connecting Transmission Owner shall construct, subject to a binding cost allocation agreement reached in accordance with Attachment S to the NYISO OATT, including Section 25.8.7 thereof, using Reasonable Efforts to accommodate Interconnection Customer’s In-Service Date, all or   
any portion of any System Upgrade Facilities or System Deliverability Upgrades required for   
Interconnection Customer to be interconnected to the New York State Transmission System   
which are included in the Base Case of the Class Year Interconnection Facilities Study for the   
Interconnection Customer, and which also are required to be constructed for another   
Interconnection Customer, but where such construction is not scheduled to be completed in time to achieve Interconnection Customer’s In-Service Date.

22

5.16 Suspension.

Interconnection Customer reserves the right, upon written notice to Connecting

Transmission Owner, to suspend at any time all work by Connecting Transmission Owner

associated with the construction and installation of Connecting Transmission Owner’s

Attachment Facilities and/or System Upgrade Facilities and/or System Deliverability Upgrades   
required for only that Interconnection Customer under this Agreement with the condition that the   
New York State Transmission System shall be left in a safe and reliable condition in accordance   
with Good Utility Practice and the safety and reliability criteria of Connecting Transmission   
Owner and NYISO. In such event, Interconnection Customer shall be responsible for all   
reasonable and necessary costs and/or obligations in accordance with Attachment S to the   
NYISO OATT including those which Connecting Transmission Owner (i) has incurred pursuant   
to this Agreement prior to the suspension and (ii) incurs in suspending such work, including any   
costs incurred to perform such work as may be necessary to ensure the safety of persons and   
property and the integrity of the New York State Transmission System during such suspension   
and, if applicable, any costs incurred in connection with the cancellation or suspension of   
material, equipment and labor contracts which Connecting Transmission Owner cannot   
reasonably avoid; provided, however, that prior to canceling or suspending any such material,   
equipment or labor contract, Connecting Transmission Owner shall obtain Interconnection   
Customer’s authorization to do so.

Connecting Transmission Owner shall invoice Interconnection Customer for such costs   
pursuant to Article 12 and shall use due diligence to minimize its costs. In the event   
Interconnection Customer suspends work by Connecting Transmission Owner required under   
this Agreement pursuant to this Article 5.16, and has not requested Connecting Transmission   
Owner to recommence the work required under this Agreement on or before the expiration of   
three (3) years following commencement of such suspension, this Agreement shall be deemed   
terminated. The three-year period shall begin on the date the suspension is requested, or the date   
of the written notice to Connecting Transmission Owner, if no effective date is specified.

5.17 Taxes.

5.17.1 Interconnection Customer Payments Not Taxable.

The Interconnection Customer and Connecting Transmission Owner intend that all

payments or property transfers made by Interconnection Customer to Connecting Transmission   
Owner for the installation of the Connecting Transmission Owner’s Attachment Facilities and   
the System Upgrade Facilities and the System Deliverability Upgrades shall be non-taxable,   
either as contributions to capital, or as an advance, in accordance with the Internal Revenue Code   
and any applicable state income tax laws and shall not be taxable as contributions in aid of   
construction or otherwise under the Internal Revenue Code and any applicable state income tax   
laws.

5.17.2 Representations and Covenants.

In accordance with IRS Notice 2001-82 and IRS Notice 88-129, Interconnection

Customer represents and covenants that (i) ownership of the electricity generated at the Large   
Generating Facility will pass to another party prior to the transmission of the electricity on the

23

New York State Transmission System, (ii) for income tax purposes, the amount of any payments   
and the cost of any property transferred to the Connecting Transmission Owner for the   
Connecting Transmission Owner’s Attachment Facilities will be capitalized by Interconnection   
Customer as an intangible asset and recovered using the straight-line method over a useful life of   
twenty (20) years, and (iii) any portion of the Connecting Transmission Owner’s Attachment   
Facilities that is a “dual-use intertie,” within the meaning of IRS Notice 88-129, is reasonably   
expected to carry only a de minimis amount of electricity in the direction of the Large   
Generating Facility. For this purpose, “de minimis amount” means no more than 5 percent of the   
total power flows in both directions, calculated in accordance with the “5 percent test” set forth   
in IRS Notice 88-129. This is not intended to be an exclusive list of the relevant conditions that   
must be met to conform to IRS requirements for non-taxable treatment.

At Connecting Transmission Owner’s request, Interconnection Customer shall provide   
Connecting Transmission Owner with a report from an independent engineer confirming its   
representation in clause (iii), above. Connecting Transmission Owner represents and covenants   
that the cost of the Connecting Transmission Owner’s Attachment Facilities paid for by   
Interconnection Customer will have no net effect on the base upon which rates are determined.

5.17.3 Indemnification for the Cost Consequences of Current Tax Liability Imposed

Upon the Connecting Transmission Owner.

Notwithstanding Article 5.17.1, Interconnection Customer shall protect, indemnify and hold harmless Connecting Transmission Owner from the cost consequences of any current tax liability imposed against Connecting Transmission Owner as the result of payments or property transfers made by Interconnection Customer to Connecting Transmission Owner under this Agreement, as well as any interest and penalties, other than interest and penalties attributable to any delay caused by Connecting Transmission Owner.

Connecting Transmission Owner shall not include a gross-up for the cost consequences   
of any current tax liability in the amounts it charges Interconnection Customer under this   
Agreement unless (i) Connecting Transmission Owner has determined, in good faith, that the   
payments or property transfers made by Interconnection Customer to Connecting Transmission   
Owner should be reported as income subject to taxation or (ii) any Governmental Authority   
directs Connecting Transmission Owner to report payments or property as income subject to   
taxation; provided, however, that Connecting Transmission Owner may require Interconnection   
Customer to provide security, in a form reasonably acceptable to Connecting Transmission   
Owner (such as a parental guarantee or a letter of credit), in an amount equal to the cost   
consequences of any current tax liability under this Article 5.17. Interconnection Customer shall   
reimburse Connecting Transmission Owner for such costs on a fully grossed-up basis, in   
accordance with Article 5.17.4, within thirty (30) Calendar Days of receiving written notification   
from Connecting Transmission Owner of the amount due, including detail about how the amount   
was calculated.

This indemnification obligation shall terminate at the earlier of (1) the expiration of the ten-year testing period and the applicable statute of limitation, as it may be extended by the Connecting Transmission Owner upon request of the IRS, to keep these years open for audit or adjustment, or (2) the occurrence of a subsequent taxable event and the payment of any related indemnification obligations as contemplated by this Article 5.17.

24

5.17.4 Tax Gross-Up Amount.

Interconnection Customer’s liability for the cost consequences of any current tax liability   
under this Article 5.17 shall be calculated on a fully grossed-up basis. Except as may otherwise   
be agreed to by the parties, this means that Interconnection Customer will pay Connecting   
Transmission Owner, in addition to the amount paid for the Attachment Facilities and System   
Upgrade Facilities and System Deliverability Upgrades, an amount equal to (1) the current taxes   
imposed on Connecting Transmission Owner (“Current Taxes”) on the excess of (a) the gross   
income realized by Connecting Transmission Owner as a result of payments or property transfers   
made by Interconnection Customer to Connecting Transmission Owner under this Agreement   
(without regard to any payments under this Article 5.17) (the “Gross Income Amount”) over (b)   
the present value of future tax deductions for depreciation that will be available as a result of   
such payments or property transfers (the “Present Value Depreciation Amount”), plus (2) an   
additional amount sufficient to permit the Connecting Transmission Owner to receive and retain,   
after the payment of all Current Taxes, an amount equal to the net amount described in clause

(1).

For this purpose, (i) Current Taxes shall be computed based on Connecting Transmission   
Owner’s composite federal and state tax rates at the time the payments or property transfers are   
received and Connecting Transmission Owner will be treated as being subject to tax at the   
highest marginal rates in effect at that time (the “Current Tax Rate”), and (ii) the Present Value   
Depreciation Amount shall be computed by discounting Connecting Transmission Owner’s   
anticipated tax depreciation deductions as a result of such payments or property transfers by   
Connecting Transmission Owner’s current weighted average cost of capital. Thus, the formula   
for calculating Interconnection Customer’s liability to Connecting Transmission Owner pursuant   
to this Article 5.17.4 can be expressed as follows: (Current Tax Rate x (Gross Income Amount -  
Present Value of Tax Depreciation))/(1 - Current Tax Rate). Interconnection Customer’s   
estimated tax liability in the event taxes are imposed shall be stated in Appendix A, Attachment   
Facilities and System Upgrade Facilities and System Deliverability Upgrades.

5.17.5 Private Letter Ruling or Change or Clarification of Law.

At Interconnection Customer’s request and expense, Connecting Transmission Owner   
shall file with the IRS a request for a private letter ruling as to whether any property transferred   
or sums paid, or to be paid, by Interconnection Customer to Connecting Transmission Owner   
under this Agreement are subject to federal income taxation. Interconnection Customer will   
prepare the initial draft of the request for a private letter ruling, and will certify under penalties of   
perjury that all facts represented in such request are true and accurate to the best of   
Interconnection Customer’s knowledge. Connecting Transmission Owner and Interconnection   
Customer shall cooperate in good faith with respect to the submission of such request.

Connecting Transmission Owner shall keep Interconnection Customer fully informed of   
the status of such request for a private letter ruling and shall execute either a privacy act waiver   
or a limited power of attorney, in a form acceptable to the IRS, that authorizes Interconnection   
Customer to participate in all discussions with the IRS regarding such request for a private letter

25

ruling. Connecting Transmission Owner shall allow Interconnection Customer to attend all meetings with IRS officials about the request and shall permit Interconnection Customer to prepare the initial drafts of any follow-up letters in connection with the request.

5.17.6 Subsequent Taxable Events.

If, within 10 years from the date on which the relevant Connecting Transmission Owner   
Attachment Facilities are placed in service, (i) Interconnection Customer Breaches the covenants   
contained in Article 5.17.2, (ii) a “disqualification event” occurs within the meaning of IRS   
Notice 88-129, or (iii) this Agreement terminates and Connecting Transmission Owner retains   
ownership of the Attachment Facilities and System Upgrade Facilities and System Deliverability   
Upgrades, the Interconnection Customer shall pay a tax gross-up for the cost consequences of   
any current tax liability imposed on Connecting Transmission Owner, calculated using the   
methodology described in Article 5.17.4 and in accordance with IRS Notice 90-60.

5.17.7 Contests.

In the event any Governmental Authority determines that Connecting Transmission

Owner’s receipt of payments or property constitutes income that is subject to taxation,

Connecting Transmission Owner shall notify Interconnection Customer, in writing, within thirty

(30) Calendar Days of receiving notification of such determination by a Governmental

Authority. Upon the timely written request by Interconnection Customer and at Interconnection   
Customer’s sole expense, Connecting Transmission Owner may appeal, protest, seek abatement   
of, or otherwise oppose such determination. Upon Interconnection Customer’s written request   
and sole expense, Connecting Transmission Owner may file a claim for refund with respect to   
any taxes paid under this Article 5.17, whether or not it has received such a determination.   
Connecting Transmission Owner reserves the right to make all decisions with regard to the   
prosecution of such appeal, protest, abatement or other contest, including the selection of counsel   
and compromise or settlement of the claim, but Connecting Transmission Owner shall keep   
Interconnection Customer informed, shall consider in good faith suggestions from   
Interconnection Customer about the conduct of the contest, and shall reasonably permit   
Interconnection Customer or an Interconnection Customer representative to attend contest   
proceedings.

Interconnection Customer shall pay to Connecting Transmission Owner on a periodic

basis, as invoiced by Connecting Transmission Owner, Connecting Transmission Owner’s

documented reasonable costs of prosecuting such appeal, protest, abatement or other contest. At   
any time during the contest, Connecting Transmission Owner may agree to a settlement either   
with Interconnection Customer’s consent or after obtaining written advice from nationally-  
recognized tax counsel, selected by Connecting Transmission Owner, but reasonably acceptable   
to Interconnection Customer, that the proposed settlement represents a reasonable settlement   
given the hazards of litigation. Interconnection Customer’s obligation shall be based on the   
amount of the settlement agreed to by Interconnection Customer, or if a higher amount, so much   
of the settlement that is supported by the written advice from nationally-recognized tax counsel   
selected under the terms of the preceding sentence. The settlement amount shall be calculated on   
a fully grossed-up basis to cover any related cost consequences of the current tax liability. Any

26

settlement without Interconnection Customer’s consent or such written advice will relieve

Interconnection Customer from any obligation to indemnify Connecting Transmission Owner for the tax at issue in the contest.

5.17.8 Refund.

In the event that (a) a private letter ruling is issued to Connecting Transmission Owner   
which holds that any amount paid or the value of any property transferred by Interconnection   
Customer to Connecting Transmission Owner under the terms of this Agreement is not subject to   
federal income taxation, (b) any legislative change or administrative announcement, notice,   
ruling or other determination makes it reasonably clear to Connecting Transmission Owner in   
good faith that any amount paid or the value of any property transferred by Interconnection   
Customer to Connecting Transmission Owner under the terms of this Agreement is not taxable to   
Connecting Transmission Owner, (c) any abatement, appeal, protest, or other contest results in a   
determination that any payments or transfers made by Interconnection Customer to Connecting   
Transmission Owner are not subject to federal income tax, or (d) if Connecting Transmission   
Owner receives a refund from any taxing authority for any overpayment of tax attributable to any   
payment or property transfer made by Interconnection Customer to Connecting Transmission   
Owner pursuant to this Agreement, Connecting Transmission Owner shall promptly refund to   
Interconnection Customer the following:

(i) Any payment made by Interconnection Customer under this Article 5.17 for taxes   
that is attributable to the amount determined to be non-taxable, together with interest thereon,

(ii) Interest on any amounts paid by Interconnection Customer to Connecting

Transmission Owner for such taxes which Connecting Transmission Owner did not submit to the   
taxing authority, calculated in accordance with the methodology set forth in FERC’s regulations   
at 18 C.F.R. §35.19a(a)(2)(iii) from the date payment was made by Interconnection Customer to   
the date Connecting Transmission Owner refunds such payment to Interconnection Customer,   
and

(iii) With respect to any such taxes paid by Connecting Transmission Owner, any   
refund or credit Connecting Transmission Owner receives or to which it may be entitled from   
any Governmental Authority, interest (or that portion thereof attributable to the payment   
described in clause (i), above) owed to the Connecting Transmission Owner for such   
overpayment of taxes (including any reduction in interest otherwise payable by Connecting   
Transmission Owner to any Governmental Authority resulting from an offset or credit);   
provided, however, that Connecting Transmission Owner will remit such amount promptly to   
Interconnection Customer only after and to the extent that Connecting Transmission Owner has   
received a tax refund, credit or offset from any Governmental Authority for any applicable   
overpayment of income tax related to the Connecting Transmission Owner’s Attachment   
Facilities.

The intent of this provision is to leave both the Interconnection Customer and Connecting   
Transmission Owner, to the extent practicable, in the event that no taxes are due with respect to   
any payment for Attachment Facilities and System Upgrade Facilities and System Deliverability

27

Upgrades hereunder, in the same position they would have been in had no such tax payments been made.

5.17.9 Taxes Other Than Income Taxes.

Upon the timely request by Interconnection Customer, and at Interconnection Customer’s   
sole expense, Connecting Transmission Owner shall appeal, protest, seek abatement of, or   
otherwise contest any tax (other than federal or state income tax) asserted or assessed against   
Connecting Transmission Owner for which Interconnection Customer may be required to   
reimburse Connecting Transmission Owner under the terms of this Agreement. Interconnection   
Customer shall pay to Connecting Transmission Owner on a periodic basis, as invoiced by   
Connecting Transmission Owner, Connecting Transmission Owner’s documented reasonable   
costs of prosecuting such appeal, protest, abatement, or other contest. Interconnection Customer   
and Connecting Transmission Owner shall cooperate in good faith with respect to any such   
contest. Unless the payment of such taxes is a prerequisite to an appeal or abatement or cannot   
be deferred, no amount shall be payable by Interconnection Customer to Connecting   
Transmission Owner for such taxes until they are assessed by a final, non-appealable order by   
any court or agency of competent jurisdiction. In the event that a tax payment is withheld and   
ultimately due and payable after appeal, Interconnection Customer will be responsible for all   
taxes, interest and penalties, other than penalties attributable to any delay caused by Connecting   
Transmission Owner.

5.18 Tax Status; Non-Jurisdictional Entities.

5.18.1 Tax Status.

Each Party shall cooperate with the other Party to maintain the other Party’s tax status.   
Nothing in this Agreement is intended to adversely affect the tax status of any Party or the status   
of any Connecting Transmission Owner with respect to the issuance of bonds including, but not   
limited to, Local Furnishing Bonds. Notwithstanding any other provisions of this Agreement,   
LIPA, NYPA and Consolidated Edison Company of New York, Inc. shall not be required to   
comply with any provisions of this Agreement that would result in the loss of tax-exempt status   
of any of their Tax-Exempt Bonds or impair their ability to issue future tax-exempt obligations.   
For purposes of this provision, Tax-Exempt Bonds shall include the obligations of the Long   
Island Power Authority, NYPA and Consolidated Edison Company of New York, Inc., the   
interest on which is not included in gross income under the Internal Revenue Code.

5.18.2 Non-Jurisdictional Entities.

LIPA and NYPA do not waive their exemptions, pursuant to Section 201(f) of the FPA, from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general ratemaking authority.

28

5.19 Modification.

5.19.1 General.

Either the Interconnection Customer or Connecting Transmission Owner may undertake   
modifications to its facilities covered by this Agreement. If either the Interconnection Customer   
or Connecting Transmission Owner plans to undertake a modification that reasonably may be   
expected to affect the other Party’s facilities, that Party shall provide to the other Party, and to   
NYISO, sufficient information regarding such modification so that the other Party and NYISO   
may evaluate the potential impact of such modification prior to commencement of the work.

Such information shall be deemed to be Confidential Information hereunder and shall include information concerning the timing of such modifications and whether such modifications are expected to interrupt the flow of electricity from the Large Generating Facility. The Party   
desiring to perform such work shall provide the relevant drawings, plans, and specifications to the other Party and NYISO at least ninety (90) Calendar Days in advance of the commencement of the work or such shorter period upon which the Parties may agree, which agreement shall not unreasonably be withheld, conditioned or delayed.

In the case of Large Generating Facility modifications that do not require Interconnection   
Customer to submit an Interconnection Request, Connecting Transmission Owner shall provide,   
within sixty (60) Calendar Days (or such other time as the Parties may agree), an estimate of any   
additional modifications to the New York State Transmission System, Connecting Transmission   
Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades   
necessitated by such Interconnection Customer modification and a good faith estimate of the

costs thereof. The Interconnection Customer shall be responsible for the cost of any such additional modifications, including the cost of studying the impact of the Interconnection Customer modification.

5.19.2 Standards.

Any additions, modifications, or replacements made to a Party’s facilities shall be

designed, constructed and operated in accordance with this Agreement, NYISO requirements and Good Utility Practice.

5.19.3 Modification Costs.

Interconnection Customer shall not be assigned the costs of any additions, modifications,   
or replacements that Connecting Transmission Owner makes to the Connecting Transmission   
Owner’s Attachment Facilities or the New York State Transmission System to facilitate the   
interconnection of a third party to the Connecting Transmission Owner’s Attachment Facilities   
or the New York State Transmission System, or to provide Transmission Service to a third party   
under the NYISO OATT, except in accordance with the cost allocation procedures in Attachment   
S of the NYISO OATT. Interconnection Customer shall be responsible for the costs of any   
additions, modifications, or replacements to the Interconnection Customer Attachment Facilities   
that may be necessary to maintain or upgrade such Interconnection Customer Attachment   
Facilities consistent with Applicable Laws and Regulations, Applicable Reliability Standards or   
Good Utility Practice.

29

Article 6. Testing And Inspection

6.1 Pre-Commercial Operation Date Testing and Modifications.

Prior to the Commercial Operation Date, the Connecting Transmission Owner shall test   
the Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades and Interconnection Customer shall test the Large Generating   
Facility and the Interconnection Customer Attachment Facilities to ensure their safe and reliable   
operation. Similar testing may be required after initial operation. Interconnection Customer and   
Connecting Transmission Owner shall each make any modifications to its facilities that are

found to be necessary as a result of such testing. Interconnection Customer shall bear the cost of all such testing and modifications. Interconnection Customer shall generate test energy at the Large Generating Facility only if it has arranged for the injection of such test energy in   
accordance with NYISO procedures.

6.2 Post-Commercial Operation Date Testing and Modifications.

Interconnection Customer and Connecting Transmission Owner shall each at its own

expense perform routine inspection and testing of its facilities and equipment in accordance with Good Utility Practice and Applicable Reliability Standards as may be necessary to ensure the continued interconnection of the Large Generating Facility with the New York State   
Transmission System in a safe and reliable manner. Interconnection Customer and Connecting Transmission Owner shall each have the right, upon advance written notice, to require   
reasonable additional testing of the other Party’s facilities, at the requesting Party’s expense, as may be in accordance with Good Utility Practice.

6.3 Right to Observe Testing.

Interconnection Customer and Connecting Transmission Owner shall each notify the

other Party, and the NYISO, in advance of its performance of tests of its Attachment Facilities.   
The other Party, and the NYISO, shall each have the right, at its own expense, to observe such   
testing.

6.4 Right to Inspect.

Interconnection Customer and Connecting Transmission Owner shall each have the right,   
but shall have no obligation to: (i) observe the other Party’s tests and/or inspection of any of its   
System Protection Facilities and other protective equipment, including Power System Stabilizers;   
(ii) review the settings of the other Party’s System Protection Facilities and other protective   
equipment; and (iii) review the other Party’s maintenance records relative to the Attachment   
Facilities, the System Protection Facilities and other protective equipment. NYISO shall have   
these same rights of inspection as to the facilities and equipment of Interconnection Customer   
and Connecting Transmission Owner. A Party may exercise these rights from time to time as it   
deems necessary upon reasonable notice to the other Party. The exercise or non-exercise by a   
Party of any such rights shall not be construed as an endorsement or confirmation of any element   
or condition of the Attachment Facilities or the System Protection Facilities or other protective   
equipment or the operation thereof, or as a warranty as to the fitness, safety, desirability, or   
reliability of same. Any information that a Party obtains through the exercise of any of its rights

30

under this Article 6.4 shall be treated in accordance with Article 22 of this Agreement and Attachment F to the NYISO OATT.

Article 7. Metering

7.1 General.

Interconnection Customer and Connecting Transmission Owner shall each comply with   
applicable requirements of NYISO and the New York Public Service Commission when   
exercising its rights and fulfilling its responsibilities under this Article 7. Unless otherwise   
agreed by the Connecting Transmission Owner and NYISO approved meter service provider and   
Interconnection Customer, the Connecting Transmission Owner shall install Metering Equipment   
at the Point of Interconnection prior to any operation of the Large Generating Facility and shall   
own, operate, test and maintain such Metering Equipment. Net power flows including MW and   
MVAR, MWHR and loss profile data to and from the Large Generating Facility shall be   
measured at the Point of Interconnection. Connecting Transmission Owner shall provide   
metering quantities, in analog and/or digital form, as required, to Interconnection Customer or   
NYISO upon request. Where the Point of Interconnection for the Large Generating Facility is   
other than the generator terminal, the Interconnection Customer shall also provide gross MW and   
MVAR quantities at the generator terminal. Interconnection Customer shall bear all reasonable   
documented costs associated with the purchase, installation, operation, testing and maintenance   
of the Metering Equipment.

7.2 Check Meters.

Interconnection Customer, at its option and expense, may install and operate, on its

premises and on its side of the Point of Interconnection, one or more check meters to check

Connecting Transmission Owner’s meters. Such check meters shall be for check purposes only and shall not be used for the measurement of power flows for purposes of this Agreement, except as provided in Article 7.4 below. The check meters shall be subject at all reasonable times to   
inspection and examination by Connecting Transmission Owner or its designee. The installation, operation and maintenance thereof shall be performed entirely by Interconnection Customer in accordance with Good Utility Practice.

7.3 Standards.

Connecting Transmission Owner shall install, calibrate, and test revenue quality Metering Equipment including potential transformers and current transformers in accordance with   
applicable ANSI and PSC standards as detailed in the NYISO Control Center Communications Manual and in the NYISO Revenue Metering Requirements Manual.

7.4 Testing of Metering Equipment.

Connecting Transmission Owner shall inspect and test all of its Metering Equipment

upon installation and at least once every two (2) years thereafter. If requested to do so by

NYISO or Interconnection Customer, Connecting Transmission Owner shall, at Interconnection   
Customer’s expense, inspect or test Metering Equipment more frequently than every two (2)   
years. Connecting Transmission Owner shall give reasonable notice of the time when any

31

inspection or test shall take place, and Interconnection Customer and NYISO may have

representatives present at the test or inspection. If at any time Metering Equipment is found to   
be inaccurate or defective, it shall be adjusted, repaired or replaced at Interconnection   
Customer’s expense, in order to provide accurate metering, unless the inaccuracy or defect is due   
to Connecting Transmission Owner’s failure to maintain, then Connecting Transmission Owner   
shall pay. If Metering Equipment fails to register, or if the measurement made by Metering   
Equipment during a test varies by more than two percent from the measurement made by the   
standard meter used in the test, Connecting Transmission Owner shall adjust the measurements   
by correcting all measurements for the period during which Metering Equipment was in error by   
using Interconnection Customer’s check meters, if installed. If no such check meters are   
installed or if the period cannot be reasonably ascertained, the adjustment shall be for the period   
immediately preceding the test of the Metering Equipment equal to one-half the time from the   
date of the last previous test of the Metering Equipment. The NYISO shall reserve the right to   
review all associated metering equipment installation on the Interconnection Customer’s or   
Connecting Transmission Owner’s property at any time.

7.5 Metering Data.

At Interconnection Customer’s expense, the metered data shall be telemetered to one or   
more locations designated by Connecting Transmission Owner, Interconnection Customer and   
NYISO. Such telemetered data shall be used, under normal operating conditions, as the official   
measurement of the amount of energy delivered from the Large Generating Facility to the Point   
of Interconnection.

Article 8. Communications

8.1 Interconnection Customer Obligations.

In accordance with applicable NYISO requirements, Interconnection Customer shall   
maintain satisfactory operating communications with Connecting Transmission Owner and   
NYISO. Interconnection Customer shall provide standard voice line, dedicated voice line and   
facsimile communications at its Large Generating Facility control room or central dispatch   
facility through use of either the public telephone system, or a voice communications system that   
does not rely on the public telephone system. Interconnection Customer shall also provide the   
dedicated data circuit(s) necessary to provide Interconnection Customer data to Connecting   
Transmission Owner and NYISO as set forth in Appendix D hereto. The data circuit(s) shall   
extend from the Large Generating Facility to the location(s) specified by Connecting   
Transmission Owner and NYISO. Any required maintenance of such communications   
equipment shall be performed by Interconnection Customer. Operational communications shall   
be activated and maintained under, but not be limited to, the following events: system paralleling   
or separation, scheduled and unscheduled shutdowns, equipment clearances, and hourly and   
daily load data.

8.2 Remote Terminal Unit.

Prior to the Initial Synchronization Date of the Large Generating Facility, a Remote   
Terminal Unit, or equivalent data collection and transfer equipment acceptable to the Parties,

32

shall be installed by Interconnection Customer, or by Connecting Transmission Owner at

Interconnection Customer’s expense, to gather accumulated and instantaneous data to be

telemetered to the location(s) designated by Connecting Transmission Owner through use of a dedicated point-to-point data circuit(s) as indicated in Article 8.1. The communication protocol for the data circuit(s) shall be specified by Connecting Transmission Owner. Instantaneous bidirectional analog real power and reactive power flow information must be telemetered directly to the location(s) specified by Connecting Transmission Owner.

Each Party will promptly advise the appropriate other Party if it detects or otherwise learns of any metering, telemetry or communications equipment errors or malfunctions that require the attention and/or correction by that other Party. The Party owning such equipment shall correct such error or malfunction as soon as reasonably feasible.

8.3 No Annexation.

Any and all equipment placed on the premises of a Party shall be and remain the property of the Party providing such equipment regardless of the mode and manner of annexation or   
attachment to real property, unless otherwise mutually agreed by the Party providing such   
equipment and the Party receiving such equipment.

Article 9. OPERATIONS

9.1 General.

Each Party shall comply with Applicable Laws and Regulations and Applicable

Reliability Standards. Each Party shall provide to the other Party and the NYISO all information that may reasonably be required by the other Party and the NYISO to comply with Applicable Laws and Regulations and Applicable Reliability Standards.

9.2 NYISO and Connecting Transmission Owner Obligations.

Connecting Transmission Owner and NYISO shall cause the New York State

Transmission System and the Connecting Transmission Owner’s Attachment Facilities to be   
operated, maintained and controlled in a safe and reliable manner in accordance with this   
Agreement and the NYISO Tariffs. Connecting Transmission Owner and NYISO may provide   
operating instructions to Interconnection Customer consistent with this Agreement, NYISO   
procedures and Connecting Transmission Owner’s operating protocols and procedures as they   
may change from time to time. Connecting Transmission Owner and NYISO will consider   
changes to their respective operating protocols and procedures proposed by Interconnection   
Customer.

9.3 Interconnection Customer Obligations.

Interconnection Customer shall at its own expense operate, maintain and control the

Large Generating Facility and the Interconnection Customer Attachment Facilities in a safe and reliable manner and in accordance with this Agreement. Interconnection Customer shall operate the Large Generating Facility and the Interconnection Customer Attachment Facilities in   
accordance with NYISO and Connecting Transmission Owner requirements, as such

33

requirements are set forth or referenced in Appendix C hereto. Appendix C will be modified to reflect changes to the requirements as they may change from time to time. Any Party may   
request that the appropriate other Party or Parties provide copies of the requirements set forth or referenced in Appendix C hereto.

9.4 Start-Up and Synchronization.

Consistent with the mutually acceptable procedures of the Interconnection Customer and   
Connecting Transmission Owner, the Interconnection Customer is responsible for the proper   
synchronization of the Large Generating Facility to the New York State Transmission System in   
accordance with NYISO and Connecting Transmission Owner procedures and requirements.

9.5 Real and Reactive Power Control.

9.5.1 Power Factor Design Criteria.

Interconnection Customer shall design the Large Generating Facility to maintain an

effective power delivery at demonstrated maximum net capability at the Point of Interconnection at a power factor within the range established by the Connecting Transmission Owner on a   
comparable basis, until NYISO has established different requirements that apply to all generators in the New York Control Area on a comparable basis.

The Interconnection Customer shall design and maintain the plant auxiliary systems to operate safely throughout the entire real and reactive power design range.

The Connecting Transmission Owner shall not unreasonably restrict or condition the reactive power production or absorption of the Large Generating Facility in accordance with Good Utility Practice.

9.5.2 Voltage Schedules.

Once the Interconnection Customer has synchronized the Large Generating Facility with   
the New York State Transmission System, NYISO shall require Interconnection Customer to   
operate the Large Generating Facility to produce or absorb reactive power within the design   
capability of the Large Generating Facility set forth in Article 9.5.1 (Power Factor Design   
Criteria). NYISO’s voltage schedules shall treat all sources of reactive power in the New York   
Control Area in an equitable and not unduly discriminatory manner. NYISO shall exercise   
Reasonable Efforts to provide Interconnection Customer with such schedules in accordance with   
NYISO procedures, and may make changes to such schedules as necessary to maintain the   
reliability of the New York State Transmission System. Interconnection Customer shall operate   
the Large Generating Facility to maintain the specified output voltage or power factor at the   
Point of Interconnection within the design capability of the Large Generating Facility set forth in   
Article 9.5.1 (Power Factor Design Criteria) as directed by the Connecting Transmission   
Owner’s System Operator or the NYISO. If Interconnection Customer is unable to maintain the   
specified voltage or power factor, it shall promptly notify NYISO.

34

9.5.3 Payment for Reactive Power.

NYISO shall pay Interconnection Customer for reactive power or voltage support service that Interconnection Customer provides from the Large Generating Facility in accordance with the provisions of Rate Schedule 2 of the NYISO Services Tariff.

9.5.4 Governors and Regulators.

Whenever the Large Generating Facility is operated in parallel with the New York State   
Transmission System, the turbine speed governors and automatic voltage regulators shall be in   
automatic operation at all times. If the Large Generating Facility’s speed governors or automatic   
voltage regulators are not capable of such automatic operation, the Interconnection Customer   
shall immediately notify NYISO, or its designated representative, and ensure that such Large   
Generating Facility’s real and reactive power are within the design capability of the Large   
Generating Facility’s generating unit(s) and steady state stability limits and NYISO system   
operating (thermal, voltage and transient stability) limits. Interconnection Customer shall not   
cause its Large Generating Facility to disconnect automatically or instantaneously from the New   
York State Transmission System or trip any generating unit comprising the Large Generating   
Facility for an under or over frequency condition unless the abnormal frequency condition   
persists for a time period beyond the limits set forth in ANSI/IEEE Standard C37.106, or such   
other standard as applied to other generators in the New York Control Area on a comparable   
basis.

9.6 Outages and Interruptions.

9.6.1 Outages.

9.6.1.1 Outage Authority and Coordination. Interconnection Customer and

Connecting Transmission Owner may each, in accordance with NYISO procedures and Good   
Utility Practice and in coordination with the other Party, remove from service any of its   
respective Attachment Facilities or System Upgrade Facilities and System Deliverability   
Upgrades that may impact the other Party’s facilities as necessary to perform maintenance or   
testing or to install or replace equipment. Absent an Emergency State, the Party scheduling a   
removal of such facility(ies) from service will use Reasonable Efforts to schedule such removal   
on a date and time mutually acceptable to both the Interconnection Customer and the Connecting   
Transmission Owner. In all circumstances either Party planning to remove such facility(ies)   
from service shall use Reasonable Efforts to minimize the effect on the other Party of such   
removal.

9.6.1.2 Outage Schedules. The Connecting Transmission Owner shall post scheduled   
outages of its transmission facilities on the NYISO OASIS. Interconnection Customer shall   
submit its planned maintenance schedules for the Large Generating Facility to Connecting   
Transmission Owner and NYISO for a minimum of a rolling thirty-six month period.   
Interconnection Customer shall update its planned maintenance schedules as necessary. NYISO   
may direct, or the Connecting Transmission Owner may request, Interconnection Customer to   
reschedule its maintenance as necessary to maintain the reliability of the New York State   
Transmission System. Compensation to Interconnection Customer for any additional direct costs

35

that the Interconnection Customer incurs as a result of rescheduling maintenance, including any   
additional overtime, breaking of maintenance contracts or other costs above and beyond the cost   
the Interconnection Customer would have incurred absent the request to reschedule maintenance,   
shall be in accordance with the NYISO OATT. Interconnection Customer will not be eligible to   
receive compensation, if during the twelve (12) months prior to the date of the scheduled   
maintenance, the Interconnection Customer had modified its schedule of maintenance activities   
other than at the direction of the NYISO or request of the Connecting Transmission Owner.

9.6.1.3 Outage Restoration. If an outage on the Attachment Facilities or System

Upgrade Facilities or System Deliverability Upgrades of the Connecting Transmission Owner or Interconnection Customer adversely affects the other Party’s operations or facilities, the Party that owns the facility that is out of service shall use Reasonable Efforts to promptly restore such facility(ies) to a normal operating condition consistent with the nature of the outage. The Party that owns the facility that is out of service shall provide the other Party and NYISO, to the extent such information is known, information on the nature of the Emergency State, an estimated time of restoration, and any corrective actions required. Initial verbal notice shall be followed up as soon as practicable with written notice explaining the nature of the outage.

9.6.2 Interruption of Service. If required by Good Utility Practice or Applicable Reliability Standards to do so, the NYISO or Connecting Transmission Owner may require   
Interconnection Customer to interrupt or reduce production of electricity if such production of electricity could adversely affect the ability of NYISO and Connecting Transmission Owner to perform such activities as are necessary to safely and reliably operate and maintain the New York State Transmission System. The following provisions shall apply to any interruption or reduction permitted under this Article 9.6.2:

9.6.2.1 The interruption or reduction shall continue only for so long as reasonably necessary under Good Utility Practice;

9.6.2.2 Any such interruption or reduction shall be made on an equitable, non-

discriminatory basis with respect to all generating facilities directly connected to the New York State Transmission System;

9.6.2.3 When the interruption or reduction must be made under circumstances which do not allow for advance notice, NYISO or Connecting Transmission Owner shall notify   
Interconnection Customer by telephone as soon as practicable of the reasons for the curtailment, interruption, or reduction, and, if known, its expected duration. Telephone notification shall be followed by written notification as soon as practicable;

9.6.2.4 Except during the existence of an Emergency State, when the interruption or

reduction can be scheduled without advance notice, NYISO or Connecting Transmission Owner   
shall notify Interconnection Customer in advance regarding the timing of such scheduling and   
further notify Interconnection Customer of the expected duration. NYISO or Connecting   
Transmission Owner shall coordinate with each other and the Interconnection Customer using   
Good Utility Practice to schedule the interruption or reduction during periods of least impact to   
the Interconnection Customer, the Connecting Transmission Owner and the New York State   
Transmission System;

36

9.6.2.5 The Parties shall cooperate and coordinate with each other to the extent

necessary in order to restore the Large Generating Facility, Attachment Facilities, and the New York State Transmission System to their normal operating state, consistent with system   
conditions and Good Utility Practice.

9.6.3 Under-Frequency and Over Frequency Conditions.

The New York State Transmission System is designed to automatically activate a load-  
shed program as required by the NPCC in the event of an under-frequency system disturbance.   
Interconnection Customer shall implement under-frequency and over-frequency relay set points   
for the Large Generating Facility as required by the NPCC to ensure “ride through” capability of   
the New York State Transmission System. Large Generating Facility response to frequency   
deviations of predetermined magnitudes, both under-frequency and over-frequency deviations,   
shall be studied and coordinated with the NYISO and Connecting Transmission Owner in   
accordance with Good Utility Practice. The term “ride through” as used herein shall mean the   
ability of a Generating Facility to stay connected to and synchronized with the New York State   
Transmission System during system disturbances within a range of under-frequency and over-  
frequency conditions, in accordance with Good Utility Practice and with NPCC Regional   
Reliability Reference Directory # 12.

9.6.4 System Protection and Other Control Requirements.

9.6.4.1 System Protection Facilities. Interconnection Customer shall, at its expense, install, operate and maintain System Protection Facilities as a part of the Large Generating   
Facility or Interconnection Customer Attachment Facilities. Connecting Transmission Owner shall install at Interconnection Customer’s expense any System Protection Facilities that may be required on the Connecting Transmission Owner Attachment Facilities or the New York State Transmission System as a result of the interconnection of the Large Generating Facility and   
Interconnection Customer Attachment Facilities.

9.6.4.2 The protection facilities of both the Interconnection Customer and Connecting Transmission Owner shall be designed and coordinated with other systems in accordance with Good Utility Practice and Applicable Reliability Standards.

9.6.4.3 The Interconnection Customer and Connecting Transmission Owner shall each be responsible for protection of its respective facilities consistent with Good Utility Practice and Applicable Reliability Standards.

9.6.4.4 The protective relay design of the Interconnection Customer and Connecting   
Transmission Owner shall each incorporate the necessary test switches to perform the tests   
required in Article 6 of this Agreement. The required test switches will be placed such that they allow operation of lockout relays while preventing breaker failure schemes from operating and   
causing unnecessary breaker operations and/or the tripping of the Interconnection Customer’s   
Large Generating Facility.

37

9.6.4.5 The Interconnection Customer and Connecting Transmission Owner will each test, operate and maintain System Protection Facilities in accordance with Good Utility Practice and NPCC criteria.

9.6.4.6 Prior to the In-Service Date, and again prior to the Commercial Operation Date,   
the Interconnection Customer and Connecting Transmission Owner shall each perform, or their   
agents shall perform, a complete calibration test and functional trip test of the System Protection   
Facilities. At intervals suggested by Good Utility Practice and following any apparent   
malfunction of the System Protection Facilities, the Interconnection Customer and Connecting   
Transmission Owner shall each perform both calibration and functional trip tests of its System   
Protection Facilities. These tests do not require the tripping of any in-service generation unit.   
These tests do, however, require that all protective relays and lockout contacts be activated.

9.6.5 Requirements for Protection.

In compliance with NPCC requirements and Good Utility Practice, Interconnection

Customer shall provide, install, own, and maintain relays, circuit breakers and all other devices   
necessary to remove any fault contribution of the Large Generating Facility to any short circuit   
occurring on the New York State Transmission System not otherwise isolated by Connecting   
Transmission Owner’s equipment, such that the removal of the fault contribution shall be   
coordinated with the protective requirements of the New York State Transmission System. Such   
protective equipment shall include, without limitation, a disconnecting device or switch with   
load-interrupting capability located between the Large Generating Facility and the New York   
State Transmission System at a site selected upon mutual agreement (not to be unreasonably   
withheld, conditioned or delayed) of the Interconnection Customer and Connecting Transmission   
Owner. Interconnection Customer shall be responsible for protection of the Large Generating   
Facility and Interconnection Customer’s other equipment from such conditions as negative   
sequence currents, over- or under-frequency, sudden load rejection, over- or under-voltage, and   
generator loss-of-field. Interconnection Customer shall be solely responsible to disconnect the   
Large Generating Facility and Interconnection Customer’s other equipment if conditions on the   
New York State Transmission System could adversely affect the Large Generating Facility.

9.6.6 Power Quality.

Neither the facilities of Interconnection Customer nor the facilities of Connecting

Transmission Owner shall cause excessive voltage flicker nor introduce excessive distortion to   
the sinusoidal voltage or current waves as defined by ANSI Standard C84.1-1989, in accordance   
with IEEE Standard 519, or any applicable superseding electric industry standard. In the event   
of a conflict between ANSI Standard C84.1-1989, or any applicable superseding electric industry   
standard, ANSI Standard C84.1-1989, or the applicable superseding electric industry standard,   
shall control.

9.7 Switching and Tagging Rules.

The Interconnection Customer and Connecting Transmission Owner shall each provide   
the other Party a copy of its switching and tagging rules that are applicable to the other Party’s   
activities. Such switching and tagging rules shall be developed on a nondiscriminatory basis.

38

The Parties shall comply with applicable switching and tagging rules, as amended from time to time, in obtaining clearances for work or for switching operations on equipment.

9.8 Use of Attachment Facilities by Third Parties.

9.8.1 Purpose of Attachment Facilities.

Except as may be required by Applicable Laws and Regulations, or as otherwise agreed to among the Parties, the Attachment Facilities shall be constructed for the sole purpose of interconnecting the Large Generating Facility to the New York State Transmission System and shall be used for no other purpose.

9.8.2 Third Party Users.

If required by Applicable Laws and Regulations or if the Parties mutually agree, such   
agreement not to be unreasonably withheld, to allow one or more third parties to use the   
Connecting Transmission Owner’s Attachment Facilities, or any part thereof, Interconnection   
Customer will be entitled to compensation for the capital expenses it incurred in connection with   
the Attachment Facilities based upon the pro rata use of the Attachment Facilities by Connecting   
Transmission Owner, all third party users, and Interconnection Customer, in accordance with   
Applicable Laws and Regulations or upon some other mutually-agreed upon methodology. In   
addition, cost responsibility for ongoing costs, including operation and maintenance costs   
associated with the Attachment Facilities, will be allocated between Interconnection Customer   
and any third party users based upon the pro rata use of the Attachment Facilities by Connecting   
Transmission Owner, all third party users, and Interconnection Customer, in accordance with   
Applicable Laws and Regulations or upon some other mutually agreed upon methodology. If the   
issue of such compensation or allocation cannot be resolved through such negotiations, it shall be   
submitted to FERC for resolution.

9.9 Disturbance Analysis Data Exchange.

The Parties will cooperate with one another and the NYISO in the analysis of

disturbances to either the Large Generating Facility or the New York State Transmission System   
by gathering and providing access to any information relating to any disturbance, including   
information from disturbance recording equipment, protective relay targets, breaker operations   
and sequence of events records, and any disturbance information required by Good Utility   
Practice.

Article 10. Maintenance

10.1 Connecting Transmission Owner Obligations.

Connecting Transmission Owner shall maintain its transmission facilities and Attachment Facilities in a safe and reliable manner and in accordance with this Agreement.

39

10.2 Interconnection Customer Obligations.

Interconnection Customer shall maintain its Large Generating Facility and Attachment Facilities in a safe and reliable manner and in accordance with this Agreement.

10.3 Coordination.

The Interconnection Customer and Connecting Transmission Owner shall confer

regularly to coordinate the planning, scheduling and performance of preventive and corrective maintenance on the Large Generating Facility and the Attachment Facilities. The   
Interconnection Customer and Connecting Transmission Owner shall keep NYISO fully   
informed of the preventive and corrective maintenance that is planned, and shall schedule all such maintenance in accordance with NYISO procedures.

10.4 Secondary Systems.

The Interconnection Customer and Connecting Transmission Owner shall each cooperate   
with the other in the inspection, maintenance, and testing of control or power circuits that operate   
below 600 volts, AC or DC, including, but not limited to, any hardware, control or protective   
devices, cables, conductors, electric raceways, secondary equipment panels, transducers,   
batteries, chargers, and voltage and current transformers that directly affect the operation of   
Interconnection Customer or Connecting Transmission Owner’s facilities and equipment which   
may reasonably be expected to impact the other Party. The Interconnection Customer and   
Connecting Transmission Owner shall each provide advance notice to the other Party, and to   
NYISO, before undertaking any work on such circuits, especially on electrical circuits involving   
circuit breaker trip and close contacts, current transformers, or potential transformers.

10.5 Operating and Maintenance Expenses.

Subject to the provisions herein addressing the use of facilities by others, and except for   
operations and maintenance expenses associated with modifications made for providing   
interconnection or transmission service to a third party and such third party pays for such   
expenses, Interconnection Customer shall be responsible for all reasonable expenses including   
overheads, associated with: (1) owning, operating, maintaining, repairing, and replacing   
Interconnection Customer Attachment Facilities; and (2) operation, maintenance, repair and   
replacement of Connecting Transmission Owner’s Attachment Facilities. The Connecting   
Transmission Owner shall be entitled to the recovery of incremental operating and maintenance   
expenses that it incurs associated with System Upgrade Facilities and System Deliverability   
Upgrades if and to the extent provided for under Attachment S to the NYISO OATT.

Article 11. Performance Obligation

11.1 Interconnection Customer Attachment Facilities.

Interconnection Customer shall design, procure, construct, install, own and/or control the   
Interconnection Customer Attachment Facilities described in Appendix A hereto, at its sole   
expense.

40

11.2 Connecting Transmission Owner’s Attachment Facilities.

Connecting Transmission Owner shall design, procure, construct, install, own and/or control the Connecting Transmission Owner’s Attachment Facilities described in Appendix A hereto, at the sole expense of the Interconnection Customer.

11.3 System Upgrade Facilities and System Deliverability Upgrades.

Connecting Transmission Owner shall design, procure, construct, install, and own the

System Upgrade Facilities and System Deliverability Upgrades described in Appendix A hereto. The responsibility of the Interconnection Customer for costs related to System Upgrade Facilities and System Deliverability Upgrades shall be determined in accordance with the provisions of Attachment S to the NYISO OATT.

11.4 Special Provisions for Affected Systems.

For the re-payment of amounts advanced to Affected System Operator for System

Upgrade Facilities or System Deliverability Upgrades, the Interconnection Customer and

Affected System Operator shall enter into an agreement that provides for such re-payment, but   
only if responsibility for the cost of such System Upgrade Facilities or System Deliverability   
Upgrades is not to be allocated in accordance with Attachment S to the NYISO OATT. The   
agreement shall specify the terms governing payments to be made by the Interconnection   
Customer to the Affected System Operator as well as the re-payment by the Affected System   
Operator.

11.5 Provision of Security.

At least thirty (30) Calendar Days prior to the commencement of the procurement,

installation, or construction of a discrete portion of a Connecting Transmission Owner’s

Attachment Facilities, Interconnection Customer shall provide Connecting Transmission Owner,   
at Interconnection Customer’s option, a guarantee, a surety bond, letter of credit or other form of   
security that is reasonably acceptable to Connecting Transmission Owner and is consistent with   
the Uniform Commercial Code of the jurisdiction identified in Article 14.2.1 of this Agreement.   
Such security for payment shall be in an amount sufficient to cover the cost for the   
Interconnection Customer’s share of constructing, procuring and installing the applicable portion   
of Connecting Transmission Owner’s Attachment Facilities, and shall be reduced on a dollar-for-  
dollar basis for payments made to Connecting Transmission Owner for these purposes.

In addition:

11.5.1 The guarantee must be made by an entity that meets the commercially

reasonable creditworthiness requirements of Connecting Transmission Owner, and contains terms and conditions that guarantee payment of any amount that may be due from   
Interconnection Customer, up to an agreed-to maximum amount.

41

11.5.2 The letter of credit must be issued by a financial institution reasonably

acceptable to Connecting Transmission Owner and must specify a reasonable expiration date.

11.5.3 The surety bond must be issued by an insurer reasonably acceptable to Connecting Transmission Owner and must specify a reasonable expiration date.

11.5.4 Attachment S to the NYISO OATT shall govern the Security that

Interconnection Customer provides for System Upgrade Facilities and System Deliverability Upgrades.

11.6 Interconnection Customer Compensation for Emergency Services.

If, during an Emergency State, the Interconnection Customer provides services at the

request or direction of the NYISO or Connecting Transmission Owner, the Interconnection

Customer will be compensated for such services in accordance with the NYISO Services Tariff.

11.7 Line Outage Costs.

Notwithstanding anything in the NYISO OATT to the contrary, the Connecting

Transmission Owner may propose to recover line outage costs associated with the installation of Connecting Transmission Owner’s Attachment Facilities or System Upgrade Facilities or System Deliverability Upgrades on a case-by-case basis.

ARTICLE 12. INVOICE

12.1 General.

The Interconnection Customer and Connecting Transmission Owner shall each submit to the other Party, on a monthly basis, invoices of amounts due for the preceding month. Each   
invoice shall state the month to which the invoice applies and fully describe the services and   
equipment provided. The Interconnection Customer and Connecting Transmission Owner may discharge mutual debts and payment obligations due and owing to each other on the same date through netting, in which case all amounts one Party owes to the other Party under this   
Agreement, including interest payments or credits, shall be netted so that only the net amount remaining due shall be paid by the owing Party.

12.2 Final Invoice.

Within six months after completion of the construction of the Connecting Transmission   
Owner’s Attachment Facilities and the System Upgrade Facilities and System Deliverability   
Upgrades, Connecting Transmission Owner shall provide an invoice of the final cost of the   
construction of the Connecting Transmission Owner’s Attachment Facilities and the System   
Upgrade Facilities and System Deliverability Upgrades, determined in accordance with   
Attachment S to the NYISO OATT, and shall set forth such costs in sufficient detail to enable   
Interconnection Customer to compare the actual costs with the estimates and to ascertain   
deviations, if any, from the cost estimates. Connecting Transmission Owner shall refund to   
Interconnection Customer any amount by which the actual payment by Interconnection

42

Customer for estimated costs exceeds the actual costs of construction within thirty (30) Calendar Days of the issuance of such final construction invoice.

12.3 Payment.

Invoices shall be rendered to the paying Party at the address specified in Appendix F

hereto. The Party receiving the invoice shall pay the invoice within thirty (30) Calendar Days of   
receipt. All payments shall be made in immediately available funds payable to the other Party,   
or by wire transfer to a bank named and account designated by the invoicing Party. Payment of   
invoices will not constitute a waiver of any rights or claims the paying Party may have under this   
Agreement.

12.4 Disputes.

In the event of a billing dispute between Connecting Transmission Owner and

Interconnection Customer, Connecting Transmission Owner shall continue to perform under this   
Agreement as long as Interconnection Customer: (i) continues to make all payments not in   
dispute; and (ii) pays to Connecting Transmission Owner or into an independent escrow account   
the portion of the invoice in dispute, pending resolution of such dispute. If Interconnection   
Customer fails to meet these two requirements for continuation of service, then Connecting   
Transmission Owner may provide notice to Interconnection Customer of a Default pursuant to   
Article 17. Within thirty (30) Calendar Days after the resolution of the dispute, the Party that   
owes money to the other Party shall pay the amount due with interest calculated in accord with   
the methodology set forth in FERC’s Regulations at 18 C.F.R. § 35.19a(a)(2)(iii).

ARTICLE 13. EMERGENCIES

13.1 Obligations.

Each Party shall comply with the Emergency State procedures of NYISO, the applicable Reliability Councils, Applicable Laws and Regulations, and any emergency procedures agreed to by the NYISO Operating Committee.

13.2 Notice.

NYISO or, as applicable, Connecting Transmission Owner shall notify Interconnection   
Customer promptly when it becomes aware of an Emergency State that affects the Connecting   
Transmission Owner’s Attachment Facilities or the New York State Transmission System that   
may reasonably be expected to affect Interconnection Customer’s operation of the Large   
Generating Facility or the Interconnection Customer’s Attachment Facilities. Interconnection   
Customer shall notify NYISO and Connecting Transmission Owner promptly when it becomes   
aware of an Emergency State that affects the Large Generating Facility or the Interconnection   
Customer Attachment Facilities that may reasonably be expected to affect the New York State   
Transmission System or the Connecting Transmission Owner’s Attachment Facilities. To the   
extent information is known, the notification shall describe the Emergency State, the extent of   
the damage or deficiency, the expected effect on the operation of Interconnection Customer’s or   
Connecting Transmission Owner’s facilities and operations, its anticipated duration and the

43

corrective action taken and/or to be taken. The initial notice shall be followed as soon as practicable with written notice.

13.3 Immediate Action.

Unless, in Interconnection Customer’s reasonable judgment, immediate action is

required, Interconnection Customer shall obtain the consent of Connecting Transmission Owner, such consent to not be unreasonably withheld, prior to performing any manual switching   
operations at the Large Generating Facility or the Interconnection Customer Attachment   
Facilities in response to an Emergency State either declared by NYISO, Connecting   
Transmission Owner or otherwise regarding New York State Transmission System.

13.4 NYISO and Connecting Transmission Owner Authority.

13.4.1 General.

NYISO or Connecting Transmission Owner may take whatever actions with regard to the   
New York State Transmission System or the Connecting Transmission Owner’s Attachment   
Facilities it deems necessary during an Emergency State in order to (i) preserve public health and   
safety, (ii) preserve the reliability of the New York State Transmission System or the Connecting   
Transmission Owner’s Attachment Facilities, (iii) limit or prevent damage, and (iv) expedite   
restoration of service.

NYISO and Connecting Transmission Owner shall use Reasonable Efforts to minimize   
the effect of such actions or inactions on the Large Generating Facility or the Interconnection   
Customer Attachment Facilities. NYISO or Connecting Transmission Owner may, on the basis   
of technical considerations, require the Large Generating Facility to mitigate an Emergency State   
by taking actions necessary and limited in scope to remedy the Emergency State, including, but   
not limited to, directing Interconnection Customer to shut-down, start-up, increase or decrease   
the real or reactive power output of the Large Generating Facility; implementing a reduction or   
disconnection pursuant to Article 13.4.2; directing the Interconnection Customer to assist with   
blackstart (if available) or restoration efforts; or altering the outage schedules of the Large   
Generating Facility and the Interconnection Customer Attachment Facilities. Interconnection   
Customer shall comply with all of the NYISO and Connecting Transmission Owner’s operating   
instructions concerning Large Generating Facility real power and reactive power output within   
the manufacturer’s design limitations of the Large Generating Facility’s equipment that is in   
service and physically available for operation at the time, in compliance with Applicable Laws   
and Regulations.

13.4.2 Reduction and Disconnection.

NYISO or Connecting Transmission Owner may reduce Capacity Resource

Interconnection Service and Energy Resource Interconnection Service or disconnect the Large   
Generating Facility or the Interconnection Customer’s Attachment Facilities, when such   
reduction or disconnection is necessary under Good Utility Practice due to an Emergency State.   
These rights are separate and distinct from any right of Curtailment of NYISO pursuant to the   
NYISO OATT. When NYISO or Connecting Transmission Owner can schedule the reduction or

44

disconnection in advance, NYISO or Connecting Transmission Owner shall notify

Interconnection Customer of the reasons, timing and expected duration of the reduction or

disconnection. NYISO or Connecting Transmission Owner shall coordinate with the

Interconnection Customer using Good Utility Practice to schedule the reduction or disconnection   
during periods of least impact to the Interconnection Customer and the New York State   
Transmission System. Any reduction or disconnection shall continue only for so long as   
reasonably necessary under Good Utility Practice. The Parties shall cooperate with each other to   
restore the Large Generating Facility, the Attachment Facilities, and the New York State   
Transmission System to their normal operating state as soon as practicable consistent with Good   
Utility Practice.

13.5 Interconnection Customer Authority.

Consistent with Good Utility Practice and this Agreement, the Interconnection Customer   
may take whatever actions or inactions with regard to the Large Generating Facility or the   
Interconnection Customer Attachment Facilities during an Emergency State in order to (i)   
preserve public health and safety, (ii) preserve the reliability of the Large Generating Facility or   
the Interconnection Customer Attachment Facilities, (iii) limit or prevent damage, and (iv)   
expedite restoration of service. Interconnection Customer shall use Reasonable Efforts to   
minimize the effect of such actions or inactions on the New York State Transmission System and   
the Connecting Transmission Owner’s Attachment Facilities. NYISO and Connecting   
Transmission Owner shall use Reasonable Efforts to assist Interconnection Customer in such   
actions.

13.6 Limited Liability.

Except as otherwise provided in Article 11.6 of this Agreement, no Party shall be liable   
to another Party for any action it takes in responding to an Emergency State so long as such   
action is made in good faith and is consistent with Good Utility Practice and the NYISO Tariffs.

Article 14. Regulatory Requirements And Governing Law

14.1 Regulatory Requirements.

Each Party’s obligations under this Agreement shall be subject to its receipt of any

required approval or certificate from one or more Governmental Authorities in the form and

substance satisfactory to the applying Party, or the Party making any required filings with, or

providing notice to, such Governmental Authorities, and the expiration of any time period

associated therewith. Each Party shall in good faith seek and use its Reasonable Efforts to obtain such other approvals. Nothing in this Agreement shall require Interconnection Customer to take any action that could result in its inability to obtain, or its loss of, status or exemption under the Federal Power Act or the Public Utility Holding Company Act of 2005 or the Public Utility   
Regulatory Policies Act of 1978, as amended.

14.2 Governing Law.

45

14.2.1 The validity, interpretation and performance of this Agreement and each of its

provisions shall be governed by the laws of the state of New York, without regard to its conflicts of law principles.

14.2.2 This Agreement is subject to all Applicable Laws and Regulations.

14.2.3 Each Party expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, rules, or regulations of a Governmental Authority.

Article 15. NOTICES

15.1 General.

Unless otherwise provided in this Agreement, any notice, demand or request required or   
permitted to be given by a Party to the other Party and any instrument required or permitted to be   
tendered or delivered by a Party in writing to the other Party shall be effective when delivered   
and may be so given, tendered or delivered, by recognized national courier, or by depositing the   
same with the United States Postal Service with postage prepaid, for delivery by certified or   
registered mail, addressed to the Party, or personally delivered to the Party, at the address set out   
in Appendix F hereto.

A Party may change the notice information in this Agreement by giving five (5) Business Days written notice prior to the effective date of the change.

15.2 Billings and Payments.

Billings and payments shall be sent to the addresses set out in Appendix F hereto.

15.3 Alternative Forms of Notice.

Any notice or request required or permitted to be given by a Party to the other Party and not required by this Agreement to be given in writing may be so given by telephone, facsimile or email to the telephone numbers and email addresses set out in Appendix F hereto.

15.4 Operations and Maintenance Notice.

Interconnection Customer and Connecting Transmission Owner shall each notify the other Party, and NYISO, in writing of the identity of the person(s) that it designates as the point(s) of contact with respect to the implementation of Articles 9 and 10 of this Agreement.

Article 16. Force Majeure

16.1 Force Majeure.

16.1.1 Economic hardship is not considered a Force Majeure event.

16.1.2 A Party shall not be responsible or liable, or deemed, in Default with respect to   
any obligation hereunder, (including obligations under Article 4 of this Agreement) , other than

46

the obligation to pay money when due, to the extent the Party is prevented from fulfilling such   
obligation by Force Majeure. A Party unable to fulfill any obligation hereunder (other than an   
obligation to pay money when due) by reason of Force Majeure shall give notice and the full   
particulars of such Force Majeure to the other Party in writing or by telephone as soon as   
reasonably possible after the occurrence of the cause relied upon. Telephone notices given   
pursuant to this Article shall be confirmed in writing as soon as reasonably possible and shall   
specifically state full particulars of the Force Majeure, the time and date when the Force Majeure   
occurred and when the Force Majeure is reasonably expected to cease. The Party affected shall   
exercise due diligence to remove such disability with reasonable dispatch, but shall not be   
required to accede or agree to any provision not satisfactory to it in order to settle and terminate a   
strike or other labor disturbance.

Article 17. DEFAULT

17.1 Default.

17.1.1 General.

No Breach shall exist where such failure to discharge an obligation (other than the

payment of money) is the result of Force Majeure as defined in this Agreement or the result of an   
act or omission of the other Party. Upon a Breach, the non-Breaching Parties shall give written   
notice of such to the Breaching Party. The Breaching Party shall have thirty (30) Calendar Days   
from receipt of the Breach notice within which to cure such Breach; provided however, if such   
Breach is not capable of cure within thirty (30) Calendar Days, the Breaching Party shall   
commence such cure within thirty (30) Calendar Days after notice and continuously and   
diligently complete such cure within ninety (90) Calendar Days from receipt of the Breach   
notice; and, if cured within such time, the Breach specified in such notice shall cease to exist.

17.1.2 Right to Terminate.

If a Breach is not cured as provided in this Article 17, or if a Breach is not capable of

being cured within the period provided for herein, the non-Breaching Party shall thereafter have the right to declare a Default and terminate this Agreement by written notice at any time until cure occurs, and be relieved of any further obligation hereunder and, whether or not those Parties terminate this Agreement, to recover from the defaulting Party all amounts due hereunder, plus all other damages and remedies to which they are entitled at law or in equity. The provisions of this Article will survive termination of this Agreement.

Article 18. Indemnity, Consequential Damages And Insurance

18.1 Indemnity.

Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and save

harmless, as applicable, the other Party’s (the “Indemnified Party”) from, any and all damages,   
losses, claims, including claims and actions relating to injury to or death of any person or   
damage to property, the alleged violation of any Environmental Law, or the release or threatened   
release of any Hazardous Substance, demand, suits, recoveries, costs and expenses, court costs,

47

attorney fees, and all other obligations by or to third parties, arising out of or resulting from (i) the Indemnified Party’s performance of its obligations under this Agreement on behalf of the Indemnifying Party, except in cases where the Indemnifying Party can demonstrate that the Loss of the Indemnified Party was caused by the gross negligence or intentional wrongdoing of the Indemnified Party or (ii) the violation by the Indemnifying Party of any Environmental Law or the release by the Indemnifying Party of any Hazardous Substance.

18.1.1 Indemnified Party.

If a Party is entitled to indemnification under this Article 18 as a result of a claim by a third party, and the indemnifying Party fails, after notice and reasonable opportunity to proceed under Article 18.1.3, to assume the defense of such claim, such Indemnified Party may at the expense of the Indemnifying Party contest, settle or consent to the entry of any judgment with respect to, or pay in full, such claim.

18.1.2 Indemnifying Party.

If an Indemnifying Party is obligated to indemnify and hold any Indemnified Party

harmless under this Article 18, the amount owing to the Indemnified Party shall be the amount of such Indemnified Party’s actual Loss, net of any insurance or other recovery.

18.1.3 Indemnity Procedures.

Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or investigation as to which   
the indemnity provided for in Article 18.1 may apply, the Indemnified Party shall notify the   
Indemnifying Party of such fact. Any failure of or delay in such notification shall not affect a   
Party’s indemnification obligation unless such failure or delay is materially prejudicial to the   
Indemnifying Party.

Except as stated below, the Indemnifying Party shall have the right to assume the defense   
thereof with counsel designated by such Indemnifying Party and reasonably satisfactory to the   
Indemnified Party. If the defendants in any such action include one or more Indemnified Parties   
and the Indemnifying Party and if the Indemnified Party reasonably concludes that there may be   
legal defenses available to it and/or other Indemnified Parties which are different from or   
additional to those available to the Indemnifying Party, the Indemnified Party shall have the right   
to select separate counsel to assert such legal defenses and to otherwise participate in the defense   
of such action on its own behalf. In such instances, the Indemnifying Party shall only be   
required to pay the fees and expenses of one additional attorney to represent an Indemnified   
Party or Indemnified Parties having such differing or additional legal defenses.

The Indemnified Party shall be entitled, at its expense, to participate in any such action,   
suit or proceeding, the defense of which has been assumed by the Indemnifying Party.   
Notwithstanding the foregoing, the Indemnifying Party (i) shall not be entitled to assume and   
control the defense of any such action, suit or proceedings if and to the extent that, in the opinion   
of the Indemnified Party and its counsel, such action, suit or proceeding involves the potential

48

imposition of criminal liability on the Indemnified Party, or there exists a conflict or adversity of   
interest between the Indemnified Party and the Indemnifying Party, in such event the   
Indemnifying Party shall pay the reasonable expenses of the Indemnified Party, and (ii) shall not   
settle or consent to the entry of any judgment in any action, suit or proceeding without the   
consent of the Indemnified Party, which shall not be unreasonably withheld, conditioned or   
delayed.

18.2 No Consequential Damages.

Other than the Liquidated Damages heretofore described and the indemnity obligations   
set forth in Article 18.1, in no event shall any Party be liable under any provision of this   
Agreement for any losses, damages, costs or expenses for any special, indirect, incidental,   
consequential, or punitive damages, including but not limited to loss of profit or revenue, loss of   
the use of equipment, cost of capital, cost of temporary equipment or services, whether based in   
whole or in part in contract, in tort, including negligence, strict liability, or any other theory of   
liability; provided, however, that damages for which a Party may be liable to another Party under   
separate agreement will not be considered to be special, indirect, incidental, or consequential   
damages hereunder.

18.3 Insurance.

Interconnection Customer and Connecting Transmission Owner shall each, at its own expense, maintain in force throughout the period of this Agreement, and until released by the other Party’s, the following minimum insurance coverages, with insurers authorized to do business in the state of New York:

18.3.1 Employers’ Liability and Workers’ Compensation Insurance providing statutory benefits in accordance with the laws and regulations of New York State.

18.3.2 Commercial General Liability Insurance including premises and operations,

personal injury, broad form property damage, broad form blanket contractual liability coverage   
(including coverage for the contractual indemnification) products and completed operations   
coverage, coverage for explosion, collapse and underground hazards, independent contractors   
coverage, coverage for pollution to the extent normally available and punitive damages to the   
extent normally available and a cross liability endorsement, with minimum limits of One Million   
Dollars ($1,000,000) per occurrence/One Million Dollars ($1,000,000) aggregate combined   
single limit for personal injury, bodily injury, including death and property damage.

49

18.3.3 Comprehensive Automobile Liability Insurance for coverage of owned and nonowned and hired vehicles, trailers or semi-trailers designed for travel on public roads, with a minimum, combined single limit of One Million Dollars ($1,000,000) per occurrence for bodily injury, including death, and property damage.

18.3.4 Excess Public Liability Insurance over and above the Employers’ Liability

Commercial General Liability and Comprehensive Automobile Liability Insurance coverage, with a minimum combined single limit of Twenty Million Dollars ($20,000,000) per   
occurrence/Twenty Million Dollars ($20,000,000) aggregate.

18.3.5 The Commercial General Liability Insurance, Comprehensive Automobile

Insurance and Excess Public Liability Insurance policies of Interconnection Customer and

Connecting Transmission Owner shall name the other Party, its parent, associated and Affiliate   
companies and their respective directors, officers, agents, servants and employees (“Other Party   
Group”) as additional insured. All policies shall contain provisions whereby the insurers waive   
all rights of subrogation in accordance with the provisions of this Agreement against the Other   
Party Group and provide thirty (30) Calendar days advance written notice to the Other Party   
Group prior to anniversary date of cancellation or any material change in coverage or condition.

18.3.6 The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Public Liability Insurance policies shall contain provisions that specify that the policies are primary and shall apply to such extent without consideration for other policies separately carried and shall state that each insured is provided coverage as though a separate policy had been issued to each, except the insurer’s liability shall not be increased beyond the amount for which the insurer would have been liable had only one insured been covered. Interconnection Customer and Connecting Transmission Owner shall each be   
responsible for its respective deductibles or retentions.

18.3.7 The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Public Liability Insurance policies, if written on a Claims First

Made Basis, shall be maintained in full force and effect for two (2) years after termination of this   
Agreement, which coverage may be in the form of tail coverage or extended reporting period   
coverage if agreed by the Interconnection Customer and Connecting Transmission Owner.

18.3.8 The requirements contained herein as to the types and limits of all insurance to be maintained by the Interconnection Customer and Connecting Transmission Owner are not intended to and shall not in any manner, limit or qualify the liabilities and obligations assumed by those Parties under this Agreement.

18.3.9 Within ten (10) days following execution of this Agreement, and as soon as

practicable after the end of each fiscal year or at the renewal of the insurance policy and in any event within ninety (90) days thereafter, Interconnection Customer and Connecting Transmission Owner shall provide certification of all insurance required in this Agreement, executed by each insurer or by an authorized representative of each insurer.

50

18.3.10 Notwithstanding the foregoing, Interconnection Customer and Connecting

Transmission Owner may each self-insure to meet the minimum insurance requirements of

Articles 18.3.2 through 18.3.8 to the extent it maintains a self-insurance program; provided that,   
such Party’s senior debt is rated at investment grade, or better, by Standard & Poor’s and that its   
self-insurance program meets the minimum insurance requirements of Articles 18.3.2 through

18.3.8. For any period of time that a Party’s senior debt is unrated by Standard & Poor’s or is   
rated at less than investment grade by Standard & Poor’s, such Party shall comply with the   
insurance requirements applicable to it under Articles 18.3.2 through 18.3.9. In the event that a   
Party is permitted to self-insure pursuant to this Article 18.3.10, it shall notify the other Party   
that it meets the requirements to self-insure and that its self-insurance program meets the   
minimum insurance requirements in a manner consistent with that specified in Article 18.3.9.

18.3.11 Interconnection Customer and Connecting Transmission Owner agree to

report to each other in writing as soon as practical all accidents or occurrences resulting in

injuries to any person, including death, and any property damage arising out of this Agreement.

Article 19. Assignment

19.1 Assignment.

This Agreement may be assigned by a Party only with the written consent of the other

Party; provided that a Party may assign this Agreement without the consent of the other Party to   
any Affiliate of the assigning Party with an equal or greater credit rating and with the legal   
authority and operational ability to satisfy the obligations of the assigning Party under this   
Agreement; provided further that a Party may assign this Agreement without the consent of the   
other Party in connection with the sale, merger, restructuring, or transfer of a substantial portion   
or all of its assets, including the Attachment Facilities it owns, so long as the assignee in such a   
transaction directly assumes in writing all rights, duties and obligations arising under this   
Agreement; and provided further that the Interconnection Customer shall have the right to assign   
this Agreement, without the consent of the NYISO or Connecting Transmission Owner, for   
collateral security purposes to aid in providing financing for the Large Generating Facility,   
provided that the Interconnection Customer will promptly notify the NYISO and Connecting   
Transmission Owner of any such assignment. Any financing arrangement entered into by the   
Interconnection Customer pursuant to this Article will provide that prior to or upon the exercise   
of the secured party’s, trustee’s or mortgagee’s assignment rights pursuant to said arrangement,   
the secured creditor, the trustee or mortgagee will notify the NYISO and Connecting   
Transmission Owner of the date and particulars of any such exercise of assignment right(s) and   
will provide the NYISO and Connecting Transmission Owner with proof that it meets the   
requirements of Articles 11.5 and 18.3. Any attempted assignment that violates this Article is   
void and ineffective. Any assignment under this Agreement shall not relieve a Party of its   
obligations, nor shall a Party’s obligations be enlarged, in whole or in part, by reason thereof.   
Where required, consent to assignment will not be unreasonably withheld, conditioned or   
delayed.

51

Article 20. Severability

20.1 Severability.

If any provision in this Agreement is finally determined to be invalid, void or

unenforceable by any court or other Governmental Authority having jurisdiction, such

determination shall not invalidate, void or make unenforceable any other provision, agreement or   
covenant of this Agreement; provided that if the Interconnection Customer (or any third party,   
but only if such third party is not acting at the direction of the Connecting Transmission Owner)   
seeks and obtains such a final determination with respect to any provision of the Alternate   
Option (Article 5.1.2), or the Negotiated Option (Article 5.1.4), then none of these provisions   
shall thereafter have any force or effect and the rights and obligations of Interconnection   
Customer and Connecting Transmission Owner shall be governed solely by the Standard Option   
(Article 5.1.1).

Article 21. Comparability

21.1 Comparability.

The Parties will comply with all applicable comparability and code of conduct laws, rules and regulations, as amended from time to time.

Article 22. Confidentiality

22.1 Confidentiality.

Certain information exchanged by the Parties during the term of this Agreement shall   
constitute confidential information (“Confidential Information”) and shall be subject to this   
Article 22.

If requested by a Party receiving information, the Party supplying the information shall provide in writing, the basis for asserting that the information referred to in this Article warrants confidential treatment, and the requesting Party may disclose such writing to the appropriate Governmental Authority. Each Party shall be responsible for the costs associated with affording confidential treatment to its information.

22.1.1 Term.

During the term of this Agreement, and for a period of three (3) years after the expiration or termination of this Agreement, except as otherwise provided in this Article 22, each Party shall hold in confidence and shall not disclose to any person Confidential Information.

22.1.2 Confidential Information.

The following shall constitute Confidential Information: (1) any non-public information   
that is treated as confidential by the disclosing Party and which the disclosing Party identifies as   
Confidential Information in writing at the time, or promptly after the time, of disclosure; or (2)

52

information designated as Confidential Information by the NYISO Code of Conduct contained in Attachment F to the NYISO OATT.

22.1.3 Scope.

Confidential Information shall not include information that the receiving Party can

demonstrate: (1) is generally available to the public other than as a result of a disclosure by the   
receiving Party; (2) was in the lawful possession of the receiving Party on a non-confidential   
basis before receiving it from the disclosing Party; (3) was supplied to the receiving Party   
without restriction by a third party, who, to the knowledge of the receiving Party after due   
inquiry, was under no obligation to the disclosing Party to keep such information confidential;

(4) was independently developed by the receiving Party without reference to Confidential

Information of the disclosing Party; (5) is, or becomes, publicly known, through no wrongful act   
or omission of the receiving Party or Breach of this Agreement; or (6) is required, in accordance   
with Article 22.1.8 of this Agreement, Order of Disclosure, to be disclosed by any Governmental   
Authority or is otherwise required to be disclosed by law or subpoena, or is necessary in any   
legal proceeding establishing rights and obligations under this Agreement. Information   
designated as Confidential Information will no longer be deemed confidential if the Party that   
designated the information as confidential notifies the other Party that it no longer is   
confidential.

22.1.4 Release of Confidential Information.

No Party shall release or disclose Confidential Information to any other person, except to   
its Affiliates (limited by FERC Standards of Conduct requirements), subcontractors, employees,   
consultants, or to parties who may be considering providing financing to or equity participation   
with Interconnection Customer, or to potential purchasers or assignees of a Party, on a need-to-  
know basis in connection with this Agreement, unless such person has first been advised of the   
confidentiality provisions of this Article 22 and has agreed to comply with such provisions.

Notwithstanding the foregoing, a Party providing Confidential Information to any person shall   
remain primarily responsible for any release of Confidential Information in contravention of this   
Article 22.

22.1.5 Rights.

Each Party retains all rights, title, and interest in the Confidential Information that each

Party discloses to the other Party. The disclosure by each Party to the other Party of Confidential Information shall not be deemed a waiver by any Party or any other person or entity of the right to protect the Confidential Information from public disclosure.

22.1.6 No Warranties.

By providing Confidential Information, no Party makes any warranties or representations   
as to its accuracy or completeness. In addition, by supplying Confidential Information, no Party   
obligates itself to provide any particular information or Confidential Information to the other

53

Party’s nor to enter into any further agreements or proceed with any other relationship or joint   
venture.

22.1.7 Standard of Care.

Each Party shall use at least the same standard of care to protect Confidential Information   
it receives as it uses to protect its own Confidential Information from unauthorized disclosure,   
publication or dissemination. Each Party may use Confidential Information solely to fulfill its   
obligations to the other Party under this Agreement or its regulatory requirements, including the   
NYISO OATT and NYISO Services Tariff. The NYISO shall, in all cases, treat the information   
it receives in accordance with the requirements of Attachment F to the NYISO OATT.

22.1.8 Order of Disclosure.

If a court or a Government Authority or entity with the right, power, and apparent

authority to do so requests or requires any Party, by subpoena, oral deposition, interrogatories,

requests for production of documents, administrative order, or otherwise, to disclose Confidential   
Information, that Party shall provide the other Party with prompt notice of such request(s) or   
requirement(s) so that the other Party may seek an appropriate protective order or waive   
compliance with the terms of this Agreement. Notwithstanding the absence of a protective order   
or waiver, the Party may disclose such Confidential Information which, in the opinion of its   
counsel, the Party is legally compelled to disclose. Each Party will use Reasonable Efforts to   
obtain reliable assurance that confidential treatment will be accorded any Confidential   
Information so furnished.

22.1.9 Termination of Agreement.

Upon termination of this Agreement for any reason, each Party shall, within ten (10)   
Calendar Days of receipt of a written request from the other Party, use Reasonable Efforts to   
destroy, erase, or delete (with such destruction, erasure, and deletion certified in writing to the   
other Party) or return to the other Party, without retaining copies thereof, any and all written or   
electronic Confidential Information received from the other Party pursuant to this Agreement.

22.1.10 Remedies.

The Parties agree that monetary damages would be inadequate to compensate a Party for   
another Party’s Breach of its obligations under this Article 22. Each Party accordingly agrees   
that the other Party shall be entitled to equitable relief, by way of injunction or otherwise, if the   
first Party Breaches or threatens to Breach its obligations under this Article 22, which equitable   
relief shall be granted without bond or proof of damages, and the receiving Party shall not plead   
in defense that there would be an adequate remedy at law. Such remedy shall not be deemed an   
exclusive remedy for the Breach of this Article 22, but shall be in addition to all other remedies   
available at law or in equity. The Parties further acknowledge and agree that the covenants

contained herein are necessary for the protection of legitimate business interests and are

reasonable in scope. No Party, however, shall be liable for indirect, incidental, or consequential

54

or punitive damages of any nature or kind resulting from or arising in connection with this Article 22.

22.1.11 Disclosure to FERC, its Staff, or a State.

Notwithstanding anything in this Article 22 to the contrary, and pursuant to 18 C.F.R.   
section 1b.20, if FERC or its staff, during the course of an investigation or otherwise, requests   
information from one of the Parties that is otherwise required to be maintained in confidence   
pursuant to this Agreement or the NYISO OATT, the Party shall provide the requested   
information to FERC or its staff, within the time provided for in the request for information. In   
providing the information to FERC or its staff, the Party must, consistent with 18 C.F.R. section   
388.112, request that the information be treated as confidential and non-public by FERC and its   
staff and that the information be withheld from public disclosure. Parties are prohibited from   
notifying the other Party to this Agreement prior to the release of the Confidential Information to   
the Commission or its staff. The Party shall notify the other Party to the Agreement when it is   
notified by FERC or its staff that a request to release Confidential Information has been received   
by FERC, at which time the Parties may respond before such information would be made public,   
pursuant to 18 C.F.R. section 388.112. Requests from a state regulatory body conducting a   
confidential investigation shall be treated in a similar manner if consistent with the applicable   
state rules and regulations. A Party shall not be liable for any losses, consequential or otherwise,   
resulting from that Party divulging Confidential Information pursuant to a FERC or state   
regulatory body request under this paragraph.

22.1.12

Except as otherwise expressly provided herein, no Party shall disclose Confidential

Information to any person not employed or retained by the Party possessing the Confidential

Information, except to the extent disclosure is (i) required by law; (ii) reasonably deemed by the   
disclosing Party to be required to be disclosed in connection with a dispute between or among   
the Parties, or the defense of litigation or dispute; (iii) otherwise permitted by consent of the   
other Party, such consent not to be unreasonably withheld; or (iv) necessary to fulfill its   
obligations under this Agreement, the NYISO OATT or the NYISO Services Tariff. Prior to any   
disclosures of a Party’s Confidential Information under this subparagraph, or if any third party or   
Governmental Authority makes any request or demand for any of the information described in   
this subparagraph, the disclosing Party agrees to promptly notify the other Party in writing and   
agrees to assert confidentiality and cooperate with the other Party in seeking to protect the   
Confidential Information from public disclosure by confidentiality agreement, protective order or   
other reasonable measures.

Article 23. Environmental Releases

23.1 Interconnection Customer and Connecting Transmission Owner Notice.

Interconnection Customer and Connecting Transmission Owner shall each notify the   
other Party, first orally and then in writing, of the release of any Hazardous Substances, any   
asbestos or lead abatement activities, or any type of remediation activities related to the Large   
Generating Facility or the Attachment Facilities, each of which may reasonably be expected to

55

affect the other Party. The notifying Party shall: (i) provide the notice as soon as practicable,

provided such Party makes a good faith effort to provide the notice no later than twenty-four hours after such Party becomes aware of the occurrence; and (ii) promptly furnish to the other Party copies of any publicly available reports filed with any Governmental Authorities   
addressing such events.

Article 24. Information Requirement

24.1 Information Acquisition.

Connecting Transmission Owner and Interconnection Customer shall each submit

specific information regarding the electrical characteristics of their respective facilities to the   
other, and to NYISO, as described below and in accordance with Applicable Reliability   
Standards.

24.2 Information Submission by Connecting Transmission Owner.

The initial information submission by Connecting Transmission Owner shall occur no   
later than one hundred eighty (180) Calendar Days prior to Trial Operation and shall include   
New York State Transmission System information necessary to allow the Interconnection   
Customer to select equipment and meet any system protection and stability requirements, unless   
otherwise mutually agreed to by the Interconnection Customer and Connecting Transmission   
Owner. On a monthly basis Connecting Transmission Owner shall provide Interconnection   
Customer and NYISO a status report on the construction and installation of Connecting   
Transmission Owner’s Attachment Facilities and System Upgrade Facilities and System   
Deliverability Upgrades, including, but not limited to, the following information: (1) progress to   
date; (2) a description of the activities since the last report; (3) a description of the action items   
for the next period; and (4) the delivery status of equipment ordered.

24.3 Updated Information Submission by Interconnection Customer.

The updated information submission by the Interconnection Customer, including

manufacturer information, shall occur no later than one hundred eighty (180) Calendar Days prior to the Trial Operation. Interconnection Customer shall submit a completed copy of the Large Generating Facility data requirements contained in Appendix 1 to the Large Facility   
Interconnection Procedures. It shall also include any additional information provided to   
Connecting Transmission Owner for the Interconnection Feasibility Study and Interconnection Facilities Study. Information in this submission shall be the most current Large Generating Facility design or expected performance data. Information submitted for stability models shall be compatible with NYISO standard models. If there is no compatible model, the   
Interconnection Customer will work with a consultant mutually agreed to by the Parties to   
develop and supply a standard model and associated information.

If the Interconnection Customer’s data is different from what was originally provided to   
Connecting Transmission Owner and NYISO pursuant to an Interconnection Study Agreement   
among Connecting Transmission Owner, NYISO and Interconnection Customer and this   
difference may be reasonably expected to affect the other Party’s facilities or the New York State

56

Transmission System, but does not require the submission of a new Interconnection Request,   
then NYISO will conduct appropriate studies to determine the impact on the New York State   
Transmission System based on the actual data submitted pursuant to this Article 24.3. Such   
studies will provide an estimate of any additional modifications to the New York State   
Transmission System, Connecting Transmission Owner’s Attachment Facilities or System   
Upgrade Facilities or System Deliverability Upgrades based on the actual data and a good faith   
estimate of the costs thereof. The Interconnection Customer shall not begin Trial Operation until   
such studies are completed. The Interconnection Customer shall be responsible for the cost of   
any modifications required by the actual data, including the cost of any required studies.

24.4 Information Supplementation.

Prior to the Commercial Operation Date, the Interconnection Customer and Connecting   
Transmission Owner shall supplement their information submissions described above in this   
Article 24 with any and all “as-built” Large Generating Facility information or “as-tested”   
performance information that differs from the initial submissions or, alternatively, written   
confirmation that no such differences exist. The Interconnection Customer shall conduct tests on the Large Generating Facility as required by Good Utility Practice such as an open circuit “step voltage” test on the Large Generating Facility to verify proper operation of the Large Generating Facility’s automatic voltage regulator.

Unless otherwise agreed, the test conditions shall include: (1) Large Generating Facility   
at synchronous speed; (2) automatic voltage regulator on and in voltage control mode; and (3) a   
five percent change in Large Generating Facility terminal voltage initiated by a change in the   
voltage regulators reference voltage. Interconnection Customer shall provide validated test   
recordings showing the responses of Large Generating Facility terminal and field voltages. In   
the event that direct recordings of these voltages is impractical, recordings of other voltages or   
currents that mirror the response of the Large Generating Facility’s terminal or field voltage are   
acceptable if information necessary to translate these alternate quantities to actual Large   
Generating Facility terminal or field voltages is provided. Large Generating Facility testing shall   
be conducted and results provided to the Connecting Transmission Owner and NYISO for each   
individual generating unit in a station.

Subsequent to the Commercial Operation Date, the Interconnection Customer shall

provide Connecting Transmission Owner and NYISO any information changes due to equipment   
replacement, repair, or adjustment. Connecting Transmission Owner shall provide the   
Interconnection Customer and NYISO any information changes due to equipment replacement,   
repair or adjustment in the directly connected substation or any adjacent Connecting   
Transmission Owner substation that may affect the Interconnection Customer Attachment   
Facilities equipment ratings, protection or operating requirements. The Interconnection   
Customer and Connecting Transmission Owner shall provide such information no later than   
thirty (30) Calendar Days after the date of the equipment replacement, repair or adjustment.

57

Article 25. Information Access and Audit Rights

25.1 Information Access.

Each Party (“Disclosing Party”) shall make available to another Party (“Requesting

Party”) information that is in the possession of the Disclosing Party and is necessary in order for   
the Requesting Party to: (i) verify the costs incurred by the Disclosing Party for which the   
Requesting Party is responsible under this Agreement; and (ii) carry out its obligations and   
responsibilities under this Agreement. The Parties shall not use such information for purposes   
other than those set forth in this Article 25.1 of this Agreement and to enforce their rights under   
this Agreement.

25.2 Reporting of Non-Force Majeure Events.

Each Party (the “Notifying Party”) shall notify the other Party when the Notifying Party becomes aware of its inability to comply with the provisions of this Agreement for a reason other than a Force Majeure event. The Parties agree to cooperate with each other and provide   
necessary information regarding such inability to comply, including the date, duration, reason for the inability to comply, and corrective actions taken or planned to be taken with respect to such inability to comply. Notwithstanding the foregoing, notification, cooperation or information   
provided under this Article shall not entitle the Party receiving such notification to allege a cause for anticipatory breach of this Agreement.

25.3 Audit Rights.

Subject to the requirements of confidentiality under Article 22 of this Agreement, each   
Party shall have the right, during normal business hours, and upon prior reasonable notice to   
another Party, to audit at its own expense the other Party’s accounts and records pertaining to the   
other Party’s performance or satisfaction of its obligations under this Agreement. Such audit   
rights shall include audits of the other Party’s costs, calculation of invoiced amounts, and each   
Party’s actions in an Emergency State. Any audit authorized by this Article shall be performed   
at the offices where such accounts and records are maintained and shall be limited to those   
portions of such accounts and records that relate to the Party’s performance and satisfaction of   
obligations under this Agreement. Each Party shall keep such accounts and records for a period   
equivalent to the audit rights periods described in Article 25.4 of this Agreement.

25.4 Audit Rights Periods.

25.4.1 Audit Rights Period for Construction-Related Accounts and Records.

Accounts and records related to the design, engineering, procurement, and construction of Connecting Transmission Owner’s Attachment Facilities and System Upgrade Facilities and   
System Deliverability Upgrades shall be subject to audit for a period of twenty-four months   
following Connecting Transmission Owner’s issuance of a final invoice in accordance with   
Article 12.2 of this Agreement.

58

25.4.2 Audit Rights Period for All Other Accounts and Records.

Accounts and records related to a Party’s performance or satisfaction of its obligations   
under this Agreement other than those described in Article 25.4.1 of this Agreement shall be   
subject to audit as follows: (i) for an audit relating to cost obligations, the applicable audit rights   
period shall be twenty-four months after the auditing Party’s receipt of an invoice giving rise to   
such cost obligations; and (ii) for an audit relating to all other obligations, the applicable audit   
rights period shall be twenty-four months after the event for which the audit is sought.

25.5 Audit Results.

If an audit by a Party determines that an overpayment or an underpayment has occurred, a notice of such overpayment or underpayment shall be given to the other Party together with   
those records from the audit which support such determination.

Article 26. Subcontractors

26.1 General.

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided, however, that each Party shall require its subcontractors to comply with all applicable terms and conditions of this Agreement in providing such services and each Party shall remain primarily liable to the other Party for the performance of such subcontractor.

26.2 Responsibility of Principal.

The creation of any subcontract relationship shall not relieve the hiring Party of any of its   
obligations under this Agreement. The hiring Party shall be fully responsible to the other Party   
for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been   
made; provided, however, that in no event shall the NYISO or Connecting Transmission Owner   
be liable for the actions or inactions of the Interconnection Customer or its subcontractors with   
respect to obligations of the Interconnection Customer under Article 5 of this Agreement. Any   
applicable obligation imposed by this Agreement upon the hiring Party shall be equally binding   
upon, and shall be construed as having application to, any subcontractor of such Party.

26.3 No Limitation by Insurance.

The obligations under this Article 26 will not be limited in any way by any limitation of subcontractor’s insurance.

Article 27. Disputes

27.1 Submission.

In the event any Party has a dispute, or asserts a claim, that arises out of or in connection   
with this Agreement or its performance (a “Dispute”), such Party shall provide the other Party

59

with written notice of the Dispute (“Notice of Dispute”). Such Dispute shall be referred to a

designated senior representative of each Party for resolution on an informal basis as promptly as practicable after receipt of the Notice of Dispute by the other Party. In the event the designated representatives are unable to resolve the Dispute through unassisted or assisted negotiations within thirty (30) Calendar Days of the other Party’s receipt of the Notice of Dispute, such   
Dispute may, upon mutual agreement of the Parties, be submitted to arbitration and resolved in accordance with the arbitration procedures set forth below. In the event the Parties do not agree to submit such Dispute to arbitration, each Party may exercise whatever rights and remedies it may have in equity or at law consistent with the terms of this Agreement.

27.2 External Arbitration Procedures.

Any arbitration initiated under this Agreement shall be conducted before a single neutral   
arbitrator appointed by the Parties. If the Parties fail to agree upon a single arbitrator within ten

(10) Calendar Days of the submission of the Dispute to arbitration, then the arbitration shall be   
conducted by a three-member arbitration panel. For purposes of the three arbitrator panel, one   
arbitrator shall be selected by Connecting Transmission Owner and one arbitrator shall be   
selected by Interconnection Customer, in each case within 20 Calendar Days of the submission   
of the Dispute to arbitration. A third arbitrator shall be selected by the first two within 10   
Calendar Days after the latter of: (a) the date Connecting Transmission Owner selected an   
arbitrator; and (b) the date Interconnection Customer selected an arbitrator. If either Connecting   
Transmission Owner or Interconnection Customer fails to make a selection of an arbitrator, then   
the arbitrator selected shall select the remaining two. If arbitrators selected by Connecting   
Transmission Owner and Interconnection Customer have not agreed on the selection of the third   
arbitrator within such 10 Calendar Day period, the third arbitrator shall be expeditiously selected   
in accordance with the rules of the American Arbitration Association.

In each case, the arbitrator(s) shall be knowledgeable in electric utility matters, including   
electric transmission and bulk power issues, and shall not have any current or past substantial   
business or financial relationships with any party to the arbitration (except prior arbitration). The   
arbitrator(s) shall provide each of the Parties an opportunity to be heard and, except as otherwise   
provided herein, shall conduct the arbitration in accordance with the Commercial Arbitration   
Rules of the American Arbitration Association (“Arbitration Rules”) and any applicable FERC   
regulations or RTO rules; provided, however, in the event of a conflict between the Arbitration   
Rules and the terms of this Article 27, the terms of this Article 27 shall prevail.

27.3 Arbitration Decisions.

Unless otherwise agreed by the Parties, the arbitrator(s) shall render a decision within

ninety (90) Calendar Days of appointment and shall notify the Parties in writing of such decision   
and the reasons therefor. The arbitrator(s) shall be authorized only to interpret and apply the   
provisions of this Agreement and shall have no power to modify or change any provision of this   
Agreement in any manner. The decision of the arbitrator(s) shall be final and binding upon the   
Parties, and judgment on the award may be entered in any court having jurisdiction. The   
decision of the arbitrator(s) may be appealed solely on the grounds that the conduct of the   
arbitrator(s), or the decision itself, violated the standards set forth in the Federal Arbitration Act   
or the Administrative Dispute Resolution Act. The final decision of the arbitrator must also be

60

filed with FERC if it affects jurisdictional rates, terms and conditions of service, Attachment Facilities, or System Upgrade Facilities, System Deliverability Upgrades.

27.4 Costs.

Each Party shall be responsible for its own costs incurred during the arbitration process   
and for the following costs, if applicable: (1) one-half of the cost of the single arbitrator jointly   
chosen by the Parties; (2) the cost of the arbitrator chosen by the Party to sit on the three-member   
panel; or (3) one‐half the cost of the third arbitrator jointly chosen by the Parties, chosen by a   
Party after the other Party’s failure to do so, or chosen under the rules of the American   
Arbitration Association.

27.5 Termination.

Notwithstanding the provisions of this Article 27, any Party may terminate this

Agreement in accordance with its provisions or pursuant to an action at law or equity. The issue of whether such a termination is proper shall not be considered a Dispute hereunder.

Article 28. Representations, Warranties And Covenants

28.1 General.

Each Party makes the following representations, warranties and covenants:

28.1.1 Good Standing.

Such Party is duly organized, validly existing and in good standing under the laws of the state in which it is organized, formed, or incorporated, as applicable; that it is qualified to do business in the state or states in which the Large Generating Facility, Attachment Facilities and System Upgrade Facilities and System Deliverability Upgrades owned by such Party, as   
applicable, are located; and that it has the corporate power and authority to own its properties, to carry on its business as now being conducted and to enter into this Agreement and carry out the transactions contemplated hereby and perform and carry out all covenants and obligations on its part to be performed under and pursuant to this Agreement.

28.1.2 Authority.

Such Party has the right, power and authority to enter into this Agreement, to become a   
Party hereto and to perform its obligations hereunder. This Agreement is a legal, valid and   
binding obligation of such Party, enforceable against such Party in accordance with its terms,   
except as the enforceability thereof may be limited by applicable bankruptcy, insolvency,   
reorganization or other similar laws affecting creditors’ rights generally and by general equitable   
principles (regardless of whether enforceability is sought in a proceeding in equity or at law).

61

28.1.3 No Conflict.

The execution, delivery and performance of this Agreement does not violate or conflict with the organizational or formation documents, or bylaws or operating agreement, of such Party, or any judgment, license, permit, order, material agreement or instrument applicable to or binding upon such Party or any of its assets.

28.1.4 Consent and Approval.

Such Party has sought or obtained, or, in accordance with this Agreement will seek or obtain, each consent, approval, authorization, order, or acceptance by any Governmental   
Authority in connection with the execution, delivery and performance of this Agreement, and it will provide to any Governmental Authority notice of any actions under this Agreement that are required by Applicable Laws and Regulations.

Article 29. Miscellaneous

29.1 Binding Effect.

This Agreement and the rights and obligations hereof, shall be binding upon and shall inure to the benefit of the successors and permitted assigns of the Parties hereto.

29.2 Conflicts.

If there is a discrepancy or conflict between or among the terms and conditions of this cover agreement and the Appendices hereto, the terms and conditions of this cover agreement shall be given precedence over the Appendices, except as otherwise expressly agreed to in   
writing by the Parties.

29.3 Rules of Interpretation.

This Agreement, unless a clear contrary intention appears, shall be construed and

interpreted as follows: (1) the singular number includes the plural number and vice versa; (2)

reference to any person includes such person’s successors and assigns but, in the case of a Party,   
only if such successors and assigns are permitted by this Agreement, and reference to a person in   
a particular capacity excludes such person in any other capacity or individually; (3) reference to   
any agreement (including this Agreement), document, instrument or tariff means such   
agreement, document, instrument, or tariff as amended or modified and in effect from time to   
time in accordance with the terms thereof and, if applicable, the terms hereof; (4) reference to   
any Applicable Laws and Regulations means such Applicable Laws and Regulations as   
amended, modified, codified, or reenacted, in whole or in part, and in effect from time to time,   
including, if applicable, rules and regulations promulgated thereunder; (5) unless expressly stated   
otherwise, reference to any Article, Section or Appendix means such Article of this Agreement   
or such Appendix to this Agreement, or such Section to the Large Facility Interconnection   
Procedures or such Appendix to the Large Facility Interconnection Procedures, as the case may   
be; (6) “hereunder”, “hereof’, “herein”, “hereto” and words of similar import shall be deemed   
references to this Agreement as a whole and not to any particular Article or other provision

62

hereof or thereof; (7) “including” (and with correlative meaning “include”) means including without limiting the generality of any description preceding such term; and (8) relative to the determination of any period of time, “from” means “from and including”, “to” means “to but excluding” and “through” means “through and including”.

29.4 Compliance.

Each Party shall perform its obligations under this Agreement in accordance with

Applicable Laws and Regulations, Applicable Reliability Standards, the NYISO OATT and Good Utility Practice. To the extent a Party is required or prevented or limited in taking any action by such regulations and standards, such Party shall not be deemed to be in Breach of this Agreement for its compliance therewith. When any Party becomes aware of such a situation, it shall notify the other Party promptly so that the Parties can discuss the amendment to this   
Agreement that is appropriate under the circumstances.

29.5 Joint and Several Obligations.

Except as otherwise stated herein, the obligations of NYISO, Interconnection Customer   
and Connecting Transmission Owner are several, and are neither joint nor joint and several.

29.6 Entire Agreement.

This Agreement, including all Appendices and Schedules attached hereto, constitutes the   
entire agreement between the Parties with reference to the subject matter hereof, and supersedes   
all prior and contemporaneous understandings or agreements, oral or written, between the Parties   
with respect to the subject matter of this Agreement. There are no other agreements,   
representations, warranties, or covenants which constitute any part of the consideration for, or   
any condition to, either Party’s compliance with its obligations under this Agreement.

29.7 No Third Party Beneficiaries.

This Agreement is not intended to and does not create rights, remedies, or benefits of any character whatsoever in favor of any persons, corporations, associations, or entities other than the Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their successors in interest and permitted their assigns.

29.8 Waiver.

The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver of any

obligation, right, or duty of, or imposed upon, such Party. Any waiver at any time by either   
Party of its rights with respect to this Agreement shall not be deemed a continuing waiver or a   
waiver with respect to any other failure to comply with any other obligation, right, duty of this   
Agreement. Termination or Default of this Agreement for any reason by the Interconnection   
Customer shall not constitute a waiver of the Interconnection Customer’s legal rights to obtain   
Capacity Resource Interconnection Service and Energy Resource Interconnection Service from   
the NYISO and Connecting Transmission Owner in accordance with the provisions of the

NYISO OATT. Any waiver of this Agreement shall, if requested, be provided in writing.

63

29.9 Headings.

The descriptive headings of the various Articles of this Agreement have been inserted for convenience of reference only and are of no significance in the interpretation or construction of this Agreement.

29.10 Multiple Counterparts.

This Agreement may be executed in two or more counterparts, each of which is deemed an original but all constitute one and the same instrument.

29.11 Amendment.

The Parties may by mutual agreement amend this Agreement, by a written instrument duly executed by all three of the Parties.

29.12 Modification by the Parties.

The Parties may by mutual agreement amend the Appendices to this Agreement, by a   
written instrument duly executed by all three of the Parties. Such an amendment shall become   
effective and a part of this Agreement upon satisfaction of all Applicable Laws and Regulations.

29.13 Reservation of Rights.

Connecting Transmission Owner shall have the right to make unilateral filings with

FERC to modify this Agreement with respect to any rates, terms and conditions, charges,

classifications of service, rule or regulation under section 205 or any other applicable provision   
of the Federal Power Act and FERC’s rules and regulations thereunder, and Interconnection   
Customer shall have the right to make a unilateral filing with FERC to modify this Agreement   
pursuant to section 206 or any other applicable provision of the Federal Power Act and FERC’s   
rules and regulations thereunder; provided that each Party shall have the right to protest any such   
filing by another Party and to participate fully in any proceeding before FERC in which such   
modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties   
or of FERC under sections 205 or 206 of the Federal Power Act and FERC’s rules and   
regulations thereunder, except to the extent that the Parties otherwise mutually agree as provided   
herein.

29.14 No Partnership.

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership among the Parties or to impose any partnership

obligation or partnership liability upon any Party. No Party shall have any right, power or

authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, any other Party.

64

29.15 Other Transmission Rights.

Notwithstanding any other provision of this Agreement, nothing herein shall be construed as relinquishing or foreclosing any rights, including but not limited to firm transmission rights, capacity rights, or transmission congestion rights that the Interconnection Customer shall be   
entitled to, now or in the future under any other agreement or tariff as a result of, or otherwise   
associated with, the transmission capacity, if any, created by the System Upgrade Facilities and System Deliverability Upgrades.

65



IN WITNESS WHEREOF, the Parties have executed this LGIA in duplicate originals, each of which shall constitute and be an original effective Agreement between the Parties.

66

APPENDICES

Appendix A

Attachment Facilities and System Upgrade Facilities

Appendix B

Milestones

Appendix C

Interconnection Details

Appendix D

Security Arrangements Details

Appendix E

Commercial Operation Date

Appendix F

Addresses for Delivery of Notices and Billings

Appendix G

Interconnection Requirements for a Wind Generating Plant

Appendix H

Operation and Maintenance

Appendix I

List of Non-Applicable Pro-Forma LGIA Provisions

APPENDIX A

Attachment Facilities and System Upgrade Facilities

1. Attachment Facilities:

(a) Interconnection Customer’s Attachment Facilities

Generating Facility produces 115kv for transmission via step-up

transformer, 13.8kv for station and all related equipment. The transmission line consists of a 115kv circuit on a double circuit tower that extends from 3 main step-up transformers to National Grid’s substation with the N Catskill V2, New Scotland #3, New Scotland #9 and Reynolds Rd #3 lines.

(b) Connecting Transmission Owner’s Attachment Facilities

Interconnection Facility switchyard at 115kv utilizing SF6 breakers,

associated revenue metering CTs and PTs, 115kv disconnect switches, wave   
traps, line tuners, CCVT’s and associated bus PTs. The switchyard connects   
from the 3 associated Attachment Facility step-up transformers to National   
Grid’s N Catskill V2, New Scotland #3, New Scotland #9 and Reynolds Rd #3   
lines.

2. System Upgrade Facilities:


a. No reinforcements or additional system upgrades are necessary to

maintain connection of the interconnection facility to the transmission

system.

3. System Deliverability Upgrades N/A

A-1



A-2

APPENDIX B   
Milestones

Generating Facility in Existence - Not Applicable

B-1

APPENDIX C

Interconnection Details

I. Description of Large Generating Facility including Point of Interconnection

The Generating Facility is a 367.733 MVA (nameplate at rated power factor) gas-fired   
combustion turbines/combined cycle facility located in Selkirk, Albany County, New York.

Interconnection Customer is extending the operational term of the Existing Facility beyond its   
initial 20 years. The Generating Facility is composed of two 105.778 MVA nameplate rated   
synchronous generators at .90 power factor each powered by two 90.120 MW Gas Turbines and   
one 156.177\_MVA nameplate rated synchronous generator at .95 power factor powered by one

96.628 MW Steam Turbine. The two gas turbines feed into one 3-winding step up transformer   
and the Steam Turbine feeds into its own 2-winding step up transformer. The step up

transformers interconnect the Generating Facility to the Connecting Transmission Owner’s   
system at 115 kV. For the avoidance of doubt, the Parties acknowledge and agree that (i) the   
Generating Facility injects power only into the Connecting Transmission Owner’s transmission   
system and injects no power into the Connecting Transmission Owner’s Distribution System;   
and (ii) the Interconnection Customer shall not be responsible for any Distribution Upgrades.

II. Developer Operating Requirements

Interconnection Customer must comply with all applicable NYISO tariffs and procedures, as amended from time to time.

Interconnection Customer must comply with Connecting Transmission Owner’s

operating instructions and requirements as set out in the most current version of National Grid’s Electric System Bulletin 756, as referenced in Article 9.3 of this Agreement, which requirements shall include the dedicated data circuits, including system protection circuits, to be maintained by Interconnection Customer in accordance with Article 8.1 of this Agreement.

With respect to Capacity Resource Interconnection Service (“CRIS”), the Large

Generating Facility has a CRIS value as of the Effective Date of 291.3 MW. Therefore, the Large Generating Facility’s CRIS value will be limited to 291.3 MW unless it is subsequently increased pursuant to an applicable provision of the NYISO OATT

C-1

APPENDIX D

Security Arrangements Details

Infrastructure security of New York State Transmission System equipment and

operations and control hardware and software is essential to ensure day-to-day New York State   
Transmission System reliability and operational security. The Commission will expect the   
NYISO, all Transmission Owners, all Interconnection Customers and all other Market   
Participants to comply with the recommendations offered by the President’s Critical   
Infrastructure Protection Board and, eventually, best practice recommendations from the electric   
reliability authority. All public utilities will be expected to meet basic standards for system   
infrastructure and operational security, including physical, operational, and cyber-security   
practices.

D-1

APPENDIX E

Commercial Operation Date

Interconnection Customer commenced Commercial Operation of the Generation Facility on January 8, 1993, the Commercial Operation Date.

E-1

APPENDIX F

Addresses for Delivery of Notices and Billings

Notices:

NYISO:

New York Independent System Operator, Inc. Attn: Vice President, Operations

3890 Carman Road

Schenectady, NY 12303   
Phone: (518) 356-6000   
Fax: (518) 356-6118

Connecting Transmission Owner:

William L. Malee

Director, Transmission Commercial National Grid

40 Sylvan Road

Waltham, MA 02451   
Phone: (781) 907-2422   
Fax: (781) 907-5707

Email: bill.malee@nationalgrid.com

Interconnection Customer:

Projects General Manager   
Selkirk Cogen Partners, LP

24 Power Park Drive   
Selkirk NY 12158   
Phone: (518) 475-5773   
Fax: (518) 428-5929

Selkirk Cogen Partners, LP

c/o Power Plant Management Services, LLC 10710 Sikes Place, Suite 300

Charlotte, NC 28277

Phone: (704) 815-8000   
Fax: (704) 815-8006   
Attn: Legal

F-1

Billings and Payments:

Connecting Transmission Owner:

William L. Malee

Director, Transmission Commercial National Grid

40 Sylvan Road

Waltham, MA 02451   
Phone: (781) 907-2422   
Fax: (781) 907-5707

Email: bill.malee@nationalgrid.com

Interconnection Customer:

Projects General Manager   
Selkirk Cogen Partners, LP

24 Power Park Drive   
Selkirk NY 12158   
Phone: (518) 475-5773   
Fax: (518) 428-5929

Selkirk Cogen Partners, LP

c/o Power Plant Management Services, LLC 10710 Sikes Place, Suite 300

Charlotte, NC 28277

Phone: (704) 815-8000   
Fax: (704) 815-8006   
Attn: Legal

Alternative Forms of Delivery of Notices (telephone, facsimile or email):

NYISO:

New York Independent System Operator, Inc. Attn: Vice President, Operations

3890 Carman Road

Schenectady, NY 12303   
Phone: (518) 356-6000   
Fax: (518) 356-6118

F-2

Connecting Transmission Owner:

William L. Malee

Director, Transmission Commercial National Grid

40 Sylvan Road

Waltham, MA 02451   
Phone: (781) 907-2422   
Fax: (781) 907-5707

Email: bill.malee@nationalgrid.com

Interconnection Customer:

Projects General Manager   
Selkirk Cogen Partners, LP

24 Power Park Drive   
Selkirk NY 12158   
Phone: (518) 475-5773   
Fax: (518) 428-5929

Selkirk Cogen Partners, LP

c/o Power Plant Management Services, LLC 10710 Sikes Place, Suite 300

Charlotte, NC 28277

Phone: (704) 815-8000   
Fax: (704) 815-8006   
Attn: Legal

F-3

APPENDIX G

INTERCONNECTION REQUIREMENTS FOR A WIND GENERATING PLANT

Appendix G sets forth requirements and provisions specific to a wind generating plant.

All other requirements of this LGIA continue to apply to wind generating plant interconnections.

A. Technical Standards Applicable to a Wind Generating Plant

i. Low Voltage Ride-Through (LVRT) Capability

A wind generating plant shall be able to remain online during voltage disturbances up to the time periods and associated voltage levels set forth in the standard below. The LVRT   
standard provides for a transition period standard and a post-transition period standard.

Transition Period LVRT Standard

The transition period standard applies to wind generating plants subject to FERC Order   
661 that have either: (i) interconnection agreements signed and filed with the Commission, filed with the Commission in unexecuted form, finally executed as conforming agreements, or filed   
with the Commission as non-conforming agreements between January 1, 2006 and December 31, 2006, with a scheduled in-service date no later than December 31, 2007, or (ii) wind   
generating turbines subject to a wind turbine procurement contract executed prior to December   
31, 2005, for delivery through 2007.

1. Wind generating plants are required to remain in-service during three-phase faults with

normal clearing (which is a time period of approximately 4 - 9 cycles) and single line to   
ground faults with delayed clearing, and subsequent post-fault voltage recovery to   
prefault voltage unless clearing the fault effectively disconnects the generator from the   
system. The clearing time requirement for a three-phase fault will be specific to the wind   
generating plant substation location, as determined by and documented by the Connecting   
Transmission Owner for the Transmission District to which the wind generating plant   
will be interconnected. The maximum clearing time the wind generating plant shall be   
required to withstand for a three-phase fault shall be 9 cycles at a voltage as low as 0.15   
p.u., as measured at the high side of the wind generating plant step-up transformer (i.e.   
the transformer that steps the voltage up to the transmission interconnection voltage or   
“GSU”), after which, if the fault remains following the location-specific normal clearing   
time for three-phase faults, the wind generating plant may disconnect from the   
transmission system.

2. This requirement does not apply to faults that would occur between the wind generator

terminals and the high side of the GSU or to faults that would result in a voltage lower than 0.15 per unit on the high side of the GSU serving the facility.

3. Wind generating plants may be tripped after the fault period if this action is intended as

part of a special protection system.

G-1

4. Wind generating plants may meet the LVRT requirements of this standard by the

performance of the generators or by installing additional equipment (e.g., Static VAr Compensator, etc.) within the wind generating plant or by a combination of generator performance and additional equipment.

5. Existing individual generator units that are, or have been, interconnected to the network

at the same location at the effective date of the Appendix G LVRT Standard are exempt from meeting the Appendix G LVRT Standard for the remaining life of the existing   
generation equipment. Existing individual generator units that are replaced are required to meet the Appendix G LVRT Standard.

Post-transition Period LVRT Standard

All wind generating plants subject to FERC Order No. 661 and not covered by the transition period described above must meet the following requirements:

1. Wind generating plants are required to remain in-service during three-phase faults with

normal clearing (which is a time period of approximately 4 - 9 cycles) and single line to   
ground faults with delayed clearing, and subsequent post-fault voltage recovery to   
prefault voltage unless clearing the fault effectively disconnects the generator from the   
system. The clearing time requirement for a three-phase fault will be specific to the wind   
generating plant substation location, as determined by and documented by the Connecting   
Transmission Owner for the Transmission District to which the wind generating plant   
will be interconnected. The maximum clearing time the wind generating plant shall be   
required to withstand for a three-phase fault shall be 9 cycles after which, if the fault   
remains following the location-specific normal clearing time for three-phase faults, the   
wind generating plant may disconnect from the transmission system. A wind generating   
plant shall remain interconnected during such a fault on the transmission system for a   
voltage level as low as zero volts, as measured at the high voltage side of the wind GSU.

2. This requirement does not apply to faults that would occur between the wind generator

terminals and the high side of the GSU.

3. Wind generating plants may be tripped after the fault period if this action is intended as

part of a special protection system.

4. Wind generating plants may meet the LVRT requirements of this standard by the

performance of the generators or by installing additional equipment (e.g., Static VAr

G-2

Compensator) within the wind generating plant or by a combination of generator performance and additional equipment.

5. Existing individual generator units that are, or have been, interconnected to the network

at the same location at the effective date of the Appendix G LVRT Standard are exempt from meeting the Appendix G LVRT Standard for the remaining life of the existing   
generation equipment. Existing individual generator units that are replaced are required to meet the Appendix G LVRT Standard.

ii. Power Factor Design Criteria (Reactive Power)

A wind generating plant shall maintain a power factor within the range of 0.95 leading to

0.95 lagging, measured at the Point of Interconnection as defined in this LGIA, if the ISO’s

System Reliability Impact Study shows that such a requirement is necessary to ensure safety or reliability.

The power factor range standard can be met using, for example without limitation, power electronics designed to supply this level of reactive capability (taking into account any   
limitations due to voltage level, real power output, etc.) or fixed and switched capacitors if   
agreed to by the Connecting Transmission Owner for the Transmission District to which the   
wind generating plant will be interconnected, or a combination of the two. The Developer shall not disable power factor equipment while the wind plant is in operation. Wind plants shall also be able to provide sufficient dynamic voltage support in lieu of the power system stabilizer and automatic voltage regulation at the generator excitation system if the System Reliability Impact Study shows this to be required for system safety or reliability.

iii. Supervisory Control and Data Acquisition (SCADA) Capability

The wind plant shall provide SCADA capability to transmit data and receive instructions from the ISO and/or the Connecting Transmission Owner for the Transmission District to which the wind generating plant will be interconnected, as applicable, to protect system reliability. The Connecting Transmission Owner for the Transmission District to which the wind generating   
plant will be interconnected and the wind plant Developer shall determine what SCADA   
information is essential for the proposed wind plant, taking into account the size of the plant and its characteristics, location, and importance in maintaining generation resource adequacy and   
transmission system reliability in its area.

G-3

APPENDIX H

Operation and Maintenance

In accordance with Article 10.5 of this Agreement, Interconnection Customer shall be

responsible for all reasonable expenses associated with the operation, maintenance, repair and

replacement of the Connecting Transmission Owner’s Attachment Facilities (“O&M Expenses”),   
as such facilities are detailed in Appendix A. Interconnection Customer shall pay Connecting   
Transmission Owner on a monthly basis for the actual invoiced cost for all such O&M Expenses.

H-1

O&M ATTACHMENT 1

Capitalized terms used in this calculation will have the following definitions: Allocation Factors

1. General Plant Allocation Factor shall equal Electric General Plant divided by the sum of

Electric General Plant plus gas general plant as reported in the Annual Report filed with the New York State Public Service Commission.

2. Gross Transmission Plant Allocation Factor shall equal the total investment in

Transmission Plant in Service divided by the sum of the total Transmission Plant in

Service plus the total Distribution Plant in Service, excluding Intangible Plant, General Plant and Common Plant.

3. Transmission Wages and Salaries Allocation Factor shall equal the ratio of Connecting

Transmission Owner’s Transmission-related direct electric wages and salaries including   
any direct wages or salaries charged to Connecting Transmission Owner by a National   
Grid Affiliate to Connecting Transmission Owner’s total electric direct wages and   
salaries including any wages charged to Connecting Transmission Owner by a National   
Grid Affiliate excluding any electric administrative and general wages and salaries.

Ratebase and Expense items

1. Administrative and General Expense shall equal electric expenses as recorded in FERC

Account Nos. 920-935.

2. Amortization of Investment Tax Credits shall equal electric credits as recorded in FERC

Account No. 411.4.

3. Distribution Plant in Service shall equal the gross plant balance as recorded in FERC

Account Nos. 360 - 374.

4. Electric Common Plant shall equal the balance of Common Plant recorded in FERC

Account Nos. 389-399 multiplied by the General Plant Allocation Factor.

5. General Plant shall equal electric gross general plant balance recorded in FERC Account

Nos. 389-399.

6. Materials and Supplies shall equal electric materials and supplies balance as recorded in

FERC Account No. 154.

7. Payroll Taxes shall equal those electric payroll tax expenses as recorded in FERC

Account Nos. 408.100, 408.110, and 408.130.

8. Prepayments shall equal electric prepayment balance as recorded in FERC Account No.

165.

H-2

9. Real Estate Tax Expenses shall equal electric transmission-related real estate tax expense

as recorded in FERC Account No. 408.140 and 408.180.

10. Transmission Operation and Maintenance Expense shall equal electric expenses as

recorded in FERC Account Nos. 560, 562-573.

11. Transmission Plant in Service shall equal the gross plant balance as recorded in FERC

Account Nos. 350-359.

12. Transmission Revenue Credits shall equal the revenue reported in Account 456

13. Transmission Related Bad Debt Expense shall equal Bad Debt Expense as reported in

Account 904 related to transmission billing.

14. Wholesale Metering Cost shall equal any costs associated with any Revenue or Remote

Terminal Unit (RTU) meters and associated equipment located at an internal or external tie at voltages equal to or greater than 23V. The cost shall be determined by multiplying the number of wholesale meters in FERC Account No. 370.3 by the average cost of the meters plus the average costs of installation.

In the event that the above-referenced FERC accounts are renumbered, renamed, or otherwise modified, the above sections shall be deemed amended to incorporate such   
renumbered, renamed, modified or additional accounts.

Revenue Requirement Components

The Revenue Requirement Component shall be the sum of Connecting Transmission   
Owner’s (A) Return and Associated Income Taxes, (B) Transmission Related Real Estate Tax   
Expense, (C) Transmission Related Amortization of Investment Tax Credits, (D) Transmission   
Related Payroll Tax Expense, (E) Transmission Operation and Maintenance Expense, (F)   
Transmission Related Administrative and General Expenses, less (G) Revenue Credits, plus (H)   
Bad Debt Expense.

A. Return and Associated Income Taxes shall equal the product of the Transmission   
 Investment Base as identified in A(1) below and the Cost of Capital Rate.

1. Transmission Investment Base shall be defined as

Transmission Related General Plant plus Transmission Related Common Plant

plus Transmission Related Regulatory Assets plus Transmission Related

Prepayments plus Transmission Related Materials and Supplies plus Transmission Related Cash Working Capital.

(a) Transmission Plant in Service shall equal the balance of Total investment

in Transmission Plant plus Wholesale Metering Cost.

H-3

(b) Transmission Related General Plant shall equal the balance of investment

in General Plant multiplied by the Transmission Wages and Salaries Allocation Factor.

(c) Transmission Related Common Plant shall equal Electric Common Plant

multiplied by the Gross Transmission Plant Allocation Factor and

multiplied by the Transmission Wages and Salaries Allocation Factor.

(d) Transmission Related Regulatory Assets shall equal balances in FERC

Account Nos. 182.3 and 254 for state and federal regulatory assets and

liabilities related to FAS109, and excess AFUDC multiplied by the Gross Transmission Plant Allocation Factor

(e) Transmission Related Prepayments shall equal the electric balance of

Prepayments multiplied by the Gross Transmission Plant Allocation

Factor.

(f) Transmission Related Materials and Supplies shall equal the balance of

Materials and Supplies assigned to Transmission added to the remainder   
of Material and Supplies not directly assigned to either Transmission or   
Distribution multiplied by the Gross Transmission Plant Allocation Factor.

(g) Transmission Related Cash Working Capital shall be a 12.5% allowance

(45 days/360 days) of the Transmission Operation and Maintenance

Expense (less FERC Account 565: Transmission of Electricity by Others) and Transmission-Related Administrative and General Expense.

2. Cost of Capital Rate

The Cost of Capital Rate shall equal the proposed Weighted Costs of Capital plus Federal Income Taxes and State Income Taxes.

(a) The Weighted Costs of Capital will be calculated for the Transmission

Investment Base using Connecting Transmission Owner’s actual capital structure and will equal the sum of (i), (ii), and (iii) below:

(i) the long-term debt component, which equals the product of the

actual weighted average embedded cost to maturity of Connecting Transmission Owner’s long-term debt then outstanding and the actual long-term debt capitalization ratio.

(ii) the preferred stock component, which equals the product of the

actual weighted average embedded cost to maturity of Connecting Transmission Owner’s preferred stock then outstanding and the actual preferred stock capitalization ratio;

(iii) the return on equity component, shall be the product of the allowed

ROE of 11.9% plus a 50 basis point adder (per FERC Order 697

H-4

and 697A) and Connecting Transmission Owner’s actual common equity capitalization ratio.

(b) Federal Income Tax shall equal

A x Federal Income Tax Rate   
(1 - Federal Income Tax Rate)

where A is the sum of the preferred stock component and the return on equity component, each as determined in Sections 2.(a)(ii) and for the ROE set forth in 2.(a)(iii) above

(c) State Income Tax shall equal

(A + Federal Income Tax) x State Income Tax Rate   
 (1 - State Income Tax Rate)

Where A is the sum of the preferred stock component and the return on equity component as determined in A.2.(a)(ii) and A.2.(a)(iii) above and Federal income Tax is determined in 2.(b) above.

B. Transmission Related Real Estate Tax Expense shall equal the Real Estate Tax Expenses

multiplied by the Gross Plant Allocation Factor.

C. Transmission Related Amortization of Investment Tax Credits shall equal the electric

Amortization of Investment Tax Credits multiplied by the Gross Transmission Plant Allocation Factor.

D. Transmission Related Payroll Tax Expense shall equal Payroll Taxes multiplied by the

Transmission Wages and Salaries Allocation Factor.

E. Transmission Operation and Maintenance Expense shall equal the Transmission

Operation and Maintenance Expense as previously defined.

F. Transmission Related Administrative and General Expenses shall equal the sum of the

electric Administrative and General Expenses multiplied by the Transmission Wages and Salaries Allocation Factor.

G. Revenue Credits shall equal all Transmission revenue recorded in FERC account 456.

H. Transmission Related Bad Debt Expense shall equal Transmission Related Bad Debt

Expense as previously defined.

H-5

Appendix I

List of Non-Applicable Pro-Forma LGIA Provisions

Transmission Owner and Interconnection Customer are already interconnected, pursuant to a   
pre-existing interconnection agreement. Therefore, certain terms of the pro-forma New York   
ISO LGIA are not applicable to this LGIA, because they relate solely to new interconnections.   
The Parties to this LGIA have nevertheless agreed to use the pro-forma New York ISO LGIA   
with almost no modifications, in accordance with FERC policy promoting the use of pro-forma   
interconnection agreements wherever possible. The Parties, however, believe that the following   
provisions of the pro-forma New York ISO LGIA are not applicable to the current LGIA:

Section 5.1 (Options), including all subsections thereof

Section 5.2 (General Conditions Applicable to Option to Build), including all subsections thereof Section 5.3 (Liquidated Damages)

Section 5.5 (Equipment Procurement), including all subsections thereof

Section 5.6 (Construction Commencement), including all subsections thereof Section 5.7 (Work Progress)

Section 5.8 (Information Exchange)   
Section 5.9 (Limited Operation)

Section 5.10 (Interconnection Customer Attachment Facilities), including all subsections thereof Section 5.11 (Connecting Transmission Owner’s Attachment Facilities Construction), including all subsections thereof

Section 5.14 (Permits)

Section 5.15 (Early Construction of Base Case Facilities)

Section 6.1 (Pre Commercial Operation Date Testing and Modification)

Section 11.4 (Special Provisions for Affected Systems)

Section 11.5 (Provision of Security), including all subsections thereof

Section 12.2 (Final Invoice)

Section 24.1 (Information Acquisition)

Section 24.2 (Information Submission by Transmission Owner)

Section 24.3 (Updated Information Submission by Interconnection Customer) Section 24.4 (Information Supplementation)

Section 25.4.1 (Audit Rights Period for Construction Related Accounts) Appendix B (Milestones)

Appendix G (Interconnection Requirements for a Wind Generating Plant)

I-1