SERVICE AGREEMENT NO. 2622

SERVICE AGREEMENT NO. 2622

ENGINEERING, PROCUREMENT, AND CONSTRUCTION AGREEMENT   
 AMONG THE

NEW YORK INDEPENDENT SYSTEM OPERATOR, INC.   
 AND

NEW YORK POWER AUTHORITY,   
 AND

NEW YORK TRANSCO, LLC   
 Dated as of June 11, 2021

SERVICE AGREEMENT NO. 2622

TABLE OF CONTENTS

Page Number

ARTICLE 1. DEFINITIONS 2

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION 6

2.1 Effective Date 6

2.2 Term of Agreement 6

2.3 Termination 6

2.4 Termination Costs 8

2.5 Survival 9

ARTICLE 3. EPC SERVICES 9

3.1 Performance of EPC Services 9

3.2 General Conditions Applicable to Affected System Upgrade Facilities Work

Performed by Transmission Developer 9

3.3 Engineering Commencement 10

3.4 Construction Commencement 10

3.5 Work Progress 10

3.6 Information Exchange 11

3.7 Ownership of Affected System Upgrade Facilities 11

3.8 Access Rights 11

3.9 Reserved 11

3.10 Permits 11

3.11 Suspension 12

3.12 Reserved 13

3.13 Tax Status 13

3.14 Modification 13

ARTICLE 4. TESTING AND INSPECTION 14

4.1 Pre-In-Service Date Testing and Modifications 14

4.2 Right to Observe Testing 14

4.3 Right to Inspect 14

ARTICLE 5. RESERVED 15

ARTICLE 6. PERFORMANCE OBLIGATION 15

6.1 EPC Services 15

6.2 Provision of Security 15

6.3 Forfeiture of Security 15

6.4 Affected System Upgrade Facility Costs 16

6.5 Line Outage Costs 16

ARTICLE 7. INVOICE 16

7.1 General 16

7.2 Refund of Remaining Security 17

7.3 Payment 17

7.4 Disputes 17

ARTICLE 8. REGULATORY REQUIREMENTS AND GOVERNING LAW 17

8.1 Regulatory Requirements 17

8.2 Governing Law 17

i

SERVICE AGREEMENT NO. 2622

ARTICLE 9. NOTICES 18

9.1 General 18

9.2 Billings and Payments 18

9.3 Alternative Forms of Notice 18

ARTICLE 10. FORCE MAJEURE 18

ARTICLE 11. DEFAULT 19

11.1 General 19

11.2 Right to Terminate 19

ARTICLE 12. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE 19

12.1 Indemnity 19

12.2 No Consequential Damages 21

12.3 Insurance 21

ARTICLE 13. ASSIGNMENT 23

ARTICLE 14. SEVERABILITY 24

ARTICLE 15. COMPARABILITY 24

ARTICLE 16. CONFIDENTIALITY 24

16.1 Confidentiality 24

16.2 Term 24

16.3 Confidential Information 24

16.4 Scope 24

16.5 Release of Confidential Information 25

16.6 Rights 25

16.7 No Warranties 25

16.8 Standard of Care 25

16.9 Order of Disclosure 26

16.10 Termination of Agreement 26

16.11 Remedies 26

16.12 Disclosure to FERC, its Staff, or a State 26

16.13 Required Notices Upon Requests or Demands for Confidential Information ..27

ARTICLE 17. AFFECTED SYSTEM OPERATOR NOTICES OF ENVIRONMENTAL

RELEASES 27

ARTICLE 18. INFORMATION REQUIRMENT 27

18.1 Information Acquisition 27

18.2 Information Submission Concerning the Affected System Upgrade Facilities 28

18.3 Information Submission Concerning the Transmission Project 28

18.4 Information Supplementation 28

ARTICLE 19. INFORMATION ACCESS AND AUDIT RIGHTS 28

19.1 Information Access 28

19.2 Reporting of Non-Force Majeure Events 29

19.3 Audit Rights 29

19.4 Audit Rights Periods 29

19.5 Audit Results 30

ARTICLE 20. SUBCONTRACTORS 30

20.1 General 30

20.2 Responsibility of Principal 30

20.3 No Limitation by Insurance 30

ii

SERVICE AGREEMENT NO. 2622

ARTICLE 21. DISPUTES 30

21.1 Submission 30

21.2 External Arbitration Procedures 31

21.3 Arbitration Decisions 31

21.4 Costs 31

21.5 Termination 31

ARTICLE 22. REPRESENTATIONS, WARRANTIES AND COVENANTS 31

22.1 General 31

ARTICLE 23. MISCELLANEOUS 32

23.1 Binding Effect 32

23.2 Conflicts 32

23.3 Rules of Interpretation 33

23.4 Compliance 33

23.5 Joint and Several Obligations 33

23.6 Entire Agreement 33

23.7 No Third Party Beneficiaries 34

23.8 Waiver 34

23.9 Headings 34

23.10 Multiple Counterparts 34

23.11 Amendment 34

23.12 Modification by the Parties 34

23.13 Reservation of Rights 34

23.14 No Partnership 35

23.15 Other Transmission Rights 35

Appendices

iii

SERVICE AGREEMENT NO. 2622

ENGINEERING, PROCUREMENT, AND CONSTRUCTION AGREEMENT

THIS ENGINEERING, PROCUREMENT, AND CONSTRUCTION AGREEMENT

(“Agreement”) is made and entered into this 11th day of June 2021, by and among New York   
Transco, LLC, a limited liability company organized and existing under the laws of the State of New York (“Transmission Developer”), the New York Independent System Operator, Inc., a notfor-profit corporation organized and existing under the laws of the State of New York   
(“NYISO”), and the New York Power Authority, a corporate municipal instrumentality   
organized and existing under the laws of the State of New York (“Affected System Operator”). Transmission Developer, the NYISO, or Affected System Operator each may be referred to as a “Party” or collectively referred to as the “Parties.”

RECITALS

WHEREAS, Transmission Developer is developing the New York Energy Solution project as the more efficient or cost effective transmission solution to Segment B of the AC Transmission Public Policy Transmission Needs (“Transmission Project”);

WHEREAS, the Transmission Project was evaluated in the NYISO’s Transmission Interconnection Procedures located in Attachment P of the NYISO OATT;

WHEREAS, Transmission Developer has entered into, or is currently in negotiations to enter   
into, the Transmission Project Interconnection Agreements concerning the Transmission Project   
with the NYISO and the Connecting Transmission Owners with which the project will   
interconnect;

WHEREAS, the Transmission Interconnection Studies for the Transmission Project identified   
certain adverse impacts resulting from the Transmission Project on the Affected System owned   
and operated by the Affected System Operator and determined that certain Network Upgrade   
Facilities were required to mitigate these impacts (“Affected System Upgrade Facilities”);

WHEREAS, Transmission Developer and Affected System Operator desire to have each perform, and each is willing to perform, certain engineering, procurement, and construction services as specified in Appendix A that are required to construct and place in service the Affected System Upgrade Facilities (“EPC Services”) in accordance with the terms and conditions hereinafter set forth; and

WHEREAS, Transmission Developer, Affected System Operator, and the NYISO have agreed   
to enter into this Agreement for the purpose of allocating the responsibilities for the performance   
and oversight of the EPC Services required to construct the Affected System Upgrade Facilities.

NOW, THEREFORE, in consideration of and subject to the mutual covenants contained herein, it is agreed:

1

SERVICE AGREEMENT NO. 2622

ARTICLE 1. DEFINITIONS

Whenever used in this Agreement with initial capitalization, the following terms shall have the

meanings specified in this Article 1. Terms used in this Agreement with initial capitalization that are not defined in this Article 1 shall have the meanings specified in Section 1 of the ISO OATT, Section 22.1 of Attachment P of the ISO OATT, Section 25.1.2 of Attachment S of the ISO   
OATT, the body of the TIP, or the body of this Agreement.

Affected System shall mean the electric system of the Affected System Operator that is affected by the interconnection of the Transmission Project.

Affected System Operator shall have the meaning set forth in the introductory paragraph.

Affected System Upgrade Facilities shall have the meaning set forth in the recitals and shall consist of the Network Upgrade Facilities identified in the Facilities Study and described in Appendix A of this Agreement.

Affiliate shall mean, with respect to a person or entity, any individual, corporation, partnership, firm, joint venture, association, joint-stock company, trust or unincorporated organization,   
directly or indirectly controlling, controlled by, or under common control with, such person or entity. The term “control” shall mean the possession, directly or indirectly, of the power to direct the management or policies of a person or an entity. A voting interest of ten percent or more shall create a rebuttable presumption of control.

Applicable Laws and Regulations shall mean all duly promulgated applicable federal, state and local laws, regulations, rules, ordinances, codes, decrees, judgments, directives, or judicial or administrative orders, permits and other duly authorized actions of any Governmental Authority, including but not limited to Environmental Law.

Applicable Reliability Councils shall mean the NERC, the NPCC and the NYSRC.

Applicable Reliability Standards shall mean the requirements and guidelines of the Applicable   
Reliability Councils, and the Transmission District in which the Affected System Upgrade   
Facilities will be constructed, as those requirements and guidelines are amended and modified   
and in effect from time to time; provided that no Party shall waive its right to challenge the   
applicability or validity of any requirement or guideline as applied to it in the context of this   
Agreement.

Breach shall mean the failure of a Party to perform or observe any material term or condition of this Agreement.

Breaching Party shall mean a Party that is in Breach of this Agreement.

Business Day shall mean Monday through Friday, excluding federal holidays.

Calendar Day shall mean any day including Saturday, Sunday or a federal holiday.

2

SERVICE AGREEMENT NO. 2622

Confidential Information shall mean any information that is defined as confidential by Article 16 of this Agreement.

Connecting Transmission Owner(s) shall mean the New York public utility or authority (or its designated agent) that (i) owns facilities used for the transmission of Energy in interstate   
commerce and provides Transmission Service under the Tariff, and (ii) owns, leases or otherwise possesses an interest in the portion of the New York State Transmission System at the Point(s) of Interconnection with the Transmission Project.

Default shall mean the failure of a Party in Breach of this Agreement to cure such Breach in accordance with Article 11 of this Agreement.

Development Agreement shall mean the agreement executed between the NYISO, Niagara Mohawk Power Corporation d/b/a National Grid, and Transmission Developer concerning the development of the Transmission Project, dated January 10, 2020, and assigned by Niagara   
Mohawk Power Corporation d/b/a National Grid to Transmission Developer on March 10, 2020, as it may be amended from time to time.

Effective Date shall mean the date determined under Article 2.1 of this Agreement.

Environmental Law shall mean Applicable Laws and Regulations relating to pollution or protection of the environment or natural resources.

EPC Services shall have the meaning set forth in the recitals and shall consist of the services described in Appendix A.

Facilities Study shall mean the study conducted pursuant to Section 22.9 of Attachment P of the NYISO OATT to determine a list of facilities required to reliably interconnect the Transmission Project (including the Network Upgrade Facilities) as identified in the System Impact Study, the cost of those facilities, and the time required to interconnect the Transmission Project with the New York State Transmission System.

Federal Power Act shall mean the Federal Power Act, as amended, 16 U.S.C. §§ 791a et seq. (“FPA”).

FERC shall mean the Federal Energy Regulatory Commission (“Commission”) or its successor.

Force Majeure shall mean any act of God, labor disturbance, act of the public enemy, war,   
insurrection, riot, fire, storm or flood, explosion, breakage or accident to machinery or   
equipment, any order, regulation or restriction imposed by governmental, military or lawfully   
established civilian authorities, or any other cause beyond a Party’s control. A Force Majeure   
event does not include acts of negligence or intentional wrongdoing by the Party claiming Force   
Majeure.

Good Utility Practice shall mean any of the practices, methods and acts engaged in or approved   
by a significant portion of the electric industry during the relevant time period, or any of the   
practices, methods and acts which, in the exercise of reasonable judgment in light of the facts   
known at the time the decision was made, could have been expected to accomplish the desired

3

SERVICE AGREEMENT NO. 2622

result at a reasonable cost consistent with good business practices, reliability, safety and

expedition. Good Utility Practice is not intended to be limited to the optimum practice, method, or act to the exclusion of all others, but rather to delineate acceptable practices, methods, or acts generally accepted in the region.

Governmental Authority shall mean any federal, state, local or other governmental regulatory or administrative agency, court, commission, department, board, or other governmental   
subdivision, legislature, rulemaking board, tribunal, or other governmental authority having   
jurisdiction over any of the Parties, their respective facilities, or the respective services they   
provide, and exercising or entitled to exercise any administrative, executive, police, or taxing authority or power; provided, however, that such term does not include Transmission Developer, NYISO, Affected System Operator, or any Affiliate thereof.

Hazardous Substances shall mean any chemicals, materials or substances defined as or

included in the definition of “hazardous substances,” “hazardous wastes,” “hazardous materials,” “hazardous constituents,” “restricted hazardous materials,” “extremely hazardous substances,” “toxic substances,” “radioactive substances,” “contaminants,” “pollutants,” “toxic pollutants” or words of similar meaning and regulatory effect under any applicable Environmental Law, or any other chemical, material or substance, exposure to which is prohibited, limited or regulated by any applicable Environmental Law.

In-Service Date shall mean the date upon which the Affected System Upgrade Facilities are   
energized consistent with the provisions of this Agreement and available to provide   
Transmission Service under the NYISO’s Tariffs. The Affected System Operator must provide   
notice of the In-Service Date to the other Parties in the form of Appendix C to this Agreement.

Interconnection Agreements shall mean the interconnection agreements concerning the Transmission Project among the Transmission Developer, the NYISO, and the Connecting Transmission Owners.

IRS shall mean the Internal Revenue Service.

NERC shall mean the North American Electric Reliability Council or its successor organization.

Network Upgrade Facilities shall mean the least costly configuration of commercially available   
components of electrical equipment that can be used, consistent with Good Utility Practice and   
Applicable Reliability Requirements, to make the modifications or additions to the New York   
State Transmission System that are required for the proposed Transmission Project to connect   
reliably to the system in a manner that meets the NYISO Transmission Interconnection Standard.

New York State Transmission System shall mean the entire New York State electric

transmission system, which includes (i) the Transmission Facilities Under ISO Operational Control; (ii) the Transmission Facilities Requiring ISO Notification; and (iii) all remaining transmission facilities within the New York Control Area.

Notice of Dispute shall mean a written notice of a dispute or claim that arises out of or in connection with this Agreement or its performance.

4

SERVICE AGREEMENT NO. 2622

NPCC shall mean the Northeast Power Coordinating Council or its successor organization.

NYISO Transmission Interconnection Standard shall mean the reliability standard that must be met by any Transmission Project proposing to connect to the New York State Transmission System. The standard is designed to ensure reliable access by the proposed project to the New York State Transmission System.

NYSRC shall mean the New York State Reliability Council or its successor organization.

Party or Parties shall mean NYISO, Affected System Operator, or Transmission Developer or any combination of the above.

Point(s) of Interconnection shall mean the point(s) where the Transmission Developer’s Transmission Project connect to the New York State Transmission System.

Reasonable Efforts shall mean, with respect to an action required to be attempted or taken by a   
Party under this Agreement, efforts that are timely and consistent with Good Utility Practice and   
are otherwise substantially equivalent to those a Party would use to protect its own interests.

Security shall mean a cash deposit, bond, irrevocable letter of credit, parent company guarantee or other form of security from an entity with an investment grade rating, provided to or executed for the benefit of the Connecting Transmission Owner, meeting the commercially reasonable requirements of the Connecting Transmission Owner with which it is required to be provided or posted pursuant to Article 6.2, and consistent with the Uniform Commercial Code of the   
jurisdiction identified in Article 8.2.1 of this Agreement.

Services Tariff shall mean the NYISO Market Administration and Control Area Tariff, as filed   
with the Commission, and as amended or supplemented from time to time, or any successor tariff   
thereto.

System Impact Study shall mean the study conducted pursuant to Section 22.8 of Attachment P of the OATT that evaluates the impact of the proposed Transmission Project on the safety and reliability of the New York State Transmission System and, if applicable, Affected System, to determine what Network Upgrade Facilities are needed for the proposed Transmission Project to connect reliably to the New York State Transmission System in a manner that meets the NYISO Transmission Interconnection Standard.

System Protection Facilities shall mean the equipment, including necessary protection signal communications equipment, required to (1) protect the New York State Transmission System from faults or other electrical disturbances occurring at the Transmission Project and (2) protect the Transmission Project from faults or other electrical system disturbances occurring on the New York State Transmission System or on other delivery systems or other generating systems to which the New York State Transmission System is directly connected.

Tariff shall mean the NYISO Open Access Transmission Tariff (“OATT”), as filed with the   
Commission, and as amended or supplemented from time to time, or any successor tariff.

Transmission Developer shall have the meaning set forth in the introductory paragraph.

5

SERVICE AGREEMENT NO. 2622

Transmission Interconnection Application shall mean Transmission Developer’s request, in the form of Appendix 1 to the TIP, to interconnect a Transmission Project to the New York State Transmission System.

Transmission Interconnection Procedures (“TIP”) shall mean the interconnection procedures applicable to a Transmission Interconnection Application pertaining to a Transmission Project that are included in Attachment P of the NYISO OATT.

Transmission Interconnection Study shall mean any of the following studies: the Optional Feasibility Study, the System Impact Study, and the Facilities Study described in the   
Transmission Interconnection Procedures.

Transmission Project shall be a Transmission Developer’s proposed transmission facility or facilities that collectively satisfy the definition of Transmission Project in Section 22.3.1 of Attachment P of the NYISO OATT.

ARTICLE 2. EFFECTIVE DATE, TERM AND TERMINATION

2.1 Effective Date.

This Agreement shall become effective upon the date of execution by the Parties, subject   
to acceptance by FERC, or if filed unexecuted, upon the date specified by FERC. The NYISO   
and Affected System Operator shall promptly file this Agreement with FERC upon its execution.   
Transmission Developer shall reasonably cooperate with the NYISO and Affected System   
Operator with respect to the filing of this Agreement with FERC and provide any information   
reasonably requested by the NYISO and Affected System Operator needed for such filing.

2.2 Term of Agreement.

Subject to the provisions of Article 2.3, this Agreement shall remain in effect until the   
later of: (i) the dates on which all of the EPC Services have been completed, and (ii) the date on   
which the final payment of all invoices issued under this Agreement have been made pursuant to   
Articles 7.1 and 7.3 and any remaining Security has been released or refunded pursuant to   
Article 7.2.

2.3 Termination.

2.3.1 Completion of Term of Agreement

This Agreement shall terminate upon the completion of the term of the Agreement pursuant to Article 2.2.

2.3.2 Written Notice.

2.3.2.1 Written Notice of Termination

This Agreement may be terminated: (i) by any Party after giving the other Parties ninety

(90) Calendar Days advance written notice following the termination of the Development

6

SERVICE AGREEMENT NO. 2622

Agreement prior to the completion of its term, subject to the suspension requirements in Section

2.3.2.2 below; or (ii) by the mutual agreement in writing of all Parties.

2.3.2.2 Suspension Period for Project Transfer

2.3.1.2.1 If the Development Agreement is terminated prior to the completion of its   
term and the NYISO exercises its right under the Development Agreement and the Tariff to   
request that a developer other than the Transmission Developer complete the Transmission   
Project, this Agreement shall be suspended. The suspension period will last until either: (i) the   
NYISO issues a written determination that the Transmission Project cannot be transferred to   
another developer and will not proceed, or (ii) the Transmission Developer completes the   
assignment of this Agreement to a new developer selected by the NYISO as set forth in Section

2.3.2.2.3. During the suspension period, the running of any advanced notice of termination time period pursuant to Section 2.3.2.1 will be paused. The Agreement shall not be terminated during the suspension period without the written agreement of all Parties.

2.3.1.2.2 During the suspension period, the Transmission Developer and Affected   
System Operator shall suspend all work associated with the construction and installation of the   
Affected System Upgrade Facilities required for only that Transmission Developer under this   
Agreement with the condition that the New York State Transmission System shall be left in a   
safe and reliable condition in accordance with Good Utility Practice and the safety and reliability   
criteria of Affected System Operator and NYISO. In such event, Transmission Developer shall   
be responsible for all reasonable and necessary costs and/or obligations in accordance with this   
Agreement, including those which Affected System Operator (i) has incurred pursuant to this   
Agreement prior to the suspension and (ii) incurs in suspending such work, including any costs   
incurred to perform such work as may be necessary to ensure the safety of persons and property   
and the integrity of the New York State Transmission System during such suspension and, if   
applicable, any costs incurred in connection with the cancellation or suspension of material,   
equipment and labor contracts which Affected System Operator cannot reasonably avoid;   
provided, however, that prior to canceling or suspending any such material, equipment or labor   
contract, Affected System Operator shall obtain Transmission Developer’s authorization to do   
so, which authorization shall not unreasonably be withheld, conditioned or delayed.

2.3.1.2.3 If, pursuant to its Tariff, the NYISO selects a new developer to complete   
the Transmission Project, Transmission Developer shall coordinate with the new developer   
concerning the assignment of this Agreement to the new developer pursuant to the assignment   
requirements in Article 13 of this Agreement. All liabilities under this Agreement existing prior   
to such transfer shall remain with the Transmission Developer, unless otherwise agreed upon by   
the Transmission Developer and the new developer as part of their good faith negotiations   
regarding the transfer.

2.3.3 Default.

Any Party may terminate this Agreement in accordance with Article 11.

7

SERVICE AGREEMENT NO. 2622

2.3.4 Compliance.

Notwithstanding Articles 2.3.1, 2.3.2, and 2.3.3, no termination of this Agreement shall become effective until the Parties have complied with all Applicable Laws and Regulations applicable to such termination, including the filing with FERC of a notice of termination of this Agreement, which notice has been accepted for filing by FERC.

2.4 Termination Costs.

If a Party elects to terminate this Agreement pursuant to Article 2.3.2 above, the

Transmission Developer shall be responsible for all costs that are the responsibility of the

Transmission Developer under this Agreement that are incurred by the Transmission Developer or the other Parties through the date, as applicable, of the other Parties’ receipt of a Party’s notice of termination or of the Parties’ mutual agreement to terminate the agreement. Such costs   
include any cancellation costs relating to orders or contracts. In the event of termination by the Transmission Developer, all Parties shall use commercially Reasonable Efforts to mitigate the costs, damages and charges arising as a consequence of termination. Upon termination of this Agreement, unless otherwise ordered or approved by FERC:

2.4.1 With respect to any portion of the Affected System Upgrade Facilities that have not yet been constructed or installed, but that is being relied upon by other projects in the manner described in Article 6.3 of this Agreement, Transmission Developer shall forfeit any remaining Security in accordance with the requirements in Article 6.3.

2.4.2 With respect to any portion of the Affected System Upgrade Facilities that has not   
yet been constructed or installed and is not being relied upon by other projects in the manner   
described in Article 6.3 of this Agreement, the Affected System Operator shall to the extent   
possible and with Transmission Developer’s authorization cancel any pending orders of, or   
return, any materials or equipment for, or contracts for construction of, such facilities; provided   
that in the event Transmission Developer elects not to authorize such cancellation, Transmission   
Developer shall assume all payment obligations with respect to such materials, equipment, and   
contracts, and the Affected System Operator shall deliver such material and equipment, and, if   
necessary, assign such contracts, to Transmission Developer as soon as practicable, at   
Transmission Developer’s expense. To the extent that Transmission Developer has already paid   
Affected System Operator for any or all such costs of materials or equipment not taken by   
Transmission Developer, Affected System Operator shall promptly refund such amounts to   
Transmission Developer, less any costs, including penalties incurred by the Affected System   
Operator to cancel any pending orders of or return such materials, equipment, or contracts.

2.4.3 Affected System Operator may, at its option, retain any portion of such materials or equipment that Transmission Developer chooses not to accept delivery of, in which case   
Affected System Operator shall be responsible for all costs associated with procuring such   
materials or equipment.

2.4.4 With respect to any portion of the EPC Services already performed pursuant to

the terms of this Agreement, Transmission Developer shall be responsible for all costs associated

8

SERVICE AGREEMENT NO. 2622

with the removal, relocation or other disposition or retirement of such related materials, equipment, or facilities.

2.5 Survival.

This Agreement shall continue in effect after termination to the extent necessary to

provide for final billings and payments and for costs incurred hereunder; including billings and payments pursuant to this Agreement; and to permit the determination and enforcement of   
liability and indemnification obligations arising from acts or events that occurred while this   
Agreement was in effect.

ARTICLE 3. EPC SERVICES

3.1 Performance of EPC Services.

The Affected System Operator’s and Transmission Developer’s respective obligations to   
perform the EPC Services shall be set forth in Appendix A hereto. The Affected System   
Operator and Transmission Developer shall each use Reasonable Efforts to complete its   
respective EPC Services by the Milestone dates set forth in Appendix A hereto. The Affected   
System Operator shall not be required to undertake any action which is inconsistent with its   
standard safety practices, its material and equipment specifications, its design criteria and   
construction procedures, its labor agreements, and Applicable Laws and Regulations. In the   
event the Affected System Operator or Transmission Developer reasonably expects that it will   
not be able to complete the EPC Services for which it is responsible by the specified dates, the   
Affected System Operator or Transmission Developer, as applicable, shall promptly provide   
written notice to the other Parties, and shall undertake Reasonable Efforts to meet the earliest   
dates thereafter. The NYISO has no responsibility, and shall have no liability, for the   
performance of any of the EPC Services under this Agreement.

3.2 General Conditions Applicable to Affected System Upgrade Facilities Work

Performed by Transmission Developer.

As Transmission Developer has assumed responsibility for the engineering of the

Affected System Upgrade Facilities as set forth in Appendix A, the following conditions apply:

3.2.1 Transmission Developer shall perform the engineering of the Affected System   
Upgrade Facilities (or portions thereof) as specified in Appendix A using Good Utility Practice   
and using standards and specifications provided in advance by the Affected System Operator;

3.2.2 Transmission Developer’s engineering of the Affected System Upgrade Facilities shall comply with all requirements of law to which Affected System Operator would be subject in the engineering of the Network Upgrade Facilities;

9

SERVICE AGREEMENT NO. 2622

3.2.3 Affected System Operator shall review and approve the engineering design of the Affected System Upgrade Facilities;

3.2.4 At any time during the engineering, should the engineering not meet the standards   
and specifications provided by Affected System Operator, the Transmission Developer shall be   
obligated to remedy deficiencies in that portion of the Affected System Upgrade Facilities;

3.2.5 Transmission Developer shall deliver to NYISO and Affected System Operator “as built” drawings, information, and any other documents that are reasonably required by NYISO or Affected System Operator to assure that the Affected System Upgrade Facilities are built to the standards and specifications required by Affected System Operator; and

3.2.6 The Transmission Developer shall be responsible for the costs that Affected System Operator incurs in executing the responsibilities enumerated to Affected System Operator under Article 3.2. The Affected System Operator shall invoice Transmission Developer for such costs pursuant to Article 7.

3.3 Engineering Commencement.

Transmission Developer shall commence engineering of the Affected System Upgrade Facilities in accordance with the date specified in Appendix A hereto, unless the Transmission Developer and Affected System Operator otherwise agree in writing.

3.4 Construction Commencement.

The Affected System Operator shall commence construction of the Affected System Upgrade Facilities as soon as practicable after the following conditions are satisfied:

3.4.1 Approval of the appropriate Governmental Authority has been obtained, to the   
extent required, for the construction of a discrete aspect of the Affected System Upgrade   
Facilities;

3.4.2 Necessary real property rights and rights-of-way have been obtained, to the extent required for the construction of a discrete aspect of the Affected System Upgrade Facilities;

3.4.3 The Affected System Operator has received written authorization to proceed with   
construction from the Transmission Developer by the date specified in Appendix B hereto; and

3.4.4 The Transmission Developer has provided Security to the Affected System Operator in accordance with Article 6.2 by the dates specified in Appendix B hereto.

3.5 Work Progress.

The Transmission Developer and Affected System Operator will keep each other, and NYISO, advised periodically as to the progress of their respective design, procurement and construction efforts. Any Party may, at any time, request a progress report from the   
Transmission Developer or Affected System Operator.

10

SERVICE AGREEMENT NO. 2622

3.6 Information Exchange.

As soon as reasonably practicable after the Effective Date, the Transmission Developer   
and Affected System Operator shall exchange information, and provide NYISO the same   
information, regarding the design of the Affected System Upgrade Facilities and compatibility of   
the Affected System Upgrade Facilities with the New York State Transmission System, and shall   
work diligently and in good faith to make any necessary design changes required by Affected   
System Operator or NYISO, in accordance with Good Utility Practice to ensure that the Affected   
System Upgrade Facilities are compatible with the technical specifications, operational control,   
and safety requirements of the Affected System Operator and NYISO. Any review by the   
NYISO of the design of the Affected System Upgrade Facilities shall not be construed as   
confirming, endorsing, or providing a warranty as to the design, fitness, safety, durability or   
reliability of the Affected System Upgrade Facilities. The Transmission Developer shall inform   
the Affected System Operator of the termination of one or more of the Interconnection   
Agreements or the Development Agreement within ten (10) days of the termination of the   
agreement(s).

3.7 Ownership of Affected System Upgrade Facilities

Affected System Operator shall own the Affected System Upgrade Facilities.

3.8 Access Rights.

Upon reasonable notice and supervision by the Granting Party, and subject to any

required or necessary regulatory approvals, the Affected System Operator and Transmission

Developer (“Granting Party”) shall each furnish the other Parties (“Access Party”) at no cost any   
rights of use, licenses, rights of way and easements with respect to lands owned or controlled by   
the Granting Party, its agents (if allowed under the applicable agency agreement), or any   
Affiliate, that are necessary to enable the Access Party to obtain ingress and egress needed for   
the performance of the EPC Services, including ingress or egress to construct, repair, test (or   
witness testing), inspect, replace or remove the Affected System Upgrade Facilities. In   
exercising such licenses, rights of way and easements, the Access Party shall not unreasonably   
disrupt or interfere with normal operation of the Granting Party’s business and shall adhere to the   
safety rules and procedures established in advance, as may be changed from time to time, by the   
Granting Party and provided to the Access Party. The Access Party shall indemnify the Granting   
Party against all claims of injury or damage from third parties resulting from the exercise of the   
access rights provided for herein.

3.9 Reserved.

3.10 Permits.

NYISO, Affected System Operator and the Transmission Developer shall cooperate with   
each other in good faith in obtaining all permits, licenses and authorizations that are necessary to   
accomplish the EPC Services in compliance with Applicable Laws and Regulations. With   
respect to this paragraph, Affected System Operator shall provide permitting assistance to the

11

SERVICE AGREEMENT NO. 2622

Transmission Developer comparable to that provided to the Affected System Operator’s own, or an Affiliate’s generation, if any.

3.11 Suspension.

Transmission Developer reserves the right, upon written notice to Affected System

Operator and NYISO, to suspend at any time all work by Affected System Operator associated   
with the EPC Services under this Agreement for Affected System Upgrade Facilities required for   
only Transmission Developer’s Transmission Project with the condition that the New York State   
Transmission System shall be left in a safe and reliable condition in accordance with Good   
Utility Practice and the safety and reliability criteria of Affected System Operator and NYISO.   
If the suspension will impact the Transmission Developer’s ability to meet any Advisory   
Milestones or Critical Path Milestones in the Development Agreement, Transmission Developer   
shall notify the NYISO in accordance with the requirements in Article 3.3 of the Development   
Agreement. NYISO reserves the right, upon written notice to Transmission Developer and   
Affected System Operator, to require the suspension of all work by Transmission Developer and   
Affected System Operator associated with the EPC Services under this Agreement if the NYISO   
terminates the Development Agreement pursuant to Article 8 of the Development Agreement.

In the event of suspension pursuant to this Article 3.11, Transmission Developer shall be   
responsible for all reasonable and necessary costs and/or obligations in accordance with the   
Facilities Study report including those which Affected System Operator (i) has incurred pursuant   
to this Agreement prior to the suspension and (ii) incurs in suspending such work, including any   
costs incurred to perform such work as may be necessary to ensure the safety of persons and   
property and the integrity of the New York State Transmission System during such suspension   
and, if applicable, any costs incurred in connection with the cancellation or suspension of   
material, equipment and labor contracts which Affected System Operator cannot reasonably   
avoid; provided, however, that prior to canceling or suspending any such material, equipment or   
labor contract, Affected System Operator shall obtain Transmission Developer’s authorization to   
do so.

Affected System Operator shall invoice Transmission Developer for such costs pursuant   
to Article 7 and shall use due diligence to minimize its costs. In the event Transmission   
Developer suspends work by Affected System Operator required under this Agreement pursuant   
to this Article 3.11, and has not requested Affected System Operator to recommence the work   
required under this Agreement on or before the expiration of three (3) years following   
commencement of such suspension, this Agreement shall be deemed terminated. The three-year   
period shall begin on the date required under this Article 3.11 or the date specified in the written   
notice of suspension.

12

SERVICE AGREEMENT NO. 2622

3.12 Reserved.

3.13 Tax Status

3.13.1 Tax Status

Each Party shall cooperate with the other Parties to maintain the other Parties’ tax status.   
Nothing in this Agreement is intended to adversely affect the tax status of any Party including   
the status of NYISO, or the status of the Affected System Operator with respect to the issuance   
of bonds including, but not limited to, Local Furnishing Bonds. Notwithstanding any other

provisions of this Agreement, Affected System Operator shall not be required to comply with

any provisions of this Agreement that would result in the loss of tax-exempt status of any of their   
Tax-Exempt Bonds or impair their ability to issue future tax-exempt obligations. For purposes   
of this provision, Tax-Exempt Bonds shall include the obligations of the Affected System   
Operator, the interest on which is not included in gross income under the Internal Revenue Code.

3.13.2 Non-Jurisdictional Entities

Affected System Operator does not waive its exemptions, pursuant to Section 201(f) of the FPA, from Commission jurisdiction with respect to the Commission’s exercise of the FPA’s general ratemaking authority.

3.14 Modification.

3.14.1 General.

If, prior to the In-Service Date, either the Transmission Developer or Affected System

Operator proposes to modify the Affected System Upgrade Facilities, they must inform the other Parties of the proposed modification and must satisfy the requirements in (i) Section 22.5.4 of   
Attachment P to the NYISO OATT, and (ii) the Development Agreement. The Transmission   
Developer shall be responsible for the costs of any such additional modifications, including the cost of studying the materiality and impact of the modification.

3.14.2 Standards.

Any additions, modifications, or replacements made to a Party’s facilities shall be

designed, constructed and operated in accordance with this Agreement, NYISO requirements and Good Utility Practice.

3.14.3 Modification Costs.

Transmission Developer or Affected System Operator, as applicable, shall not be

assigned the cost of any additions, modifications, or replacements that the other Party makes to   
the New York State Transmission System to facilitate the interconnection of a third party to the   
New York State Transmission System, or to provide Transmission Service to a third party under   
the ISO OATT, except in accordance with the cost allocation procedures in Attachment S of the   
ISO OATT.

13

SERVICE AGREEMENT NO. 2622

ARTICLE 4. TESTING AND INSPECTION

4.1 Pre-In-Service Date Testing and Modifications.

Prior to the In-Service Date, the Affected System Operator shall test the Affected System   
Upgrade Facilities and Transmission Developer shall coordinate with the Affected System   
Operator concerning the testing of the Affected System Upgrade Facilities and the Transmission   
Project under the Interconnection Agreements to ensure the safe and reliable operation of the   
Affected System Upgrade Facilities. Similar testing may be required after initial operation.   
Transmission Developer and Affected System Operator shall each make any modifications to   
their facilities that are found to be necessary as a result of such testing. Transmission Developer   
shall bear the cost of all such testing and modifications. Transmission Developer shall   
coordinate with the Affected System Operator to generate test energy at the Affected System   
Upgrade Facilities only if it has arranged for the injection of such test energy in accordance with   
NYISO procedures.

4.2 Right to Observe Testing.

Affected System Operator shall notify Transmission Developer and the NYISO, in

advance of its performance of tests of the Affected System Upgrade Facilities. Transmission

Developer and the NYISO shall each have the right, at its own expense, to observe such testing.

4.3 Right to Inspect.

Transmission Developer and Affected System Operator shall each have the right, but   
shall have no obligation to: (i) observe the other Party’s tests and/or inspection of any of its   
System Protection Facilities and other protective equipment; (ii) review the settings of the other   
Party’s System Protection Facilities and other protective equipment; and (iii) review the other   
Party’s maintenance records relative to the Affected System Upgrade Facilities, the System   
Protection Facilities and other protective equipment. NYISO shall have these same rights of   
inspection as to the facilities and equipment of Transmission Developer and Affected System   
Operator. A Party may exercise these rights from time to time as it deems necessary upon   
reasonable notice to the other Party. The exercise or non-exercise by a Party of any such rights   
shall not be construed as an endorsement or confirmation of any element or condition of the   
Affected System Upgrade Facilities or the System Protection Facilities or other protective   
equipment or the operation thereof, or as a warranty as to the fitness, safety, desirability, or   
reliability of same. Any information that a Party obtains through the exercise of any of its rights   
under this Article 4.3 shall be treated in accordance with Article 16 of this Agreement and   
Attachment F to the ISO OATT.

14

SERVICE AGREEMENT NO. 2622

ARTICLE 5. RESERVED

ARTICLE 6. PERFORMANCE OBLIGATION

6.1 EPC Services

Affected System Operator and Transmission Developer shall perform their respective EPC Services described in Appendix A hereto and as otherwise set forth by the terms of this Agreement at Transmission Developer’s expense.

6.2 Provision of Security.

Within thirty (30) Calendar Days of the effective date of this Agreement, Transmission Developer shall provide Affected System Operator with Security in the amount of the cost   
estimate for the Affected System Upgrade Facilities documented in the Facilities Study report in accordance with Section 22.9.3 of Attachment P of the ISO OATT. This amount is set forth in Appendix A of this Agreement.

6.3 Forfeiture of Security

The Security the Transmission Developer provides Affected System Operator in   
accordance with Article 6.2 of this Agreement shall be irrevocable and shall be subject to   
forfeiture in the event that the Transmission Developer subsequently terminates or abandons   
development of the Transmission Project or the Affected System Upgrade Facilities. Any   
Security provided by the Transmission Developer shall be subject to forfeiture to the extent   
necessary to defray the cost of: (1) Affected System Upgrade Facilities required for other   
Transmission Developers whose Transmission Project interconnection studies included the   
Transmission Developer’s Transmission Project and Affected System Upgrade Facilities in their   
base cases; and (2) System Upgrade Facilities and System Deliverability Upgrade Facilities   
required for projects for which the Transmission Project and Affected System Upgrade Facilities   
were included in their Annual Transmission Reliability Assessment and/or Class Year   
Deliverability Study, as applicable. If Transmission Developer’s Security is subject to forfeiture   
to defray the costs of an affected upgrade pursuant to this Article 6.3 and the Security is not in a   
form that can be readily drawn on by the Affected System Operator to defray the costs of the   
affected upgrade, Transmission Developer shall negotiate in good faith with the Affected System   
Operator to replace the Security with cash or an alternative form of Security that can be readily   
drawn on by Affected System Operator up to the amount required to satisfy Transmission   
Developer’s Security obligations under this Agreement, including defraying the costs of the   
affected upgrade. Affected System Operator shall only be responsible for using Transmission   
Developer’s Security to defray the costs of an affected upgrade to the extent Transmission   
Developer has provided cash or Security in a form that the Affected System Operator can readily   
draw on to defray such costs.

15

SERVICE AGREEMENT NO. 2622

6.4 Affected System Upgrade Facility Costs

6.4.1 If the actual cost of Affected System Upgrade Facilities is less than the agreed-to and secured amount, Transmission Developer is responsible only for the actual cost figure.

6.4.2 If the actual cost of Affected System Upgrade Facilities is greater than the agreed-  
to and secured amount because other projects have been expanded, accelerated, otherwise   
modified or terminated, Transmission Developer is responsible only for the agreed-to and   
secured amount for the Affected System Upgrade Facilities. The additional cost is covered by   
the developers of the modified projects, or by the drawing on the cash that has been paid and the   
Security that has been posted for terminated projects, depending on the factors that caused the   
additional cost. Such forfeitable Security from other developers will be drawn on only as needed   
for this purpose, and only to the extent that the terminated project associated with that Security   
has caused additional cost.

6.4.3 If the actual cost of the Affected System Upgrade Facilities is greater than the   
agreed-to and secured amount for reasons other than those set forth in Section 6.4.2,   
Transmission Developer will pay the additional costs to Affected System Operator to the extent   
such costs are prudently incurred. Disputes between Transmission Developer and Affected   
System Operator concerning costs in excess of the agreed-to and secured amount will be   
resolved by the parties in accordance with the terms and conditions of Article 21.

6.5 Line Outage Costs.

Notwithstanding anything in the ISO OATT to the contrary, Affected System Operator may propose to recover line outage costs associated with the installation of the Affected System Upgrade Facilities on a case-by-case basis.

ARTICLE 7. INVOICE

7.1 General.

Affected System Operator will draw upon the Security provided by Transmission

Developer in accordance with Article 6.2 of this Agreement to satisfy Transmission Developer’s   
obligation to pay for Affected System Operator’s performance of the EPC Services. Affected   
System Operator shall provide Transmission Developer on a monthly basis with an invoice that   
describes the services and equipment provided and the Security drawn upon to satisfy these EPC   
Services. If the actual cost of the EPC Services is greater than the agreed-to and secured amount   
for such services and Affected System Operator can recover such additional costs pursuant to   
Section 6.4.3, Affected System Operator shall submit to Transmission Developer, on a monthly   
basis, invoices of amounts due for the preceding month. Each invoice shall state the month to   
which the invoice applies and fully describe the services and equipment provided. Within six   
months after completion of the EPC Services, Affected System Operator shall provide a final

invoice to Transmission Developer of any remaining amounts due associated with the EPC Services.

16

SERVICE AGREEMENT NO. 2622

7.2 Refund of Remaining Security.

Following the later of Affected System Operator’s completion of the EPC Services and   
Transmission Developer’s payment of any final invoice issued under Article 7.1, the Affected   
System Operator shall refund to the Transmission Developer any remaining portions of its   
security. Affected System Operator shall provide Transmission Developer with the refunded   
amount within thirty (30) Calendar Days of the Parties’ satisfaction of the requirements in this   
Article 7.2.

7.3 Payment.

Invoices shall be rendered to Transmission Developer at the address specified in

Appendix F hereto. Transmission Developer shall pay the invoice within thirty (30) Calendar

Days of receipt. All payments shall be made in immediately available funds payable to Affected System Operator, or by wire transfer to a bank named and account designated by Affected   
System Operator. Payment of invoices will not constitute a waiver of any rights or claims   
Transmission Developer may have under this Agreement.

7.4 Disputes.

In the event of a billing dispute between Parties, the Party owed money shall continue to   
perform under this Agreement as long as the other Party: (i) continues to make all payments not   
in dispute; and (ii) pays to the Party owed money or into an independent escrow account the   
portion of the invoice in dispute, pending resolution of such dispute. If the Party that owes   
money fails to meet these two requirements for continuation of service, then the Party owed   
money may provide notice to the other Party of a Default pursuant to Article 11. Within thirty

(30) Calendar Days after the resolution of the dispute, the Party that owes money to the other

Party shall pay the amount due with interest calculated in accord with the methodology set forth in FERC’s Regulations at 18 C.F.R. § 35.19a(a)(2)(iii).

ARTICLE 8. REGULATORY REQUIREMENTS AND GOVERNING LAW

8.1 Regulatory Requirements.

Each Party’s obligations under this Agreement shall be subject to its receipt of any

required approval or certificate from one or more Governmental Authorities in the form and

substance satisfactory to the applying Party, or the Party making any required filings with, or

providing notice to, such Governmental Authorities, and the expiration of any time period

associated therewith. Each Party shall in good faith seek and use its Reasonable Efforts to obtain such other approvals. Nothing in this Agreement shall require a Party to take any action that   
could result in its inability to obtain, or its loss of, status or exemption under the Federal Power Act or the Public Utility Holding Company Act of 2005 or the Public Utility Regulatory Policies Act of 1978, as amended.

8.2 Governing Law.

17

SERVICE AGREEMENT NO. 2622

8.2.1 The validity, interpretation and performance of this Agreement and each of its

provisions shall be governed by the laws of the state of New York, without regard to its conflicts of law principles.

8.2.2 This Agreement is subject to all Applicable Laws and Regulations.

8.2.3 Each Party expressly reserves the right to seek changes in, appeal, or otherwise contest any laws, orders, rules, or regulations of a Governmental Authority.

ARTICLE 9. NOTICES

9.1 General.

Unless otherwise provided in this Agreement, any notice, demand or request required or permitted to be given by a Party to the other Parties and any instrument required or permitted to be tendered or delivered by a Party in writing to the other Parties shall be effective when   
delivered and may be so given, tendered or delivered, by recognized national courier, or by   
depositing the same with the United States Postal Service with postage prepaid, for delivery by certified or registered mail, addressed to the Party, or personally delivered to the Party, at the   
address set out in Appendix B hereto.

A Party may change the notice information in this Agreement by giving five (5) Business Days written notice prior to the effective date of the change.

9.2 Billings and Payments.

Billings and payments shall be sent to the addresses set out in Appendix B hereto.

9.3 Alternative Forms of Notice.

Any notice or request required or permitted to be given by a Party to the other Parties and not required by this Agreement to be given in writing may be so given by telephone, facsimile or email to the telephone numbers and email addresses set out in Appendix B hereto.

ARTICLE 10. FORCE MAJEURE

10.1 Economic hardship is not considered a Force Majeure event.

10.2 A Party shall not be responsible or liable, or deemed, in Default with respect to

any obligation hereunder, other than the obligation to pay money when due, to the extent the

Party is prevented from fulfilling such obligation by Force Majeure. A Party unable to fulfill any   
obligation hereunder (other than an obligation to pay money when due) by reason of Force   
Majeure shall give notice and the full particulars of such Force Majeure to the other Parties in   
writing or by telephone as soon as reasonably possible after the occurrence of the cause relied   
upon. Telephone notices given pursuant to this Article shall be confirmed in writing as soon as   
reasonably possible and shall specifically state full particulars of the Force Majeure, the time and   
date when the Force Majeure occurred and when the Force Majeure is reasonably expected to

18

SERVICE AGREEMENT NO. 2622

cease. The Party affected shall exercise due diligence to remove such disability with reasonable dispatch, but shall not be required to accede or agree to any provision not satisfactory to it in order to settle and terminate a strike or other labor disturbance.

ARTICLE 11. DEFAULT

11.1 General.

No Breach shall exist where such failure to discharge an obligation (other than the

payment of money) is the result of Force Majeure as defined in this Agreement or the result of an   
act or omission of the other Parties. Upon a Breach, the non-Breaching Parties shall give written   
notice of such to the Breaching Party. The Breaching Party shall have thirty (30) Calendar Days   
from receipt of the Breach notice within which to cure such Breach; provided however, if such   
Breach is not capable of cure within thirty (30) Calendar Days, the Breaching Party shall   
commence such cure within thirty (30) Calendar Days after notice and continuously and   
diligently complete such cure within ninety (90) Calendar Days from receipt of the Breach   
notice; and, if cured within such time, the Breach specified in such notice shall cease to exist.

11.2 Right to Terminate.

If a Breach is not cured as provided in this Article 11, or if a Breach is not capable of

being cured within the period provided for herein, the non-Breaching Parties acting together shall thereafter have the right to declare a Default and terminate this Agreement by written notice at any time until cure occurs, and be relieved of any further obligation hereunder and, whether or not those Parties terminate this Agreement, to recover from the defaulting Party all amounts due hereunder, plus all other damages and remedies to which they are entitled at law or in equity. The provisions of this Article will survive termination of this Agreement.

ARTICLE 12. INDEMNITY, CONSEQUENTIAL DAMAGES AND INSURANCE

12.1 Indemnity.

Each Party (the “Indemnifying Party”) shall at all times indemnify, defend, and save

harmless, as applicable, the other Parties (each an “Indemnified Party”) from, any and all

damages, losses, claims, including claims and actions relating to injury to or death of any person   
or damage to property, the alleged violation of any Environmental Law, or the release or   
threatened release of any Hazardous Substance, demand, suits, recoveries, costs and expenses,   
court costs, attorney fees, and all other obligations by or to third parties (any and all of these a   
“Loss”), arising out of or resulting from (i) the Indemnified Party’s performance of its   
obligations under this Agreement on behalf of the Indemnifying Party, except in cases where the   
Indemnifying Party can demonstrate that the Loss of the Indemnified Party was caused by the   
gross negligence or intentional wrongdoing of the Indemnified Party or (ii) the violation by the   
Indemnifying Party of any Environmental Law or the release by the Indemnifying Party of any   
Hazardous Substance.

19

SERVICE AGREEMENT NO. 2622

12.1.1 Indemnified Party.

If a Party is entitled to indemnification under this Article 12 as a result of a claim by a third party, and the Indemnifying Party fails, after notice and reasonable opportunity to proceed under Article 12.1.3, to assume the defense of such claim, such Indemnified Party may at the expense of the Indemnifying Party contest, settle or consent to the entry of any judgment with respect to, or pay in full, such claim.

12.1.2 Indemnifying Party.

If an Indemnifying Party is obligated to indemnify and hold any Indemnified Party

harmless under this Article 12, the amount owing to the Indemnified Party shall be the amount of such Indemnified Party’s actual Loss, net of any insurance or other recovery.

12.1.3 Indemnity Procedures.

Promptly after receipt by an Indemnified Party of any claim or notice of the

commencement of any action or administrative or legal proceeding or investigation as to which   
the indemnity provided for in Article 12.1 may apply, the Indemnified Party shall notify the   
Indemnifying Party of such fact. Any failure of or delay in such notification shall not affect a   
Party’s indemnification obligation unless such failure or delay is materially prejudicial to the   
Indemnifying Party.

Except as stated below, the Indemnifying Party shall have the right to assume the defense   
thereof with counsel designated by such Indemnifying Party and reasonably satisfactory to the   
Indemnified Party. If the defendants in any such action include one or more Indemnified Parties   
and the Indemnifying Party and if the Indemnified Party reasonably concludes that there may be   
legal defenses available to it and/or other Indemnified Parties which are different from or   
additional to those available to the Indemnifying Party, the Indemnified Party shall have the right   
to select separate counsel to assert such legal defenses and to otherwise participate in the defense   
of such action on its own behalf. In such instances, the Indemnifying Party shall only be   
required to pay the fees and expenses of one additional attorney to represent an Indemnified   
Party or Indemnified Parties having such differing or additional legal defenses.

The Indemnified Party shall be entitled, at its expense, to participate in any such action,   
suit or proceeding, the defense of which has been assumed by the Indemnifying Party.   
Notwithstanding the foregoing, the Indemnifying Party (i) shall not be entitled to assume and   
control the defense of any such action, suit or proceedings if and to the extent that, in the opinion   
of the Indemnified Party and its counsel, such action, suit or proceeding involves the potential   
imposition of criminal liability on the Indemnified Party, or there exists a conflict or adversity of   
interest between the Indemnified Party and the Indemnifying Party, in such event the   
Indemnifying Party shall pay the reasonable expenses of the Indemnified Party, and (ii) shall not   
settle or consent to the entry of any judgment in any action, suit or proceeding without the   
consent of the Indemnified Party, which shall not be unreasonably withheld, conditioned or   
delayed.

20

SERVICE AGREEMENT NO. 2622

12.2 No Consequential Damages.

Other than the indemnity obligations set forth in Article 12.1, in no event shall any Party be liable under any provision of this Agreement for any losses, damages, costs or expenses for any special, indirect, incidental, consequential, or punitive damages, including but not limited to loss of profit or revenue, loss of the use of equipment, cost of capital, cost of temporary   
equipment or services, whether based in whole or in part in contract, in tort, including   
negligence, strict liability, or any other theory of liability; provided, however, that damages for which a Party may be liable to another Party under separate agreement will not be considered to be special, indirect, incidental, or consequential damages hereunder.

12.3 Insurance.

Affected System Operator and Transmission Developer shall each, at its own expense,   
procure and maintain in force throughout the period of this Agreement and until released by the   
other Parties, the following minimum insurance coverages, with insurance companies licensed to write insurance or approved eligible surplus lines carriers in the state of New York with a   
minimum A.M. Best rating of A or better for financial strength, and an A.M. Best financial size   
category of VIII or better:

12.3.1 Employers’ Liability and Workers’ Compensation Insurance providing

statutory benefits in accordance with the laws and regulations of New York State.

12.3.2 Commercial General Liability (“CGL”) Insurance including premises and

operations, personal injury, broad form property damage, broad form blanket contractual liability   
coverage products and completed operations coverage, coverage for explosion, collapse and   
underground hazards, independent contractors coverage, coverage for pollution to the extent   
normally available and punitive damages to the extent normally available using Insurance   
Services Office, Inc. Commercial General Liability Coverage (“ISO CG”) Form CG 00 01 04 13   
or a form equivalent to or better than CG 00 01 04 13, with minimum limits of Two Million   
Dollars ($2,000,000) per occurrence and Two Million Dollars ($2,000,000) aggregate combined   
single limit for personal injury, bodily injury, including death and property damage.

12.3.3 Comprehensive Automobile Liability Insurance for coverage of owned

and non-owned and hired vehicles, trailers or semi-trailers designed for travel on public roads, with a minimum, combined single limit of One Million Dollars ($1,000,000) per occurrence for bodily injury, including death, and property damage.

12.3.4 If applicable, the Commercial General Liability and Comprehensive

Automobile Liability Insurance policies should include contractual liability for work in

connection with construction or demolition work on or within 50 feet of a railroad, or a separate Railroad Protective Liability Policy should be provided.

12.3.5 Excess Liability Insurance over and above the Employers’ Liability,

Commercial General Liability and Comprehensive Automobile Liability Insurance coverages,   
with a minimum combined single limit of Twenty Million Dollars ($20,000,000) per occurrence

21

SERVICE AGREEMENT NO. 2622

and Twenty Million Dollars ($20,000,000) aggregate. The Excess policies should contain the same extensions listed under the Primary policies.

12.3.6 The Commercial General Liability Insurance, Comprehensive Automobile

Insurance and Excess Liability Insurance policies of Affected System Operator and Transmission   
Developer shall name the other Party, its parent, associated and Affiliate companies and their   
respective directors, officers, agents, servants and employees (“Other Party Group”) as additional   
insureds using ISO CG Endorsements: CG 20 33 04 13, and CG 20 37 04 13 or CG 20 10 04 13   
and CG 20 37 04 13 or equivalent to or better forms. All policies shall contain provisions   
whereby the insurers waive all rights of subrogation in accordance with the provisions of this   
Agreement against the Other Party Group and provide thirty (30) Calendar days advance written   
notice to the Other Party Group prior to anniversary date of cancellation or any material change   
in coverage or condition.

12.3.7 The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Liability Insurance policies shall contain provisions that specify that the policies are primary and non-contributory. Affected System Operator and Transmission Developer shall each be responsible for its respective deductibles or retentions.

12.3.8 The Commercial General Liability Insurance, Comprehensive Automobile

Liability Insurance and Excess Liability Insurance policies, if written on a Claims First Made Basis, shall be maintained in full force and effect for at least three (3) years after termination of this Agreement, which coverage may be in the form of tail coverage or extended reporting period coverage if agreed by the Transmission Developer and Affected System Operator.

12.3.9 If applicable, Pollution Liability Insurance in an amount no less than

$7,500,000 per occurrence and $7,500,000 in the aggregate. The policy will provide coverage for claims resulting from pollution or other environmental impairment arising out of or in   
connection with work performed on the premises by the other party, its contractors and and/or subcontractors. Such insurance is to include coverage for, but not be limited to, cleanup, third party bodily injury and property damage and remediation and will be written on an occurrence basis. The policy shall name the Other Party Group as additional insureds, be primary and   
contain a waiver of subrogation.

12.3.10 The requirements contained herein as to the types and limits of all

insurance to be maintained by the Affected System Operator and Transmission Developer are not intended to and shall not in any manner, limit or qualify the liabilities and obligations assumed by those Parties under this Agreement.

12.3.11 Within ten (10) days following execution of this Agreement, and as soon

as practicable after the end of each fiscal year or at the renewal of the insurance policy and in any event within ninety (90) days thereafter, Affected System Operator and Transmission Developer shall provide certificate of insurance for all insurance required in this Agreement, executed by each insurer or by an authorized representative of each insurer.

22

SERVICE AGREEMENT NO. 2622

12.3.12 Notwithstanding the foregoing, Affected System Operator and

Transmission Developer may each self-insure to meet the minimum insurance requirements of   
Articles 12.3.1 through 12.3.9 to the extent it maintains a self-insurance program; provided that,   
such Party’s senior debt is rated at investment grade, or better, by Standard & Poor’s and that its   
self-insurance program meets the minimum insurance requirements of Articles 12.3.1 through

12.3.9. In the event that a Party is permitted to self-insure pursuant to this Article 12.3.12, it

shall notify the other Party that it meets the requirements to self-insure and that its self-insurance program meets the minimum insurance requirements in a manner consistent with that specified in Articles 12.3.1 through 12.3.9 and provide evidence of such coverages. For any period of   
time that a Party’s senior debt is unrated by Standard & Poor’s or is rated at less than investment grade by Standard & Poor’s, such Party shall comply with the insurance requirements applicable to it under Articles 12.3.1 through 12.3.9.

12.3.13 Transmission Developer and Affected System Operator agree to report to

each other in writing as soon as practical all accidents or occurrences resulting in injuries to any person, including death, and any property damage arising out of this Agreement.

12.3.14 Subcontractors of Affected System Operator and Transmission Developer

must maintain the same insurance requirements stated under Articles 12.3.1 through 12.3.9 and comply with the Additional Insured requirements herein. In addition, their policies must state that they are primary and non-contributory and contain a waiver of subrogation.

ARTICLE 13. ASSIGNMENT

This Agreement may be assigned by a Party only with the written consent of the other

Parties; provided that a Party may assign this Agreement without the consent of the other Parties   
to any Affiliate of the assigning Party with an equal or greater credit rating and with the legal   
authority and operational ability to satisfy the obligations of the assigning Party under this   
Agreement; provided further that a Party may assign this Agreement without the consent of the   
other Parties in connection with the sale, merger, restructuring, or transfer of a substantial   
portion or all of its assets, so long as the assignee in such a transaction directly assumes in   
writing all rights, duties and obligations arising under this Agreement; and provided further that   
the Transmission Developer shall have the right to assign this Agreement, without the consent of   
the NYISO or Affected System Operator, for collateral security purposes to aid in providing   
financing for the Affected System Upgrade Facilities, provided that the Transmission Developer   
will promptly notify the NYISO and Affected System Operator of any such assignment. Any   
financing arrangement entered into by the Transmission Developer pursuant to this Article will   
provide that prior to or upon the exercise of the secured party’s, trustee’s or mortgagee’s   
assignment rights pursuant to said arrangement, the secured creditor, the trustee or mortgagee   
will notify the NYISO and Affected System Operator of the date and particulars of any such   
exercise of assignment right(s) and will provide the NYISO and Affected System Operator with   
proof that it meets the requirements of Articles 6.2 and 12.3. Any attempted assignment that   
violates this Article is void and ineffective. Any assignment under this Agreement shall not   
relieve a Party of its obligations, nor shall a Party’s obligations be enlarged, in whole or in part,   
by reason thereof. Where required, consent to assignment will not be unreasonably withheld,   
conditioned or delayed.

23

SERVICE AGREEMENT NO. 2622

ARTICLE 14. SEVERABILITY

If any provision in this Agreement is finally determined to be invalid, void or

unenforceable by any court or other Governmental Authority having jurisdiction, such

determination shall not invalidate, void or make unenforceable any other provision, agreement or covenant of this Agreement.

ARTICLE 15. COMPARABILITY

The Parties will comply with all applicable comparability and code of conduct laws, rules and regulations, as amended from time to time.

ARTICLE 16. CONFIDENTIALITY

16.1 Confidentiality.

Certain information exchanged by the Parties during the term of this Agreement shall   
constitute confidential information (“Confidential Information”) and shall be subject to this   
Article 16.

If requested by a Party receiving information, the Party supplying the information shall provide in writing, the basis for asserting that the information referred to in this Article warrants confidential treatment, and the requesting Party may disclose such writing to the appropriate Governmental Authority. Each Party shall be responsible for the costs associated with affording confidential treatment to its information.

16.2 Term.

During the term of this Agreement, and for a period of three (3) years after the expiration or termination of this Agreement, except as otherwise provided in this Article 16, each Party shall hold in confidence and shall not disclose to any person Confidential Information.

16.3 Confidential Information.

The following shall constitute Confidential Information: (1) any non-public information that is treated as confidential by the disclosing Party and which the disclosing Party identifies as Confidential Information in writing at the time, or promptly after the time, of disclosure; or (2) information designated as Confidential Information by the NYISO Code of Conduct contained in Attachment F to the ISO OATT.

16.4 Scope.

Confidential Information shall not include information that the receiving Party can

demonstrate: (1) is generally available to the public other than as a result of a disclosure by the   
receiving Party; (2) was in the lawful possession of the receiving Party on a non-confidential   
basis before receiving it from the disclosing Party; (3) was supplied to the receiving Party   
without restriction by a third party, who, to the knowledge of the receiving Party after due   
inquiry, was under no obligation to the disclosing Party to keep such information confidential;

24

SERVICE AGREEMENT NO. 2622

(4) was independently developed by the receiving Party without reference to Confidential

Information of the disclosing Party; (5) is, or becomes, publicly known, through no wrongful act   
or omission of the receiving Party or Breach of this Agreement; or (6) is required, in accordance   
with Article 16.9 of this Agreement, Order of Disclosure, to be disclosed by any Governmental   
Authority or is otherwise required to be disclosed by law or subpoena, or is necessary in any   
legal proceeding establishing rights and obligations under this Agreement. Information   
designated as Confidential Information will no longer be deemed confidential if the Party that   
designated the information as confidential notifies the other Party that it no longer is   
confidential.

16.5 Release of Confidential Information.

No Party shall release or disclose Confidential Information to any other person, except to   
its Affiliates (limited by FERC Standards of Conduct requirements), subcontractors, employees,   
consultants, or to parties who may be considering providing financing to or equity participation   
with Transmission Developer, or to potential purchasers or assignees of a Party, on a need-to-  
know basis in connection with this Agreement, unless such person has first been advised of the   
confidentiality provisions of this Article 16 and has agreed to comply with such provisions.

Notwithstanding the foregoing, a Party providing Confidential Information to any person shall   
remain primarily responsible for any release of Confidential Information in contravention of this   
Article 16.

16.6 Rights.

Each Party retains all rights, title, and interest in the Confidential Information that each Party discloses to the other Party. The disclosure by each Party to the other Parties of   
Confidential Information shall not be deemed a waiver by any Party or any other person or entity of the right to protect the Confidential Information from public disclosure.

16.7 No Warranties.

By providing Confidential Information, no Party makes any warranties or representations   
as to its accuracy or completeness. In addition, by supplying Confidential Information, no Party   
obligates itself to provide any particular information or Confidential Information to the other   
Parties nor to enter into any further agreements or proceed with any other relationship or joint   
venture.

16.8 Standard of Care.

Each Party shall use at least the same standard of care to protect Confidential Information it receives as it uses to protect its own Confidential Information from unauthorized disclosure, publication or dissemination. Each Party may use Confidential Information solely to fulfill its obligations to the other Parties under this Agreement or its regulatory requirements, including the ISO OATT and NYISO Services Tariff. The NYISO shall, in all cases, treat the information it receives in accordance with the requirements of Attachment F to the ISO OATT.

25

SERVICE AGREEMENT NO. 2622

16.9 Order of Disclosure.

If a court or a Government Authority or entity with the right, power, and apparent

authority to do so requests or requires any Party, by subpoena, oral deposition, interrogatories,

requests for production of documents, administrative order, or otherwise, to disclose Confidential   
Information, that Party shall provide the other Parties with prompt notice of such request(s) or   
requirement(s) so that the other Parties may seek an appropriate protective order or waive   
compliance with the terms of this Agreement. Notwithstanding the absence of a protective order   
or waiver, the Party may disclose such Confidential Information which, in the opinion of its   
counsel, the Party is legally compelled to disclose. Each Party will use Reasonable Efforts to   
obtain reliable assurance that confidential treatment will be accorded any Confidential   
Information so furnished.

16.10 Termination of Agreement.

Upon termination of this Agreement for any reason, each Party shall, within ten (10)   
Calendar Days of receipt of a written request from the other Parties, use Reasonable Efforts to   
destroy, erase, or delete (with such destruction, erasure, and deletion certified in writing to the   
other Parties) or return to the other Parties, without retaining copies thereof, any and all written   
or electronic Confidential Information received from the other Parties pursuant to this   
Agreement.

16.11 Remedies.

The Parties agree that monetary damages would be inadequate to compensate a Party for   
another Party’s Breach of its obligations under this Article 16. Each Party accordingly agrees   
that the other Parties shall be entitled to equitable relief, by way of injunction or otherwise, if the   
first Party Breaches or threatens to Breach its obligations under this Article 16, which equitable   
relief shall be granted without bond or proof of damages, and the receiving Party shall not plead   
in defense that there would be an adequate remedy at law. Such remedy shall not be deemed an   
exclusive remedy for the Breach of this Article 16, but shall be in addition to all other remedies   
available at law or in equity. The Parties further acknowledge and agree that the covenants

contained herein are necessary for the protection of legitimate business interests and are

reasonable in scope. No Party, however, shall be liable for indirect, incidental, or consequential   
or punitive damages of any nature or kind resulting from or arising in connection with this   
Article 16.

16.12 Disclosure to FERC, its Staff, or a State.

Notwithstanding anything in this Article 16 to the contrary, and pursuant to 18 C.F.R.   
section 1b.20, if FERC or its staff, during the course of an investigation or otherwise, requests   
information from one of the Parties that is otherwise required to be maintained in confidence   
pursuant to this Agreement or the ISO OATT, the Party shall provide the requested information   
to FERC or its staff, within the time provided for in the request for information. In providing the   
information to FERC or its staff, the Party must, consistent with 18 C.F.R. section 388.112,   
request that the information be treated as confidential and non-public by FERC and its staff and   
that the information be withheld from public disclosure. Parties are prohibited from notifying

26

SERVICE AGREEMENT NO. 2622

the other Parties to this Agreement prior to the release of the Confidential Information to the

Commission or its staff. The Party shall notify the other Parties to the Agreement when it is

notified by FERC or its staff that a request to release Confidential Information has been received by FERC, at which time the Parties may respond before such information would be made public, pursuant to 18 C.F.R. section 388.112. Requests from a state regulatory body conducting a   
confidential investigation shall be treated in a similar manner if consistent with the applicable state rules and regulations. A Party shall not be liable for any losses, consequential or otherwise, resulting from that Party divulging Confidential Information pursuant to a FERC or state   
regulatory body request under this paragraph.

16.13 Required Notices Upon Requests or Demands for Confidential Information

Except as otherwise expressly provided herein, no Party shall disclose Confidential

Information to any person not employed or retained by the Party possessing the Confidential

Information, except to the extent disclosure is (i) required by law; (ii) reasonably deemed by the   
disclosing Party to be required to be disclosed in connection with a dispute between or among   
the Parties, or the defense of litigation or dispute; (iii) otherwise permitted by consent of the   
other Party, such consent not to be unreasonably withheld; or (iv) necessary to fulfill its   
obligations under this Agreement, the ISO OATT or the NYISO Services Tariff. Prior to any   
disclosures of a Party’s Confidential Information under this subparagraph, or if any third party or   
Governmental Authority makes any request or demand for any of the information described in   
this subparagraph, the disclosing Party agrees to promptly notify the other Party in writing and   
agrees to assert confidentiality and cooperate with the other Party in seeking to protect the   
Confidential Information from public disclosure by confidentiality agreement, protective order or   
other reasonable measures.

ARTICLE 17. AFFECTED SYSTEM OPERATOR NOTICES OF ENVIRONMENTAL   
 RELEASES

Affected System Operator shall notify Transmission Developer, first orally and then in

writing, of the release of any Hazardous Substances, any asbestos or lead abatement activities, or any type of remediation activities related to the Affected System Upgrade Facilities, each of which may reasonably be expected to affect the Transmission Developer. The Affected System Operator shall: (i) provide the notice as soon as practicable, provided such Party makes a good faith effort to provide the notice no later than twenty-four hours after such Party becomes aware of the occurrence; and (ii) promptly furnish to the other Party copies of any publicly available reports filed with any Governmental Authorities addressing such events.

ARTICLE 18. INFORMATION REQUIRMENT

18.1 Information Acquisition

Affected System Operator and Transmission Developer shall each submit specific   
information regarding the electrical characteristics of their respective facilities to the other   
Parties and to the NYISO as described below and in accordance with Applicable Reliability   
Standards.

27

SERVICE AGREEMENT NO. 2622

18.2 Information Submission Concerning the Affected System Upgrade Facilities

On a monthly basis, Affected System Operator and Transmission Developer shall each provide the other Parties a status report on the engineering, construction, and installation of the Affected System Upgrade Facilities for which it has responsibility pursuant to Appendix A,   
including, but not limited to, the following information: (1) progress to date; (2) a description of the activities since the last report; (3) a description of the action items for the next period; and (4) the delivery status of equipment ordered.

18.3 Information Submission Concerning the Transmission Project

Transmission Developer shall submit a completed copy of the Transmission Project data   
requirements contained in Appendix 1 to the Transmission Interconnection Procedures. It shall   
also include any additional information provided to Affected System Operator for the Facilities   
Study. Information in this submission shall be the most current Transmission Project design or   
expected performance data. Information submitted for stability models shall be compatible with   
NYISO standard models. If there is no compatible model, the Transmission Developer will work   
with a consultant mutually agreed to by the Parties to develop and supply a standard model and   
associated information.

If the Transmission Developer’s data is different from what was originally provided to   
Affected System Operator and NYISO pursuant to a Transmission Interconnection Study   
agreement among Affected System Operator, NYISO and Transmission Developer and this   
difference may be reasonably expected to affect the other Parties’ facilities or the New York   
State Transmission System, but does not require the submission of a new Transmission   
Interconnection Application, then NYISO will conduct appropriate studies to determine the   
impact on the New York State Transmission System based on the actual data submitted pursuant   
to this Article 18.3. Such studies will provide an estimate of any additional modifications to the   
New York State Transmission System or Network Upgrade Facilities based on the actual data   
and a good faith estimate of the costs thereof. The Transmission Developer shall not begin Trial   
Operation for the Transmission Project until such studies are completed. The Transmission   
Developer shall be responsible for the cost of any modifications required by the actual data,   
including the cost of any required studies.

18.4 Information Supplementation

Affected System Operator and Transmission Developer shall supplement its information submissions described above in this Article 18 with any and all “as built” information or “as   
tested” performance information that differs from the initial submissions or, alternatively, written confirmation that no such differences exist.

ARTICLE 19. INFORMATION ACCESS AND AUDIT RIGHTS

19.1 Information Access.

Each Party (“Disclosing Party”) shall make available to another Party (“Requesting

Party”) information that is in the possession of the Disclosing Party and is necessary in order for

28

SERVICE AGREEMENT NO. 2622

the Requesting Party to: (i) verify the costs incurred by the Disclosing Party for which the

Requesting Party is responsible under this Agreement; and (ii) carry out its obligations and

responsibilities under this Agreement. The Parties shall not use such information for purposes other than those set forth in this Article 18.1 of this Agreement and to enforce their rights under this Agreement.

19.2 Reporting of Non-Force Majeure Events.

Each Party (the “Notifying Party”) shall notify the other Parties when the Notifying Party becomes aware of its inability to comply with the provisions of this Agreement for a reason other than a Force Majeure event. The Parties agree to cooperate with each other and provide   
necessary information regarding such inability to comply, including the date, duration, reason for the inability to comply, and corrective actions taken or planned to be taken with respect to such inability to comply. Notwithstanding the foregoing, notification, cooperation or information   
provided under this Article shall not entitle the Party receiving such notification to allege a cause for anticipatory breach of this Agreement.

19.3 Audit Rights.

Subject to the requirements of confidentiality under Article 16 of this Agreement, each   
Party shall have the right, during normal business hours, and upon prior reasonable notice to   
another Party, to audit at its own expense the other Party’s accounts and records pertaining to the other Party’s performance or satisfaction of its obligations under this Agreement. Such audit   
rights shall include audits of the other Party’s costs, and calculation of invoiced amounts. Any   
audit authorized by this Article shall be performed at the offices where such accounts and   
records are maintained and shall be limited to those portions of such accounts and records that   
relate to the Party’s performance and satisfaction of obligations under this Agreement. Each   
Party shall keep such accounts and records for a period equivalent to the audit rights periods   
described in Article 18.4 of this Agreement.

19.4 Audit Rights Periods.

19.4.1 Audit Rights Period for Construction-Related Accounts and Records.

Accounts and records related to the design, engineering, procurement, and construction of the Affected System Upgrade Facilities shall be subject to audit for a period of twenty-four   
months following the issuance by Affected System Operator or Transmission Developer, as   
applicable, of a final invoice in accordance with Article 7.2 of this Agreement.

19.4.2 Audit Rights Period for All Other Accounts and Records.

Accounts and records related to a Party’s performance or satisfaction of its obligations   
under this Agreement other than those described in Article 18.4.1 of this Agreement shall be   
subject to audit as follows: (i) for an audit relating to cost obligations, the applicable audit rights   
period shall be twenty-four months after the auditing Party’s receipt of an invoice giving rise to   
such cost obligations; and (ii) for an audit relating to all other obligations, the applicable audit   
rights period shall be twenty-four months after the event for which the audit is sought.

29

SERVICE AGREEMENT NO. 2622

19.5 Audit Results.

If an audit by a Party determines that an overpayment or an underpayment has occurred, a notice of such overpayment or underpayment shall be given to the other Party together with   
those records from the audit which support such determination.

ARTICLE 20. SUBCONTRACTORS

20.1 General.

Nothing in this Agreement shall prevent a Party from utilizing the services of any

subcontractor as it deems appropriate to perform its obligations under this Agreement; provided, however, that each Party shall require its subcontractors to comply with all applicable terms and conditions of this Agreement in providing such services and each Party shall remain primarily liable to the other Parties for the performance of such subcontractor.

20.2 Responsibility of Principal.

The creation of any subcontract relationship shall not relieve the hiring Party of any of its   
obligations under this Agreement. The hiring Party shall be fully responsible to the other Parties   
for the acts or omissions of any subcontractor the hiring Party hires as if no subcontract had been   
made; provided, however, that in no event shall the NYISO or Affected System Operator be   
liable for the actions or inactions of the Transmission Developer or its subcontractors with   
respect to obligations of the Transmission Developer under Article 5 of this Agreement. Any   
applicable obligation imposed by this Agreement upon the hiring Party shall be equally binding   
upon, and shall be construed as having application to, any subcontractor of such Party.

20.3 No Limitation by Insurance.

The obligations under this Article 19 will not be limited in any way by any limitation of subcontractor’s insurance.

ARTICLE 21. DISPUTES

21.1 Submission.

In the event any Party has a dispute, or asserts a claim, that arises out of or in connection   
with this Agreement or its performance (a “Dispute”), such Party shall provide the other Parties   
with written notice of the Dispute (“Notice of Dispute”). Such Dispute shall be referred to a   
designated senior representative of each Party for resolution on an informal basis as promptly as   
practicable after receipt of the Notice of Dispute by the other Parties. In the event the designated   
representatives are unable to resolve the Dispute through unassisted or assisted negotiations   
within thirty (30) Calendar Days of the other Parties’ receipt of the Notice of Dispute, such   
Dispute may, upon mutual agreement of the Parties, be submitted to arbitration and resolved in   
accordance with the arbitration procedures set forth below. In the event the Parties do not agree   
to submit such Dispute to arbitration, each Party may exercise whatever rights and remedies it   
may have in equity or at law consistent with the terms of this Agreement.

30

SERVICE AGREEMENT NO. 2622

21.2 External Arbitration Procedures.

Any arbitration initiated under this Agreement shall be conducted before a single neutral   
arbitrator appointed by the Parties. If the Parties fail to agree upon a single arbitrator within ten

(10) Calendar Days of the submission of the Dispute to arbitration, each Party shall choose one   
arbitrator who shall sit on a three-member arbitration panel. In each case, the arbitrator(s) shall   
be knowledgeable in electric utility matters, including electric transmission and bulk power   
issues, and shall not have any current or past substantial business or financial relationships with   
any party to the arbitration (except prior arbitration). The arbitrator(s) shall provide each of the   
Parties an opportunity to be heard and, except as otherwise provided herein, shall conduct the   
arbitration in accordance with the Commercial Arbitration Rules of the American Arbitration   
Association (“Arbitration Rules”) and any applicable FERC regulations or RTO rules; provided,   
however, in the event of a conflict between the Arbitration Rules and the terms of this Article 20,   
the terms of this Article 20 shall prevail.

21.3 Arbitration Decisions.

Unless otherwise agreed by the Parties, the arbitrator(s) shall render a decision within

ninety (90) Calendar Days of appointment and shall notify the Parties in writing of such decision   
and the reasons therefor. The arbitrator(s) shall be authorized only to interpret and apply the   
provisions of this Agreement and shall have no power to modify or change any provision of this   
Agreement in any manner. The decision of the arbitrator(s) shall be final and binding upon the   
Parties, and judgment on the award may be entered in any court having jurisdiction. The   
decision of the arbitrator(s) may be appealed solely on the grounds that the conduct of the   
arbitrator(s), or the decision itself, violated the standards set forth in the Federal Arbitration Act   
or the Administrative Dispute Resolution Act. The final decision of the arbitrator must also be   
filed with FERC if it affects jurisdictional rates, terms and conditions of service or Affected   
System Upgrade Facilities.

21.4 Costs.

Each Party shall be responsible for its own costs incurred during the arbitration process   
and for the following costs, if applicable: (1) the cost of the arbitrator chosen by the Party to sit   
on the three member panel; or (2) one-third the cost of the single arbitrator jointly chosen by the   
Parties.

21.5 Termination.

Notwithstanding the provisions of this Article 20, any Party may terminate this

Agreement in accordance with its provisions or pursuant to an action at law or equity. The issue of whether such a termination is proper shall not be considered a Dispute hereunder.

ARTICLE 22. REPRESENTATIONS, WARRANTIES AND COVENANTS

22.1 General.

Each Party makes the following representations, warranties and covenants:

31

SERVICE AGREEMENT NO. 2622

22.1.1 Good Standing.

Such Party is duly organized, validly existing and in good standing under the laws of the state in which it is organized, formed, or incorporated, as applicable; that it is qualified to do business in the State of New York; and that it has the corporate power and authority to own its properties, to carry on its business as now being conducted and to enter into this Agreement and carry out the transactions contemplated hereby and perform and carry out all covenants and obligations on its part to be performed under and pursuant to this Agreement.

22.1.2 Authority.

Such Party has the right, power and authority to enter into this Agreement, to become a   
Party hereto and to perform its obligations hereunder. This Agreement is a legal, valid and   
binding obligation of such Party, enforceable against such Party in accordance with its terms,   
except as the enforceability thereof may be limited by applicable bankruptcy, insolvency,   
reorganization or other similar laws affecting creditors’ rights generally and by general equitable   
principles (regardless of whether enforceability is sought in a proceeding in equity or at law).

22.1.3 No Conflict.

The execution, delivery and performance of this Agreement does not violate or conflict with the organizational or formation documents, or bylaws or operating agreement, of such   
Party, or any judgment, license, permit, order, material agreement or instrument applicable to or binding upon such Party or any of its assets.

22.1.4 Consent and Approval.

Such Party has sought or obtained, or, in accordance with this Agreement will seek or obtain, each consent, approval, authorization, order, or acceptance by any Governmental   
Authority in connection with the execution, delivery and performance of this Agreement, and it will provide to any Governmental Authority notice of any actions under this Agreement that are required by Applicable Laws and Regulations.

ARTICLE 23. MISCELLANEOUS

23.1 Binding Effect.

This Agreement and the rights and obligations hereof, shall be binding upon and shall inure to the benefit of the successors and permitted assigns of the Parties hereto.

23.2 Conflicts.

If there is a discrepancy or conflict between or among the terms and conditions of this cover agreement and the Appendices hereto, the terms and conditions of this cover agreement shall be given precedence over the Appendices, except as otherwise expressly agreed to in   
writing by the Parties.

32

SERVICE AGREEMENT NO. 2622

23.3 Rules of Interpretation.

This Agreement, unless a clear contrary intention appears, shall be construed and

interpreted as follows: (1) the singular number includes the plural number and vice versa; (2)

reference to any person includes such person’s successors and assigns but, in the case of a Party,   
only if such successors and assigns are permitted by this Agreement, and reference to a person in   
a particular capacity excludes such person in any other capacity or individually; (3) reference to   
any agreement (including this Agreement), document, instrument or tariff means such   
agreement, document, instrument, or tariff as amended or modified and in effect from time to   
time in accordance with the terms thereof and, if applicable, the terms hereof; (4) reference to   
any Applicable Laws and Regulations means such Applicable Laws and Regulations as   
amended, modified, codified, or reenacted, in whole or in part, and in effect from time to time,   
including, if applicable, rules and regulations promulgated thereunder; (5) unless expressly stated   
otherwise, reference to any Article, Section or Appendix means such Article of this Agreement   
or such Appendix to this Agreement, or such Section to the Transmission Interconnection   
Procedures or such Appendix to the Transmission Interconnection Procedures, as the case may   
be; (6) “hereunder”, “hereof’, “herein”, “hereto” and words of similar import shall be deemed   
references to this Agreement as a whole and not to any particular Article or other provision   
hereof or thereof; (7) “including” (and with correlative meaning “include”) means including   
without limiting the generality of any description preceding such term; and (8) relative to the   
determination of any period of time, “from” means “from and including”, “to” means “to but   
excluding” and “through” means “through and including”.

23.4 Compliance.

Each Party shall perform its obligations under this Agreement in accordance with

Applicable Laws and Regulations, Applicable Reliability Standards, the ISO OATT and Good Utility Practice. To the extent a Party is required or prevented or limited in taking any action by such regulations and standards, such Party shall not be deemed to be in Breach of this Agreement for its compliance therewith. When any Party becomes aware of such a situation, it shall notify the other Parties promptly so that the Parties can discuss the amendment to this Agreement that is appropriate under the circumstances.

23.5 Joint and Several Obligations.

Except as otherwise stated herein, the obligations of NYISO, Transmission Developer and Affected System Operator are several, and are neither joint nor joint and several.

23.6 Entire Agreement.

This Agreement, including all Appendices and Schedules attached hereto, constitutes the   
entire agreement between the Parties with reference to the subject matter hereof, and supersedes   
all prior and contemporaneous understandings or agreements, oral or written, between the Parties   
with respect to the subject matter of this Agreement. There are no other agreements,   
representations, warranties, or covenants which constitute any part of the consideration for, or   
any condition to, either Party’s compliance with its obligations under this Agreement.

33

SERVICE AGREEMENT NO. 2622

23.7 No Third Party Beneficiaries.

This Agreement is not intended to and does not create rights, remedies, or benefits of any character whatsoever in favor of any persons, corporations, associations, or entities other than the Parties, and the obligations herein assumed are solely for the use and benefit of the Parties, their successors in interest and permitted their assigns.

23.8 Waiver.

The failure of a Party to this Agreement to insist, on any occasion, upon strict

performance of any provision of this Agreement will not be considered a waiver of any

obligation, right, or duty of, or imposed upon, such Party. Any waiver at any time by either   
Party of its rights with respect to this Agreement shall not be deemed a continuing waiver or a   
waiver with respect to any other failure to comply with any other obligation, right, duty of this   
Agreement. Any waiver of this Agreement shall, if requested, be provided in writing.

23.9 Headings.

The descriptive headings of the various Articles of this Agreement have been inserted for convenience of reference only and are of no significance in the interpretation or construction of this Agreement.

23.10 Multiple Counterparts.

This Agreement may be executed in two or more counterparts, each of which is deemed an original but all constitute one and the same instrument.

23.11 Amendment.

The Parties may by mutual agreement amend this Agreement, by a written instrument duly executed by all three of the Parties.

23.12 Modification by the Parties.

The Parties may by mutual agreement amend the Appendices to this Agreement, by a   
written instrument duly executed by all three of the Parties. Such an amendment shall become   
effective and a part of this Agreement upon satisfaction of all Applicable Laws and Regulations.

23.13 Reservation of Rights.

NYISO and Affected System Operator shall have the right to make unilateral filings with   
FERC to modify this Agreement with respect to any rates, terms and conditions, charges,   
classifications of service, rule or regulation under section 205 or any other applicable provision   
of the Federal Power Act and FERC’s rules and regulations thereunder, and Transmission   
Developer shall have the right to make a unilateral filing with FERC to modify this Agreement   
pursuant to section 206 or any other applicable provision of the Federal Power Act and FERC’s   
rules and regulations thereunder; provided that each Party shall have the right to protest any such   
filing by another Party and to participate fully in any proceeding before FERC in which such

34

SERVICE AGREEMENT NO. 2622

modifications may be considered. Nothing in this Agreement shall limit the rights of the Parties   
or of FERC under sections 205 or 206 of the Federal Power Act and FERC’s rules and   
regulations thereunder, except to the extent that the Parties otherwise mutually agree as provided   
herein.

23.14 No Partnership.

This Agreement shall not be interpreted or construed to create an association, joint

venture, agency relationship, or partnership among the Parties or to impose any partnership

obligation or partnership liability upon any Party. No Party shall have any right, power or

authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, any other Party.

23.15 Other Transmission Rights.

Notwithstanding any other provision of this Agreement, nothing herein shall be construed   
as relinquishing or foreclosing any rights, including but not limited to firm transmission rights,   
capacity rights, or transmission congestion rights that the Transmission Developer shall be   
entitled to, now or in the future under any other agreement or tariff as a result of, or otherwise   
associated with, the transmission capacity, if any, created by the Affected System Upgrade   
Facilities.

35

SERVICE AGREEMENT NO. 2622

IN WITNESS WHEREOF, the Parties have executed this Agreement in duplicate originals,   
each of which shall constitute and be an original effective Agreement between the Parties.

New York Independent System Operator, Inc.

By:

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
Title:

Date:

New York Power Authority

By:

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
Title:

Date:

New York Transco, LLC

By: By: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name: Paul Haering Name: Victor Mullin

Title: Vice President of Capital Investment Title: President

Date: Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

36

SERVICE AGREEMENT NO. 2622

APPENDICES

Appendix A

EPC Services

Appendix B

Addresses for Delivery of Notices and Billings

Appendix C

In-Service Date

SERVICE AGREEMENT NO. 2622

APPENDIX A

EPC SERVICES

I. Affected System Upgrade Facilities

The Transmission Developer is developing the Transmission Project, which was selected by the NYISO as the more efficient or cost effective transmission solution to address Segment B of the AC Transmission Public Policy Transmission Needs. The Transmission Interconnection Studies for the Transmission Project identified certain potential adverse impacts at Connecting Transmission Owner’s 345 kV Dolson Ave Substation. As detailed below, Transmission   
Developer will evaluate the existing relay calculations and settings for the Dolson Ave.   
Substation and shall prepare all necessary relay calculations and settings for relays that are   
required to be reset as a result of the Transmission Project. Affected System Operator will   
perform any required modifications to the relay settings.

A. Affected System Operator’s EPC Services

The Affected System Operator’s work responsibilities under this Agreement shall

generally consist of the following, which shall be performed in accordance with the terms of this Agreement:

• Project management and engineering services (at no cost to Affected System Operator)

associated with the collection and transfer of all materials and data required for the

Transmission Developer or its contractor to perform the evaluation of existing relay

calculations and settings for the Dolson Ave. Substation, which are considered Network Upgrade Facilities in connection with the Transmission Project.

• Project management and engineering services (at no cost to Affected System Operator) to

support the Transmission Developer’s performance and completion of a relay setting evaluation, which may include the provision of relay setting calculations, vendor   
drawings, specifications, procedures, and any design, procurement and/or construction standards as may become necessary for the Transmission Developer or its contractor to complete the design, procurement and construction of any relays that are required to be replaced as a result of the relay evaluation. All drawings shall be provided in the format in which they are available, primarily PDF or Vellum.

• Timely review of the Transmission Developer’s (1) relay setting evaluation results, (2) if

required, any revised relay setting calculations, and (3) if relay replacement is required to   
achieve the desired protective performance, then engineering documents and packages,   
approval of technical designs, equipment specifications, construction drawings, relay   
settings will also be provided for Affected System Operator review and approval. In the   
event that relay procurement specifications are required for any relays, they shall be   
provided to Affected System Operator for its review and approval. The Transmission   
Developer or its contractor will create and issue any purchase orders as needed.

A-1

SERVICE AGREEMENT NO. 2622

• Provide Transmission Developer or its contractor and subcontractors reasonable access to   
 the Dolson Ave. Substation as needed to perform the engineering, procurement, and   
 construction activities as may be required.

The Affected System Operator’s specific work responsibilities under this Agreement   
shall consist of the following, which shall be performed in accordance with the terms of this   
Agreement:

1. The Facilities Study Report for the Transmission Project has determined that relays,

located at the Dolson Ave. Substation may be affected by the Transmission Project.

2. It is anticipated that the Transmission Project upgrades and modifications to the

Dolson Ave. Substation will require the existing relay protection and control schemes   
to be reviewed and evaluated for impacts by the Transmission Project. Affected   
System Operator shall provide any existing substation relay setting calculations and   
relay files, in currently available format. Affected System Operator shall provide   
standard protection guidelines or system protection philosophies to be followed   
during the evaluation.

3. At no cost to Affected System Operator, in the event that relays cannot be reset to

achieve the required protective level, certain relays may require replacement. As   
such, Affected System Operator will support procurement and related procurement   
activities as requested by the Transmission Developer. Transmission Developer or its   
contractor is responsible for identifying and procuring any long-lead time items.

4. Participate in, or establish as requested, design review meetings to discuss relay

settings evaluation results and proposals, designs submitted, standards that are to be   
included/adjusted, make station field visits if existing relay replacements are required,   
and have necessary attendance at regularly occurring project review and   
coordination/review meetings during the course of the Transmission Project.

5. Develop a detailed schedule, and status updates, for the completion of implementing

any Affected System Operator relay settings and/or relay replacements if deemed

necessary to achieve the relays’ required protective levels. In the event that relay

resetting or replacement is required, then the Transmission Project’s in-service date of mid-2023 must be factored into consideration when looking at implementation

6. Perform start up commissioning and testing, and any notifications as may be required

by the NYISO RAD Manual (Manual 24).

7. Update Affected System Operator’s substation equipment procedures to reflect relay

modifications as may be needed.

8. Provide contact information for the Affected System Operator designees for review of

relay calculation and setting review evaluation.

A-2

SERVICE AGREEMENT NO. 2622

9. Approve the use of outside experts, counsel, consultants, and contractors in

furtherance of Affected System Operator’s work responsibilities contemplated herein as needed, or as requested by the Transmission Developer.

10. Provide a detailed listing of any technical materials that are required by Affected   
 System Operator to complete the relay evaluation.

For the avoidance of doubt: Affected System Operator shall not have any responsibility   
for seeking or acquiring any real property rights in connection with Affected System Operator’s   
work responsibilities under this Agreement, the Transmission Project, or this Agreement,   
including, without limitation, licenses, consents, permissions, certificates, approvals, or   
authorizations, or fee, easement or right of way interests. Although the Transmission Developer   
shall undertake any permitting activities, Affected System Operator acknowledges that formal   
signature by Affected System Operator may be required as determined by local permitting   
requirements. If so required, Affected System Operator agrees to execute such permits on a   
timely basis.

For further avoidance of any doubt, Affected System Operator’s work responsibilities

described in this Appendix A and under this Agreement shall occur at no cost to Affected System Operator.

B. Transmission Developer’s EPC Services

Transmission Developer’s specific work responsibilities under this Agreement shall   
consist of the following, which shall be performed in accordance with the terms of this   
Agreement:

1. Transmission Developer or its designee shall review relevant data and information

related to the Dolson Ave. Substation relay settings, including the CPV Valley RTDS   
Test Specification & Final Report, and evaluate the acceptability of the existing   
settings for the transmission system currents resulting from the Transmission Project.

2. Transmission Developer or its designee shall prepare and submit to Affected System   
 Operator for its review and approval the results of the completed relay evaluation   
 study, including results of RTDS Tests, if required, and all necessary   
 calculations/files for relays that are required to be reset.

3. In the event that relays cannot be reset and achieve the required protective levels,

Transmission Developer or its designee shall prepare and submit to Affected System Operator for its review and approval all necessary relay procurement / equipment specifications and drawings.

4. Transmission Developer or its designee shall prepare and submit to Affected System   
 Operator for its review and approval all necessary engineering packages as may be   
 needed.

A-3

SERVICE AGREEMENT NO. 2622

5. Transmission Developer or its designee shall setup, run and coordinate, at a

minimum, monthly meetings for relay evaluation study status, support and updates. This includes coordination with Central Hudson Gas and Electric Corporation on status of relay settings evaluation/implementation at Rock Tavern Station.

6. Other responsibilities, including performance of RTDS Tests if required, and access   
 deemed necessary by Transmission Developer or Affected System Operator to   
 facilitate performance of the Affected System Operator’s work responsibilities under   
 this Agreement.

7. Transmission Developer or its designee will perform the procurement of equipment   
 and materials required to incorporate the Transmission Project.

8. Transmission Developer will work with equipment suppliers to ensure that the

manufacturers’ warranties are in the name of Affected System Operator for Affected System Operator’s owned / retained upgrades.

Transmission Developer’s work responsibilities under this Agreement, along with

Affected System Operator’s work responsibilities under this Agreement, shall be performed at Transmission Developer’s cost, and at no cost to Affected System Operator.

II. Affected System Upgrade Facilities Estimated Total Costs

Description Estimated Costs

Affected System Upgrade Facilities $ 179,840

Total $ 179,840

III. Security

In accordance with Articles 6.2 and 7.1 of this Agreement, Transmission Developer shall make a lump sum payment of $179,840 as Security for Affected System Operator’s estimated costs to construct and install the Affected System Upgrade Facilities, such payment to be made within thirty (30) Calendar Days after the Effective Date of this Agreement.

The Affected System Operator shall not be obligated to commence engineering or

construction, as applicable, unless the Affected System Operator has received payment in full of the Security as contemplated above.

The Affected System Operator may draw upon the Security to fulfill its obligations to construct the Affected System Upgrade Facilities as required under this Agreement.

The Parties acknowledge that the Security as set forth above are estimated costs only and,   
subject to Article 6.4.3 of this Agreement, shall not limit Transmission Developer’s obligation to   
pay Affected System Operator for all costs actually incurred by Affected System Operator to   
construct, and install the Affected System Upgrade Facilities as contemplated by this Agreement,

A-4

SERVICE AGREEMENT NO. 2622

and for any other unpaid amounts due and payable by Transmission Developer under the terms   
of this Agreement. If the actual cost of the Affected System Upgrade Facilities is greater than   
the agreed-to and secured amount for reasons other than those set forth in Article 6.4.2, Affected   
System Operator will invoice Transmission Developer in accordance with Articles 6.4.3 and 7.1   
for such excess costs to the extent such costs are prudently incurred, and Transmission   
Developer shall pay any such properly-issued invoice within thirty (30) Calendar Days of receipt   
in accordance with Article 7.3. Disputes between Transmission Developer and Affected System   
Operator concerning costs in excess of the agreed-to and secured amount will be resolved by the   
parties in accordance with Article 21.

Final invoicing and any final refund of Security shall be made in accordance with Articles 7.1 and 7.2 of this Agreement.

IV. Milestones

Item Milestone Date Responsible Party

1. Kick off meeting August 1, 2021 Transmission

Developer

2. 30% Calcs & Setting Review September 16, 2021 Transmission

Developer

3. Affected System Operator Review 20 Business Days Affected System

of 30% Calcs & Setting Review After Receipt of Operator

Package Review Package

4. 90% Calcs & Setting Review December 15, 2021 Transmission

Developer

5. Affected System Operator Review 20 Business Days Affected System

of 90% Calcs & Setting Review After Receipt of Operator

Package Review Package

6. Issued for Construction January 15, 2022 Transmission

Developer

7. In-Service Date On or before October Affected System

1, 2022 Operator

Transmission Developer or its contractor shall endeavor to complete the work in the

timeframe mutually agreed upon by Transmission Developer and Affected System Operator as set forth in the milestone table. At the 30% Review milestone, Transmission Developer shall provide Affected System Operator with Transmission Developer’s assessment of relay setting review and if the settings will need to be updated. Affected System Operator agrees to provide comments or approvals in accordance with the agreed upon schedule.

A-5

SERVICE AGREEMENT NO. 2622

APPENDIX B

ADDRESSES FOR DELIVERY OF NOTICES AND BILLINGS

Notices:

NYISO:

New York Independent System Operator, Inc.

Attn: Vice President, System and Resource Planning

10 Krey Boulevard

Rensselaer, NY 12144   
Phone: (518) 356-6000   
Fax: (518) 356-6118

Affected System Operator:

Sr Vice President Power Supply   
New York Power Authority   
Blenheim-Gilboa Power Project   
397 Power Plant Access Road   
Gilboa, NY 12076

Phone: (518) 287 6301   
Fax: (518) 287 6356

Transmission Developer:

New York Transco, LLC Attn: Paul Haering

Vice President Capital Investments One Hudson City Center

Hudson, NY 12534

Phone: (518) 444-4880

Email: paul.haering@nytransco.com

Billings and Payments:

Affected System Operator:

Sr Vice President Power Supply   
New York Power Authority   
Blenheim-Gilboa Power Project   
397 Power Plant Access Road   
Gilboa, NY 12076

Phone: (518) 287 6301

Or

B-1

SERVICE AGREEMENT NO. 2622

Wire payments to:

New York Power Authority Operating Fund c/o

J.P. Morgan Chase N.A.   
ABA No. 021000021   
Account No. 573-804206

Transmission Developer:

New York Transco, LLC   
One Hudson City Center   
Hudson, NY 12534

Attn: Vice President, Capital Investments Phone: ((518) 444-4880

Email: paul.haering@nytransco.com

Alternative Forms of Delivery of Notices (telephone, facsimile or email):

NYISO:

New York Independent System Operator, Inc.

Attn: Vice President, System and Resource Planning

10 Krey Boulevard

Rensselaer, NY 12144   
Phone: (518) 356-6000   
Fax: (518) 356-6118

E-mail: interconnectionsupport@nyiso.com

Affected System Operator:

Sr Vice President Power Supply   
New York Power Authority   
Blenheim-Gilboa Power Project   
397 Power Plant Access Road   
Gilboa, NY 12076

Phone: (518) 287 6301   
Fax: (518) 287 6356   
Brian.Saez@nypa.gov

B-2

SERVICE AGREEMENT NO. 2622

Transmission Developer:

New York Transco, LLC   
One Hudson City Center   
Hudson, NY 12534

Attn: Vice President, Capital Investments Phone: (518) 444-4880

Email: paul.haering@nytransco.com

B-3

SERVICE AGREEMENT NO. 2622

APPENDIX C

IN-SERVICE DATE

[Date]

New York Independent System Operator, Inc. Attn: Vice President, Operations

10 Krey Boulevard

Rensselaer, NY 12144

New York Transco, LLC   
One Hudson City Center   
Hudson, NY 12534

Attn: Vice President, Capital Investments

Re: \_\_\_\_\_\_\_\_\_\_\_\_\_ [Affected System Upgrade Facilities]

Dear \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_:

On [Date] [Affected System Operator] has completed the [describe Affected System Upgrade Facilities]. This letter confirms that [describe Affected System Upgrade Facilities] have   
commenced service, effective as of [Date plus one day].

Thank you.

[Signature]

[Affected System Operator Representative]

C-1